## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
6bc27707-5b5c-4bb7-b0e5-55e0e5a5e216 | checklist | ITP-002 - Feeder Conduits and Pits Rev2 | itp | ITP-002 - Feeder Conduits and Pits
ed4aa4e0-e109-4830-b754-92d3b536c6c6 | section | Preliminary Works
4d13e635-7487-4683-89ca-e1eada2db927 | checkpoint | 1.1 Check for correct documentation
dc587bfd-ada9-57f7-ac75-d0f34d30b1ea | note | FREQUENCY: Prior to commencing any activity
8b619cde-74f1-532f-9eee-9d4eec5e37fb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
598d6b2c-f7fc-56dc-a161-9559090d6caf | note | — using the correct and complete set of drawings
a67e8be9-85f1-5e63-9b0d-fc971bf8995e | note | — all drawings are the latest revision
b114146b-ee5f-5db3-81e3-632d6410a558 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
564275de-0757-513a-b2b8-6b4beaf711c1 | note | INSPECTION/TEST METHOD: Visual inspection
b3bb2285-c4cb-5f3c-a838-7e5e76a5b762 | note | RECORD OF CONFORMITY: This ITP signed off
55b2bd47-8f43-5f0f-a4c8-cb56b00d3309 | note | HP*
cfca2e1f-0323-5925-9ba0-92b879be8e2c | note | RESPONSIBILITY: Fulton Hogan Engineer
e86e1942-e293-5d83-b7c4-422ec176c910 | textbox | Date Completed:
a8ffc39e-0583-40b1-8359-cf83e72d9847 | checkpoint | 1.2 Implementation of all measures and controls
6644e048-b1a8-504d-bd3b-97855b0f900b | note | FREQUENCY: Prior to commencing any activity
dbd6f751-423c-5657-9aa0-f3e15a1828cf | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
a284ee21-c515-5771-a8a7-060bccfbf6ac | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
6a581608-fd05-54be-abef-73c8e6f3c2a1 | note | INSPECTION/TEST METHOD: Visual Inspection
485c7d6b-97a6-5fb2-b5c2-c4a0e42caacc | note | RECORD OF CONFORMITY: This ITP signed off
51b27c91-f859-58b4-8639-701c2cbe9cae | note | HP*
a2a14dbe-81e4-5d10-bcc8-0093a6103971 | note | RESPONSIBILITY: Fulton Hogan Engineer
58f50831-5706-52f0-ba70-80a0b1037e8a | textbox | Date Completed:
fe83e5b9-9a6f-46c2-9097-bd8c0e7ccd1b | checkpoint | 1.3 Materials
97cf413d-1f0f-532c-bdd5-2c6f7771700f | note | FREQUENCY: Per Batch
70270785-c3a7-500b-8fc6-f1efbf0aa7cd | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be Orange
633c2189-9ecf-5c66-be2a-ac22701dd74a | note | ○ Heavy Duty 100mm diameter UPVC
2b93258f-1f10-5ffd-9fba-9b133c39cd52 | note | ○ Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw
70f5e7bd-e9f5-549c-b8e5-57dbba4b5c3c | note | ○ All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
997523f9-00e7-5088-83fc-64e1ef64cdf0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4, AS 2053
ecba8aa9-2bae-5a44-a1d5-1ebe58367760 | note | INSPECTION/TEST METHOD: Verify
7143cb13-3cf8-59aa-af96-bafa18c9f561 | note | RECORD OF CONFORMITY: This ITP signed
8ef091e4-ba4f-57ce-8646-e9aa47e177e0 | note | HP*
41b4d2fb-cee4-5943-bb47-6997f41433a0 | note | RESPONSIBILITY: Fulton Hogan Engineer
93851680-968f-5a6e-8e4c-cbae6be944ca | textbox | Date Completed:
cfd674bb-6060-4e6f-ba35-a8569776319d | section | Construction Works
622e3ff9-bc5a-4815-b522-556ba53cf733 | checkpoint | 2.1 Survey set-out
c8cbd0e0-080f-5a6d-b405-38ee68b044cc | note | FREQUENCY: As required
d8a38251-5426-56da-a4c4-7368711b9066 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
56b7c8ff-4081-5a3c-9195-d2537e3e6f6e | note | ○ Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
e63eaa75-f30a-5db8-8577-3c987d51ae3e | note | REFERENCE DOCUMENTS: Work procedure
7ff5b70e-e158-5076-a8d6-9e16a905111e | note | INSPECTION/TEST METHOD: Verify
fdabb3d5-ad6a-53ce-8539-b526475073e1 | note | RECORD OF CONFORMITY: This ITP signed
0d4d545b-8566-56f5-9e2f-c04205eeb5de | note | HP*
279398e5-f19a-514f-b636-6666456e6d9b | note | RESPONSIBILITY: Fulton Hogan Engineer
b6c9674b-159a-5f2f-b1fe-b71c7e81bffd | textbox | Date Completed:
f5d90975-c47a-4d76-ade9-c033c83db2d5 | checkpoint | 2.2 Excavation and Trenching
4c6041b1-34a3-5d46-9b33-c116834c1b94 | note | FREQUENCY: Prior to Installation
f5ca7766-a4a6-5e3c-8dbb-fcded95a4c4a | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
17acecdb-7b6c-5798-ba4f-3aa8ce108e9b | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
1805beae-5ca2-5c92-8f26-94fc39aa29fc | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
93c10154-2a70-5f39-ad77-16fd595eb483 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
eba6534c-341c-5235-96f6-a7272d7f92e5 | note | INSPECTION/TEST METHOD: Verify
99e8c505-1cb9-5f0c-bc51-e8a0aedd197d | note | RECORD OF CONFORMITY: This ITP signed
9c3f68c9-1c34-56fd-8b49-867031f85b49 | note | WP
3d7c969b-c62c-527f-929d-594754b34577 | note | RESPONSIBILITY: Fulton Hogan Engineer
3f8384db-5667-513d-9671-33e3abceb922 | textbox | Date Completed:
4bae17aa-c076-41cf-9225-3ea01fefe2ec | checkpoint | 2.3 Installation of Conduits and pits
cd1444bd-6e01-5f82-9d74-cbe1e06b17e4 | note | FREQUENCY: Each Lot
21683916-b529-5b39-b845-b44aa1c24cc1 | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
5a14c5fe-2e30-5bb1-a9c9-00ff13ab8e3a | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
54edde7f-d415-5d95-be63-8c6b90eac504 | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
e26449dc-4e1c-5c3c-bd64-4a0778e5bbeb | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
9d02dbe9-025d-5be1-8621-00a20d76db49 | note | ○ Conduits shall not be subject to construction loadings
485288e6-98de-5309-ab93-1cbf061dbc86 | note | ○ Pits shall be constructed as to allow for class D rated covers
87937a88-4154-5219-ac40-d82ffdb95ae6 | note | ○ Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
77efcb0f-cc28-55de-8a21-53a883b44b4b | note | ○ Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
150ea2ad-a426-5b98-b516-f72f7406af7a | note | ○ Conduits shal be placed a minimum of 100mm above pit floor
5e0087d4-0acd-5160-8d66-17e00cf1b97b | note | ○ Conduits installed for future connections shall be installed to the track Margin
79f8d2a0-7a58-521e-af02-a1c61de70fa0 | note | ○ 100mm of concrete around and under pit lid
260438de-57de-551d-8ae2-b59d11846da9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
f691f669-9d35-5f60-a134-96b43786a2c6 | note | INSPECTION/TEST METHOD: Visual inspection
3df9f6e8-0aa5-550a-b592-b15091b6d971 | note | RECORD OF CONFORMITY: This ITP signed
7d4aa763-cd8f-51d9-97bc-661c3bf42858 | note | WP
31156abc-9ce1-5030-a9bd-8ed9944b4bb6 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
c11af1a4-61a9-5f27-aa43-9d295d071f6f | textbox | Date Completed:
a029e747-1388-447c-becf-e2051d8af0ad | checkpoint | 2.4 Inspection of conduit installation
81689b24-0ec4-5245-90e7-6e6ac6c1245d | note | FREQUENCY: Each Lot
ec6de7bd-964a-5fbb-b51b-6b776507744d | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
c64b9046-b644-58e5-a4e8-3e3fc59c6e83 | note | REFERENCE DOCUMENTS: Work procedure
5333a0b3-46f0-549b-87d6-4fca6d19fad3 | note | INSPECTION/TEST METHOD: Visual Inspection
839a9447-5d1e-5e7c-befd-02d938f7423f | note | RECORD OF CONFORMITY: This ITP Signed
e1ee2d1e-02e2-5ac0-9111-87acc728b99d | note | *HP
f4dab1a7-ace3-5fc2-a730-70a43db7faf4 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
1b1b1426-12fb-580b-90ec-a9c50cd3deb3 | textbox | Date Completed:
49c9bead-d1ae-4f6a-949b-fe09bbe812ab | checkpoint | 2.5 Back Fill of Trenches
20a43c59-c4ba-5662-9929-b6488d94c4a6 | note | FREQUENCY: Each Lot
0c17a9cb-6a5e-5a7f-83aa-9f61bef23e7c | note | ACCEPTANCE CRITERIA: Backfilling (Only to be used for road crossing trenches)
5f30a3f0-52c3-58cf-a2de-c728b63461f1 | note | — conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
c29b5801-709c-51e6-bf84-59db0ad24b20 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
7419c4f6-a4d4-5490-9655-6faa5f161db6 | note | INSPECTION/TEST METHOD: Verify
1cd4f078-bd36-572e-b872-a848f7b0d9c5 | note | RECORD OF CONFORMITY: This ITP signed
ed0b2ee0-b737-56bf-866a-953801ddfb6a | note | WP
0bbffaae-56a5-56c9-9c24-d978d13db920 | note | RESPONSIBILITY: Fulton Hogan Engineer
5a48b3d4-eff3-53fd-922e-385b017e07a8 | textbox | Date Completed:
c1994943-70ea-4c2e-b166-d53c9531b267 | checkpoint | 2.6 Installation of Draw Cords
e88a4fc5-2b60-521e-beb7-3e42c1bb1a9c | note | FREQUENCY: Each Lot
8754b29c-5ca6-5989-9b8b-0d4302004cb2 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
13ccb1ce-adcf-5f87-a1a1-e62186000efe | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
1569ed92-f113-5266-aff2-a32902843685 | note | INSPECTION/TEST METHOD: Verify
ad1ce4e0-0f90-59f3-9e81-a8f7ec0e0921 | note | RECORD OF CONFORMITY: This ITP signed
da3b67db-7bdb-5813-912d-adadeba85f2b | note | WP
9c6e8878-f84c-58a9-9c43-18d7bba51ca4 | note | RESPONSIBILITY: Fulton Hogan Engineer
0db81098-8cd9-5742-93c2-988a72c54790 | textbox | Date Completed:
d41adaff-54d7-4733-ab92-7c4ec8c504f2 | checkpoint | 2.7 Compaction
9d3b6d64-98a9-5f1c-842b-9999c4843768 | note | FREQUENCY: Each Lot
98595789-695e-5b3d-8de0-c419db794203 | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant
e1a2e603-08ea-5eab-94de-56fc71014f95 | note | ○ During compaction optimum moisture content of bedding and select fill is within 85% to 115%
8ea55f7c-0bbb-5c4e-97b8-7fe3b42da1c1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
a883a388-61cb-58ee-a7d7-c6d8624a89ca | note | INSPECTION/TEST METHOD: Verify
8437dd8a-95f5-594d-b3ce-6216b2800823 | note | RECORD OF CONFORMITY: This ITP signed
c9ba3351-a26e-519c-8ce8-dc5dd0cdcb6a | note | IP
e07a8322-5009-519a-b005-90b2cef14fc8 | note | RESPONSIBILITY: Fulton Hogan Engineer
5418b61d-ebb5-534e-a25d-de2316da106c | textbox | Date Completed:
de1a3e88-8d82-4c2d-8102-8bd94966b86e | checkpoint | 2.8 Feeder Pits & Pit Lids
4712bc26-fe31-5f87-9c6a-eb54667f735b | note | FREQUENCY: Each Lot
4355a523-7834-5c44-afd8-315f38cc2a62 | note | ACCEPTANCE CRITERIA: Feeder Pits constructed and installed as per drawings
066dde0e-d4e0-53b8-80bf-6a3d3ea8dcd3 | note | ○ All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
e9862d84-9949-56f4-8182-cb42b657e451 | note | ○ Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
fd12de11-a206-541d-b8e8-986c91fc0af6 | note | ○ Gatic pit lids shall be filled with structural grade concrete.
6efae0f2-db04-5c6e-93d9-19d974b89442 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
f0b26608-c218-54b9-bad1-3f23199ae49e | note | INSPECTION/TEST METHOD: Verify
47e21acb-e5d0-5291-a2bb-fb49618fa6b8 | note | RECORD OF CONFORMITY: This ITP signed
b51393c5-401c-5326-9995-c3243412d6cf | note | WP
fee461f2-1e35-5871-b895-10b95a9a5a11 | note | RESPONSIBILITY: Fulton Hogan Engineer
37a1e15a-411b-5731-b7f2-f32b11b858d2 | textbox | Date Completed:
4090db74-dd99-4ceb-b09b-4a33fb59ec82 | checkpoint | Final Inspection
692b30cf-4ba4-5c17-9c7f-0f18c88ebd2b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
03ad4f2e-dfbf-5ef8-9e21-800e8a9697bb | textbox | Print Name:
643bb9f2-511b-5c1b-af1e-6e5fa073c26c | textbox | Position:
51925782-1909-53f7-929c-0fc068efbd13 | textbox | Date:
37fb0abb-bc34-433c-83ff-9bc1074906d7 | checklist | ITP-008 - Hot Mix Asphalt Rev0 | itp | ITP-008 - Hot Mix Asphalt
058bfbfc-4c85-4cb7-8ff5-f051731ecc63 | section | Construction Works
ad8e4774-d687-4253-873a-9c70382a9ef9 | checkpoint | 1.1 Submission of Mix Design
0e32ce52-6fe8-5160-824e-1fd8f606d9de | note | FREQUENCY: Prior to commencing paving
c64e1af7-5f15-594f-a550-946ce085b4af | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
770fe415-6723-53ce-b1de-ae2e0e1eea8b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
df4c4514-d6a5-5a65-92e1-c71604469aab | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
06d445f0-5e01-5ee9-a060-59ea1dc8f5d0 | note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
2f3a756a-5623-530c-89d1-40f0d770b0ea | note | HP
3c40e402-0fcb-5c59-92a1-abdb68d7ca00 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
458780bc-bfa4-5b7c-b02d-accdc270b38f | textbox | Date Completed:
4bf384c9-5e42-4193-8629-a9d918dae4ce | signoff | AUTHORITY HOLDPOINT
60ca549f-b397-439b-8ba1-0c239efc8d9e | checkpoint | 1.2 Site Inspection and Base Condition
97add140-9acd-5335-b647-f0575a6986f0 | note | FREQUENCY: Prior to commencing paving
001f19c2-9e88-59eb-9f00-90eb3256419f | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
2f3e1548-0c8c-5b70-9475-10c0cefb6ec5 | note | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
d8790e74-180c-534a-8287-c91934610aa5 | note | INSPECTION/TEST METHOD: Visual Inspection
ee99c4e9-4e0e-59b9-aa00-23654e468de7 | note | RECORD OF CONFORMITY: ITP Signed
5c39fe08-4e38-57d1-89de-9363ffe09132 | note | WP
ae17d32c-0c4c-5837-adc2-c97a7191e6ad | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
ded5fec6-34f9-5aa0-bd8a-1ffe642062c0 | textbox | Date Completed:
15bbe64e-11f7-492e-963c-b7b0eb87678f | checkpoint | 1.3 Ambient Conditions for Placing
0e96ac10-6a77-5f8b-b0b1-9d2c05e1094e | note | FREQUENCY: Prior to commencing paving
c45e9d90-91ba-5954-84a0-89608f799990 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
79c7a632-f5bd-5789-8b5f-b941fbf57742 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
a87518d3-bb01-55ad-b504-c39656f42341 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
2432fad2-ec43-55e9-8c4b-d8a7d259cfd3 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
5e498b6f-3724-5006-9a5e-593c5d0f6e9a | note | INSPECTION/TEST METHOD: Verify
f370cd2d-f843-5786-88b7-96d10aea461c | note | RECORD OF CONFORMITY: Thermometer
b2fbcf54-f543-5029-b2a7-cf96182e8a18 | note | IP
56136bd3-58ea-5693-bab5-7a55792e7523 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6a84932c-edc9-58fe-bb96-6f486f2d1047 | textbox | Date Completed:
e16a5d96-cd41-446d-8ddc-c82b864a5c48 | checkpoint | 1.4 Planning of Joints
c796522f-c244-5923-ae9f-130f775d231b | note | FREQUENCY: Prior to commencing paving
5ae7e823-bf98-5050-b395-afb0c23eaaf7 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
981db267-ef09-53f6-9d8e-27d9279a3f54 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
6c967b6d-b52c-5c56-96d9-43d1adf82ac2 | note | ○ Longitudinal Joints Offset from layer to layer by at least
581f70fe-1b64-5dec-9057-8f9b46a99cd5 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
e2c6b27e-171a-5331-b7f3-2c5e51f200ac | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c), Pavement Drawings
f7b04fd2-ea4a-545c-89aa-10d00f890b48 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
6b932372-b3ab-5442-8368-072ae04cf122 | note | RECORD OF CONFORMITY: Paving Plan
c25ed4bf-b913-5bcc-91fa-ed2c8d5d7395 | note | WP
a6926863-9ee5-52db-a90a-cc4ca90cf819 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
e9e786e2-d40e-512e-a01e-e4bf9ea0accf | textbox | Date Completed:
c104f415-907d-43ff-8369-5a557e9eaf33 | checkpoint | 1.5 Longitudinal Joints with existing Pavement
f0a1c539-6594-555f-a85c-cf405485b592 | note | FREQUENCY: Prior to commencing paving
5f6a0da3-5130-5651-b284-3a9759e28b78 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
d720345c-7095-5ee2-899e-6e6f58d37cb8 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
1cf84450-9c9e-5102-8e6b-78957115ef2a | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c), Project Specs. Section 3040.06 (d)(vii)
7f06daf2-bc12-5070-8ff4-4ef99cd8234c | note | INSPECTION/TEST METHOD: Visual Inspection
d2e197b5-981d-53a4-b43e-c5a3a4ad16bb | note | RECORD OF CONFORMITY: ITP Signed
fa2d97bf-dbf8-5a42-95ae-44b489a88acc | note | WP
724447f1-920d-519b-a343-2a8923fdb726 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
5d6efd95-1b20-5928-ab4b-bd344e82fa0e | textbox | Date Completed:
fcc685da-e506-4b1d-afae-95abb1262849 | section | Asphalt Placement works
3d34d77e-9501-44e7-809b-e96e36757957 | checkpoint | 2.1 Commencement of Placing
0ad3d3c7-d430-5e3a-8d21-2c218db32cd2 | note | FREQUENCY: Prior to commencing Paving
e2e6820f-107a-50a0-aced-7a4b12064558 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
8b74a1d6-43a1-585f-8e0a-6ea2330aa096 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
bed11f9f-689d-5132-be05-d75ed4abe7e7 | note | INSPECTION/TEST METHOD: Visual Inspection
acfffcab-0423-58ce-a3db-4aef54accf12 | note | RECORD OF CONFORMITY: ITP Signed
75ef0e7e-5df5-52ef-bc5d-884e4a4372d1 | note | HP
a58d796c-52db-5cb5-8a75-b40f2398bdd8 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
9d02d78e-6ce4-5f25-8ac0-283cb78ff333 | textbox | Date Completed:
23602f9d-9850-4469-bb15-f5dbfef4ecdb | signoff | AUTHORITY HOLDPOINT
e579148f-db32-4ba4-b1dc-c1d88cb492cc | checkpoint | 2.2 Mix Design Confirmation
4d254118-71df-5a93-814d-0972f2e3fd3f | note | FREQUENCY: Each lot
1f110f5d-0069-5f1d-8dd0-1e01b81c2aea | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt mix shall be 10H in accorande with Yarra Trams Track Structure standard drawing.
929e36be-3de1-5631-987c-bdd67c9e389b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
4d879bed-d9d6-5561-a95a-b7ed04696e05 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
568aadce-db07-51e7-af13-e0f63b980c6c | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
6c85bc90-6df4-568c-80df-b1570ec51b65 | note | HP*
1399ed5c-f88a-54ac-bc6e-d7c6f43d6142 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
af3ffc97-8259-588a-b89f-b1cefae57807 | textbox | Date Completed:
9a9f0ede-e864-4919-9753-875202a8a76d | checkpoint | 2.3 Delivery of Mix
5ea367ae-3a58-5494-a366-a34c034f257d | note | FREQUENCY: Each load
3e9e52fd-01ae-5702-bf1d-701fc02a7bf0 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
e8ba9e1b-c1e3-539b-83e3-c446418de911 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20, Table 407.111
17c463a0-c061-59a4-80ec-63c69ff19f47 | note | INSPECTION/TEST METHOD: Visual Inspection
84b9057b-48cd-5105-8f9d-31e4e46a2075 | note | RECORD OF CONFORMITY: Delivery Docket
9a5c26d0-3363-546c-95ec-5407a561024e | note | WP
fdac9380-7591-52e7-98d0-e23c87832053 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2415cd37-43b9-582f-8999-0f888036f166 | textbox | Date Completed:
ebff6988-1264-4b86-bfb7-900a79115052 | checkpoint | 2.4 Traceability
c976ff1c-d78c-5727-868f-944ca88af493 | note | FREQUENCY: Each lot
b2794161-119d-5a85-b23d-a307ba518c88 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
38ce1d74-d756-5a94-a931-9945fc704a63 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
00f44852-b8d7-5960-a155-638ac44527a8 | note | INSPECTION/TEST METHOD: Verify
44548fe4-10c9-5287-a840-f598e2394bb1 | note | RECORD OF CONFORMITY: Daily Lot Record
1f7f7ec0-5b79-5445-a026-d135739a70c8 | note | IP
a638cb18-fb8c-5c2c-8234-af9e84e923e9 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
a186bde4-4a46-5262-8a01-5c67b2f10e2b | textbox | Date Completed:
a278b34a-f0bd-4caa-9cc3-605d4681409b | checkpoint | 2.5 Layer Thickness and Level Control
c931d231-0d72-5622-b6fb-18a1ef5ce2a9 | note | FREQUENCY: Regularly during paving
2a641043-84c9-5b95-8aa8-85c5a5a9c494 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
1a444419-1ae8-5b66-b862-652866c9e75f | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
90f361fc-21af-5a0b-a431-7e9edd282d06 | note | INSPECTION/TEST METHOD: Verify
e3e1932f-2195-5407-90c1-33a75955e96b | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
0da34069-60c7-55b0-9091-eec9b632649f | note | WP
4bc823d5-5923-5d2a-ab73-4b7511e56385 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
dc7278e0-5049-54c8-add7-90ad259a38d7 | textbox | Date Completed:
69796baa-11cc-4ea5-9b8e-2f612202e9d9 | checkpoint | 2.6 Surface Finish of Wearing Course
603f867b-f3c0-5d54-a90e-31c077317b5e | note | FREQUENCY: During paving and after final roll
baa84352-32a5-5bc5-a7a3-460e74f27271 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
93c9e3e3-34f3-5e8a-8282-b126925bbe30 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
125580a1-99a0-5675-9ca0-917651a31f75 | note | INSPECTION/TEST METHOD: Visual Inspection
3f5d95ba-803b-590b-b65a-30b0285061cb | note | RECORD OF CONFORMITY: ITP Signed
b478da3f-823a-531d-984a-aa2ea29f7748 | note | WP
4744c1fc-7d23-5823-a6a6-b2282712a23d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
d7cf9e27-6172-5247-b78f-f3c5abdadc54 | textbox | Date Completed:
37f3c1f6-98c8-474a-8186-a412ea28de7f | checkpoint | 2.7 Alignment of layers not placed against concrete edge
f9342415-6801-57ed-97d3-12acd72a5d5c | note | FREQUENCY: During paving and at completion of work
9fb8bddf-66ce-57d6-a361-de2cb0c4007e | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
49cee408-9ea3-5018-82f1-a3c2cf120e55 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
a9ba3aed-6893-5590-b8e5-db0fbbe07524 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv) Drawings
80cb0c48-6263-5993-a2bc-ec5892bee342 | note | INSPECTION/TEST METHOD: Visual Inspection
c098f9ef-4da0-5925-85ee-e59602315941 | note | RECORD OF CONFORMITY: ITP Signed
0b0f4843-64fb-5345-b844-af8738e60100 | note | IP
9597540d-cdb9-59e7-9188-8061ff7a9681 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
0fa45ab8-4302-5f98-aee9-836bdf77382c | textbox | Date Completed:
2a3342ce-1147-4e99-8833-31fa2d9a0bc2 | section | Testing
b5d254a7-c531-41bb-b558-2a3069976962 | checkpoint | 3.1 Compaction
faa0cafd-f5b8-50a2-9465-248a34e195ca | note | FREQUENCY: Per Lot
4d6a6611-2b74-55ff-af2d-6987f95cbd8d | note | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is:
38f95167-7a95-5696-92da-c38447523ff1 | note | ○ 94.0% or greater Accept lot
1f8dd4d6-e969-5d39-a778-828d2e7cfcb1 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
d65c44c1-267c-5d8c-8a6b-e4c8b19fd6da | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
1003d1fa-79fa-5d89-a612-a6cd784c909d | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
db5f7867-4598-585a-a511-9e3227dad670 | note | INSPECTION/TEST METHOD: Verify
455338c2-4cd9-5d4f-8275-bbc648479569 | note | RECORD OF CONFORMITY: Test Report
3726ffb9-6835-5e37-b9b1-6935aaebaa27 | note | TP
8234240f-d6c5-5c13-aae0-e879b49567d1 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
0c67362a-60ef-5cb0-b474-a5aa7e36c244 | textbox | Date Completed:
f291523b-6000-4370-9c13-687524253c55 | checkpoint | Final Inspection
397dd731-91d0-59e1-9801-f77da9c2b0a3 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a60e2084-4dcf-5894-abd2-1966486b8310 | textbox | Print Name:
24256627-feac-5c83-9894-bb662a1dd15c | textbox | Position:
fa8f4179-d70c-5628-8963-7d924d4c5950 | textbox | Date:
243d07aa-3e9d-4cc1-a48b-1ab47674f890 | checklist | ITP-020 - Exothermic Welding Rev0 | itp | ITP-020 - Exothermic Welding
70c23f91-fb1a-4a49-b64c-dd7fa75791ac | section | Preliminary Works
2ca31229-94b2-4687-affa-b1ba3e37f0e6 | checkpoint | 1.1 Check for correct documentation
230a485b-7563-52c8-945c-85f54f2a2ec8 | note | FREQUENCY: Prior to commencing any activity
7020f3b6-016f-5375-be8e-8b51b200c323 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
1235477d-f9be-5ca8-8733-99010e37aaee | note | REFERENCE DOCUMENTS: Drawings and drawing registers
fe2f1d0c-a27b-59af-a8b8-e7eb27c1c120 | note | INSPECTION/TEST METHOD: Visual inspection
4832db1c-bf60-59a0-9f34-43411d4bfdb1 | note | RECORD OF CONFORMITY: This ITP signed off
0faf4867-7ff2-5543-84fe-d121dcc50aad | note | HP*
8ae461f1-9fae-54d4-88f9-9d99e781c24f | note | RESPONSIBILITY: Fulton Hogan Engineer
75ca3076-b7d9-529c-96c4-48ef514fc8c8 | textbox | Date Completed:
0b90f402-0f89-45a1-9884-5ece6036232f | checkpoint | 1.2 Implementation of all measures and controls
58ede2ff-7c2b-5c85-a665-5589102f58e5 | note | FREQUENCY: Prior to commencing any activity
6268c66b-6e5f-51fb-b755-503af76e3e33 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
8c99cc38-3ebf-5eb6-9f4b-bf15db063e3d | note | ○ Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
807a2dce-9de4-5520-9513-1b9d0dd54e1b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0dfca402-246b-546f-bc67-3e2095ec02a7 | note | INSPECTION/TEST METHOD: Visual Inspection
046eba33-7c27-59c9-b4a9-7b3b2c7a3926 | note | RECORD OF CONFORMITY: This ITP signed off
496b64f4-3355-5b99-ae1c-420f2007f5c8 | note | IP
8dae365b-94d8-56e3-8cd2-98788ff3fd26 | note | RESPONSIBILITY: Fulton Hogan Engineer
cd29a2bc-a4e2-5f7c-98dd-527db9f53881 | textbox | Date Completed:
fc49cfd3-1ee3-4867-a198-4f4728aaa862 | checkpoint | 1.5 Materials Check
22f29c42-62b6-5d7f-8941-1fb7305a155f | note | FREQUENCY: Prior to commencing any activity
cd3e3d76-7b9e-5b67-ba15-78c0eb07d0ec | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made. Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
cac92e0a-a3d1-5a89-8ee8-ee634a46d40a | note | 1. Mould part number:
cd326aeb-7a57-5b2c-9ff3-4b91d8f70325 | note | 2. Conductor size:
169e7ff8-56ec-51f1-9494-d7800fa0147c | note | 3. Welding material required
5396b386-e1cc-5ddf-bd6f-8cfa0e6110b4 | note | ○ Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
f83d4102-42ff-5b7a-8a2f-b2f53fa02ed1 | note | ○ Ensure a working fire extinguisher is available within 10 metres of the working area.
1cc85cb1-0ead-5817-b418-91b9144c69cc | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
ec1e516f-69fb-5ec3-b0c8-39d5c73001a8 | note | INSPECTION/TEST METHOD: Visual inspection
1c38317d-513d-5aac-b4fb-ae5b145ccde7 | note | RECORD OF CONFORMITY: This ITP signed off
32a3dea2-6d33-5d68-9b77-96962a0a2fed | note | HP*
d6960500-3762-5d3f-b513-239687384ec0 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f289bc2-5ce1-5b3c-bcae-90687b209cc1 | textbox | Date Completed:
49d351e2-26f9-4a46-87d3-2e007b7d060a | section | Construction Works
969a869c-1530-4fad-af9f-1aa472379457 | checkpoint | 2.1 Preparation
a82646bd-bbd9-54a3-a407-fea20bc6cafb | note | FREQUENCY: Each Weld
f42bbeab-fe5f-5833-9718-e5bf38aede54 | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct.
579ca6fd-135d-56cb-8a73-92f220ef7d96 | note | ○ Heat mould to ensure it is dry.
4c06890a-509e-5bfc-87e4-81e19b5820b6 | note | ○ Strip & clean conductors, ensure they are dry & clean.
aae2d9f6-1a06-540f-8916-a33f3abbef68 | note | REFERENCE DOCUMENTS: Design Drawings and Register
a0c9e430-b324-580e-bb2e-26aead3443b0 | note | INSPECTION/TEST METHOD: Visual inspection
216f0163-8f4c-5a76-9b5e-fd21dc424e5b | note | RECORD OF CONFORMITY: This ITP signed off
cf6c991f-22e6-591a-aa7e-e941b29869b8 | note | IP
186b1e3d-a51c-5275-8e50-18b68df9e337 | note | RESPONSIBILITY: Fulton Hogan Engineer
b52cf2c1-ba11-5b6c-abec-b14ba95af3f6 | textbox | Date Completed:
17ca78ce-3d9f-48be-b1a1-dec28dfd4eb0 | checkpoint | 2.2 Welding
c75c616d-e299-56a6-8f58-a56b9370e860 | note | FREQUENCY: Each Weld
125478c5-a4be-589c-98c9-91817d7d6044 | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly.
ed65bc4d-44ac-59c6-b116-349bfae1fd53 | note | ○ Ensure welding material has been insected and is intact.
f60f9dc4-6e6e-5ec8-a1f4-8234531442ea | note | ○ Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
f2de2c84-20bc-5b06-a7ad-c12c27fce9b8 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
c997fb1c-c00d-50bf-a6dc-2c275e62403c | note | INSPECTION/TEST METHOD: Verify
a0fd204b-0d18-5b94-aa5d-6c6dd2a9b1b3 | note | RECORD OF CONFORMITY: This ITP signed off
032e7405-1a61-5dbd-b0e2-1f9649e4750b | note | IP
16ebdb3c-ba12-57d6-b5f6-d8cc8850fb1c | note | RESPONSIBILITY: Fulton Hogan Engineer
f34df621-68f9-5585-8cb0-175e3ccc9f6f | textbox | Date Completed:
02562895-a0eb-4048-9c39-b73b7a0bab28 | section | Testing
1c0dc9ae-e879-47b3-ac2e-2bac1c451c07 | checkpoint | 3.1 Weld Review
918facf4-f626-54bb-ac95-c43f9137024d | note | FREQUENCY: Each lot
9b5ec967-1add-5c61-9040-a199f2d556a8 | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made. All welds shall be inspected a Fulton Hogan engineer.
75e369ae-4ac7-5a53-8731-48cc1d8b1324 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
6170e884-bae7-53b3-8277-094eabf7ef1c | note | INSPECTION/TEST METHOD: Verify
22c8a86e-cc32-5299-b8cc-af8f19d18251 | note | RECORD OF CONFORMITY: This ITP signed off
3ae60d79-958e-5348-990b-2b3e43da742c | note | TP
dabe0e51-0196-5ce7-98b3-620428c47377 | note | RESPONSIBILITY: Fulton Hogan Engineer
21dc3d98-6367-53e8-8261-65e72f741c76 | textbox | Date Completed:
0c96f03f-c3e9-40a2-9b90-fbb903da88cd | checkpoint | Final Inspection
3e7ef7ee-aa03-59eb-b9e4-961ec99e96f1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
576eb020-b200-5e4e-8950-56efc0e8b6a8 | textbox | Print Name:
0be1db94-6fe1-56a6-9ffa-786fbe7357d9 | textbox | Position:
5afaa092-c613-53d9-90ca-f491ed74edde | textbox | Date:
77d2f222-7b94-45d5-822f-4d39dbcb3182 | checklist | ITP-021 - Construction of Track in Ballast Sections Rev0 | itp | ITP-021 - Construction of Track in Ballast Sections
b04277e8-5875-4538-a71f-6386e8e3ed81 | section | Preliminary Works
464a529a-0abd-4bd1-8b82-892a51a5b439 | checkpoint | 1.1 Check for Correct Documentation
1e44a481-4b13-5adc-ad3a-72353465b396 | note | FREQUENCY: Prior to Commencing Works
9aef013c-a018-5571-9c87-5c5cbd3aa73f | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
e8a1201f-5c0d-5a26-8941-184a131c0f98 | note | REFERENCE DOCUMENTS: Design Drawings and Register
6ee9ed08-45ea-5cf3-a3b9-425e82c92feb | note | INSPECTION/TEST METHOD: Visual Inspection
86a0a5f0-c55b-58e8-80b7-69c53fd5ea61 | note | RECORD OF CONFORMITY: This ITP Signed Off
b8b262e1-5673-5ce2-ad79-7970ba400ec5 | note | HP*
8aef5834-76a0-52d5-b126-c75990f797c3 | note | RESPONSIBILITY: Fulton Hogan Engineer
84c9da57-1b07-5aa4-b9d4-edfb7867faad | textbox | Date Completed:
fb96b5c8-fcc8-402b-bd77-dabc7a1343fe | checkpoint | 1.2 Check Materials
7a05a83c-b709-5c13-b482-fec8fa91b578 | note | FREQUENCY: Prior to Commencing Works
52d1fa08-f053-54bb-a018-8f5ec7a9fd3a | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
b2bda34d-09d0-5aee-af1a-c335fc15c9b5 | note | ○ Check condition of rail sleepers
ee51e43a-1c4f-56be-868b-6ac86024ce4c | note | ○ Ensure rail jewellery is of sound condition
c0fc0ad8-7937-5700-81a6-9bfb5f7368b1 | note | ○ Ensure ballast is clean, free from clay, dirt and other deleterious matter or weathered pieces of rock and free of dust.
17ddf649-1410-5a79-8851-56e18996c1b3 | note | ○ Ensure ballast has been tested for conformity by a NATA certified laboratory and the results have been documented and recorded. On-site testing shall be completed for the particle size and shape of the ballast used.
068245ec-73f5-5de6-b80d-4783f7196fb0 | note | REFERENCE DOCUMENTS: AS 1085 & CE-019-ST-0033 cl 4.8.1
4947801c-adb0-56ad-b5f2-09a09edf75b4 | note | INSPECTION/TEST METHOD: Visual Inspection
83eea2d5-cfb0-5274-ae26-bcaa216d087a | note | RECORD OF CONFORMITY: This ITP Signed Off
9a9ba8a7-b141-5be7-a11e-335196f14ded | note | HP*
5208d2ca-e4d9-5ea3-9a43-a1744f782a40 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
0f480b5a-4bdc-52e2-a275-8603d48f5b09 | textbox | Date Completed:
a7d4475b-2442-4bbf-81b4-55ace3af136d | checkpoint | 1.3 Check Base Course
e0ba36cd-7cb8-59cb-971d-74fa6b4a6975 | note | FREQUENCY: Prior to Commencing Works
73c81146-08e0-5464-a169-510003e6780b | note | ACCEPTANCE CRITERIA: Ballast track construction shall not be carried out over any length of formation until the formation has been checked and approved by the superintendent.
f868a44c-b367-5b53-ae5e-e431ccfef590 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.1
c9007bb9-b246-56bc-aa84-b4cf91e6ca81 | note | INSPECTION/TEST METHOD: Visual Inspection
5d3417c2-400b-552d-9041-f516db707c07 | note | RECORD OF CONFORMITY: This ITP Signed Off
175a332e-f647-593c-be37-06068006ebc2 | note | HP
69943a73-1955-5d81-9bf8-9574959dab65 | note | RESPONSIBILITY: Fulton Hogan Engineer
891b8eac-f6de-5595-874f-16ba1c0a685e | textbox | Date Completed:
11c56231-7ebc-45f5-b4f4-ae50111d1d57 | signoff | AUTHORITY HOLDPOINT
222d6790-ce48-4f58-a7c3-2755d90011e4 | checkpoint | 1.3 Check Special Works Components
0816bf92-51ad-5bd2-92cd-5eeb5b053bf5 | note | FREQUENCY: Prior to Commencing Works
73bc6ed7-d7a3-5f19-9edf-d2cafb4a845d | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
1dbbaee9-0ec1-584c-9cc8-eb67416a067b | note | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails.
5e747a57-6602-55e0-8e93-d10283b4d1cf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
18cfd594-33af-5c98-8196-f872b1f65605 | note | INSPECTION/TEST METHOD: Verify
e0bcbc57-7669-5847-b42f-bd52bf5e143f | note | RECORD OF CONFORMITY: This ITP Signed Off
51d1bcca-2442-5cee-82b8-139f53a77e71 | note | IP
d078e7f2-3ff8-5c43-8c00-bfdc0548d064 | note | RESPONSIBILITY: Fulton Hogan Engineer
7980b0e9-4e27-5a33-8185-3f4b767802b8 | textbox | Date Completed:
56caa10c-b742-41e2-b9fe-a50c5431006a | checkpoint | 1.4 Check Curved rail
671d1473-b568-5910-9825-de0e49605af0 | note | FREQUENCY: Prior to Commencing Works
716838ab-35c6-5908-8f2b-3f62be832f91 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
3854ee1f-7513-587e-9283-63665725c1ce | note | ○ Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.
515b40ec-b9a6-5499-b925-3d8f714fb652 | note | ○ This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
2fd71645-3509-555e-8466-9a1d81b5632b | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
ed1d191b-647a-56ce-a882-335bb9089f14 | note | INSPECTION/TEST METHOD: Verify
1950e0c7-61ef-5d17-8df9-a107f3001c03 | note | RECORD OF CONFORMITY: This ITP Signed Off
bc0d42e4-e7d3-5515-b6f1-8bcbcd5e2afa | note | HP*
8462eeef-8a34-5f00-b2f4-ac146e645ee2 | note | RESPONSIBILITY: Fulton Hogan Engineer
26652010-5776-55f4-a83f-ecf4feb56365 | textbox | Date Completed:
0719cc6a-7292-49ec-9972-fe65624714af | checkpoint | 1.5 Welders Qualifications
27c9d021-3ac3-5ddb-863e-b7b498740e02 | note | FREQUENCY: Prior to Commencing Works
90fce857-a8fa-52b3-8f7f-ec63509172fb | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
022f32e9-23b6-5fad-933b-819c59d71856 | note | ○ TLIW2012 Grind Rails
d0c1e588-99dd-5f3f-ae43-9a0b99d1bbf1 | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
57bf01f8-2444-51e1-a12c-c1cb4c7fcbe0 | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
33b70c0c-4cd4-5acf-a56c-d283ff4cb44e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
4dbd2f86-e2c5-506c-91b9-96befd4df678 | note | INSPECTION/TEST METHOD: Verify
378e7524-1160-5288-87ba-afccbd7aa91a | note | RECORD OF CONFORMITY: This ITP Signed Off
63583423-77de-5f36-8c16-ae4cdc902854 | note | HP*
191bf925-3217-5def-abf6-e86f711bb2ee | note | RESPONSIBILITY: Fulton Hogan Engineer
9ea62366-a140-5b54-9dc8-dbfcc8335428 | textbox | Date Completed:
4a1744e4-f630-42af-926f-7327483c62d5 | checkpoint | 1.6 Ultrasonic Testers Qualifications
67f19f2a-ecdb-519c-a3f5-17f453b880c7 | note | FREQUENCY: Prior to Commencing Works
68046df1-2665-5505-90f2-47e4a41d557e | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
850d70a0-2912-55e8-ae51-839d6a7c51b0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
2b9b0040-0471-5966-8b83-9e9ad7041d23 | note | INSPECTION/TEST METHOD: Verify
75d848ea-2082-5ad1-b23f-f2371e6916f0 | note | RECORD OF CONFORMITY: This ITP Signed Off
fd12ffbc-b5e8-523d-a70a-69a085a13448 | note | HP*
c937ccb9-9c3e-5c1f-a5b4-f2f351f9bd31 | note | RESPONSIBILITY: Fulton Hogan Engineer
5570e7f1-bd29-501b-b466-c7afdefa1919 | textbox | Date Completed:
a1fc6504-8a49-4093-a770-8b3cc2e8c351 | section | Construction Works
0d9cf5b0-74a0-4182-a5eb-a259c1ebbb8d | checkpoint | 2.1 Placement and Compaction of Ballast
7fdc33ad-02dc-5d8c-a822-a00fcd499303 | note | FREQUENCY: Each Lot
84e55142-6c80-5565-aa6d-254d11844b47 | note | ACCEPTANCE CRITERIA: Prior to laying sleepers, 50mm Ballast shall be placed, graded and compacted in one or more layers to a total minimum depth of 150mm.
5b278f2e-9264-5d63-9dd6-ed52160a0632 | note | ○ Compaction shall be by a smooth wheeled vibrating roller as specified for earthworks.
631d2acc-d8b6-5517-b193-22fe3ef9f646 | note | ○ The superintendent shall inspect completed work prior to placement of sleepers.
e4724941-744e-53e4-b636-4308dcbc3d1a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.1
2c227239-5d01-5097-b9a1-1f12f31900db | note | INSPECTION/TEST METHOD: Visual Inspection
e3e76d81-82e4-54f5-b589-d5b78e6c4b30 | note | RECORD OF CONFORMITY: This ITP Signed Off
79a2fe9a-5bdb-5200-b1a9-4520e657b76b | note | HP
a79c536b-a7c3-523a-b077-6b1c7d442b37 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccf078f9-689e-5035-8ba0-757a05df4f06 | textbox | Date Completed:
70c2eb30-1a3b-4b0a-afe5-0e1d71616547 | signoff | AUTHORITY HOLDPOINT
453dd922-14e0-41cc-94e8-daeca9b0a4bb | checkpoint | 2.2 Installation of Sleeper
18fb065f-9a1a-55bc-b534-9d2fc9b17aff | note | FREQUENCY: Each Lot
de7c06b6-ed33-5675-810f-e914f5bfa7a5 | note | ACCEPTANCE CRITERIA: Concrete tramway sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement
d4e69655-a420-5547-bb80-fda5a4a1e5d0 | note | ○ Concrete tramway sleepers shall also comply with the design offsets at each chainage.
f307126c-b9e3-5e41-b97d-3f4ad3f324b8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.2
676666b0-6c73-5bef-9e59-4599a2755bf8 | note | INSPECTION/TEST METHOD: Visual Inspection
6c4ddd09-25b7-5199-b3b2-39b179e970ac | note | RECORD OF CONFORMITY: This ITP Signed Off
7567816d-6dee-50d2-993c-07d3f6b2e2b4 | note | IP
7ec80af5-04ef-5582-8a98-a7b13e82332f | note | RESPONSIBILITY: Fulton Hogan Engineer
4a586702-3e04-5199-a4a9-672caab2755f | textbox | Date Completed:
601aef7e-203d-4c9f-8179-4dd56acc55bf | checkpoint | 2.3 Placement of Rail
1d565b4e-654f-5817-9988-69c4a7022726 | note | FREQUENCY: Each Lot
a62699b1-1369-5597-9797-bc93b5595878 | note | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
5eb054f9-5326-5090-a903-eab945b1edec | note | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
ac6c5e4d-4766-574b-bb81-1f669645287a | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
c88199b0-fa7e-5629-b99d-0a9f247bf04f | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
bd9081fa-d702-54a2-a9c0-0a906532f96c | note | ○ Geometry tolerances as follows:
fe632b7b-645b-5abc-90de-8e5879fb5866 | note | — Centreline location: +/- 3mm
ff2bfb2c-a3f1-55f3-9fdc-331c4615771b | note | — Level: +/- 3mm
3f734a3e-b822-5e8a-b646-b630742a7b32 | note | — Line measured (>10m chord): +/- 3mm
653b2ecd-b1b7-521b-b7e5-e99dda31bd74 | note | — Twist (3.5m chord): +/- 2mm
c46a3278-50e6-5091-9a7a-ac3cdb42d1c6 | note | — Cant: +/- 3mm
f38a2684-553a-5c7e-a481-744f83edab8b | note | — Gauge (open track): +3mm, -0mm
44634981-e093-5751-a52e-bde5f269e2ba | note | — Gauge,Turnouts (opposite crossings):+2, -0mm
3c3386ee-51f1-5f96-9c57-4831ddf587d6 | note | — Gauge, Diamonds and ‘H’ Crossings:+2, -0mm
efeea9e2-cc60-528d-a7fd-82f0ca839165 | note | ○ Note: Cant shall be applied uniformly over transitions
d089fa37-38f6-5475-ad15-4c6f85db2a7d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
02da3ed1-0f5d-5908-b4d9-6e8d2adc8fec | note | INSPECTION/TEST METHOD: Visual Inspection
89281f90-63ea-5ce4-ada0-9ed0e78a1b72 | note | RECORD OF CONFORMITY: Completion of track charts
b5e6e2e3-0690-5af0-bba1-6d43f0fcb1cd | note | HP
806a84ae-f7c9-5e87-9983-15bfd5889529 | note | RESPONSIBILITY: Fulton Hogan Engineer
b427c87b-02e0-51ad-ba29-8d1f16cb1665 | textbox | Date Completed:
5ca0b95f-9871-490b-900e-9145ed36a5ab | signoff | AUTHORITY HOLDPOINT
95cb3201-e8c7-456d-8c3d-2636eb0ab619 | checkpoint | 2.4 Fastening of Rail
eeca0b49-9328-5375-9de9-9a774dd5e838 | note | FREQUENCY: Each Lot
43569e6d-7ac0-594d-a9b2-bf2179ad8b32 | note | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to rail with approved jewellery and rail clips.
29421a0d-5d87-5341-8669-3a89be876a5d | note | ○ Clips shall be installed with panpuller or equivalent.
ae78e5a7-f34a-525c-b488-8ad9e77cfc7d | note | ○ All fasteners shall be sealed as per agreed method with Yarra Trams.
c9867bc8-6e22-579d-a7e5-558230588b4e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.3
c1986035-2970-52ee-b432-c643087a80a9 | note | INSPECTION/TEST METHOD: Visual Inspection
9bc00a9c-d053-5ce6-bd56-b9bd148dd731 | note | RECORD OF CONFORMITY: This ITP Signed Off
6fd71d51-4f42-59ca-89d0-2856e681a92d | note | WP
498a8be0-b2fc-50b8-bd70-db879069146c | note | RESPONSIBILITY: Fulton Hogan Engineer
4f977057-58db-5b60-99a5-4d2274a2ccaa | textbox | Date Completed:
1948c8f9-b358-489c-aff2-8a8fc6678293 | checkpoint | 2.5 Tampering of Ballast & Sleepers
407667fb-2db3-5726-8001-d2fc58fea894 | note | FREQUENCY: Each Lot
abbeb3e2-cd9e-58f4-8bf8-d793f89bc6bf | note | ACCEPTANCE CRITERIA: After track construction and prior to tamping, cribs and shoulers are to be filled to top of sleeper with extra ballast.
f73e6abd-9814-571a-90e0-ad85ed8a9125 | note | ○ All sleepers shall be lifted, lined and tamped after installation and fastening of rails.
6dcbafa1-bcfc-502c-af9b-0b6788ee9934 | note | ○ The depth of ballast following tamping shall be 200mm from top of sub ballast to bottom of sleepers.
ed2dd616-8049-542a-be09-aca8755db463 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
973f170d-8fb8-5b3a-8ffc-7a4b3fa4c969 | note | INSPECTION/TEST METHOD: Visual Inspection
6c52e5a4-eddc-573a-8a88-c12c76c1cdf3 | note | RECORD OF CONFORMITY: This ITP Signed Off
5ca23d36-17bf-57b6-90fe-5ded0bdb1f3f | note | WP
9106cd3d-d77b-58d0-b8d4-dadd6ad43b43 | note | RESPONSIBILITY: Fulton Hogan Engineer
9f4aea59-e037-5950-a04e-26f6bdc36deb | textbox | Date Completed:
7f62a049-cf7e-451c-b185-b3654f7f215b | checkpoint | 2.6 Rail End Preparation
1032f75b-2e3e-5840-bc41-8fd327a107c6 | note | FREQUENCY: Each Lot
8a877717-bd6f-5b24-a677-f20d61c9b395 | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
236674cc-8623-551f-bf73-336e58841197 | note | ○ Minimum closure length from proximity of welds shall be 3m
047fd721-59e0-5a94-8ca3-154abbc7cdd4 | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
9668d39d-11fe-5dcc-a138-0771cb7bd8cc | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
c855c942-9030-5b4a-b1cf-3615dd402577 | note | INSPECTION/TEST METHOD: Visual Inspection
f08464a5-f776-5fec-8b48-91b43de2000a | note | RECORD OF CONFORMITY: This ITP Signed Off
da5807e2-5d65-5efd-900d-18871d120bac | note | WP
7e953ede-a1a9-58e9-a5eb-c4c212c98ddd | note | RESPONSIBILITY: Fulton Hogan Engineer
339e724a-c92d-5bf6-b050-d9ee8ea14e3e | textbox | Date Completed:
0967d868-554a-4b1b-8baf-a3aebc21e18e | checkpoint | 2.7 Welding of Rail
f86bbe93-69ff-5a6b-8ac8-e32826477da0 | note | FREQUENCY: Each Weld
759d342c-f28e-5508-8328-d675d65cebf4 | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
39e5ba2f-ada4-5c8d-a500-f02cb85f227f | note | ○ Maximum skew at square joints shall be 65mm
5efd60a8-2f28-5d8f-8cfb-e6e0ab3a96ed | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
93be408a-0e21-5b1f-94ab-f748c1b3186a | note | ○ Welds shall not be within:
47e99ea1-3868-5a0f-b6e6-b5866806c13e | note | — 3m of another weld
d242a474-cfb9-585e-bc12-49fa00930e92 | note | — 3m of a rail end
c0cefc4d-bd4b-5ce6-bfcc-05d5759665de | note | — 1.5m of a glued insulation joint assembly
57626486-1959-5b2b-8742-508dbc364dc2 | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
4c2527fe-ee34-53a6-99aa-3f55a17cc8ca | note | ○ Weld Return forms shall be completed by qualified welder
3b7fc8cb-04e4-5930-83f3-8e4c28a2fc48 | note | ○ Welds shall be grinded after 1 hour
43b7c099-2cbc-54bc-ac66-5bdc84a2b07a | note | ○ Welds shall be free of water
d72d73e7-21bf-5805-931b-6f5b64bcd1b4 | note | ○ Post grinding, welds shall be cleaned for visual inspection
d6aba3f3-edbe-50fc-93ad-3f5334024e69 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
7899b76f-89bc-5083-aa87-738a73511df4 | note | INSPECTION/TEST METHOD: Visual Inspection
90d11b50-be81-57a9-9f61-4607088d4029 | note | RECORD OF CONFORMITY: This ITP Signed Off
95afc2c0-4c63-56be-9b22-ec23b6c09f5a | note | TP
a5d13405-2e5f-5956-893e-0106d53c8114 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c7c213a-cc02-5501-9672-2253020fe793 | textbox | Date Completed:
b0b17074-462b-45ba-982e-820025779713 | checkpoint | 2.8 Grinding & Cleaning Welds
07a49999-8b03-54b8-a1d6-5aa4043e4a5f | note | FREQUENCY: Each Weld
fe51fee8-b478-51fb-9adc-5804b03113eb | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
a12b62b3-489e-5921-bd3f-585ae7500e2e | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
19ce9612-0959-544e-8206-9079569c046a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
a246c88c-4eb0-5064-9b77-67b8c65e9e37 | note | INSPECTION/TEST METHOD: Visual Inspection
4e4f6181-302a-5b84-8f7a-c0b6c90ba75f | note | RECORD OF CONFORMITY: This ITP Signed Off
9ed0534c-9f76-5c3e-ab17-866ef5a3f3bf | note | IP
8fff8b96-b58f-55e6-bc03-191203b4ff7f | note | RESPONSIBILITY: Fulton Hogan Engineer, YT
157dddb6-0c6a-59c0-8067-4be44fb92529 | textbox | Date Completed:
2d82d282-8689-428f-bebe-db52f02dee25 | checkpoint | 2.9 Installation of Check Plate
50d6116c-b7e9-5477-ac4a-d19b603626b6 | note | FREQUENCY: When required
c2bf161a-4a95-5dba-a6e4-4ce4363933da | note | ACCEPTANCE CRITERIA: Where Tee Head Rails are used at special works, crossovers, or on curves up to 325m, check plates shall be fitted in accordance with Table 2 of the Yarra Trams Infrastructure Tram Track Construction Standard.
05f56c75-65fb-5c13-a9e7-246ac2b744e0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.7
fa47cb20-0354-588c-8d98-bb755dbd4ba5 | note | INSPECTION/TEST METHOD: Verify
32324e1d-6890-5a0f-bc53-100ef1d2d7c5 | note | RECORD OF CONFORMITY: This ITP Signed Off
7cc84a2c-8ec4-5095-a442-32aa381fcd06 | note | IP
f9086b64-e751-5dd3-8aee-80cbd65e06a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
c11ef54f-a105-5de3-88f5-364db656d553 | textbox | Date Completed:
15c5180b-2516-4b58-80d9-655525311b25 | checkpoint | 2.10 Track Adjustment
51afb6d2-1f19-5050-9fdf-9442b80f94b1 | note | FREQUENCY: When required
dd508c32-1c26-5cc2-b8f0-55a28ea243a9 | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress.In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
5b4d6b60-cbe8-5ad6-aa3d-fcb2ad58da63 | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
3b095f2e-dec8-5238-8f55-1bcd8ab10357 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
804ea9ec-b8f3-5047-8902-3c0e7b90da01 | note | INSPECTION/TEST METHOD: Visual Inspection
97449578-7bd0-583b-9503-5c338f763aa2 | note | RECORD OF CONFORMITY: This ITP Signed Off
f3bd1d73-8589-5331-9d00-bd5ac2dbd512 | note | IP
80e92fc5-1710-52e8-9b35-70bd2a5ce12e | note | RESPONSIBILITY: Fulton Hogan Engineer
16686df0-9c9e-5449-a32d-94eb26683556 | textbox | Date Completed:
380cf6a8-458a-4807-bff7-4762ea49173f | checkpoint | 2.11 Track Bonds
117ba198-99e9-53d0-baca-de3e35b36d07 | note | FREQUENCY: Each Lot
8619af85-47a3-524e-95b8-68431546e4d6 | note | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
fcee26a3-40d9-5099-ae7c-695ff5c03035 | note | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
703b9425-06cb-5f5f-a32c-ddf614e2cb35 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5, Design Drawings
f5249306-1509-52bd-989d-7b9be1c8b5dd | note | INSPECTION/TEST METHOD: Inspection / Test Method
b40b47a8-de4a-5ead-8eb8-38d879972a7b | note | RECORD OF CONFORMITY: This ITP Signed Off
36e6b043-9bc8-5398-b35a-c37287204484 | note | IP
e58016f5-cfd7-5182-be99-928ebba2ef44 | note | RESPONSIBILITY: Fulton Hogan Engineer
b578e6f9-18b7-5cdc-9f83-192bf898c00a | textbox | Date Completed:
6f9404de-44c1-43d9-9917-98f91aed589d | section | Testing
84ae1526-1591-4a44-841c-8fce85870ab2 | checkpoint | 3.1 Track Testing
0ccf32f7-e795-5882-a0dc-f87085b41fdb | note | FREQUENCY: Each Weld
65ca3575-c55d-556c-ab2a-8ae65a057735 | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator
233cbe62-2ea0-513c-85cf-fa2e40eae47f | note | ○ Failed welds shall be cut out and replaced
5c481a51-585f-52a4-bd81-7b98769b59a0 | note | ○ Testing documentation shall be recorded and supplied to the superintendent
7e5fd57b-a70b-58a1-bc0e-90ffbc25610b | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
eea452d6-693b-5fa2-8789-4eb3ce4fb7de | note | INSPECTION/TEST METHOD: Inspection / Test Method
0a41dbfe-3f94-5ace-95a5-57731253561a | note | RECORD OF CONFORMITY: This ITP Signed Off
7ce7ecfe-3656-5d23-8674-9714fa8c4a02 | note | TP
f71724bd-06df-5ab2-9302-f314b02eef22 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
f7f84ace-34bf-5312-8b56-e654a0a8a6b7 | textbox | Date Completed:
e4e0416d-0c5d-42de-b7b4-eea4f880621a | checkpoint | Final Inspection
be8141fc-6314-5b36-afd0-3c07be9e40ce | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3554718b-1cf8-591b-9ff3-fba79e4f13a0 | textbox | Print Name:
ee7b0eb1-fc7c-5fea-b641-b5855ef219eb | textbox | Position:
a4c4cd58-92c2-5598-85f4-acdc251631a5 | textbox | Date:
179ecd37-58dd-4ead-98fc-740122375829 | checklist | ITP-024 - De-stressing Rail Rev1 | itp | ITP-024 - De-stressing Rail
0c5e2b50-c40e-4656-9d4e-f0deed5456e2 | section | Design and Submissions
309d9746-401d-4bf5-9605-ce61fdb4c26b | checkpoint | 1.1 Check for correct documentation
81d77a7f-51be-57f0-8eea-77a2df91cede | note | FREQUENCY: Prior to commencing any activity
02265f3c-440d-5b99-bef3-996a0c10a363 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
950e053f-8ee6-5521-9de7-87f5b9928369 | note | — using the correct and complete set of drawings
ddb538ca-c288-5e66-b91b-4093ae06ba8b | note | — all drawings are the latest revision
61b10909-c130-557a-8a51-cb98b2077707 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0c4eb24a-8b6a-58aa-b57d-2f01ddd0fa26 | note | INSPECTION/TEST METHOD: Visual inspection
8cf3c42c-2300-5f45-88de-3ffc8a3e61cb | note | RECORD OF CONFORMITY: This ITP signed
d828009e-6e1d-503b-9871-a79b0c8e6df8 | note | HP*
0b2c256f-28ed-5419-b969-ec5cff5364c2 | note | RESPONSIBILITY: Fulton Hogan Engineer
c647ef7c-b8cb-5e81-8415-90cee8d1ec6d | textbox | Date Completed:
f3a2b09a-ecb8-45b3-b792-0ee5a40a566e | checkpoint | 1.2 Implementation of all measures and controls
82c74b98-385d-5694-913f-485cfba037d9 | note | FREQUENCY: Prior to commencing any activity
bc7af811-24ab-5a09-b034-c24808c2c497 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
5f2aa078-7208-574b-8350-8c2b07aea989 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0131886d-97f6-5b61-8798-69d65c8ce5c9 | note | INSPECTION/TEST METHOD: Visual Inspection
25d69059-1946-5391-9cd2-b33b42e203f0 | note | RECORD OF CONFORMITY: This ITP signed
7a847005-9fde-5532-8057-5e4d0ac2923e | note | HP*
1be7e727-71f1-5733-9ad9-cd2b5ab4e5a7 | note | RESPONSIBILITY: Fulton Hogan Engineer
5e7022cc-49ca-55ee-bce7-26904487f902 | textbox | Date Completed:
ac6f5351-b6d7-4685-9e06-5e0fb5d94f87 | checkpoint | 1.3 Stress Free Temperature
6aac2b4e-750a-56d1-9ee5-32389cd48dcc | note | FREQUENCY: Each lot
3ce6b38e-012c-5e42-9978-4e6ba94421a4 | note | ACCEPTANCE CRITERIA: To ensure lateral stability, ensure that the stress free temperature of the rail conforms to the design value (38° C).
ae38e300-ece6-51bf-8a70-b05d9f29a6ec | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.1
b949ec91-eace-5822-ad68-e272a97ca0b6 | note | INSPECTION/TEST METHOD: Verify
d4e77092-a29f-5dcd-a683-42ff57d3dfc1 | note | RECORD OF CONFORMITY: This ITP signed
557ee536-ca56-5e7c-a708-4a6137ea5aa8 | note | IP
d0bdced7-3089-51d7-a83c-b33fbf6d4754 | note | RESPONSIBILITY: Fulton Hogan Engineer
371d071e-9395-5173-9e87-97115534a796 | textbox | Date Completed:
302be5d8-8a3a-4035-b4f6-ddc12455deba | checkpoint | 1.4 Module Lengths
7a98d671-11d8-57f2-9b0e-5a6be237e22b | note | FREQUENCY: Each lot
8941c119-a4d0-543b-b3af-51ffb9db336f | note | ACCEPTANCE CRITERIA: The preferred stress adjustment module length is 330 m. The maximum stress adjustment module length is 440 m on timber sleepers and 500 m on concrete sleepers.
8e570a9e-aace-5cec-bbbb-6b2ace7ed6a8 | note | ○ Shorter modules are permitted if the distance between fixed points is less than 330m
2c886cef-8747-5d3e-967b-bc391732ddbb | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.1.3
582e3c33-4602-5596-beff-fccde42ac90d | note | INSPECTION/TEST METHOD: Verify
c13737e8-5cbf-500f-af59-c3f0daf8fe11 | note | RECORD OF CONFORMITY: This ITP signed
7d70baaf-9492-5b4c-8389-bd230616dbad | note | HP*
e6a8f293-e724-576d-9c5f-b22585642350 | note | RESPONSIBILITY: Fulton Hogan Engineer, YT
4f2bd9fa-cef0-5b1b-bbaa-4cabd2922f8e | textbox | Date Completed:
eece87d3-de99-4d19-b07f-9b1be31275ed | checkpoint | 1.5 Closing Weld
4a15fdc8-d28e-5365-912b-769d91903c1c | note | FREQUENCY: Each lot
0e76aea6-eafd-5c01-89d4-66f4901e85fa | note | ACCEPTANCE CRITERIA: Closing weld is to be located as near as practicable to the centre of the module length (within 13.7m of centre)
b0e191f9-4057-5ddd-856e-db10ba195f9d | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.1.4
0bce1f88-5efa-58e9-bc67-eda36ee022b5 | note | INSPECTION/TEST METHOD: Verify
b69321e2-dec0-5cf5-854a-c3c698867333 | note | RECORD OF CONFORMITY: This ITP signed
691da2b3-77cc-59bd-84c5-9c462c255a00 | note | IP
7ac43246-feab-5c0f-bfc3-4f99d88447d1 | note | RESPONSIBILITY: Fulton Hogan Engineer
ac47e6d0-bb1e-5a75-8c37-cd5816b3a840 | textbox | Date Completed:
8fa921d6-8ad2-4012-a811-772432693d82 | checkpoint | 1.6 Weld Record Sheet
e1d684a9-17d4-57ab-b238-4dce1e353f37 | note | FREQUENCY: Each Lot
163b6604-0cb1-56a8-95d3-2031416ca6d1 | note | ACCEPTANCE CRITERIA: Each weld must be recorded on the weld record sheet
d4a8d6c9-9c17-5a63-bd09-203d45f86780 | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.1.7
d7a2b644-986e-55f0-9d62-e4188a96e94d | note | INSPECTION/TEST METHOD: Verify
ad599f66-7589-505e-b289-0f0344bf11c0 | note | RECORD OF CONFORMITY: This ITP signed
673f1691-c2b9-51da-b41c-a74323438701 | note | IP
31c1fed6-0fc9-54d0-aa45-ad70fe98be82 | note | RESPONSIBILITY: Fulton Hogan Engineer
89eef09a-d209-54b6-a0ca-3ceaa15a1fb2 | textbox | Date Completed:
5ee6de2b-2182-4cce-942c-21e7150b5a3d | section | Preparation
dfa22a86-b511-47fb-86c2-c1bf8669d338 | checkpoint | 2.1 Set up closing weld
14eb76d8-caef-5cd1-a033-67d0af5c046e | note | FREQUENCY: Each lot
c530bf2c-8db6-5ae3-abcb-03cf08077905 | note | ACCEPTANCE CRITERIA: Mark location of closing weld.
bfe8d74a-540c-536d-a651-3311aa5a2202 | note | ○ Punch mark the field side of the rail head in two places a minimum of 2m clear of each side of the closing weld.
c9bf673c-fc5e-53c5-84ba-5dbcc7b42b4e | note | ○ Measure the distance between the punch marks and record on the weld record sheet
b9b2a5bb-e5fc-5043-ae46-acdf64b6fd8a | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.2
1db11df9-ea00-57e1-82a4-6d1da7771f5d | note | INSPECTION/TEST METHOD: Verify
fc6762ab-6605-588b-bff5-bfed7bc29253 | note | RECORD OF CONFORMITY: This ITP signed
77f87b48-e96f-5200-85ef-451b3531ada5 | note | IP
a8cf8cbe-7427-5194-8c9a-6c4bb54ef356 | note | RESPONSIBILITY: Fulton Hogan Engineer
b079af95-d055-5ba3-8359-d5ef701b2fae | textbox | Date Completed:
bbda0ed4-3295-4f7b-9cd4-a27f9374f372 | checkpoint | 2.2 Measure pre-existing (initial) gap in rail
8756a98e-dc82-527c-8321-ac369c6b41ee | note | FREQUENCY: Each lot
a10a6c0b-a9f8-507c-b4b5-9f70175212e1 | note | ACCEPTANCE CRITERIA: If no gap exists, record zero as initial gap.
eec354b4-5dff-59f2-8ace-8bc392aab610 | note | ○ If there is an initial gap (incluing zero), measure and record the rail temperature at the time of preparation.
a58dfba0-68b0-5532-947e-5f207b9b017a | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.2
f0290f37-030c-570d-b2d6-20a652e92c98 | note | INSPECTION/TEST METHOD: Verify
7925d3d3-8c9d-5bd8-aa7b-79e7225c1284 | note | RECORD OF CONFORMITY: This ITP signed
734165db-74db-5ff0-b630-e8847eb350df | note | IP
28d1ff26-9d10-552b-8459-10b560fb179b | note | RESPONSIBILITY: Fulton Hogan Engineer
4e658e46-ad2e-5801-861c-db028a125291 | textbox | Date Completed:
16430253-7141-4d35-a90a-9876c3212c36 | section | Stressing Adjustment
127eb686-5748-4b7a-b9be-13dd596547af | checkpoint | 3.1 Creating the module length
cfe4c401-f0b0-5214-a7ce-3c03a70c6f48 | note | FREQUENCY: Each lot
e6c1a32b-41da-57b1-9e6c-803963cfee49 | note | ACCEPTANCE CRITERIA: Measure and record the module length.
fb1de58d-b85d-5dd2-a6d7-4be9718c015e | note | — Provide anchor blocks as shown in Figure 15 and Table 18 of NIST-2650
398f8223-32d6-5c36-b1a3-6d78a08fd1e7 | note | — Remove all clips and fastenings over the module length, to ensure free movement of rail
1ee60422-72d7-5917-9de3-a40a47627a99 | note | — Place a chalk or paint mark through the sleeper at each end of the module length (to monitor for any rail movement extending beyond module) and the quarter points of the module (to monitor for correct rail movement)
2c78db92-2c81-513c-b8eb-18ff467d568d | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.2
2e7c260c-9cd0-509a-91c4-6661a86e049d | note | INSPECTION/TEST METHOD: Verify
5ecc63de-6a88-5027-a9b5-550cdc195ce6 | note | RECORD OF CONFORMITY: This ITP signed
3e9343ba-c882-5704-b3aa-6f408ece605c | note | RESPONSIBILITY: Fulton Hogan Engineer
a731eb0e-4485-530a-a2fd-7b835ac922dd | textbox | Date Completed:
1e4e3136-41ba-468e-b53a-d191830d7dcb | checkpoint | 3.2 Destressing the rail
017d22f3-e9e8-52a7-96eb-eacc264d3a24 | note | FREQUENCY: Each lot
34a26028-e7bd-5212-b0fc-13afa6bd25aa | note | ACCEPTANCE CRITERIA: Ensure module is in a stress free state by using the tensor to close the gap by the distance set out in Table 19 of NIST-2650
e963c2a1-b518-59a3-a6cc-61e33e8bd5ba | note | — Lightly tap rail on the web at frequent intervals until the gap stops opening
ba13c568-ef70-5a2f-8a24-33d851c777d2 | note | — Check that sleepers do not lock up
f80be0da-fc29-5205-a3fb-730aaa4ebdae | note | — Check the quarter points to ensure rail is moving freely
411fdf5b-72c4-5497-8416-e29a3e7ec691 | note | — Check to ensure there is no movement of the rail at the extreme ends of the module
94fa684f-0f34-5a2b-b6c1-26c0bd0d5b62 | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.3
e6242fa2-270d-50e0-b4e1-5e01f4eac53d | note | INSPECTION/TEST METHOD: Verify
6e85a015-0dc0-5893-a6ba-7fda558d9e40 | note | RECORD OF CONFORMITY: This ITP signed
db5f060a-e36e-5f7e-a8c8-c394b0633609 | note | RESPONSIBILITY: Fulton Hogan Engineer
3a043e9a-da42-5cce-9815-ce72da2a70fc | textbox | Date Completed:
f6bb3c39-f0a7-4416-9f0b-24b4d2d07144 | checkpoint | 3.3 Punch length
8362c573-a337-5842-ae56-b2c590b02156 | note | FREQUENCY: Each lot
67eff8e8-eb5f-5724-a4cc-0a2a867f59f3 | note | ACCEPTANCE CRITERIA: Upon completion of destressing process, record the distance between the punch marks "Punch Length After Destress"
68dc95c0-fde2-5e06-b823-fd18a04ae3e3 | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.3
6e48ce0c-9e55-5f96-b101-a658a65f6c12 | note | INSPECTION/TEST METHOD: Verify
f11292b3-896f-5e77-adca-a00d7234bbf7 | note | RECORD OF CONFORMITY: This ITP signed
b7b52969-1690-5bd0-b038-486770d48105 | note | RESPONSIBILITY:
a86d22f5-6e03-5019-947c-e8aa21d61b19 | textbox | Date Completed:
83d5ce54-d501-4c64-a96b-141976324c07 | section | Closing weld
0d000eb8-8a35-4393-b99a-0a2a0f5f8957 | checkpoint | 4.1 Rail temperature
078fe60c-f11b-5bae-974a-12f3da44c7b8 | note | FREQUENCY: Each lot
bf108e81-6ea6-5000-9896-475edc4d262d | note | ACCEPTANCE CRITERIA: Measure the rail temperature and record it on the Weld Record Sheet. If rail temperature exceeds 40° C, provision of stress adjustment gap and tensing of the rail is not required.
6fd33248-f635-50bb-bc2e-ff81e14156b7 | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
d2711680-465b-5718-b5a2-c5a3fc5bbc78 | note | INSPECTION/TEST METHOD: Verify
b9f36131-3c1f-57bf-8ed6-b889cf4c9735 | note | RECORD OF CONFORMITY: This ITP signed
5537a3a7-f990-590e-8999-3d4eff2f97e4 | note | IP
e4dfde6c-b7bb-5fb0-88f7-be8cfccb4618 | note | RESPONSIBILITY: Fulton Hogan
0e5a9ee1-47c0-533b-928a-27904c7fdb78 | textbox | Date Completed:
9a731ce7-7218-4258-a7ce-9f5ace31a8a4 | checkpoint | 4.3 Tense gap to weld gap
08cf510f-6810-5b32-8ad9-e18858c6b2c3 | note | FREQUENCY: Each lot
dc4434cd-04a5-5c61-b11d-65821624967b | note | ACCEPTANCE CRITERIA: Cut the end of one rail to give the required gap, and tense the rail to provide the weld gap
fc89b2e9-1098-56ec-8115-d485cde32e86 | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
41c07a80-bcfa-5c1d-8496-9e82a71d7bfb | note | INSPECTION/TEST METHOD: Verify
054d5891-3b9e-59e7-be2b-b1f0b80c408b | note | RECORD OF CONFORMITY: This ITP signed
26614cb1-c4f3-5685-a764-64a88a76b753 | note | IP
8c44302b-2d15-5f7d-a6f6-b8cda3541257 | note | RESPONSIBILITY: Fulton Hogan
ef965268-1970-51c5-862f-b37e60f8f93a | textbox | Date Completed:
dcd029c4-f896-45a4-b689-b62518855daa | checkpoint | 4.4 Carry out weld
bd1eabce-48e5-5dff-b46f-304c1cf6c241 | note | FREQUENCY: Each lot
c619d0af-2f57-5595-9f38-d96e711f18c7 | note | ACCEPTANCE CRITERIA: After completing weld, wait at least 20 minutes before removing the tensor
da3f04cc-b05c-5e61-86d0-3f4a84922bcd | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
aa1ac984-3eba-584f-824f-f1ca51e0b7c0 | note | INSPECTION/TEST METHOD: Verify
7ffbc76a-ceb1-55bd-9ad3-2e837ec7877a | note | RECORD OF CONFORMITY: This ITP signed
e88f930f-4809-5541-afa8-3545bbbee830 | note | IP
deb8cfd6-de0e-5498-b668-bd5f3a71dd45 | note | RESPONSIBILITY: Fulton Hogan
c50ab415-c6e9-5674-bb4a-d4e25d6624fd | textbox | Date Completed:
b4df3f9d-2061-4cff-8688-b51e20a365bc | checkpoint | 4.5 Stress distribution
4dcdac94-241e-5e98-b2ee-165c240ce287 | note | FREQUENCY: Each lot
2566788e-e792-5eb7-aee4-14dccc6f7f3f | note | ACCEPTANCE CRITERIA: When the weld has cooled, tap the rail to distribute stresses evenly and reapply clips to the module
60b42417-9003-5470-9d9e-ef6b3b5a6bd1 | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
1984f56d-d875-5aaf-8b62-311aa0bd985d | note | INSPECTION/TEST METHOD: Verify
d4c01312-fe42-5ef7-b187-657594d47ec8 | note | RECORD OF CONFORMITY: This ITP signed
469fc8ba-150a-50ea-b2ce-f6151af77b5a | note | IP
c38b97e6-faff-5cc4-bc7a-f0ce825498ca | note | RESPONSIBILITY: Fulton Hogan
b1839294-1f92-52ae-a41e-63ad1a568e5b | textbox | Date Completed:
238eebac-20ae-4dde-b25f-ae283fa095ac | section | Completion
3339523c-e985-4cf6-b1be-8294f221052f | checkpoint | 5.1 Punch marks
d6b7350a-5890-54af-aa3c-ffb653b826ef | note | FREQUENCY: Each lot
f221b2ff-4ed1-5489-a680-597a1a81d2be | note | ACCEPTANCE CRITERIA: Remeasure the distance between punch marks and record on weld record sheet
af43341d-81e7-5284-a1e4-e28ca364a71a | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
8fc5d499-c732-5159-a4f9-28886d41b3b2 | note | INSPECTION/TEST METHOD: Verify
c381d07e-571f-5d5b-a6bd-719d87f6af52 | note | RECORD OF CONFORMITY: This ITP signed
2e3f4982-604c-5703-a196-9f8eca085066 | note | IP
3b669a8f-43cf-5ddb-a4b7-73c58cc7a2be | note | RESPONSIBILITY: Fulton Hogan
d30c9929-70b0-5cc5-9a72-0f9579266633 | textbox | Date Completed:
8fad3ede-51ae-4026-813c-19c4f4e20df3 | checkpoint | 5.2 Quarter points
48788f8e-11a0-57f4-bc0e-50fdb94d6cd4 | note | FREQUENCY: Each lot
62e7e067-7c1c-5fd3-9640-2214e7987077 | note | ACCEPTANCE CRITERIA: Measure and record the movement of quarter points
bc4b1724-cf4d-5975-aba5-94797624c0f1 | note | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
5133334c-d2ae-58c8-80fa-c3d069369328 | note | INSPECTION/TEST METHOD: Verify
9548a214-2e24-5b96-8e2a-757402d44990 | note | RECORD OF CONFORMITY: This ITP signed
cf259866-0eb0-5f75-a5cb-0ef7eb75c72e | note | IP
85d6ed38-4c68-51f8-b5b1-6e998e1dc4db | note | RESPONSIBILITY: Fulton Hogan
cf0d5454-ec2e-561e-9676-42176bdd6702 | textbox | Date Completed:
7d16af8e-173f-4933-8d31-1237a7fd4417 | checkpoint | Final Inspection
33423a0d-20fd-55a5-9788-c2bf668a7cf8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9fa8a2e3-f850-5f55-a4d9-73e262fc12df | textbox | Print Name:
6ae63cac-23f1-5755-aafc-1b033b45cb07 | textbox | Position:
ac10e2b8-2150-5d17-b866-17bd9a5ee440 | textbox | Date: