## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-281-RAIL-PSD-Rail Permanent Fencing & Gates
ITP Description: |  | PSD-Rail Permanent Fencing & Gates
Discipline (e.g. CIV/STR/RAIL: |  | 281-RAIL
Revision Number: |  | 0
Revision Date: |  | 2025-06-06
ITP created by: |  | Jake Argentaro
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP for Progress Street Project
Inspection & Test Plan - Rail Delineation Fencing
|  |  | Doc. No.: ITP-281-RAIL-PSD-Rail Delineation Permanent Fencing | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-06-06
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings: MRP-DPK-091-00-CPW-0063 VicTrack STD_C0031 Installation of ARC “Garden Style” Fence Typical Details AS 1725.1-2010: Chain Link Fabric Fencing. A1524 Railway Corridor Fencing Standard Rev 3. | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Concrete Footings Mix | IFC Drawings | VicRoads Compliant Mix, Minimum of 20 MPa compressive strength as per IFC drawings and nominally VR330/32 with 30% SCM per DNG_C9246 Note 5. Enter: Teambinder Material Approval number | Document Review | Each Mix | HP | SE/Site Supervisor | Material approval in TeamBinder This ITP Signed Off Certificate of Compliance
2.2 | Steel components | IFC Drawings AS41000 AS1163 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. | Document Review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Preliminaries-Documentations
3.1 | Excavation for post foundations | IFC Drawings | Excavation for post foundations must not undermine track and comply with PTDT requirements. Follow asset owners guidelines for work around their service. Excavation must use Non Destructive Digging in the rail corridor subject to minimum mechanical clearances to underground services. | Visual | Each element | IP | SE/Site Supervisor | This ITP Signed Off
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, post locations, refuge bays (where applicable). Offset checked against the running edge prior to installation of posts against MTM Transit Space Clearances Standard. Engineer to verify alignment of posts using string line or equivalent. | Measure Visual inspect | Each element | IP | Surveyor SE/PE/SPE | This ITP Signed Off
5 | Construction / Installation Activities
5.1 | Ground Conditions | IFC Drawings | All post foundations/ beams to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. | Visual | Each post | IP | SE/Site Supervisor | This ITP Signed Off
5.2 | Post Foundation(s) | IFC Drawings | Fencing Post Foundation - as per STD_C0031 - 600mm Depth - 200mm Diameter - 2405mm c/c Spacing Single Lead Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing. - 1,000mm Depth - 300mm Diameter - 1,500mm c/c Spacing 8.0m Wide Double Leaf Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing. - 1,400mm Depth - 400mm Diameter - 8,000mm c/c Spacing Drop-bolt footings W300 x L350 x D350 for closed-gate position and 150 dia x 350mm deep for the opened gate position. | Measure | Each footing | IP | SE/Site Supervisor | This ITP Signed Off
5.3 | Concrete Footing | Site Sampling & Testing Procedure 610.16 (b) | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. | Test | Each element | IP | Concrete Tester Foreman SE/PE/SPE | This ITP Signed Off Concrete Pour Record
5.4 | Post Installation | IFC Drawings | Fencing: Maximum fence post spacing to be 2405mm Max. post height 1800mm above ground level Vertical Tolerance: ±20mm from the design line. Single Lead Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing. - 50 x 5 SHS frame with 75 x 5 SHS Posts w/ End Cap 8.0m Wide Double Leaf Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing. - 100 x 5 SHS Posts w/ End Cap | Measure | Each post | IP | SE/Site Supervisor | This ITP Signed Off
5.5 | Fence Panel Installation | IFC Drawings | Galvanised fence panels 1820x2405x55 to be fixed to fence post with 25mm U-clip, using TEK screw. A minimum of 2 brackets must be used and fastened to each post. Minimum ground clearance under panels 50mm Maximum ground clearance under panels 80mm | Visual Meaaure | Each element | IP | SE/Site Supervisor | This ITP Signed Off
5.6 | Gate Panel Installation | IFC Drawings | Single Lead Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing. - 1.8m high weld mesh fence panel with heavy striker plate, opening to allow access from both sides, 5P locked. 8.0m Wide Double Leaf Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing. - 1.8m high weld mesh fence panel with gate long shoot bolt locking mechanism with 5P lock. Minimum ground clearance under panels 50mm Maximum ground clearance under panels 80mm | Visual Meaaure | Each element | IP | SE/Site Supervisor | This ITP Signed Off
5.7 | Bracing | IFC Drawings | 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners | Visual | Each element | IP | SE/Site Supervisor | This ITP Signed Off
6 | Post-construction / Post-installation Activities
6.1 | Fence Height and Track Clearance | IFC Drawings | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | Measure | Each lot | IP | SE/Site Supervisor | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /