## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-281-RAIL-PSD-Rail Delineation Permanent Fencing | itp |  |  |  |  | ITP-281-RAIL-PSD-Rail Delineation Permanent Fencing Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-281-RAIL-PSD-Rail Permanent Fencing & Gates
label | ITP Description: PSD-Rail Permanent Fencing & Gates
label | Discipline (e.g. CIV/STR/RAIL): 281-RAIL
label | Revision Number: 0
label | Revision Date: 6/06/2025
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Non Dependent
label | Reference: IFC Drawings: MRP-DPK-091-00-CPW-0063
label | ○ VicTrack STD_C0031 Installation of ARC “Garden Style” Fence Typical Details
label | ○ AS 1725.1-2010: Chain Link Fabric Fencing.
label | ○ A1524 Railway Corridor Fencing Standard Rev 3.
section | Preliminaries-Materials
checkpoint | 2.1 Concrete Footings Mix
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: VicRoads Compliant Mix, Minimum of 20 MPa compressive strength as per IFC drawings and nominally VR330/32 with 30% SCM per DNG_C9246 Note 5.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Mix
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off, Certificate of Compliance
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Steel components
label | REFERENCE: IFC Drawings AS41000, AS1163
label | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | METHOD: Document Review, Visual and Measure
label | FREQUENCY: All elements
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
section | Preliminaries-Documentations
checkpoint | 3.1 Excavation for post foundations
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Excavation for post foundations must not undermine track and comply with PTDT requirements.
label | ○ Follow asset owners guidelines for work around their service.
label | ○ Excavation must use Non Destructive Digging in the rail corridor subject to minimum mechanical clearances to underground services.
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays (where applicable).
label | ○ Offset checked against the running edge prior to installation of posts against MTM Transit Space Clearances Standard.
label | ○ Engineer to verify alignment of posts using string line or equivalent.
label | METHOD: Measure, Visual inspect
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Ground Conditions
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: All post foundations/ beams to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | METHOD: Visual
label | FREQUENCY: Each post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | 5.2 Post Foundation(s)
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Fencing Post Foundation - as per STD_C0031
label | — 600mm Depth
label | — 200mm Diameter
label | — 2405mm c/c Spacing
label | ○ Single Lead Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing.
label | — 1,000mm Depth
label | — 300mm Diameter
label | — 1,500mm c/c Spacing
label | ○ 8.0m Wide Double Leaf Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing.
label | — 1,400mm Depth
label | — 400mm Diameter
label | — 8,000mm c/c Spacing
label | ○ Drop-bolt footings W300 x L350 x D350 for closed-gate position and 150 dia x 350mm deep for the opened gate position.
label | METHOD: Measure
label | FREQUENCY: Each footing
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 Concrete Footing
label | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | — 0m³ to 10m³ = 1 sample
label | — 10m³ to 25m³ = 2 samples
label | — 25m³ to 50m³ = 3 samples
label | — 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken.
label | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | METHOD: Test
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | Date Completed:
checkpoint | 5.4 Post Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Fencing: Maximum fence post spacing to be 2405mm
label | ○ Max. post height 1800mm above ground level
label | ○ Vertical Tolerance: ±20mm from the design line.
label | ○ Single Lead Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing.
label | — 50 x 5 SHS frame with 75 x 5 SHS Posts w/ End Cap
label | ○ 8.0m Wide Double Leaf Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing.
label | — 100 x 5 SHS Posts w/ End Cap
label | METHOD: Measure
label | FREQUENCY: Each post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 Fence Panel Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Galvanised fence panels 1820x2405x55 to be fixed to fence post with 25mm U-clip, using TEK screw. A minimum of 2 brackets must be used and fastened to each post.
label | ○ Minimum ground clearance under panels 50mm
label | ○ Maximum ground clearance under panels 80mm
label | METHOD: Visual, Measure
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | 5.6 Gate Panel Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Single Lead Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing.
label | — 1.8m high weld mesh fence panel with heavy striker plate, opening to allow access from both sides, 5P locked.
label | ○ 8.0m Wide Double Leaf Gate - Per DNG_C9246 and AS 1725.1-2010: Chain Link Fabric Fencing.
label | — 1.8m high weld mesh fence panel with gate long shoot bolt locking mechanism with 5P lock.
label | ○ Minimum ground clearance under panels 50mm
label | ○ Maximum ground clearance under panels 80mm
label | METHOD: Visual, Meaaure
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | 5.7 Bracing
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | ○ Bracing to be installed on both sides of the fence at the fence corners
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Fence Height and Track Clearance
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | METHOD: Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP