## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0015 Precast Stormwater Drainage Pits |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0015 Precast Stormwater Drainage Pits | 2451c140-96d4-4351-8545-ddea0bf57254
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Design
label | c4c87fb5-dadc-5fe0-8fb1-23433361b853 |  | note | Ref docs - 705.08(a)
label | 6f9eedff-44c6-5b20-b875-f052e88c6b57 |  | note | Acceptance criteria - Design has been provided, including Proof Engineering (by prequalified VicRoads engineer) to confirm that all requirements of AS5100 and additional loading requirements have been met.
label | 8546f544-06ab-5f1e-b7e5-aa40d016a218 |  | note | Freq - Each Lot
label | bb8a192a-bdc9-5f57-b651-90d4fc7121a3 |  | note | Key - R
label | 43e84a19-35f5-56f2-be1a-0ec2cd82b619 |  | note | Resp - SE
label | 3f8d9ad8-413a-52e5-9392-fd19310191b6 |  | note | Remarks/record - Design
label | 0a97706d-d509-5ad5-be28-88e4d7c1abdb |  | note | Remarks/record - Proof Engineer Certificate
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | c8065e8c-5a49-5248-98bc-4377752c814a |  | button | Lot map | Yes,No,N/A
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 5532ea74-bd2d-5797-9fe9-37ecc7c3c48f |  | button | Environmental permit | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 1.2 - Concrete Mix Design
label | 36aaf60a-d80c-555e-acae-8d8cf4db3631 |  | note | Ref docs - 705.04(b)
label | 86532d9c-cdbe-5dba-887b-27195e9c6ac7 |  | note | Acceptance criteria - The concrete mix design used by the pre-cast supplier is approved and current in accordance with the requirements of VR610.
label | 2a72d99d-4d92-59e3-8bb3-bce0e607e23a |  | note | Freq - Each Lot
label | deb4eb81-72bd-54c2-9a6f-37065e07af7c |  | note | Key - R
label | 33b29f07-d8f2-597b-a5c6-56fb2bb2d6db |  | note | Resp - SE
label | 2ec4ab79-6ac9-53e8-ad4b-a52a01aae0ed |  | note | Remarks/record - Concrete mix design
checkpoint-status |  |  | checkpoint | 1.3 - Concrete Supply
label | 76fcdcd9-7888-5377-88ab-814568f0bdc1 |  | note | Ref docs - 705.04(a)
label | cc637b2f-5e20-5e4f-84c9-ecf33259bdc0 |  | note | Acceptance criteria - Concrete has been provided in accordance with VR610 and VR705. The minimum grade of concrete is VR450/50.
label | 9e7e34c0-d4aa-51d6-9f49-b69d46419ab0 |  | note | Freq - Each Lot
label | e088742b-cd12-554b-a6c6-0fe70fdf2fd6 |  | note | Key - R
label | f04c4339-cb43-5019-8721-be0755198138 |  | note | Resp - SE
label | 45263553-b465-5297-a99c-c2319419de56 |  | note | Remarks/record - Compliance Certificates or Dockets by Supplier
checkpoint-status |  |  | checkpoint | 1.4 - Fibres
label | 606cbb8c-8f13-5c33-b361-d495329a1fc8 |  | note | Ref docs - 705.04(f) 705.08(d)
label | 42d05a32-2a33-5e46-aaf1-d53251894381 |  | note | Acceptance criteria - Fibres comply with the requirements of ASTM C1116 and have been supported with documentary evidence confirming their long term resistance to deterioration when in contact with the moisture and alkalis present in cementitious paste or the substances present in chemical admixtures.
label | 3d3d5c4a-36e5-591d-bdb9-8e691d54fc47 |  | note | • Fibres have been tested to the requirements of ASTM C1609 (flexural toughness) and ASTM C1399 (average residual strength of fibre reinforced concrete) and comply with the requirements of AS 5100.
label | 4eb3e1d2-2320-52bb-976a-827e519ce465 |  | note | • Evidence has been provided by the supplier than the minimum fibre content has been achieved.
label | 80fb8845-42cb-5b05-936f-4f8439b2abac |  | note | • The worksheet and/or report for determination of fibre content shall be submitted to review by the Superintendent.
label | b51b0a92-22d4-5ec3-9987-1adb363f02b7 |  | note | Freq - Each Lot
label | 90b8b4d1-4e44-5299-a7ec-e5272288c4b6 |  | note | Key - R
label | 71102c05-8ebf-5180-8d21-95a79aadec81 |  | note | Resp - SE
label | ef7ec0e2-aae8-54f0-9e96-aa8a3792d5d0 |  | note | SI Key - R
label | 0cf4ef8f-0da9-55ae-b271-8c05573d4a14 |  | note | Remarks/record - Compliance Certificates and/or Test Reports
label | fddf9b45-a119-5067-b796-d098b61b2203 |  | note | Remarks/record - Worksheet for determination of fibre content
checkpoint-status |  |  | checkpoint | 1.5 - Wall thickness
label | 8285db7d-c6cb-549f-b202-2b7a06f08640 |  | note | Ref docs - BTN033
label | 655bfb2d-93aa-5f51-bde9-4b81d36b2e22 |  | note | Acceptance criteria - For concrete drainage pits up to 2 m deep, the minimum wall and base thickness must be 100 mm. For concrete drainage pits more than 2 m deep, the minimum wall and base thickness must be 150 mm or thicker if required.
label | 6389ff46-f1d0-58b3-80cd-2ca65cc94195 |  | note | • Where the depth of the concrete drainage pit exceeds 2 m there may be a need to adopt two different wall thicknesses in the construction of the complete pit. The wall thickness at the bottom will need to be a minimum of 150 mm thick whilst the wall thickness of the riser must be a minimum of 100 mm thick.
label | 7505c325-18a2-5bab-869f-b5b0101dd5c2 |  | note | • The depth of drainage pit must be measured from the bottom of the pit towards the surface. The bottom 2 m must have 150 mm minimum wall thickness.
label | 6c570f0a-d3fc-51af-9439-269e305883aa |  | note | • Where the depth of the drainage pit is over 2 m in height then it is acceptable to construct the complete pit as one section with 150 mm wall thickness.
label | ef4bf2c2-e3cf-5c7e-9d5b-6ca742bb7d36 |  | note | • Where the depth of the drainage pit is greater than 4 m, the wall thickness and reinforcement requirements must be structurally designed and Proof Engineered, but not less what has been specified under Section 5 for unhaunched concrete drainage pits up to 4 m in depth.
label | 6faed019-5117-59a6-aea8-4f9682db958f |  | note | Freq - Each Lot
label | b4872027-28c0-57aa-a47b-93a97fb5aa90 |  | note | Key - R
label | b612ccda-6801-5b9a-ad08-a0c5e8d860e3 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.6 - Supply Precast Covers, Grates, Lids
label | 5026090b-8741-57c0-badf-2cfe4e49dd92 |  | note | Ref docs - 705.04(c)
label | 8dc4b6c8-98b9-532e-8b51-e46da0e0dc80 |  | note | Acceptance criteria - Pit covers and grates have been designed in accordance with AS 3996 and table 7 from BTN 033.
label | d80cd302-27b1-5c46-aada-95b91079cfe4 |  | note | Freq - Each Lot
label | 13a9da6c-4ccf-5c6c-9188-d22f2b941c6b |  | note | Key - R
label | fd1d3b95-acdf-50dc-b91f-9d0cb9d36c16 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.7 - Step Irons (pits greater than 1.0m)
label | e21df7ad-b9f9-5131-a2bf-4eff23926249 |  | note | Ref docs - 705.04(d)
label | 8e122a32-a2aa-5678-a2c6-dfe3522cd375 |  | note | Acceptance criteria - Ensure step irons are manufactured from steel AS/NZS 3679.1 grade 250. Step irons are hot dip galvanised as per AS/NZS 4680 or 13 mm steel bar covered with polypropylene shall be approved by design.
label | ab8c49ae-4162-50ca-9c2d-5f73e2be925a |  | note | Freq - Each Lot
label | 13634822-1dde-5801-8b7b-374c374b3e16 |  | note | Key - R
label | f6c38933-927e-5648-8830-76456b1f8ae9 |  | note | Resp - SE
label | d158241f-6bdc-5251-8f46-9b6ea75ffec5 |  | note | Remarks/record - Compliance Certificates Superintendent Approval (for polypropylene step irons)
checkpoint-status |  |  | checkpoint | 1.8 - Weep Holes
label | 2d8e3d98-08ea-5cc1-ad09-9cb13e17e254 |  | note | Ref docs - 705.09(c)
label | fd84f395-1ad4-5706-8523-f6ba786d26f2 |  | note | Acceptance criteria - Weepholes of 50 mm diameter shall be provided in all precast pits and shall be placed between the midpoint and top of the stormwater drain in those walls which have openings for drains.
label | 1fc2162e-0411-581c-8063-0c5b13a96658 |  | note | Freq - Each Lot
label | ad94d417-b8bf-58b7-bdb9-42acb85fa003 |  | note | Key - R
label | 56b2a246-81a2-5bfa-9169-32f044938856 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.9 - Segments
label | 407c67f2-fd65-5076-8dc6-9234b71cb0fe |  | note | Ref docs - 705.09(b)
label | 42a21176-1180-50bc-bc5f-b8cb046d42b0 |  | note | Acceptance criteria - If a precast drainage pit is cast in segments, each section of the drainage pit shall be rebated to ensure correct alignment and to prevent horizontal movement. A minimum rebate of 15 mm shall be used.
label | 59140a36-ff4c-5364-ac16-f9b164153e64 |  | note | Freq - Each Lot
label | f60749d7-6c17-54ba-83d2-f40bf358cb8d |  | note | Key - R
label | 5ec00a63-a4fd-5d7f-8918-d3b3d59d2ed0 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.10 - Repair to Defective Pits (if applicable)
label | 2e18e2dd-2386-5590-b3fa-1a767a3c4c36 |  | note | Ref docs - VR Clause 689 687
label | fe81a189-2980-5c9b-b031-576ad5328d27 |  | note | Acceptance criteria - Any Pits damaged due to handling onsite post acceptance at delivery of non-defective product are to be repaired as per the approved Cracks and/or Patch repair procedure. A Non-conformance to be raised for the defects identified and issued to the State and IR for information and refer it to the Designer for assessment.
label | 04ae2a45-b271-5af5-9eb0-a19b0e109a6f |  | note | • Prior to any patch repair of concrete, Symal shall assess the damaged pit to determine the influence of spalled, deteriorated, damaged or honeycombed concrete on load bearing capacity, serviceability and durability, and submit the assessment to the Superintendent for review.
label | 78248d72-e392-52af-b0f4-73a3e4617aae |  | note | • The Designer and the Engineering team to agree upon an appropriate repair treatment(s) and materials, consistent with the requirements of VR Spec. Section 687 and 689.
label | bf74d206-c2a4-518c-ab6c-fab6f7ed5189 |  | note | • Complete ITP for either crack repair or patch repair.
label | 75a072d8-d133-556b-a595-1b7aeb9034f9 |  | note | • Measure, document and photograph the dimensions and condition of the defects.
button | 1a858ce3-f08c-5fab-ae55-6b11b9bba182 |  | button | Has all of the above been completed and approved? | Yes,No,N/A
label | 2b1cea1d-f65a-570d-bbbd-52e8888fae39 |  | note | Freq - Prior to start of works. Each Lot
label | 2a8f29cd-8740-5c2c-b36b-c81fdee2f9cb |  | note | Key - H W
label | b5297e82-0e09-5839-82a3-8c28c478bbb0 |  | note | Resp - SE
label | 960a2d8e-0847-5bde-a478-eaabec297737 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Excavation
checkpoint-status |  |  | checkpoint | 2.1 - Conformity with Drawings
label | 6ff3e672-dc1e-51d3-839a-57d5c2c49c21 |  | note | Acceptance criteria - Prior to commencement of excavation for the pits the Contractor shall confirm the position of all pits with the Superintendent.
label | 22bd148e-8817-5e83-8022-7fa25806cf24 |  | note | • The location of each pit may be altered to suit site constraints ±1m with both the approval of Survey and the superintendent.
button | 294b791a-8c5d-56d5-b8c7-13e239a1009d |  | button | Approval to proceed? | Yes,No,N/A
label | 546fc7d1-3707-5ac2-b17a-f816c99dafc9 |  | note | Freq - Prior to start of works
label | 12246ffa-3cc2-5084-8c4f-b8e457a66305 |  | note | Key - H
label | 66363737-2869-5605-93a2-a168528211bc |  | note | Resp - SE
label | c0d04504-59dc-5b9c-88b4-c8c287dd27b2 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Excavation for Pits
label | f6c62df3-3e71-50dc-bf6b-485a37755901 |  | note | Ref docs - VR Clause 705.05
label | 8a0b79b2-60b8-5fc8-a1d3-b00bcdb74ec8 |  | note | Acceptance criteria - Excavate to required depth which shall also include excavation necessary to prepare the pit foundation & provide the full specified depth of pit bedding. Maintain excavation width clearance. Excavation for pits shall not be less than 400 mm from external wall to side of excavation.
button | 998a6ba7-fbd6-5bc3-81de-bdba76e2b4b5 |  | button | Has all of the above been completed? | Yes,No,N/A
label | c0b679ad-708d-57df-9b4a-96c8662b80c3 |  | note | Freq - Each Lot
label | afdde096-ed4c-5df4-b3e4-af54084a16c5 |  | note | Key - S
label | 9da36e9b-394c-57bc-b2eb-e40e0e919cee |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Bedding
checkpoint-status |  |  | checkpoint | 3.1 - Bedding
label | 80dfbdfa-5416-56e5-838a-4d754f9d759b |  | note | Ref docs - VR Clause 705.05 Table 701.091 & 701.092
label | d6e76c0f-aa15-5044-a8dc-b37e5f25aae4 |  | note | Acceptance criteria - Bedding placed and compacted to a thickness not less than 80 mm on clay foundation or 150 mm on rock foundation.
label | 6211ed6b-b214-5a38-9751-e56c5f1f36c8 |  | note | • Bedding needs to conform to Table 701.091 & Table 701.092.
button | e9099129-2c15-5739-b10f-ee7625000ac8 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 54be929e-efc1-5026-9ddc-83036dcdbecf |  | note | Freq - Each Lot
label | 272ce974-a9e7-5e4a-9c98-0388cf857725 |  | note | Key - S
label | f7aad43f-57e8-5d9b-8a8b-3744961ea0f8 |  | note | Resp - SE
button | 712eaff3-cba6-568b-9531-f7f925d3f37e |  | button | Remarks/record - Bedding and Backfill Material Conformance | Yes,No,N/A
checkpoint-group |  |  | section | 4.0 Installation of Pits
checkpoint-status |  |  | checkpoint | 4.1 - Installation of Pits
label | 4bb3c86c-52b0-59bb-9869-dd77557520c2 |  | note | Ref docs - VR Clause 705.07 705.08 705.09 705.11
label | 2161dce2-efd1-55bf-98b0-1b4d2e32393c |  | note | Acceptance criteria - Precast pits shall be installed at the locations and to the dimensions shown on the drawings.
label | 4f86518d-5044-584f-bdb2-e7a0875ba54f |  | note | • Subsurface Drainage Connections – Holes for subsurface drainage shall be 150 mm diameter (cored not broken), unless specified on the drawings.
label | 86881686-c6a4-52bf-9c0f-222eb4b10dc5 |  | note | • Segments – If a precast pit is cast in segments, each section of the pit shall be rebated to ensure correct alignment and to prevent horizontal movement. A minimum rebate of 15 mm shall be used.
button | 99b38b3a-b8eb-5d35-8eb1-6b9ef8785c45 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 42a50711-2ad9-5055-aecc-ee36e8fac32a |  | note | Freq - Each Lot
label | c157ad8c-09c7-5b9c-9304-e33cf570bfad |  | note | Key - I
label | 1853a7a0-ad4e-5afa-a4d3-3abf33ed543d |  | note | Resp - SE
button | 3100447a-3dfc-5668-8938-f36265c2c12e |  | button | Remarks/record - Test results for fibres and fibre content (if applicable) (Compliance Certificate provided by Supplier) | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 4.2 - Pits with Risers
label | e66fab0c-14c8-5306-b989-41ad4db3380e |  | note | Ref docs - BTN033
label | 98b54c3f-3c2f-53bb-9908-5e5884d43802 |  | note | Acceptance criteria - Where a drainage pit is manufactured in multiple sections with different wall thicknesses, the internal wall face must be vertically aligned, and the step in the wall thickness is to be located on the outside face of the pit. Joints must be sealed with cement mortar to provide watertight joints. No bonded anchors to be used for the construction of the drainage pits.
label | 0fd37816-a118-5c18-a672-f530a2160263 |  | note | Freq - Each Lot
label | 1cce5e35-2405-5596-bd78-8e0494f4c8ab |  | note | Key - R
label | 15cdcaed-65a8-554e-9370-61d34d495d2a |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.3 - Step Iron Fitting
label | 330e83fc-a66f-5e70-a5fa-41c96ed0b54a |  | note | Ref docs - VR Clause 705.12
label | 0db24bcc-25cb-5914-9420-635f6f2f3d10 |  | note | Acceptance criteria - Pits greater than 1.0 meter shall be fitted with step irons. Step irons shall not obstruct openings or be fitted to a wall which has openings.
label | 07046fd7-2e46-557b-a6d2-05a052b108a1 |  | note | • Step Irons shall be installed in accordance with the manufacturer’s instructions and shall be an approved proprietary type.
button | dbcfa8d0-f534-5465-956d-ae7a997c14c6 |  | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
label | 02973095-82e0-513c-880c-192879c20473 |  | note | Freq - Each Lot
label | 8c2130d6-8099-5511-913b-676adf831b21 |  | note | Key - S
label | d048ce73-3db9-5aab-a75e-9bbf3c87d373 |  | note | Resp - SE
button | aea4fe7f-a6a5-5769-a42e-150491ea5ca1 |  | button | Remarks/record - Material Conformance Certificates | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 4.4 - Shaping the floor
label | 10402814-f54a-5b38-88d3-14e1ce923387 |  | note | Ref docs - VR Clause 705.13
label | 583f9cf1-46dd-549a-bdc9-9f4c0539326b |  | note | Acceptance criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar, to provide a profile that will ensure smooth flow conditions between inlet and outlet pipes and prevent any snagging of debris. The cementitious mortar shall comply with the requirements of clause 610.33
button | 80f67807-0d95-54ef-97fe-58cd2e6ae20a |  | button | Has all of the above been completed? | Yes,No,N/A
label | c00e04a3-b4e9-5b24-976d-cafba102a0ce |  | note | Freq - Each Lot
label | 1516c909-ff92-5d5f-8f2d-8af4c7e73c93 |  | note | Key - S
label | ac8ff956-d6dc-59fe-a3a8-13aa5de72e40 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.5 - Jointing
label | 480e23bd-37f1-58a4-bf7e-9ca797bf7851 |  | note | Ref docs - VR Clause 705.14 705.16 610.33
label | 9fedef23-a59c-52f7-8a7f-2ebe265a178a |  | note | Acceptance criteria - The joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
label | df1cc141-09d0-5302-b62a-72230a37aaad |  | note | • Mortared joints and recesses shall be cured for a period of not less than 48 hours with no backfilling until the curing period is finished.
button | 31d7b099-62e1-5098-b72e-64426e190386 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 3f843ed2-cc9e-5cb0-888a-3a3a4f8d0061 |  | note | Freq - Each Lot
label | 4020d288-9af9-5c7a-8506-987bf9287c21 |  | note | Key - W
label | dd31c1a2-2d50-5232-b03a-21108eba248b |  | note | Resp - SE
checkpoint-group |  |  | section | 5.0 Backfilling
checkpoint-status |  |  | checkpoint | 5.1 - Survey Location Confirmation.
label | 5581731b-f62f-5e81-98f5-037bd6160559 |  | note | Acceptance criteria - The location of each drainage pit shall be verified by a survey certificate prior to backfilling the drainage pit.
label | 925be89f-6b2b-5dfa-8c7a-1937d946edb6 |  | note | • Offset of entry pits required to match lines of kerbs or barriers ±20 mm.
label | 1bfe2c6d-bf7c-553f-9587-f7e99ef4417e |  | note | • Plan location of pits other than offsets to kerb lines or barriers ±100 mm.
label | 0d96c718-ac02-5ba1-b5f5-c6d40aec099d |  | note | Freq - Each Lot
label | bebe0b16-97d4-5109-b92e-21279c9f1890 |  | note | Key - R
label | 018c7694-befe-54fb-ae45-78dbc18fd884 |  | note | Resp - SE SV
button | 43740099-8fc6-5c9c-99a5-0ed666b71d46 |  | button | Remarks/record - Survey Conformance Report | Yes,No
checkpoint-status |  |  | checkpoint | 5.2 - Backfill Material
label | 49478161-53c6-52e7-bafb-7f6498323610 |  | note | Ref docs - PS3030.07 (a)
label | 25ca2e77-26ec-5e78-a160-e4f55396c5f3 |  | note | Acceptance criteria - Backfill material shall conform to the requirements for type A material.
button | fe6207c7-04ed-57e0-ab61-0fcb0b18be0f |  | button | Has all of the above been completed? | Yes,No,N/A
label | 86445d82-ee5b-5aa0-9a5f-28c2f442a074 |  | note | Freq - Each Lot
label | 22954d0b-4e3d-5c06-a719-ec05000e091c |  | note | Key - R
label | bf48ebc0-7bf1-595e-b35d-9f877c8f954a |  | note | Resp - SE
button | 7e2a4df7-2b06-5dab-a4f9-2fdc1edce1a6 |  | button | Remarks/record - NATA Test Report: Grading/PI | Yes,No
checkpoint-status |  |  | checkpoint | 5.3 - Backfill Pits
label | 13df0a99-e537-5da3-8f8f-3ad46de7d60f |  | note | Ref docs - VR Clause 705.18 PS3030.07 (b. iv)
label | 244b7901-1650-593e-8218-aaa65e43aff8 |  | note | Acceptance criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment.
label | 49dbc2f5-c993-58fd-b649-99ff149453b2 |  | note | • Superintendent must inspect before backfilling as indicated in PS3030.07 (b. iv).
button | 8eb1e5a4-cd31-5e5a-832d-a45dafcc5bed |  | button | Has all of the above been completed? | Yes,No,N/A
label | 97cea43f-d210-5a58-93f1-fe826212d3b1 |  | note | Freq - Each Lot
label | 8295f170-8edf-583e-ba53-cac56f7b30c8 |  | note | Key - S
label | 16762890-e62f-5718-9336-04e21716cf9a |  | note | Resp - SE
label | bbb02d9a-8879-5c96-bacd-8a9b2db3aeb3 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.0 Completion
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | c51a6fb7-0841-59af-be76-fc11b90861c6 |  | note | Ref docs - VR Clause 705.19 610.46
label | dd9f64e4-1955-59e8-b0ad-506fd0e1bcb2 |  | note | Acceptance criteria - Survey complies with specified requirements.
label | fee2296c-6f68-516b-9619-a319c59948fc |  | note | • The level at every point of the pit covers perimeter shall be within 10 mm of the design level. The line of the cover shall be within 10mm of the design kerb line
label | a9438fa6-30d0-5027-9635-4eb5a4f0627d |  | note | • Offset of entry pits required to match lines of kerbs or barriers ±20 mm.
label | fa1137a2-3e5f-5d61-b510-8ee5d08baa37 |  | note | • Plan location of pits other than offsets to kerb lines or barriers ±100 mm.
label | 12bb5b9f-0886-5a57-9021-4ec9e9a821e9 |  | note | • The tolerance listed in Clause 610.46 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
button | 83d35d06-d9e4-508b-852e-ed6f8d1fe9b2 |  | button | Has all of the above been proven and meets requirements? | Yes,No,N/A
label | 70eec5f7-ae7f-59ca-8208-12c2a2ba7550 |  | note | Freq - Each Lot
label | 94a02cc0-a402-5bc5-bad6-4c1b5f470c19 |  | note | Key - R
label | 503a9e0a-9e8f-51cc-82d4-286ec078c5a5 |  | note | Resp - SE
button | d7c0d839-d107-5fa7-8a3e-62405d9ffa37 |  | button | Remarks/record - Survey Conformance Certificate | Yes,No
checkpoint-group |  |  | section | 7.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 7.1 - Test Reports
label | b73bb617-abc9-5251-a087-1b07f5cd8489 |  | note | Ref docs - DoT Specs
label | 6da64a56-f07b-5238-b82c-873b9b3bcfaa |  | note | Acceptance criteria - All Test reports received and Reviewed
label | a5914969-4062-5b29-a66e-ccab8c952025 |  | note | Freq - Each Lot
label | d633c025-2c29-545a-a57f-442376e1610f |  | note | Key - R
label | 24dae65c-83ac-5c80-a63e-f2c9edf0be16 |  | note | Resp - SE
button | bdbdf54f-cca3-501f-9e95-087a8a60cc7f |  | button | Remarks/record - NATA Endorsed Test Reports | Yes,No
checkpoint-status |  |  | checkpoint | 7.2 - Product Non-Conformance
label | f83d11a8-0eae-5c7f-a49c-fb9635bc9768 |  | note | Ref docs - CQMP
label | 868968b4-1562-5541-b80e-735c72c16428 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 6a01f8dc-f357-5976-99b4-dd093f586ce2 |  | note | Freq - Each Lot
label | 0fd9aa62-7902-5ad2-b1df-b6dc4f0e97dd |  | note | Key - R
label | ecc3daa5-6dde-534c-a03f-f899df71ff9c |  | note | Resp - SE
button | b8bff080-8173-5851-bbfe-2bf8e1d3d213 |  | button | Remarks/record - NCR reports | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
label | 7ef4b7c4-c025-572b-830f-102ffa85c31e |  | note | Ref docs - CQMP Lot Records
label | 0c0e7dab-9134-532b-982a-d409a27da34e |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 06315200-038d-5202-a000-479298df02a7 |  | note | Freq - Each Lot
label | 77ceacb6-1c6d-5f49-b1d6-3098866afe22 |  | note | Key - R
label | 75c028a4-83dc-5f2f-b65d-3ecf09549573 |  | note | Resp - SE
label | cf15468c-f60c-5001-b8fc-aa7cdcdef22c |  | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
checkpoint-status |  |  | checkpoint | Works complete
text | cb4f4601-c113-5514-9e69-3327f5d51ad2 |  | textbox | Name:
text | 57c62934-fd63-5f80-856d-88e7ca588d99 |  | textbox | Position:
text | 1f11137e-442a-5f54-ae37-a7722bc878e2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | b5554e7a-f484-510f-8a2e-7cf865f7ee67 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 37a95579-15e7-5f3f-b0bd-574d300993b9 |  | textbox | Lot opened date:
text | 4aecb02a-3372-55c9-a32d-8b76fc51b80f |  | textbox | Lot opened by:
text | 70f89fd7-5a3d-5082-b2a0-0e585f5784cb |  | textbox | Date lot closed:
button | d3c2cf52-dc07-5486-ad98-2db5b5764ecc |  | button | NCR raised? | Yes, No
text | a8752c00-271d-5dae-aa33-cc36e28063d3 |  | textbox | NCR Raised Date:
button | a8e041d4-2b94-5d36-9cf1-c38cc764f9ab |  | button | NCR closed? | Yes, No
text | 71e0c37c-6d75-5e3f-849f-b3e9be048f78 |  | textbox | NCR Closed Date:
text | b7662269-8d4a-5da0-bdb2-c9f00e219d15 |  | textbox | NCR Number:
text | e21c63f7-1860-586a-af99-0b6ace6f99e1 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B | 3111f2df-fd4d-4607-ba81-ecbd85e8df1e
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Work Lot
label | f8fa8744-13b2-595c-98cc-5859150f61f7 |  | note | Ref docs - 173.02 204.03 (h) Table 204.142
label | d1ea8105-ee7f-591a-8a11-cf1e60ef4236 |  | note | • Quality Management Plan
label | 39a8c9d4-027d-5918-a9d9-4f96876e37ba |  | note | • Lot Diagram
label | f7650654-fefc-5b5e-bfb4-1486c27d2111 |  | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works.
label | 6c69807b-c950-5009-b94a-9b772664fe74 |  | note | • Lot diagram to be provided clearly marking up extents of lot area.
label | 1ef85644-cc9d-512f-a208-6d9367fc4fea |  | note | • Work Lot open on TeamBinder.
label | a27b5b57-cf0a-5840-a13e-ec109c455015 |  | note | • Lot size with no more than one day’s production or a maximum of 10000m² for Type B Material.
label | e043f336-5a94-5ae2-a395-e00c15916d1f |  | note | • In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
button | 4aa1afbb-375c-5a7e-ac1a-5fda953d13ee |  | button | Has all of the above been completed and approved? | Yes, No
label | 51e77f8a-25a9-54bc-8d9c-b1377033a817 |  | note | Freq - Prior to start of works
label | 02f07382-4226-50c2-9891-8c218a386800 |  | note | Key - R S
label | dd7a00e0-c420-5602-bfe6-856a64eb27da |  | note | Resp - SE
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | a527cbc1-0923-5c2e-ad31-06011b6ba5f7 |  | button | Lot map | Yes,No,N/A
checkpoint-group |  |  | section | 2.0 Set Out
checkpoint-status |  |  | checkpoint | 2.1 - Set Out Survey Completed
label | 118def92-7ae8-52bd-b7c1-ea6f3cef4ac3 |  | note | Ref docs - VR Clause 204.03 (a)
label | 083d1f38-9c86-5175-acba-f078f9465f9c |  | note | • IFC Drawings
label | a87b551f-99f5-5e2e-9c83-fffacbde0053 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
button | df6f0577-1631-5a38-b0c9-16f6c114cbaf |  | button | Has all of the above been completed and approved? | Yes, No
label | 2407d0e7-d52d-5181-b4d3-0a9dfcebc940 |  | note | Freq - Each Lot
label | 81be863e-484c-5078-a26c-f7cc0949fd96 |  | note | Key - R
label | 46a738c1-b9ef-55d1-ad30-b8cea37b6831 |  | note | Resp - SE
checkpoint-no-status |  |  | checkpoint | 2.1.1 - Surveyor Report Reference
button | d0773029-ab7c-5a97-a6e3-6fee281402ef |  | button | Surveyor report reference | Yes,No,N/A
checkpoint-group |  |  | section | 3.0 Placement of Type B Material
checkpoint-no-status |  |  | checkpoint | 3.0.1 - Incoming Material Docket
button | b966ac30-4021-58e8-9e25-53ac22743838 |  | button | Incoming material docket | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 3.1 - Underlying Layer Conformance
label | bd08aef2-18fe-5935-9b33-534f3172ffee |  | note | Ref docs - VR Clause 204.10(b)
label | bed0d4e8-4bf8-5135-9c69-31ce505ae231 |  | note | • Construction Document
label | 7b201fa8-bc5e-5218-a9b7-ff88bbdbd546 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
button | e2e69e54-079b-54e8-bf2a-853bfcdc9f85 |  | button | Approval to proceed granted? | Yes, No
label | 1d76b062-9cf5-56bb-ac26-05353f135e50 |  | note | Freq - Each Lot
label | 7deae25b-6a43-55c8-9c0a-e03d78545609 |  | note | Key - H W
label | fc7d1e8e-a611-5846-ad63-1d9f6fb5cc32 |  | note | Resp - SE
label | efbf72a2-32fa-5bdb-8151-f91635077240 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Placing Geotextiles (if applicable)
label | c2034b4b-82fc-5d1f-8cf5-18254a913649 |  | note | Ref docs - VR Clause 210.05 Table PS3020.071
label | b412a3a4-e44c-569c-83cc-e43719c8b8c1 |  | note | • IFC Drawing
label | ac42204d-bfaa-5ef5-92af-13c35b074e8f |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent.
label | a2d77c7f-be3a-53b5-b980-46659f5d2cca |  | note | • Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with
label | f7afb9f1-9e7e-5743-945b-18b0c379a85a |  | note | • imperfections shall not be used.
label | 58de0113-ad2f-5738-b895-9d8385cd944c |  | note | • All joints shall be overlapped or sewn in accordance with the Geotextile Record.
label | d81479cd-00a9-57e4-a8a6-fc50ebd29eea |  | note | • Geotextiles shall be covered by filling within 48 hours of placement.
button | fb6c1e43-1fa9-51aa-9b3f-c6167f221205 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | ddec750e-39c0-59b4-bde8-4e6fadcb24db |  | note | Freq - Each Lot
label | c91a7505-60de-556a-a6ff-be74ce9a57d1 |  | note | Key - H W
label | 3ae27b8b-0063-5e42-ba64-8d61a385df27 |  | note | Resp - SE
label | 82556293-1b7c-5a49-98ef-3d6145622c23 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Placing Subsurface Drainage
label | 7439b7b5-66df-50e3-a649-1a765a24b725 |  | note | Ref docs - 1630-P200-SYM-TPW-RPT-0001 Appendix B – Table 5
label | 28d26d1c-81e3-58b0-bc4d-813f00975d6d |  | note | Acceptance criteria - Subsurface drainage mat to be prepared in accordance with drawings.
label | 3a6b356c-7c7b-51c3-969e-8aa27e959b17 |  | note | • Superintendent to review and approve prior to placement of any fill on top of subsurface drainage mat.
button | d507a032-f181-5036-a2fb-f8af3dd72c5f |  | button | Approval to proceed granted? | Yes, No
label | 381e8f85-d34e-5ad1-9948-f65d4724db91 |  | note | Freq - Each Lot
label | f3d345ed-beab-5838-a56e-0c928bd4059b |  | note | Key - H
label | 1d3d8f53-25e9-51be-9fe7-3d1bf0212b2e |  | note | Resp - SE
label | fb1fd68f-3689-503a-b2a3-30945ae7f1aa |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Placing of Fill
label | 104e13ea-72e4-50b7-9030-c40ac7450b5f |  | note | Ref docs - VR Clause 204.10(d)
label | d2dc909a-758d-540a-b4b6-7ab223f911c2 |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm.
label | e9791f4e-7e59-56c9-ab57-d49d73cfbe7d |  | note | • Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
label | 38f8450d-1e00-59b9-8d76-7e00e071fde9 |  | note | • Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material.
label | 314a6108-2574-5fbc-90da-06ab1b524735 |  | note | • Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
label | b107da41-6929-541f-a597-a3e3252f3b38 |  | note | • Material shall be compacted at minimum moisture ratio of 80%
button | 4a29c030-b1ba-5c93-9e80-70926b846973 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | e6df2306-34ae-55bf-99f5-166ca6cd7ffc |  | note | Freq - Once Each Lot
label | 0ed218b3-9346-596e-a98c-2b61bbed0ba0 |  | note | Key - W
label | 93986a07-6a29-55bc-8bcf-f93982acb552 |  | note | Resp - SE
button | edc14315-1eec-5fa6-a7a2-2359b9b53bdd |  | button | Verification Records: Layer Thickness at least every three layers | Yes, No
button | 4b004435-85b8-5337-b074-7f21a86b6652 |  | button | Material Compliance Certificates & Material Approval Register | Yes, No
button | eed86837-8847-562d-9751-a40ab2653789 |  | button | VicRoads registration of recycled material blend (if applicable) | Yes, No
checkpoint-status |  |  | checkpoint | 3.5 - Keyed Fill Layers
label | 983500ac-6324-5b1f-a3a5-760b49f65ccf |  | note | Ref docs - VR Clause 204.10(c) 204.10(d)
label | 03ab576d-3c63-5c45-8e37-c69b63ee2ebc |  | note | • Construction Document
label | 8ac0100a-3cc4-57a2-827d-242ef2f85a73 |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
label | 8ab6705a-6931-59b9-9435-644477ea4b54 |  | note | • Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | e1633663-4a1e-5a62-a78a-21738e56505f |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 4ac2db4a-8b83-5c58-9a16-585bedd8a7e1 |  | note | Freq - Once Each Lot
label | 217b824b-a26a-5a00-abd7-1baf1c824518 |  | note | Key - W
label | a7733f88-456d-5861-80a7-2e93b24c4b8e |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Test Roll of Type B fill layer
label | a4810167-86c5-5440-a8f4-045b186645db |  | note | Ref docs - VR Clause 204.12 173.03
label | 45a0352e-c31f-5aa6-9eff-0a009224c43d |  | note | • Construction Document (Test roll Procedure in specification 173.03)
label | f96f803d-b391-52ea-b794-8befd62d86a5 |  | note | • 1630-P200-SYM-GEO-DPK-0001 Table 43
label | 67343215-be75-5c27-b8d7-f09ebd168b85 |  | note | Acceptance criteria - Test Roll in accordance with Section 173.
label | dc3ad455-ee27-59f4-af30-018174f27a78 |  | note | • Surface shall withstand test rolling without visible deformation or springing.
label | 2f8c38f9-a9ca-5b46-bf6b-d9ef04f84855 |  | note | • Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass.
label | b19d176e-cc32-57de-a9f2-2e603517c7c4 |  | note | • Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted.
label | bce1ad60-b581-5f0f-ad31-55936a8b5014 |  | note | • The Contractor shall provide for the Superintendent to be present during all test rolling.
button | 9cd85883-6751-561e-8b28-022788358b85 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | fedea765-b8fb-56a5-b2dc-c5f76ffedbc1 |  | note | Freq - Each Lot
label | 6878c82f-f0a0-5809-b49c-55b399d92467 |  | note | Key - H
label | 2ed9baeb-2371-5896-9eec-2cdd98ce380f |  | note | Resp - SE
label | 5827d578-ef52-5212-be3b-e56f06afda64 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 3.6.1 - Proof roll if applicable
button | 7d20b188-3a8b-5b38-b7c2-48c9ff2d1a8b |  | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
text | 4a6027b9-7852-54f0-b437-47adc79b621e |  | textbox | Chainage
checkpoint-group |  |  | section | 4.0 Geotechnical Analysis
checkpoint-status |  |  | checkpoint | 4.1 - CBR/Swell – Initial Testing
label | 91bfb728-5fdd-56b5-9e6b-ac3930a0339c |  | note | Ref docs - VR Clause 204.04(c) PS3020.05 (c)(v)
label | 98ae63c7-d3ea-549d-a559-f013517b318d |  | note | Acceptance criteria - First lot tested to determine assigned CBR and Swell:
label | ac9f9e30-d565-5a74-9fdf-c652b63fbf0f |  | note | • CBR ? 2.5%
label | 40712dda-c500-5516-a3be-ee59d7a2ffb7 |  | note | • Swell < 2.5%
label | c8fd70c5-d39f-5296-8304-b8ba47b10ce4 |  | note | • If swell exceeds 2.5%, material shall be classified as expansive. Raise RFI and request approval from Superintendent to use material.
label | 74cdb9ed-6770-53e7-b2a8-6609f5dccd6f |  | note | Freq - Each Lot
label | 62941524-c285-5027-9c3c-e3c947cef67d |  | note | Key - R
label | 7c85ecca-e400-55e4-9984-6aa85352f368 |  | note | Resp - SE
button | 5af2ccd3-3031-5d0a-b331-4d94cd946b32 |  | button | NATA Test Report: CBR and Swell | Yes, No
checkpoint-status |  |  | checkpoint | 4.2 - Compaction Testing / Moisture Testing
label | 7c0ba699-a638-5e26-b8a7-5e1c5d91cb62 |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) Table PS3020.072
label | 365f91d9-d18a-5119-932e-47785f1bf2d3 |  | note | Acceptance criteria - All areas of the job will be considered as scale A.
label | 212572ac-70c5-508f-b9ca-53060fd99d7a |  | note | • Scale A Testing: HWKR Rd, Princes Freeway, All Freeway Interchange Ramps, All other arterial roads.
label | 7ee65017-459d-559c-b479-746fda37da19 |  | note | • Scale B Testing: All other local roads, SUP.
label | 2f174dd1-5828-59a2-b6eb-a3fb2d21dade |  | note | • Type B material placed within 400 mm of top of Type B material: 99% (Scale A)
label | 63df42a2-8de3-5d69-a0f4-cb1441ceb73b |  | note | • Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A)
label | 12c0681f-8950-55a5-af8d-bed53a51f43f |  | note | • Type B material placed within 400 mm of top of Type B material: 98% (Scale B)
label | c17b1b5c-307a-5be3-b77d-618e417bcd29 |  | note | • Type B Material placed more than 400 mm below top of Type B Material: 95% (Scale B)
label | 1c49a7b5-13e6-5104-9d8c-e51023541254 |  | note | • Type B material is to be tested as per table 201.142. And should meet the moisture content requirements as per VR204.
label | 4c4325f5-a2eb-595c-aeb8-4fa5fa196f09 |  | note | • >70% for any material within 150mm of subgrade.
label | 6864dc93-2ff2-597b-be3e-333a8a6e0ea7 |  | note | • >80% for all material below cut floor level.
button | 93d15fb4-c8bf-5773-9678-b2b60d35f8fb |  | button | Have the results been achieved? | Yes, No
label | ba39e6a5-b6fb-5ab4-8cd9-d92b0271b339 |  | note | Freq - Each Lot
label | b654dc38-3ff9-58b6-ba21-8539363b5c51 |  | note | Key - R
label | 9c6d5e95-5e1e-5d3e-a0ff-48acaa61cc9e |  | note | Resp - SE
button | 15761318-036d-54de-a751-fa8d2dd404c5 |  | button | NATA Test Report: Compaction | Yes, No
checkpoint-status |  |  | checkpoint | 4.3 - Material Requirements
label | 44b65fdc-6368-5473-9181-924946fa2b1c |  | note | Ref docs - VR Clause Table 204.041
label | 4379448b-b6d0-523c-895a-3a8037cefebd |  | note | Acceptance criteria - Maximum Particle Distribution (MPD) ? 150 mm within 400 mm of Top of Type B. or MPD ? 40mm at depths greater than 400 mm below the top of Type B material.
button | e93b3fa0-8dfe-5d84-97ec-8c2e52a68c6c |  | button | Have the results been achieved? | Yes, No
label | 2114a86e-059c-513d-8ac6-c29e058925f5 |  | note | Freq - Each Lot
label | f1bf0faf-db49-5dfa-aa54-d6a4039fe6f3 |  | note | Key - R
label | c6f2522f-598b-54ce-9292-02bb59549387 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.4 - LL and PI Testing
label | d76fb0de-d97d-5ad8-bb27-d9cad57deddc |  | note | Ref docs - VR Clause Table 204.141 Table 204.142 173.04(d)
label | b43e6d06-8615-5fbf-9c35-94e547b16dad |  | note | Acceptance criteria - LL and comparison of PI against LL, (identification of silt) is required for Type B Material. Initial testing is 1 Test per 2 lots.
button | 2d8a3c83-32fb-5e62-945e-811f84c8e672 |  | button | Have the results been achieved? | Yes, No
label | 8a87e1fc-e8f2-5058-b430-c4a92ab6be0a |  | note | Freq - Each Lot
label | a074bc31-e9e7-5db8-9466-23e5ee89dbed |  | note | Key - R
label | a1a2e96e-f8cb-5c9f-8320-4dd0eb3b590d |  | note | Resp - SE
button | 5e59158b-3225-586c-ba9a-0f1a244dfb02 |  | button | NATA Test Report: LL, PI | Yes, No
checkpoint-status |  |  | checkpoint | 4.5 - Reduced Frequency Post compaction testing of initial lots.
label | c1479262-f6af-5c15-8091-aea0aeeec38f |  | note | Ref docs - VR Clause 204.14 – Table 204.141 PS3020.07 (f)
label | 6ca61033-2d69-5dfe-b061-4ac3da306207 |  | note | Acceptance criteria - Test initial lot for CBR/Swell.
label | 6a5f862d-a29f-5c5d-8c92-8c70cd03c944 |  | note | • Test initial 3 lots for compaction.
label | 3dc0e1e8-ee11-519d-9fd4-64846fc3338b |  | note | • Once material and work have achieved the specified requirements in the first test. And;
label | 8e90521c-245d-5507-83d5-0d8399de7d38 |  | note | • Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
label | c146e570-2dc6-55a0-aa24-a0e65def17fa |  | note | • If Reduced frequency has been granted, the testing can be conducted at the following frequency.
label | 90769965-a46f-5dcf-b97c-69c6347f2a09 |  | note | • 1 test per every 8 lots for CBR/Swell
label | 85d87464-9a88-5dac-968c-3ab7b678f556 |  | note | • 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing.
label | 6d34f96d-4895-5b35-bb0b-e076b5114d76 |  | note | • 1 test per 4 lots of LL and comparison of PI against LL.
button | 98404032-c260-52f1-b2c1-d684e7b4d057 |  | button | Has the criteria been achieved? | Yes, No
label | 62c7bb6b-86dc-5ec1-8058-f1017a9a105a |  | note | Freq - Each Lot
label | 6f56bbda-c8a8-5593-bcd7-98839f3d65c7 |  | note | Key - R
label | 6610f325-093b-5730-a0b6-f5990129546b |  | note | Resp - SE
label | 2ad28cee-3061-52a9-ac78-8535637aa9a9 |  | note | SI Key - R
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
label | d1345fae-145b-5b0d-af14-74c5227c0a94 |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | e7ab7d81-c896-592e-a99b-d0cc763d63c6 |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements.
label | af2cb4d9-359c-50dd-a958-2d376315462b |  | note | Scale A: 80 measurements per lot
label | e697266b-9e3a-583d-a9ca-703f6478ac6e |  | note | Mean +5 / -15 mm Max Std Dev. 12 mm
button | 57eed39e-620e-516e-b12b-e8601eb7111f |  | button | Does the final product conform to the above criterial? | Yes, No
label | 7e3734b0-d44c-5430-8d10-c4df18b361a7 |  | note | Freq - Each Lot
label | ffd92195-084d-576a-8f26-dcf60131aafc |  | note | Key - R
label | 5ef8ba29-032e-54b5-8b18-6f3446dd71a6 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 02eb49a0-3f89-5637-8bf6-d42b2315dec8 |  | note | Ref docs - VR Clause 204.15
label | 6a9e98f9-e1dd-5121-9cbe-fa3007557e1c |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
label | a5e66414-f1c3-501d-b611-fd5fb5a245dd |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | acd96646-20c0-58e3-a7d7-c8045e83f782 |  | button | Does the final product conform to the above criterial? | Yes, No
label | b8d92a8d-0ee1-5320-a7f5-11f9adcbe01a |  | note | Freq - Each Lot
label | 23697983-92a5-572a-bc45-af87969c195b |  | note | Key - R
label | b58f0636-5780-500d-b5bf-0f358a1ecf94 |  | note | Resp - SE
checkpoint-group |  |  | section | 6.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 6.1 - Test Reports
label | 1c5e28cd-b7a9-5172-831f-e6eeb8f870fb |  | note | Ref docs - DoT Specs
label | 9825c7b4-8b07-5800-a59a-a24f61edc366 |  | note | Acceptance criteria - All Test reports received and reviewed
label | e650331a-449c-5697-a402-dd04edaeca4b |  | note | Freq - Each Lot
label | 0a39f398-8347-5ff8-91c6-4028ececdb48 |  | note | Key - R
label | a835032b-54f1-5e3d-9bc4-434f31806b21 |  | note | Resp - SE
label | 301e79f9-cc24-5399-b011-84686b184546 |  | note | NATA Endorsed Test Reports
checkpoint-status |  |  | checkpoint | 6.2 - Product Non-Conformance
label | 7e067f12-75f7-5cb1-998c-30bec7510d73 |  | note | Ref docs - QMP
label | 87a3287c-1139-5a79-9f05-8820e0e93eb5 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 4fb2e3d3-112c-5769-a2e0-0987651e0f94 |  | note | Freq - Each Lot
label | a4f426b2-0b77-53c9-b298-95adbd8fcf6a |  | note | Key - R
label | 5948400e-70e1-5ca6-a1ff-bc0bb4eed080 |  | note | Resp - PE
label | 922db5e6-793c-5502-a517-9305dd6a331e |  | note | NCR reports
checkpoint-status |  |  | checkpoint | Works complete
text | e6466221-d572-56f8-8d61-0f15daf79e56 |  | textbox | Name:
text | feb18dff-780e-5219-a3ec-35f990bceeec |  | textbox | Position:
text | 12d106e1-c754-517c-9452-b660a99ce2a7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 44cafff3-cf30-576b-bff4-110e03ffad77 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 60877274-ee3d-5e63-92f7-3ba3635121bd |  | textbox | Lot opened date:
text | 3027fa8d-93f4-5bb4-92a6-7bebfac36889 |  | textbox | Lot opened by:
text | 74f59420-8cdf-5e5f-b6ea-5437550ab3dd |  | textbox | Date lot closed:
button | 2267fbfb-5bb1-5148-a955-6fbd41ccbbf6 |  | button | NCR raised? | Yes, No
text | ec8a1f86-6596-5999-b32d-6c8ff841a065 |  | textbox | NCR Raised Date:
button | 8efcdfcf-1aad-5d35-95d4-e29c7a073df2 |  | button | NCR closed? | Yes, No
text | 401507d0-8b6c-5b09-9728-9bac861c0953 |  | textbox | NCR Closed Date:
text | 3541c639-320f-57f7-a55f-4e1a6e547a3a |  | textbox | NCR Number:
text | 28dfa006-393c-58f5-9340-f63073a8909d |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0019 Lower Subbase Layers |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0019 Lower Subbase Layers | 3526fc3e-f635-4689-99f3-f7af02eba99f
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Check Survey Set-out and TCM’s
label | b99e4d74-7856-5dad-92c3-a78c2d07213e |  | note | Acceptance criteria - Record existing TCM’s on TCM offset sheet. Survey set out including frame, benchmark, and recovery points in place.
label | 07a641cc-9de2-56c7-9ca8-56b7d62939b7 |  | note | Freq - Prior to start of Works
label | 559f184a-50bf-53b4-beb1-69c10045e48c |  | note | Key - H
label | 8c5c8bae-02b5-5f26-b6a3-941d751d9508 |  | note | Resp - SE
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 8dea6dc8-3b70-5aa9-99cf-2aa6bd2e4ade |  | button | Lot map | Yes,No,N/A
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 4afa04ca-c2e4-59ef-a235-195718fc4045 |  | button | Environmental permit | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 1.2 - Subgrade preparation
label | 928bef34-6dca-5390-a922-9a93985a9a88 |  | note | Ref docs - DoT Clause 304.04
label | cab27010-71b9-537a-9368-671d59f969e2 |  | note | Acceptance criteria - The subgrade should conform to the requirements (compaction and levels) of Section 204 before the lower subbase can be placed.
label | e8cc7b87-f06c-5e63-9a72-be11c7190e01 |  | note | Freq - Prior to start of works
label | 00c3ac6a-e1ca-5844-a922-53a0dca990aa |  | note | Key - H
label | 00022e9d-9e78-538c-bed2-7bb830bcfb84 |  | note | Resp - SE
label | 8b7a02af-e1dc-5457-82cc-52b736a5d4a2 |  | note | SI Key - R
label | 9a377d97-e484-53da-aa1a-31b72e481c77 |  | note | Remarks/record -
button | 8f80b867-9d91-5510-a6a9-24cfb671b338 |  | button | • Survey Conformance Certificate | Yes,No
button | 38e04c9a-2cbf-5631-b6de-7a49f382b886 |  | button | • Test Reports | Yes,No
checkpoint-status |  |  | checkpoint | 1.3 - Material procurement for construction
label | 9deb86ac-fb0c-5781-9781-3320e40094d2 |  | note | Ref docs - DoT Clause 304.03, 812, 204.04
label | 4e5f9488-d476-5ee3-aa4c-c467a5653eba |  | note | Acceptance criteria - HP: All crushed rock proposed for use on VicRoads funded works shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
label | 7c52698a-13d9-55e5-bbbc-cc50129794c6 |  | note | • The Contractor shall be responsible for the procurement of sufficient specified material to complete the work. The Contractor shall supply details demonstrating compliance of the materials with Section 801.
label | 1d9d6343-5e7f-5bf7-a71e-74aa089cd861 |  | note | • Water added to the pavement will be clean and suitable for construction and substantially free from detrimental impurities such as oils, salts, acids, alkalis, and vegetable substances, and have no more 1000 mg/L of suspended solids.
label | 417b795c-37c4-54f7-a938-e03a753dc5d4 |  | note | Freq - Prior to start of works
label | 87da74e8-cacd-5dc0-be33-9c206a372fbd |  | note | Key - H W I
label | 7d5b9f60-dd4d-556a-82fe-9ec8094604a5 |  | note | Resp - SE
label | 1d5843bf-6eba-5ddd-82ae-ffaa17b2e224 |  | note | SI Key - H
label | a9ea14e3-28c8-5904-b211-63335f7a7efa |  | note | Remarks/record -
button | 8c3c9034-6854-57c7-978e-0d902ed35612 |  | button | • Crushed Rock Mix Registration | Yes,No
button | af01d87f-f1c7-512c-9c69-95c3bde76f9b |  | button | • Delivery docket and material compliance checklist | Yes,No
button | 6123e4f5-b36c-549c-8b90-c59b0c1849b7 |  | button | • VicRoads Materials conformance | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Installation of Lower Subbase Layer
checkpoint-status |  |  | checkpoint | 2.1 - Construction - Jointing
label | 78900972-6ba4-5a01-9e32-4f0d48f26b49 |  | note | Ref docs - DoT Clause 304.07
label | 30130d8c-00aa-5acc-bd93-8bbb7fda5992 |  | note | Acceptance criteria - Transverse - Offset by not less than 2 m to any underlying pavement layers.
label | 275f9e27-36bc-59bd-9eec-1d17a862e22f |  | note | • Longitudinal - Offset by not less than 150 mm to any underlying pavement layers. Located within 300 mm of the traffic lane lines or within 300 mm of the centre of a traffic lane.
label | 6fd2b3f9-492c-5746-aa9d-cf65798f7c9e |  | note | • The exposed end of each lot and the exposed edges of any part width construction shall be kept moist until spreading and compaction has been completed over the entire layer.
label | 46f30bdc-e10b-5e7a-b334-c58a7366880f |  | note | Freq - Each Lot
label | 01861c8a-ecb8-56eb-ad70-e0ec498427bb |  | note | Key - S I
label | 7979ffe7-3c84-5086-885e-05c397e0787d |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.2 - Placement of Material & Testing Compaction
label | dd955adb-2c72-59e7-a6f1-5cc6f08bef5b |  | note | Ref docs - DoT Clause
label | 4b5ffe9e-476b-543e-aea3-73c14b7bc1a6 |  | note | • 304.06
label | 1313efe3-2520-5c18-9229-ac055b53c2cf |  | note | • 304.06 (b)
label | f04cfa67-6402-5be0-8f76-50c83db28258 |  | note | • 304.06 (c)(i)
label | 36174cc9-6fc6-5790-9fcc-37e1ee05a164 |  | note | • 304.06 (d)
label | d966b78d-1fd5-595b-b7e4-2c8baef071c7 |  | note | • 304.08(a)
label | 29b69ee5-667c-586d-83d7-9887b7f27bd5 |  | note | • IFC Drawings
label | bc55cd16-16a6-55b5-bb4f-9e721c480c34 |  | note | • Construction Work Pack
label | 577642c7-4777-592e-9a9b-b875bd2a32c1 |  | note | Acceptance criteria - Place and compact layers so that the surface finish is smooth and uniform.
label | 2f9311a1-87a4-5ffc-bc4b-41e2220fcb71 |  | note | • HP: Any material that has been compacted and then trimmed from the compacted surface to conform to the correct level or thickness as shown on the drawings shall not be re-used in the pavement construction without the approval of the Superintendent.
label | 3eea983c-2e2a-52ad-b5f4-d25a9f5f79c1 |  | note | • The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | f911cf37-83db-54b0-bbfb-3a49cb17f311 |  | note | • The subbase course shall be not less than the specified thickness by more than 15 mm.
label | 7b62a0fa-f09c-5207-8c08-a57c2cba6cad |  | note | • No point > 8 mm below a 3 m straight edge in any direction
label | d90793b4-dac7-58c6-940f-dabd6177673f |  | note | • No point >10 mm below a 6 m straight edge in any direction
label | 397849d2-1ea5-5efd-8d6c-b0d1ea9ce12b |  | note | • No Ponding of Water.
label | 775f7d64-d09b-56f8-8305-0db9c4303561 |  | note | ○ For material of nominal size > 40mm:
label | 5fc00657-ac1d-59db-bfab-cf9111c25fbd |  | note | • The first lot shall be placed as a trial section. Following acceptance of the trial section, the Contractor shall then confirm the moisture control and compaction procedure and submit the procedure to the Superintendent for review and record.
label | bc0dfdac-b01b-52cb-bddc-4f1f4ae62d85 |  | note | ○ For material of nominal size < 40mm:
label | a76dbbda-b70a-5385-b531-7b8a630f426f |  | note | • No trial sections needed.
label | 3f3c5324-02db-551f-b88a-a12295b4efc2 |  | note | Freq - Each Lot
label | 84135121-b28b-55ae-9347-aec9e1906f36 |  | note | Key - H I W
label | e9085903-830d-5e25-886a-1371b6ccab4c |  | note | Resp - SE
label | cea73a5c-2786-5329-8742-b473915284a7 |  | note | SI Key - H R
label | 356b02ec-d241-52ea-8a3d-17c9f1755373 |  | note | Remarks/record -
button | 49898788-ff7b-515d-ad99-c1936bf76db1 |  | button | • NATA Test for Compaction | Yes,No
button | 1eb745d5-492c-5234-933b-3fa78db037be |  | button | • NATA Test Report for Material | Yes,No
checkpoint-status |  |  | checkpoint | 2.3 - Testing – Stability (Proof Roll)
label | abb749de-297e-59f1-98fc-f85ab0add235 |  | note | Ref docs - DoT Clause 304.08(b)
label | 431e7726-69f8-54df-a8b5-36ace7c613b8 |  | note | Acceptance criteria - Test rolling of the subbase layer, irrespective of material size, shall be in accordance with the test rolling procedure that was submitted to, and approved by, the Superintendent.
label | 61537bf4-3a01-5296-a5bb-3834e8c8155c |  | note | • Area shall withstand test rolling without visible deformation or springing.
label | f94f5eb7-bbf5-59b1-a2ba-be419b06461d |  | note | Freq - Each Lot
label | d8721f56-2e85-57af-a2a9-502fac353ff2 |  | note | Key - H W
label | 955d2626-a43c-5aec-8d69-809d0d48a486 |  | note | Resp - SE
label | 330383b7-ef04-5e51-a201-d7533ec92b4c |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Protection of compacted layer
label | 6fc04e0b-e0a8-5b18-922d-64b0a3bfe29a |  | note | Ref docs - DoT Clause 304.09 Construction Work Pack
label | e0ffd55a-75b3-5e20-b623-30deea323680 |  | note | Acceptance criteria - Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
label | b97285c4-9630-57c7-9159-0a69ee6ec003 |  | note | Freq - Each Lot
label | 2527abfe-8635-519f-af47-0a0870756ba4 |  | note | Key - I
label | 1289f08d-81c4-5df6-8926-0c6f95aea369 |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Testing
checkpoint-status |  |  | checkpoint | 3.1 - Testing – Compaction
label | 71cb93ea-2e8b-54fd-a021-dbab1f515a21 |  | note | Ref docs - DoT Clause 304.08(b) 304.10 304.11 Table 304.111
label | 72a2548b-4971-5497-8e34-042c6c3d26fc |  | note | Acceptance criteria - Characteristic Density Ratio % (six tests): Not less than 98.0% Modified
label | b0565aab-5cba-51ff-8cdc-9157f61b6080 |  | note | Freq - As required by section 3.2
label | 61b8cf09-5efe-5338-86fd-b0af3fab6256 |  | note | Key - R
label | 83d894a2-eb50-59dd-8ef6-6d54da2f126d |  | note | Resp - SE
label | 439c9d50-31be-5b83-ae88-9e3c963087a6 |  | note | SI Key - R
label | 2441d932-081f-5ef9-88e4-61bb85a16893 |  | note | Remarks/record -
button | b253cbe6-a430-5884-85e7-6fb8599f03d0 |  | button | • NATA Test Report | Yes,No
checkpoint-status |  |  | checkpoint | 3.2 - Scale A Requirements for Post Compaction Grading and PI Testing
label | 693f8002-ac4b-5e7f-a407-435743e14913 |  | note | Ref docs - DoT Clause 304.11 (c) (i)
label | 2a32281a-aa94-569c-a690-bb64d40e8bed |  | note | Acceptance criteria - Where testing is specified in Clause 304.10(c) or (d) and Clause 304.12 requires it to be Scale A, all pavement layers shall be tested for post-compaction grading and PI at the frequency specified in Table 304.111.
label | a182f3d5-906a-5843-86ea-07187fe59d5d |  | note | • The first lot of each pavement layer shall be tested for post-compaction grading and PI.
label | 95d30c17-b67e-5835-8845-9f81066cca73 |  | note | • The Contractor shall immediately notify the Superintendent of any lot that does not meet the specified requirements and any subsequent lot shall be tested as if it were the initial lot.
label | 609053d8-25a1-52f5-a77b-a5b74777e9fe |  | note | • If any lot meets the specified requirements but is reworked to comply with the specified compaction requirements, it shall be retested for compliance with specified requirements.
label | d69dda11-2519-50ef-8f43-de6fc8c8fe80 |  | note | Freq - Each Lot
label | 5a8cbc8a-98aa-5f7c-8bdf-18fc7a659e5b |  | note | Key - H
label | cdb4da61-392c-5ad3-9481-a3665913cc93 |  | note | Resp - SE
label | e6a2e5a7-7dd4-5932-ac2d-d8bfa5b42e4d |  | note | SI Key - H
label | cd4e7bfa-2c0b-5fe8-bb3e-62e6dc95ff93 |  | note | Remarks/record -
button | 96d78990-e3dc-5a92-a363-94c77effcd30 |  | button | • NATA Test Report | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Post Compaction Grading (Nominal Size = 20mm)
label | d81a2dcf-fd84-5e48-9803-e1fd1cfe315a |  | note | Ref docs - VR Clause 304.10 (a)
label | 9f7e93fe-1ead-5b14-84b7-c5bc16076892 |  | note | Acceptance criteria - Sieve 26.5 mm – 100% passing by mass,
label | 7d1c6e73-a3f8-5f74-94e5-6b23760797cd |  | note | • Sieve 19.0 mm – 95 - 100% passing by mass,
label | c0a6ed53-61c7-5850-9575-f0076ebe9230 |  | note | • Sieve 13.2 mm – 75 – 95% passing by mass,
label | d90bb3c0-20d7-5a0b-935b-216022449248 |  | note | • Sieve 9.5 mm – 60 - 90% passing by mass,
label | 4c9370d0-767a-59c1-95b6-5ed9e069ccaa |  | note | • Sieve 4.75 mm – 42 - 76% passing by mass,
label | e8bc41ce-8be3-583c-8516-1b7757f9a4ee |  | note | • Sieve 2.36 mm – 28 - 61% passing by mass,
label | fd7ed6b8-9c1b-59e9-9d1e-1e8ce341f89f |  | note | • Sieve 0.425 mm – 14 - 29% passing by mass,
label | 63424bb2-38ea-55bd-98b9-a693efd5131d |  | note | • Sieve 0.075 mm – 6 - 14% passing by mass.
label | c8a065b2-563c-5198-b89a-39005e641ce2 |  | note | • Initial testing frequency: 1 test for each lot tested for compaction until 3 consecutive lots achieve specified requirements.
label | f462c67b-c35d-5ce1-9be5-738abe842228 |  | note | Freq - Each Lot
label | 45d43ea0-2286-5d53-8211-86ec27e5b648 |  | note | Key - R
label | dbc9bc92-fcc0-5b01-a683-7eaa35c7a1d7 |  | note | Resp - SE
label | a6110f33-7dc5-552d-b9a7-40f723681180 |  | note | Remarks/record -
button | 09d54dcc-ed10-5489-92e7-2281d4c7c170 |  | button | • NATA Test Report: Grading | Yes,No
button | 54bb9329-97ea-5c2b-965f-f09d6d98d093 |  | button | • Visual Inspections for Maximum Particle Dimension | Yes,No
checkpoint-status |  |  | checkpoint | 3.4 - Plasticity Index
label | 8d702aa9-4981-5cbc-bf80-1000612986b3 |  | note | Ref docs - VR Clause 304.10 (b)
label | 7371eb74-9e9f-51a1-a727-54deabb4c3f0 |  | note | Acceptance criteria - PI: 0 – 10%, Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
label | d62d3c2b-743c-5e61-8e3b-0b511a041645 |  | note | Freq - Each Lot
label | 662eb067-bc98-56c4-bb7e-6123fd230b47 |  | note | Key - R
label | 84d5c91f-b1a5-5975-99ba-cb27c33d1eae |  | note | Resp - SE
label | 4be01b32-5af9-5016-a3b1-e882b9da6962 |  | note | Remarks/record -
button | 8f643088-d301-5e90-a5fe-a8f01dd34c6c |  | button | NATA Test Report: Atterberg Limits | Yes,No
checkpoint-status |  |  | checkpoint | 3.5 - Testing – Reduced Frequency
label | faa7e5a7-8e06-5a69-b1c3-f1801d20b31a |  | note | Ref docs - DoT Clause 304.11 Table 304.111 Table PS3040.061
label | e2cb4b68-a4a4-5cc2-b329-3eee0bcc0f20 |  | note | Acceptance criteria - Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
label | a8f6f1d1-785a-5f38-aad3-45618a18b75a |  | note | • Testing may then be completed at the minimum frequency outlined in Table 304.111 and Table PS3040.061.
label | d9c93473-3917-5321-89bd-da8c995ec3e3 |  | note | • For Subbase, one Characteristic Density Ratio % (six tests) will be completed for every second lot.
label | 4624fb76-e2ca-5538-b0e2-0f01a149d614 |  | note | • Testing will be completed at the minimum frequency until such time as a lot fails to achieve the specified requirements. After a failed result, all subsequent lots will be tested until three consecutive lots of like material and work have achieved the specified standard, at which time the frequency of testing may revert to the minimum frequency.
label | a0e1a91b-769c-5958-b068-fb0956002c78 |  | note | Freq - Each lot
label | f00ae2e2-23e4-5c50-bb41-2b16f914abe1 |  | note | Key - R
label | 32f87c21-d203-503e-a1d6-ce7fe23ca9a7 |  | note | Resp - SE
label | 0819bcf7-26b3-5ddf-8d44-2414e7be275e |  | note | SI Key - R
label | 3f1c9a48-4c12-5a33-b4df-c14227c6d08c |  | note | Remarks/record -
text | 5cc30595-ce03-5d8a-aa26-f196568b35ab |  | textbox | • If using reduced frequency, provide lot number of previous lot tested:
checkpoint-group |  |  | section | 4.0 Completion
checkpoint-status |  |  | checkpoint | 4.1 - Survey as built
label | 40516cd4-e82b-52ee-bb5f-87b36832c897 |  | note | Ref docs - DoT Clause 304.06 Table 304.061 Table 304.062
label | 3b3f18dc-0d20-51dd-80e5-5a05105c855b |  | note | Acceptance criteria - Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
label | cb35fb57-7ea7-5800-9b8b-229cd131e105 |  | note | ○ Surface level checked for compliance with 304.06:
label | da2a24c8-fdd0-5d4a-a918-a7c8ee6982a7 |  | note | • Mean +6 mm to -10 mm with a max std deviation of 10 mm (Scale A)
label | c8e79556-b99c-572b-8895-dda6329e153f |  | note | • Min 80 measurements per lot (Scale A)
label | 782e2166-1ee6-5fe9-9e3a-89db758ee1c0 |  | note | ○ Number of survey points to be at random locations in accordance with VicRoads test method with minimum number in accordance with Table 304.061.
label | 898c2fad-d45c-57d1-ab32-4cf4b871ce77 |  | note | Freq - Each Lot
label | ad21d2e1-0c08-56f1-87a9-621e26e86b4d |  | note | Key - R I
label | b0293030-f8ad-5795-b2a6-62c48a1347af |  | note | Resp - SE
label | d873418c-2963-5853-95f4-78c29e97d23f |  | note | Remarks/record -
button | c24bd7d2-b4b7-503d-b52f-b50af1f89832 |  | button | Survey Conformance Certificate | Yes,No
checkpoint-status |  |  | checkpoint | 4.2 - Thickness of Pavement Layers
label | 00592ccf-6db4-546c-a304-c75cd20b9464 |  | note | Ref docs - VR Clause 304.06 (c)
label | 76421ecd-4a40-5dcc-b7b9-fbcf0a16e21b |  | note | Acceptance criteria - The following tolerances shall apply to the thickness of any pavement layer:
label | 9562c98d-2635-5a0f-aebf-a37e1f1eb6f6 |  | note | • The subbase course shall be not less than the specified thickness by more than 15 mm;
label | dfa5820d-c96d-5d8f-9074-6398428e7638 |  | note | • The base course shall be not less than the specified thickness by more than 10 mm and the average thickness of base over every 100 m section, over the full carriageway width, shall be not less than the specified thickness;
label | 1257b284-6902-590f-9edc-2ab8079c0296 |  | note | • The combined thickness of subbase and base courses shall be not less than the specified thickness by more than 15 mm.
label | 6110d383-d99f-59dd-8d1d-fecc83618153 |  | note | Freq - Each Lot
label | 0f929b1e-ec48-5c0d-8f77-716d125a532e |  | note | Key - R I
label | 42e02618-d257-53ac-9c80-2952bdd09af8 |  | note | Resp - SE
label | 9c71bc51-4efb-5ee2-a601-0834151af502 |  | note | Remarks/record -
button | cda87787-52b3-5a62-94f7-580fdfa240c3 |  | button | • Survey Conformance Certificate | Yes,No
checkpoint-group |  |  | section | 5.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 5.1 - Test Reports
label | f380ea94-538c-527f-a9c2-b95eb7c802a6 |  | note | Ref docs - VIC Roads Specifications
label | db73627c-167c-5a50-8786-624d6225b4c5 |  | note | Acceptance criteria - All Test reports received and Reviewed.
label | 37927a82-e42a-5284-8b8b-25559fafaf03 |  | note | Freq - Each Lot
label | 868846d0-3248-593d-a394-4a92d13bff4b |  | note | Key - R
label | e6ce1c12-3a38-5b60-b495-a457c75bb730 |  | note | Resp - SE
label | 73c0e856-8f89-5766-aca4-b1c24e6a6089 |  | note | Remarks/record -
button | a2ada059-7c23-5066-9db6-51d2e5bfc4dd |  | button | • NATA Endorsed Test Reports | Yes,No
checkpoint-status |  |  | checkpoint | 5.2 - Product Non-Conformance
label | 22c854ba-0ff1-575e-a995-e2f17a09a5f4 |  | note | Ref docs - CQMP
label | dfea45df-ecbe-5148-bf0f-f6c0ab0a3deb |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | d41d9b3e-0402-54d1-af1e-ccc41844b23f |  | note | Freq - Each Lot
label | e982308e-7ad0-594f-8195-33ec793f9694 |  | note | Key - R
label | fde1d45d-f03d-5655-8e77-f8da714d2910 |  | note | Resp - SE
label | b9505a46-1304-5c69-bea9-8e83ba3b2bc7 |  | note | Remarks/record -
button | f980fd33-2799-502e-90fa-9655afa1ffc4 |  | button | • NCR reports | Yes,No
checkpoint-status |  |  | checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
label | 1381efa3-d1e5-5822-bcd4-1ddd02867e82 |  | note | Ref docs - CQMP Lot Records
label | 73ed2239-6812-58c6-954c-4c966a71f679 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 23b243a8-ae1d-5f11-aaa0-ed5a4abee708 |  | note | Freq - Each Lot
label | cc3d85e0-fad7-5b6f-ad13-0e71b4a82841 |  | note | Key - R
label | c1bbf8a5-77f5-571d-8de0-5467b0cd9723 |  | note | Resp - SE
label | 75ae5bea-294a-5cf9-9bbb-7ce6f6458267 |  | note | Remarks/record -
button | 7aa62367-e24e-5204-b89b-07dcd9631157 |  | button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No
checkpoint-status |  |  | checkpoint | Works complete
text | 3a47eb81-9610-5dde-99ab-7ff2905e2412 |  | textbox | Name:
text | 8c3cc53f-3325-58b7-91e4-4ee784016eef |  | textbox | Position:
text | cd683afa-4f6c-56f5-af3e-d8a5a0535449 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 4e6ddc2f-1fb0-50c4-9c74-134cf8577471 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | dfbb99df-e935-53f9-adb0-eb81aae27235 |  | textbox | Lot opened date:
text | a6867644-50eb-52b2-a3e8-6351d470ad56 |  | textbox | Lot opened by:
text | e18ccb71-2db7-527a-8a82-e3d6f85a7687 |  | textbox | Date lot closed:
button | 1af647e6-a929-5f70-8906-8eaf48fda169 |  | button | NCR raised? | Yes, No
text | 1c48cb9b-3201-5241-8c50-9c3f3fcfcfed |  | textbox | NCR Raised Date:
button | 17a2c0c0-5f97-5f79-84f9-12ad68f30422 |  | button | NCR closed? | Yes, No
text | 0fe8b53b-6760-5b9c-86bf-f04bf2a54640 |  | textbox | NCR Closed Date:
text | 4a6a3124-6ed6-5c66-ba96-4f77f037a243 |  | textbox | NCR Number:
text | 90e01917-a5a8-5ba7-bb0d-37ba3aeb0b15 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0021 Conduit and Pit Installation |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0021 Conduit and Pit Installation | 5c965879-5d7d-41ee-992c-fdf141116985
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Boring under Carriageways
label | 2f713103-617a-5c3d-923a-76d8a5b2c458 |  | note | Ref docs - VR Clause 733.05
label | 5df04e79-e95d-542f-8120-eaf9662a1649 |  | note | Acceptance criteria - Boring by water jet not permitted.
label | 968fd953-5c07-5212-8f51-8c53f5312bc5 |  | note | • Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work.
button | 823fffd2-d9ca-5314-8286-2b3c64901d98 |  | button | Approval to proceed? | Yes,No,N/A
label | a2b1f52f-d66a-5863-8bf8-bfeab56d79bb |  | note | Freq - Prior to start of works
label | 24c6c6e4-c0b6-50d1-9f36-5244ef021436 |  | note | Key - H
label | 07acf559-c7fd-5147-bdb0-09532e014864 |  | note | Resp - SE
label | 49022b87-db93-5abc-a082-7db45fec5ca8 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 735f5e70-348d-511f-b99a-24bc661a8479 |  | button | Lot map | Yes,No,N/A
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 15c1828e-c21a-50a5-8209-76b6c7e4154e |  | button | Environmental permit | Yes,No,N/A
checkpoint-group |  |  | section | 2.0 Conduit Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance – Conduits and bends
label | 6f482625-6055-5a3f-85bd-02694d3fe93f |  | note | Ref docs - VR Clause 733.02 Table 733.041
label | 82befed0-7a06-5d20-9dce-7be674937cc7 |  | note | Acceptance criteria - Conduits are correct type, class & diameter and comply with AS1477, AS2053, AS4130 (as relevant), unless noted otherwise.
label | 2195aa03-fda0-5a4f-82dc-865f1e49f57f |  | note | • Electrical – Heavy Duty Grade, Rigid orange UPVC conduit to AS/NZS 2053.2.
label | 434942a8-0ab1-56f0-b815-6be9e47308bd |  | note | • Communications – Heavy Duty Grade, Rigid White UPVC communication conduit to AS/NZS 2053.2.
button | 4bf95e97-b172-5c45-ba17-46abc9680b7e |  | button | Have all the above materials been approved? | Yes,No
label | ca44bde3-19fa-5fa6-93f2-8723d3c4e57f |  | note | Freq - Each Lot & Each possession
label | 768b5955-c3a6-5e67-b80a-a99af822e350 |  | note | Key - R
label | 3819045d-b995-5514-8891-325d836a9627 |  | note | Resp - SE
label | 1bba3948-2a89-50cf-9dd4-51b9f6fcfab8 |  | note | Remarks/record -
button | 4bb8c6c7-a41d-5a2a-a6cc-cd63491482a8 |  | button | • Supplier Compliance Certificate | Yes,No
checkpoint-group |  |  | section | 3.0 Conduit Cover
checkpoint-status |  |  | checkpoint | 3.1 - Excavation and Cover Requirements
label | 2b3f3f1b-5688-5904-b4fb-e35ffc194d77 |  | note | Ref docs - VR Clause 733.05 Table 733.051
label | 401cf1a4-6a5d-58d5-9944-2b977048a598 |  | note | Acceptance criteria - Cover requirements for both electrical and communications conduits shall be:
label | 57fb2218-48d5-50f8-baee-855cb4bbb832 |  | note | • Pavement surface to top of conduit minimum 1200 mm.
label | 782c7cdd-3bea-5a85-8d79-f4874116c1a6 |  | note | • Invert of open drain to top of conduit minimum 750 mm.
label | 858789b2-6966-512f-bbbd-2f05fbdf066f |  | note | • Unpaved areas to top of conduit minimum 600 mm.
label | ea9eac26-a75f-5931-ad30-39d78d030569 |  | note | ○ Or else as specified on design drawings.
button | 4d627fe2-353b-561d-92d9-e05a21b100d1 |  | button | Has all the above been completed and approved? | Yes,No
label | 985aec8d-fa47-5ca7-ace0-c93e62539bc9 |  | note | Freq - Each Lot & Each possession
label | f9b1dfe5-33e6-5878-90ab-de3918c91cdd |  | note | Key - S
label | 1566fb7d-8743-52ec-8a26-d7374ecd9d83 |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0 Installation of Conduits
checkpoint-status |  |  | checkpoint | 4.1 - General
label | 224f2f7a-982b-58ba-8bd9-399530206724 |  | note | Ref docs - VR Clause 733.06 Table 733.061 AS/NZS 3000 AS/ACIF S009
label | 899e6132-aa2e-5d86-ad57-6d29fa4bf041 |  | note | Acceptance criteria - All conduits shall be installed as shown on the VicRoads Standard Drawings and Contract specific drawings, or as otherwise specified.
label | 10d1fd33-3d1e-530a-b575-6a3f1a2c6c64 |  | note | All conduits for electrical and communications cabling shall be installed to conform to the relevant requirements of controlling legislation, regulations, industry codes and standards, including:
label | 39a65921-46fc-5e64-8709-74e62bf8ac2b |  | note | • AS/NZS 3000 Electrical installations (Australian/New Zealand Wiring Rules)
label | 39768788-d8dc-5650-ae33-0086e59ec620 |  | note | • AS/ACIF S009 Installation requirements for customer cabling (Wiring Rules), and any other relevant requirements of the Australian Communications and Media Authority (ACMA) for connections to telecommunication carriers’ network.
label | 26f7637c-60b1-513d-94b5-610214e4aad3 |  | note | ○ Installation of conduits shall be carried out in accordance with the following:
label | 86c111c9-d771-5bd3-8faa-1d691ade537d |  | note | • HD UPVC Plain to be Thrust bore or Open Trench.
label | 7437cead-c0d9-5d3a-a0ad-26824570bf92 |  | note | • HDPE continuous (must have ID not less than that of 100 mm HD UPVC for electrical and 90 mm HD UPVC for communications) to be Directional Bore.
label | 1b4f90fd-7da9-52e2-b629-ccec66191ed6 |  | note | Freq - Each Lot
label | f2245e67-04bb-540f-b4b0-f96263914c39 |  | note | Key - I
label | fbe0ffeb-a64a-50a4-8992-c098c7087148 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.2 - Bedding Material/Placement
label | c1ac7761-6b01-5775-8def-36d010f5af25 |  | note | Ref docs - VR Clause 733.08
label | d8c55378-7fa5-597c-ae88-05367fe8ff89 |  | note | Acceptance criteria - Bedding material does comply with the requirements of Table 733.081.
label | 0d7decc0-4971-571f-8fd5-69ec9c7cdeb3 |  | note | • Minimum 80 mm bedding below conduits on earth foundation.
label | 3941b85e-975b-52f7-9961-11e15a79d1d0 |  | note | • Minimum 200 mm bedding below conduits on rock foundation.
label | ce1114d5-ad70-5f92-a514-295c4c4511c3 |  | note | • Bedding placed to full width of trench, and between conduits as shown on trench details on latest revision IFC drawings.
label | 7ed90e44-b4df-5d34-906e-df537400f4c2 |  | note | • Shaped sufficiently to maintain the conduit in line as the sections are placed.
button | d6d441e5-48f6-5b19-bcd2-db3c398d4a7a |  | button | Has all the above been completed? | Yes,No
label | 4f362462-c847-5998-909c-0c49929eca72 |  | note | Freq - Each Lot
label | 830dedc3-a290-54e1-9dd2-8bc83713cb4e |  | note | Key - I
label | 957ed6b2-7270-53e5-9148-8f91abf0f349 |  | note | Resp - SE
label | 7317d926-629d-542b-840f-0bea1aad3b50 |  | note | Remarks/record -
button | 859ec677-aea2-5121-b3d3-cbd93bbdbbe3 |  | button | • Material Compliance for Bedding/NATA Test Report | Yes,No
checkpoint-status |  |  | checkpoint | 4.3 - Bedding Material/Placement
label | f1a34b93-19bb-5928-8967-102d621bca7f |  | note | Ref docs - VR Clause 733.08
label | 703e10b8-20c4-5114-8446-d74194366010 |  | note | Acceptance criteria - Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by Superintendent.
button | b96e271a-aca6-5ac4-b920-f6c1bf92a749 |  | button | Approval to proceed? | Yes,No
label | d1259096-4fda-5cea-9b41-bc6eb1274294 |  | note | Freq - Each Lot
label | a03018af-fd3f-5c1c-a188-1cc14cc36815 |  | note | Key - H I
label | 8363fd9f-70fc-51e4-87e8-fb4264db6ffa |  | note | Resp - SE
label | 105f9681-b754-5991-9434-ab791088b820 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Bedding Material/Placement
label | 07ce8da0-e9ed-541f-a13d-8492246e2952 |  | note | Ref docs - VR Clause 733.08
label | 937b6d75-4b34-5bcd-b53e-50717a357535 |  | note | Acceptance criteria - When conduit sections are in position, additional layers of bedding material shall be placed and compacted to a height 150 mm above the bedding previously placed.
label | 873ef3cf-ed73-5db6-9793-d2133def20e9 |  | note | • Bedding material must not be the same material excavated for the trench, it shall be clearly identifiable as introduced material.
button | 72996614-1a6b-5ca5-acce-a56654cf11ea |  | button | Has all the above been completed? | Yes,No
label | 93e078b0-bf1e-59ea-b6d0-b224b5e12fd7 |  | note | Freq - Each Lot
label | 06672ae7-7068-5bb5-8395-55a15b5a5d36 |  | note | Key - I
label | c7d28aa2-a848-5621-82ee-8e4f874061f7 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.5 - Conduits for Traffic Signals/ITS/Public Lighting
label | 388b87c4-6d74-56db-84e1-29a39deab04b |  | note | Ref docs - VR Clause 733.06
label | 73d62461-e454-5c10-b666-a1cd6b3d027b |  | note | Acceptance criteria - a) All conduits shall terminate in a pit in accordance with VicRoads Standard Drawing TC 1207, TC-1230 and TC-2200 – TC223.
label | 5a41ff75-4722-545a-9b4f-310b0dbe5c55 |  | note | b) Only one size conduit shall be used for a complete run between pits; unequal size conduits shall not be joined in the ground.
label | 8e11b10e-4c14-5525-bfdf-2ae6dfe71a5e |  | note | c) All conduits shall be temporarily sealed prior to cabling to avoid blockage.
label | e550a327-0aab-547f-810f-e2a9a0fb9476 |  | note | d) Changes in conduit direction or depth shall be made by natural set or in the case of bottom entry, by means of a swept bend; elbows or tees shall not be used.
label | bc87a144-c825-5154-8dfc-0fb5037d5dae |  | note | e) All conduit joints shall be correctly prepared and sealed with approved solvent cement.
label | aa1f51e9-4251-52c2-960c-61f815135099 |  | note | f) Conduits for detector cables shall be installed as shown in VicRoads Standard Drawings TC 1207 and TC 1320; and
label | f4874ab0-1eee-5e93-8482-623b7f1691a5 |  | note | • A 50 mm electrical (orange) conduit shall be used to convey the detector feeder cable from the detector pit to the cable pit, as shown in VicRoads Standard Drawing TC 1207.
button | 01a5b2ae-6a44-5415-b4b6-ff6dd618915e |  | button | Has all the above been completed correctly and to a high standard? | Yes,No
label | 1235b95a-73f1-5654-89f4-e8793eec6a24 |  | note | Freq - Each Lot
label | f5584f9a-94c1-519d-a017-68eeb10c692a |  | note | Key - S I
label | 8c2ae869-ad5c-5cd1-a863-2813d83c02e1 |  | note | Resp - SE
label | 8d437bf9-fedc-5235-9cf9-1c94e8dc13eb |  | note | Remarks/record -
button | ab181abc-38d7-5b92-a8b3-b97937dd96d3 |  | button | • Installation Records from Subcontractor | Yes,No
checkpoint-status |  |  | checkpoint | 4.6 - Draw Cords
label | 5d56464f-d09a-5559-9e36-69493c271704 |  | note | Ref docs - VR Clause 733.07
label | 46fd5b54-ccc7-5b32-8fa5-40c25aa2bd65 |  | note | Acceptance criteria - Draw Cords to be 3 mm diameter and with a minimum breaking strain of 1.6 kN.
label | 9c8d12de-4f10-5abd-b89b-5a354e7f267d |  | note | ○ Where the conduit terminates in a pit
label | 40a6f279-c26d-55f2-a1ed-f5de365d19d7 |  | note | • Have no less than 500 mm of the draw cord tied to a marker peg 25 mm x 25 mm, no less than 300 mm long, left coiled in the pit for future use.
label | 930bb6d8-7d31-51a3-8cf6-f2f005bfbcf7 |  | note | ○ Where conduits do not terminate into a pit.
label | 64c70085-b87e-55dd-9d48-9d798be3afd2 |  | note | • Be tied to a marker peg 100 mm x 100 mm, not less than 400 mm long, driven firmly into the ground with the top 50 mm projecting above finished surface and painted yellow.
button | 798b14ae-b056-50b6-8896-501c534e6c08 |  | button | Has all the above been completed correctly and to VicRoads standard? | Yes,No,N/A
label | d303d998-09b6-5960-8828-5142e1aa78d8 |  | note | Freq - Each Lot
label | 23e9751a-3aa7-5cae-86e7-09fbb5a1529d |  | note | Key - I
label | 1d728f65-1bd3-5ecf-a0eb-390e472d08ec |  | note | Resp - SE
label | 00fa2c9f-b196-54a2-830a-1dd0d937f1f0 |  | note | Remarks/record -
button | ea61a4f7-5e60-51f8-8498-780d073ed458 |  | button | • Installation Records from Subcontractor | Yes,No
button | e514a86e-41f9-509d-ab39-83ab76c919f1 |  | button | • Material Conformance Certificate | Yes,No
checkpoint-group |  |  | section | 5.0 Backfill
checkpoint-status |  |  | checkpoint | 5.1 - Bore access excavation
label | e7a840ef-d2fd-59b4-8e70-168a4b0fd721 |  | note | Ref docs - VR Clause 733.05
label | 685a3020-6e57-5f0a-9073-f58d1b1381c1 |  | note | Acceptance criteria - Before backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative.
button | cfd40866-ad28-5b4e-b4a0-6d3cb957c7e8 |  | button | Has all the above been completed? | Yes,No
label | 8272c4c4-1cb1-56bf-a37d-8d4182000de4 |  | note | Freq - Each Lot
label | 3edb9183-2ed4-530a-b6bf-7a67150d019e |  | note | Key - H
label | f4ceb1fe-fc78-5d0b-8cbe-1d0a53446243 |  | note | Resp - SE
label | 51554504-036f-595a-80ae-079f456f5068 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material Properties
label | 4d248082-5992-5684-b184-e42777dcc0ad |  | note | Ref docs - VR Clause Table 733.081
label | ce7c2973-1e9e-570b-9e52-cfbc02ca1420 |  | note | Acceptance criteria - Backfill material properties to be as per Table 733.081.
button | 361b1edc-788a-5b0e-a3b7-a92edfb21e8d |  | button | Has all the above been completed? | Yes,No
label | c80e1313-b6f2-5e3a-a85d-18c2a7bdd4c5 |  | note | Freq - Each Lot
label | 564e566b-227f-5aa6-80fe-27a1d22d3814 |  | note | Key - R
label | 4101b591-eafa-544c-9bb4-65a64be25fc9 |  | note | Resp - SE
label | fd3f3dc2-ee3b-5adc-8190-7bf349b6d5a9 |  | note | Remarks/record -
button | 4f84725b-42b5-536a-8153-c0c7e7fd7872 |  | button | • NATA Test Report (if applicable) | Yes,No
checkpoint-status |  |  | checkpoint | 5.3 - Filling
label | 66f317ea-85b2-5cbf-81be-107d2e540c27 |  | note | Ref docs - VR Clause 733.08
label | c24cc143-5f84-5697-ace4-41a03cd633f1 |  | note | Acceptance criteria - Unless otherwise specified or shown on the drawings, selected and common backfill shall be placed and compacted as follows under, around, and above the conduit after the sections are bedded:
label | d23ee5c4-902e-5999-b4cc-2ff3499900e7 |  | note | • Place and compact selected backfill 400 mm above bedding (in non-trafficable areas) remaining fill to be common backfill.
label | c2cdd5d7-6fb6-51cc-93c4-264f8ff434ac |  | note | • Place and compact selected backfill to subgrade level (in area’s to be paved)
label | 9afa6fd6-22c8-58ba-bba4-6347ad46752c |  | note | Freq - Each Lot
label | 85b01c3e-5140-5adf-b8a5-f6beb3d51c6d |  | note | Key - R
label | bce7daac-dbe9-51fa-bae7-824c504d3f02 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.4 - Compaction - Areas not to be paved and below pavement
label | 4a17bec3-51fa-5391-8bf2-a9cbf3a91b82 |  | note | Ref docs - VR Clause 733.08
label | 3d20e959-f46f-5a3d-88fb-b1655eedad24 |  | note | Acceptance criteria - All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
label | 36dd9f44-bf4d-549f-808c-485fe3b0fce2 |  | note | • Compacted to refusal using handheld mechanical equipment.
button | b0e8e5ea-982a-57f0-80ec-ab3c74ba4fd4 |  | button | Has all the above been completed? | Yes,No
label | c6c67d7e-471c-5a8b-a884-2b766286855f |  | note | Freq - Each Lot
label | 8c6c121e-6a69-575b-b4ae-ec5ad4d62b7c |  | note | Key - R
label | e4b41784-aac1-51f6-adcc-9ecb5fc1d6b4 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.5 - Compaction – Area’s pavement layer
label | 66070f80-1df2-562e-aaa3-bb2f1d881c71 |  | note | Ref docs - VR Clause 733.08
label | 78ec6b14-bc49-5d69-a773-568a52c6f827 |  | note | Acceptance criteria - Where specified, pavement material shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three.
label | 74b05730-ab29-5dd6-a87a-67199c0d18e2 |  | note | • All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
label | 351b23e0-be36-502d-976d-fceb7acf273e |  | note | • All pavement layers shall be placed and compacted in layers to a density ratio of not less than 98%. The calculation of density ratio shall be based on Modified compactive effort.
label | 5d10baef-d2da-5f6b-9b53-4e8048fc86f6 |  | note | • Compacted to refusal using handheld mechanical equipment.
button | 648591fd-fe0f-5345-98f0-bb42f639845e |  | button | Has all the above been completed? | Yes,No
label | 879f0825-2347-51d7-af7d-9c4a7ac788ff |  | note | Freq - Each Lot
label | 9d043d10-a87b-5999-a3da-5b6eb6dde889 |  | note | Key - R
label | ebd61d4a-25ee-5749-8e74-8e6ddab7b4c8 |  | note | Resp - SE
label | ad7e2341-e96a-5471-964c-0be4f94bf4ef |  | note | Remarks/record -
button | afa74d2b-c245-5002-8eb4-65eb5b867571 |  | button | • NATA Test Report (if applicable) | Yes,No
checkpoint-status |  |  | checkpoint | 5.6 - Warning Tape
label | a7038d60-b0dc-59fd-b974-c31ea879910c |  | note | Ref docs - AS/NZS2648.1
label | ef84ea1f-ee9c-5faa-883b-23a637c99d76 |  | note | Acceptance criteria - Where marker tapes overlap electrical tape to overlay communications tape:
label | b5bef862-2b9c-5a2a-9850-3ac38dbb00c0 |  | note | • Marker tape 100 mm wide complying with AS/NZS2648.1 coloured orange with black lettering “DANGER BURIED ELECTRIC CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits in all trenches where electrical conduits are provided.
label | e94e3b9e-3ca0-5ed4-a4b7-6effc0b505b6 |  | note | • Marker tape 100 mm wide with two stainless steel tracer wires coloured white with black lettering “DANGER BURIED COMMUNICATION CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits. In all trenches where communication conduits are provided at least two meters of each tracer wire shall be anchored to and neatly coiled in each communication pit.
label | 3e2b0365-b9a7-554a-8c8d-1470844d0061 |  | note | • Where both electrical and communication conduits are provided in a trench two marker tapes shall be provided one for electrical and the other for communication conduits.
button | e07e1649-8060-590a-a66d-1fb530477299 |  | button | Has all of the above been completed? | Yes,No
label | 6c8ecb60-44db-5ed8-96cc-e0c6c74a107f |  | note | Freq - Each Lot
label | 57a3c365-b0b7-55d8-914f-7a95501cccf2 |  | note | Key - S
label | f3c198d7-e6de-5e16-b882-8c3613d173aa |  | note | Resp - SE
checkpoint-group |  |  | section | 6.0 Installation of Pits, Lids and Cables
checkpoint-status |  |  | checkpoint | 6.1 - Cable Pits & Pit Lids
label | ccc76270-d86c-59ca-926b-76970fb6cd2a |  | note | Ref docs - VR Clause 733.09
label | 899262eb-8b2a-5433-9c0c-4aecad00cbb7 |  | note | Acceptance criteria - Before the pit lid surround or pre-formed collar is cemented into position an inspection by VicRoads Superintendent or representative must be carried out.
label | 3a2107c1-6f82-5cad-8888-f69c94d6a682 |  | note | • Install cable pits in accordance with the design drawings and VicRoads Standard Drawings TC-1210, TC-1220 and TC-1230, TC2200-TC2232.
label | 3e399717-f832-51ab-8abe-47f8eb5f1bcc |  | note | • Top of pit lid matches the surrounding finished surface level fits neatly without movement.
label | f653ec13-8fa0-546e-b70a-08c150f2f2e3 |  | note | • Pits watertight and suitably drained.
label | 5d47d084-838a-543f-8d52-c1aaebde2963 |  | note | • All conduit connections to cable pits shall be neatly made and the ends of the conduits trimmed off and fitted with a conduit bush. The area between the conduit bush and pit wall shall be stopped with a suitable sealant that bonds to the pit wall and the conduit.
label | b5c82cd1-20bc-5dce-b94d-9a0e99ab5010 |  | note | • Heavy Duty Pit lids provided for pits in the road pavement.
button | 859c00fe-5062-5215-a524-114805f9c42c |  | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
label | 09745fce-7dd1-569d-8cbb-dde3a6f53b2a |  | note | Freq - Each Pit & Each possession
label | 7e82d65b-c82a-5cef-8aae-2657e6194871 |  | note | Key - S I
label | f960f603-6bc7-558d-a909-f2103242db6c |  | note | Resp - SE
label | e414f501-9240-5e32-85cc-cdcdd375d69c |  | note | SI Key - H I
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Detector Pits for Traffic Signals
label | ce1260f2-aa78-5567-8649-5e7881ef7c58 |  | note | Ref docs - VR Clause 733.10
label | ef81f1be-81fa-5fc3-9d53-7184b94ad329 |  | note | Acceptance criteria - Install detector pits in accordance with the design drawings and VicRoads Standard Drawings TC-1310 and TC-1320.
label | 911cbbe4-3b46-5110-a90e-eeabb6fe7c7d |  | note | • Fix pit cover securely using the fixing device supplied.
button | 881beee6-726b-56a3-b13f-9e7ae39efcf2 |  | button | Has all the above been completed correctly and to a high standard? | Yes,No,N/A
label | 76a1e091-2f43-5581-948a-4385fe9e7fca |  | note | Freq - Each Lot
label | 92504c3a-18dd-5760-a40b-46e74f1624fd |  | note | Key - S
label | 146d0d41-c457-5b2f-b0a8-159d0af4501e |  | note | Resp - SE
checkpoint-group |  |  | section | 7.0 Completion
checkpoint-status |  |  | checkpoint | 7.1 - As-built Information
label | 4f936f2a-2e03-542b-b566-aab18d8b3bcb |  | note | Ref docs - VR Clause 733.12
label | 7e3a2a9f-8c1b-56d6-b149-3dabc97aa3ed |  | note | Acceptance criteria - Identification and recording as follows:
label | 937c4b94-392a-50fb-8141-5bb6d311c528 |  | note | • All conduit locations not identified by pits immediately installed at the ends shall be marked with pegs 75 x 38 mm stakes projecting 0.4 m above the ground, with the top 150 mm painted yellow, or as otherwise agreed by the Superintendent.
label | 3bce82db-d1c4-5540-9dce-c4a5997863d2 |  | note | • Conduits under road pavement shall be marked with stakes clear of the road pavement.
label | 95b5487c-3d7c-5eb4-b6a0-dc813f03e881 |  | note | • Conduits not under road pavement shall be marked with stakes at the ends, at changes of direction, and at intervals of not more than 30 m.
label | 8aabdee1-a578-5f3a-b237-25bf2d8b67e3 |  | note | • The actual installed location and depth of conduits on the as-built drawings.
button | 2d53349a-ece4-5777-a488-c45881b72d90 |  | button | Has all the above been completed correctly and to a high standard? | Yes,No,N/A
label | 115e63ad-1a2e-54b8-b14f-34b0868507ca |  | note | Freq - Each Lot
label | eda43d3f-39a4-5648-86bf-ae7b0847c3bd |  | note | Key - R
label | 5ebd348b-1d0b-568f-9a62-2ffdfb27ac83 |  | note | Resp - SE
label | 21b61705-b439-5ef6-b80a-a5d18c3f23a0 |  | note | Remarks/record -
button | f9aa62a3-3822-5a27-8e90-d2dbe8cffb86 |  | button | • Survey Conformance Report | Yes,No
checkpoint-group |  |  | section | 8.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 8.1 - Test Reports
label | 2eac14ce-462c-5233-b133-171e51cf6eb0 |  | note | Ref docs - VIC Roads Specifications
label | 4f93723b-0448-576b-8797-59a15a166b01 |  | note | Acceptance criteria - All Test reports received and reviewed.
button | 6ed198c5-ca75-5426-93b9-82a7d62767e2 |  | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | ce602c01-e0bf-5262-96ad-f92d6dfd3120 |  | note | Freq - Each Lot
label | 33b59de8-047b-5ff1-964c-6d9018fb4520 |  | note | Key - R I
label | a515282b-d63d-55a2-932d-70b39a219280 |  | note | Resp - SE
label | ca9e87a6-834e-51d4-b9ea-e2700deff95a |  | note | Remarks/record -
button | fa619d9d-bc93-591f-9617-ab695457c1b6 |  | button | • NATA Endorsed Test Reports | Yes,No
checkpoint-status |  |  | checkpoint | 8.2 - Product Non-Conformance
label | 4abf9de0-aa3c-5321-8a23-3fe13b7154e4 |  | note | Ref docs - CQMP
label | e8648647-76da-5d6b-9a53-48faccb217e1 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
button | a1834f63-f8b0-5115-a585-431939b4004c |  | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | a941677a-2ce7-5e66-bed0-3cb609941c09 |  | note | Freq - Each Lot
label | cc178ab3-071f-5607-9637-4a5de8835bd3 |  | note | Key - R
label | 8f9e8d18-e7c1-5dcd-9dbf-8e39ed8c9995 |  | note | Resp - SE
label | a0683b24-3773-57ac-813b-47b9070189ea |  | note | Remarks/record -
button | ae918ab1-df6a-5ca1-9d6e-ea0a2c7887b4 |  | button | • NCR reports | Yes,No
checkpoint-status |  |  | checkpoint | Works complete
text | 45968b91-e51d-5c2b-bbd6-ae7cb76de694 |  | textbox | Name:
text | ae75437b-d62e-5aea-a0f7-57580366dc96 |  | textbox | Position:
text | 91d6fe5b-7653-5e56-93b7-853779aa10f5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 57cefa97-ae51-5ee7-bfd8-1c7ed787f5a5 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | f84904ef-30b5-5d71-a7db-cdabfd642bf9 |  | textbox | Lot opened date:
text | c858b63a-0872-5da1-a0fc-44735173b675 |  | textbox | Lot opened by:
text | 88987da4-bc8a-5cb2-bb5f-aa10421e8645 |  | textbox | Date lot closed:
button | ff5ea8c1-bad3-5d5a-ab7b-8bb0b7222b72 |  | button | NCR raised? | Yes, No
text | ec2ea67d-9b72-5e0c-82c1-7db7c0c9859a |  | textbox | NCR Raised Date:
button | 431d01de-de21-52e9-bc93-f50215bc028f |  | button | NCR closed? | Yes, No
text | 804aa37f-51a5-53a3-a48a-89f11a2b1bfb |  | textbox | NCR Closed Date:
text | 4ffe176c-2efd-5a56-b2ce-a4d7e473ed18 |  | textbox | NCR Number:
text | 5a819f84-5186-5822-a61b-b1e2fcdda70a |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A | 7c815c14-dd38-4c3e-885f-4d0e050c79e6
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.2 - Site excavation and Material classification and supply (Site only)
label | 4899ce53-c870-5fbe-aba0-fbc8647ecbe3 |  | note | Ref docs - VR Clause 204.06 (c) 204.04 (b)
label | 74386f2a-0e78-52c9-a725-726f91b15b15 |  | note | Acceptance criteria - For site-won material: Prior to commencing excavation in any area and during excavation work, the Surveillance Officer and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04. Material classified as silt prior to compaction shall not be used as Type A material without stabilisation to the satisfaction of the Surveillance Officer.
button | 9f6ba596-8d3d-5477-a677-ce80a731e6d7 |  | button | Has all of the above been completed and approved? | Yes, No
label | b05f62c2-84ba-586c-ab0a-9f5cdd7384b7 |  | note | Freq - Each Lot
label | 510d51d8-b578-5468-961f-c838fe513115 |  | note | Key - H
label | a00d8b79-cf54-5caf-ad3b-b2be78bc1738 |  | note | Resp - SE
label | b4b78f0f-ba67-5338-8129-0b69d141434f |  | note | SI Key - H
button | b1cd9f41-4938-5cf2-9a3d-08212627471b |  | button | Remarks/record - Compliance Certificates/ Test Reports | Yes, No
button | 7d46934f-60b2-505c-bfbc-bc04afe293da |  | button | NATA Test Reports: CBR, Swell, Permeability, Grading, PI | Yes, No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Set out
checkpoint-status |  |  | checkpoint | 2.1 - Set out and survey land appropriately for intended works.
label | c55496ea-53fd-5c32-90ed-3e941dc6ff68 |  | note | Ref docs - VR Clause 204.03 (a)
label | 8d5cd10f-6bc3-55f1-9b56-3b2a58dedf52 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per design IFC drawings.
button | 68172d3f-14e1-5015-b5d3-aebf0f8c6921 |  | button | Has all of the above been completed and approved? | Yes, No
label | 95312752-fd59-5177-97cc-8e2155c957ff |  | note | Freq - Each lot
label | e66e8784-3ba2-5e89-a187-c4498a844e62 |  | note | Key - R
label | 499f7f2e-ad9a-5a49-871f-d3e324b1f758 |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Placement of Type A Material
checkpoint-status |  |  | checkpoint | 3.1 - Underlying Layer Conformance
label | b453ce4b-5e3f-53af-b716-cfbc1ad5aad5 |  | note | Ref docs - VR Clause 204.10(b) 204.06
label | 485ecb09-e2f9-5418-9adc-0a5865b956c6 |  | note | Acceptance criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. Any unstable areas detected by test rolling shall be rectified. Where ground water or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. The Contractor shall not commence playing any fill on the prepared areas until the area has been reviewed by the Superintendent.
button | a6b1b539-962e-580c-ade7-263e28bb8311 |  | button | Approval to proceed granted? | Yes, No
label | e4d25c49-d015-57ab-8a44-9f127d524482 |  | note | Freq - Each lot
label | fbba7f81-4305-5d82-9428-fde4635d7b73 |  | note | Key - H
label | a4135598-bd83-583f-b3d1-c7d959d2709a |  | note | Resp - SE
label | 9b86f2da-8ce4-56d2-b8ca-0ee4745cc991 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Placing of Geotextiles (If applicable)
label | 24756120-dffe-5e53-85ba-a31b45acc026 |  | note | Ref docs - VR Clause 210.05 IFC Drawing
label | 67cb12dc-9c45-5d95-8ecb-161e34066fc4 |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval from the relevant Surveillance Officer. Geotextile shall be placed to the limits as shown on IFC Drawings without punctures or tears. If these occur, they shall be rectified, or the entire roll of geotextile replaced prior to covering. Geotextiles in subsurface drains shall be placed to conform to the approximate shape of the excavation and fully envelop the drainage material. All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
button | 6607846f-a186-59de-ac78-d4c01358da03 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 5242bca1-d5fe-5668-99a2-4d874d152303 |  | note | Freq - Each lot
label | bc6c2605-2209-5549-8fa1-e7cf75642ffa |  | note | Key - H
label | 60b5fef1-2192-5805-8d35-ae66d4a7e1ed |  | note | Resp - SE
label | 926b67c8-d192-532e-acd3-1588f2c84699 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Placing of Fill
label | 0d0cbde3-fe2a-578e-80ba-5f0a66c48de6 |  | note | Ref docs - VR Clause 204.10(d)
label | 8718ae92-4f66-5f8c-a445-510311acdd6b |  | note | Acceptance criteria - Spread and compact in uniform layers not exceeding a compacted thickness of 200 mm. Visual Inspection for maximum particle dimension Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4H:1V, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be not less than 1 m.
button | e9957b99-ceb0-5e7d-86b7-6993c36f1ff8 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | ac16f695-a77c-5210-be67-bc280d3adacd |  | note | Freq - Each lot
label | 31955e35-e343-5725-819b-65101a1a227c |  | note | Key - R
label | 79cc6b74-2e6c-541e-8cfe-8bed8bd68faf |  | note | Resp - SE
button | 6abd6bc3-97aa-532f-b5fa-335d010c1f97 |  | button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
checkpoint-status |  |  | checkpoint | 3.4 - Keyed Fill Layers
label | 54faa6e4-7a37-5ac1-a39f-4f1db79c2d7d |  | note | Ref docs - VR Clause 204.10(d) Construction Work Pack
label | e617b562-28f3-5cef-b773-ec90f6c2055f |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
button | f732a7e8-d829-5c4e-aaed-f3f759ea1ba0 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | b6be02f0-a5bc-5d1d-9c1b-948493378bdd |  | note | Freq - Each lot
label | 2a9a7f22-199f-589d-9806-c530de4c9039 |  | note | Key - R
label | 17e2d07f-9f1e-59f1-8737-b84ee5edf579 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Test Roll of Type A fill layer.
label | bfa68bdb-1caf-53d1-bad3-f78b0a600521 |  | note | Ref docs - VR Clause 204.12 173.03 Construction Work Pack (Test roll procedure in specification 173.03)
label | d8c3e18b-4225-5f09-9cb4-995df79438e5 |  | note | Acceptance criteria - Each layer should be test rolled immediately following completion of compaction but if test rolling is carried out at a later time the surface of the layer shall be watered and given a minimum of three passes with the test roller prior to commencement of test rolling. Surface shall withstand test rolling without visible deformation or springing.
button | 84b6b8e7-9cd5-59eb-bbdf-e455881a9ef7 |  | button | Has all of the above been completed per standard and approved by relevant authorities? | Yes, No
label | 27b64875-46c7-59e4-afb8-2d233d6a705a |  | note | Freq - Each lot
label | f2ad810a-72e0-55ad-81ad-9a931271aa39 |  | note | Key - H
label | 45b736b7-3d59-5e4f-ae2c-86066a0ba948 |  | note | Resp - SE
label | 6eabd4ee-e282-5aa5-8554-7cdc51a59364 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Fill at Structures (if applicable)
label | 3d1b9a45-4621-57ad-a7c9-cf0beea4c082 |  | note | Ref docs - VR Clause 204.11 (b) Table 204.111 Construction Work Pack
label | 1fc89f7d-4430-5597-9227-891163c80480 |  | note | Acceptance criteria - No Fill to be placed within 3 m of structure until the foundation is reviewed by the relevant Surveillance Officer. Culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
button | bb907021-fea1-5fdb-bd70-b839fa653df0 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | e5c682f6-6406-5766-bb00-41abe75b33c8 |  | note | Freq - Each Lot
label | 640d9219-33d6-5949-8ae4-e0b2bb3e495b |  | note | Key - H
label | 13d9aa9f-e227-537d-a8a4-b2e0b98c88d9 |  | note | Resp - SE
label | 77a79162-e95e-5f89-a9c8-696111904ac9 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Fill within 300mm of structures
label | affbe707-1bc5-5236-a6da-7f69070fb8f1 |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | b41634b6-29db-509c-95e2-d7ad9d92cbeb |  | note | Acceptance criteria - Use of geo-composite drainage material or Permeable Fill in accordance with 204.04(f). Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111. The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
button | 8e2e6033-c0a3-5e68-9314-7703e8c1cd41 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 67a1399e-1e02-57b2-8ee1-b6db3a04a422 |  | note | Freq - Each Lot
label | ddf7b854-5dbb-5b94-9000-aca75116e63d |  | note | Key - R
label | de751cc3-3cc5-5a76-9547-b9fa65a27587 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.8 - Fill Material against Concrete Structures
label | b902bf33-1cb9-5a6f-aa24-f816f79dcdbe |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | b63b0405-2dc4-5c65-b47d-4a6617279f1b |  | note | Acceptance criteria - No material shall be placed against concrete within 14 days of casting.
button | f1290e94-ac1b-5055-8f6c-41d48cb6be1e |  | button | Has all of the above been completed per standard? | Yes, No
label | e897928b-bf04-5f65-8831-6be5af45e6f6 |  | note | Freq - Each Lot
label | 420740cf-2f89-526b-916f-20acf92d21b8 |  | note | Key - R
label | a33797c3-7f56-5be6-847f-0beb74c3f160 |  | note | Resp - SE
label | 8d962ebf-3ea1-5453-aceb-1239ee1ddc00 |  | note | Remarks/record - Concrete Pour Recorded
label | 03f5f130-b929-5b07-afa1-39bed07d7d8d |  | note | NATA Test Reports: Compressive Strength
checkpoint-status |  |  | checkpoint | 3.9 - Treatment of Unsuitable Material
label | e78820e0-cd0d-5c20-bd95-ebdaf86ce2f4 |  | note | Ref docs - VR Clause 204.07
label | fd6faa92-6512-5c07-9836-aec3d9bc0e5b |  | note | Acceptance criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
label | 8fda4ebf-153a-5c85-95d5-e1fb7a8e0952 |  | note | Freq - Each Lot
label | 11b22116-1b63-5ca3-b53c-7cf269139c7e |  | note | Key - H
label | bcb4f358-384a-5f04-8046-cfd646641e3f |  | note | Resp - SE
label | 6c8cc94d-6757-58f5-a5f6-d29b6c589589 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Geotechnical Testing
checkpoint-status |  |  | checkpoint | 4.1 - CBR / Swell
label | de53b4d7-42b2-5e6b-a835-c495f3eaa7d5 |  | note | Ref docs - VR Clause Table 204.041 204.141 Table PS3020.051
label | 2e71621e-01d4-5aa0-8736-08e99a87d343 |  | note | Acceptance criteria - Unless otherwise specified: CBR: ≥ 6%, Swell: ≤ 1.5% (1.0% for Verge Material). Initial testing frequency: 1 Lot test to determine Assigned CBR and swell.
button | c958215b-a34f-53ab-ad01-6ff13f3575e3 |  | button | Have the ideal results been achieved? | Yes, No
label | 29939a0a-e62b-582f-add8-c783a089a0d8 |  | note | Freq - Each Lot
label | c517dd61-af63-543a-9002-fe5e697a2a84 |  | note | Key - R
label | e6ff0a67-45c3-56f7-98d7-ad1befb5574c |  | note | Resp - SE
button | a7727933-9ffe-5ce3-8386-aeef7a1d459d |  | button | Remarks/record - NATA Test Report: CBR, Swell | Yes, No
checkpoint-status |  |  | checkpoint | 4.2 - Post Compaction Grading
label | 517683b8-140c-515b-9dc4-c2eb651618b6 |  | note | Ref docs - VR Clause Table 204.041
label | 6c528777-71db-5fce-9572-166fec6941b0 |  | note | Acceptance criteria - Sieve 75.0 mm – 100% passing by mass, Sieve 4.75 mm – 40 - 80% passing by mass, Sieve 0.075 mm – 10 - 40% passing by mass. Initial testing frequency: 1 test for each lot tested for compaction until 3 consecutive lots achieve specified requirements.
button | 9026adc5-7043-53c1-b6b0-b6506991f6d4 |  | button | Have the ideal results been achieved? | Yes, No
label | ca6e2599-2c17-501b-a898-03d217a165f6 |  | note | Freq - Each Lot
label | b34f22b9-fb7e-5000-834b-461b8854a4d4 |  | note | Key - R
label | 9071ce16-e3e9-5c7d-a8be-f4e2b203975d |  | note | Resp - SE
button | 860492a3-a25e-546f-8519-8057fa576f41 |  | button | Remarks/record - NATA Test Report: Grading | Yes, No
button | 8d5ca5ef-72a3-513b-b944-9ad78164baa5 |  | button | Visual Inspections for Maximum Particle Dimension | Yes, No
checkpoint-status |  |  | checkpoint | 4.3 - Plasticity Index
label | 491730d0-800b-5504-870b-1da5d5e32186 |  | note | Ref docs - VR Clause Table 204.041
label | d14d52d0-da24-5e4a-b30f-353b2e4ddadd |  | note | Acceptance criteria - PI: 6 - 25, PI x % Passing 0.425mm: 1000 Max. Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
button | f9d6b7df-4775-5d8b-9080-297cb7deab3d |  | button | Have the ideal results been achieved? | Yes, No
label | 34b5672f-c9d8-5d88-a8cc-f2067f7a2446 |  | note | Freq - Each Lot
label | e879b056-4aa9-5f35-a05b-5370c7cc415c |  | note | Key - R
label | 573a220e-e621-5d68-a508-1852c38b3344 |  | note | Resp - SE
button | 97cc3f8d-9844-587e-b1c7-68f7c8993793 |  | button | Remarks/record - NATA Test Report: Atterberg Limits | Yes, No
checkpoint-status |  |  | checkpoint | 4.4 - Permeability (Capping & Verge Material only)
label | 844cfb8b-0fd3-537c-bfa3-e08ec72b6405 |  | note | Ref docs - VR Clause Table 204.041
label | 624850d0-be2c-54fb-a047-7dccfaa0a41a |  | note | Acceptance criteria - Permeability: 5E-9 m/s Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
button | ce5be331-73d3-550b-a5bb-4be0a605bed3 |  | button | Have the ideal results been achieved? | Yes, No
label | 28847810-fc67-5410-8113-25b736b308e6 |  | note | Freq - Each Lot
label | 76c2b7dc-3689-5b8f-80fd-4a2d97ac6d8b |  | note | Key - R
label | 27af8b3c-32d3-5125-ae1e-121eaa0b2806 |  | note | Resp - SE
button | b5c41d48-d8bf-5200-a18b-51527c2a7fcf |  | button | Remarks/record - NATA Test Report: Permeability | Yes, No
checkpoint-status |  |  | checkpoint | 4.5 - Compaction Testing
label | 5b680f9d-00ec-5e49-89ba-c0c84e67682c |  | note | Ref docs - VR Clause Table 204.131 173.04(d)
label | 2a81a371-0149-59be-b302-5e41b0d20cf6 |  | note | Acceptance criteria - Minimum Characteristic Value of Density Ratio: 99% (Scale A), 98% (Scale B). For small areas (<500 m2): Mean value of density ratio: 101% (Scale A), 100% (Scale B). Initial testing frequency: Each lot until 3 consecutive lots meet compaction requirements.
button | c3c95374-84e0-5591-9202-7edf12b25977 |  | button | Have the ideal results been achieved? | Yes, No
label | 7d736c5a-6fd1-59f8-9f6d-c0b8833a6ed1 |  | note | Freq - Each Lot
label | 91f3743a-5aa2-5a36-85ca-61069548c53d |  | note | Key - R
label | d5024776-0401-586b-81a0-0ddefd057ed7 |  | note | Resp - SE
button | 550d1ab2-2499-5a8c-b0ec-398164519437 |  | button | Remarks/record - NATA Test Report: Compaction and Moisture Content | Yes, No
checkpoint-status |  |  | checkpoint | 4.6 - Reduced Frequency of Testing
label | 4a15c94e-89d5-5102-8dd4-0eb2c8df9785 |  | note | Ref docs - VR Clause 204.14 – Table 204.141
label | f78852ab-8bb0-5afe-9fcb-dc850bbd6249 |  | note | Acceptance criteria - Unless otherwise specified: Material properties (Scale A): Test at the initial testing frequency, if compliant, seek approval from Surveillance Officer for minimum testing frequency. Material Properties (Scale A): CBR/Swell: 1 test every 2 lots. Grading: 1 Test for every 2nd lot PI: 1 test every 4 lots Permeability: 1 test every 4 lots Material properties (Scale B): Test initial lot and no further testing required until changes in physical property/material source are observed. Compaction / Moisture Content: Reduced frequency: Test every 2nd lot.
button | 7b6c43d6-f0e6-5d85-9ab5-58bac61d2c0b |  | button | Have the ideal results been achieved? | Yes, No
label | bb538ba0-e24b-5fb3-a439-5ecc164f2744 |  | note | Freq - Each Lot
label | 9c84ded7-3dac-5e9f-9478-c07fdac94353 |  | note | Key - R
label | be3a3b5f-eb01-505f-b982-4c9a1f3bbaa9 |  | note | Resp - SE
label | e2f3690f-effc-5c3d-97a4-bd03f683676d |  | note | SI Key - R
button | ec588487-7ceb-5c00-abfb-15db4926cad6 |  | button | Remarks/record - NATA Test Reports: CBR / Swell Grading PI (Atterberg Limits) Permeability Compaction | Yes, No
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - Conformity with Drawings
label | e4e2bb80-bb5b-5839-9927-9d757372f611 |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | 2c6cecff-e831-592d-b071-c3a039666011 |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements. · Scale A: mean +5 / -15 mm Max S 12 mm. · Scale B: mean +5 / -25 mm Max S 15 mm. · Alignment: ±50 mm. Scale C - random levelling not required, no point > +10 / -30 mm.
button | 384cf521-0d80-5d30-b217-20fa4948015f |  | button | Does the final product conform to the above criteria? | Yes, No
label | 64fb6347-cf20-55f6-a48c-ee1e76e2159b |  | note | Freq - Each Lot
label | 097bc6ab-f57b-5bb2-897f-b7f82051fda3 |  | note | Key - R
label | 5a532c9c-98d6-56d1-885b-20e0e6608e3b |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | c04d6b9a-291a-569e-b9c0-dde17178aab1 |  | note | Ref docs - VR Clause 204.15
label | 6bf075e7-48aa-5650-9b3b-57906bee5db6 |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | 86ffd096-ffcd-5d57-8511-2c2e1f91377e |  | button | Does the final product conform to the above criteria? | Yes, No
label | 233e309a-7324-5979-ad22-1f2f97486b10 |  | note | Freq - Each Lot
label | 2edf02e2-f682-5830-9d40-e546c1fe024e |  | note | Key - R
label | 0cdb54af-aebf-53e3-a569-cc42d8dfc039 |  | note | Resp - SE
checkpoint-group |  |  | section | 6.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 6.1 - Test Reports
label | 625cbc8f-1289-5cfb-ac58-a5023f4822ed |  | note | Ref docs - VicRoads Specifications
label | 2791355a-cc34-5ff3-b9e0-8ca73c1bc53c |  | note | Acceptance criteria - All Test reports received and Reviewed
label | bddca4c4-7de7-5378-994c-0e01957c64e5 |  | note | Freq - Each Lot
label | b4765b0c-7925-5180-a7da-b710a298cba1 |  | note | Key - R
label | 3eb74f90-1dd6-5a22-ae18-f68634536a7b |  | note | Resp - SE
button | 28b307ef-dcf9-5fa6-b27d-35a7e96b0609 |  | button | Remarks/record - NATA Endorsed Test Reports | Yes, No, N/A
checkpoint-status |  |  | checkpoint | 6.2 - Product Non-Conformance
label | 9573e644-2c84-5796-bb0e-d0ae9f888e40 |  | note | Ref docs - CQMP
label | 84c83fc4-3b37-5db4-96cc-3c368767e759 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | acde3ba7-960a-55cb-8260-1b9ebfb50eba |  | note | Freq - Each Lot
label | fbbfb24c-b075-56ec-8f42-80e04337c89d |  | note | Key - R
label | fa67be75-3bec-522d-bf9f-810942ca5262 |  | note | Resp - SE
label | 57573743-0620-5b0f-a432-e53eec370f66 |  | note | Remarks/record - NCR reports
checkpoint-status |  |  | checkpoint | 6.3 - Quality Representative to check the above criteria and records to confirm
label | 5ef6fdef-69dc-54d0-833f-2518c225a9ae |  | note | Ref docs - CQMP Lot Records
label | 9e6f3316-8ccf-59e7-9991-1213bf509dc2 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 2dabd172-d171-5bf5-90ab-c0b0562e8589 |  | note | Freq - Each Lot
label | cde7d992-b46b-5d8e-b207-c01fee7d6287 |  | note | Key - R
label | 53be04dc-f203-57b3-b31d-30cbf8256d8f |  | note | Resp - SE
button | d2e5f00d-f09a-54da-b6ec-3798dd125ef5 |  | button | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached. | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Works complete
text | 8d961215-1c02-56b9-b456-0271b8e3739b |  | textbox | Name:
text | f3fff7ae-8294-5af0-baec-c1b02bfb806f |  | textbox | Position:
text | 15eb1486-17e3-571e-8ce3-93ebe7ac4883 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot conforms
text | d04e6aa7-d6a1-575c-9d95-0771e5885a21 |  | textbox | Name:
text | a701c460-510f-56eb-916d-70d19ca4cc07 |  | textbox | Position:
text | 8191c1b2-f998-5192-b9f6-e5d16d8d82ec |  | textbox | Date lot closed:
text | 523b5f42-956a-5554-9894-23b6ba3b564e |  | textbox | NCR/s no. raised:
text | 904f3590-4613-50ed-a9a2-0efda33c9e3b |  | textbox | Date NCR closed for this lot:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing | a073e436-6148-4f4e-a1cf-0ac516489764
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Lot
label | 1aeaacd4-4230-5865-95c7-c87b67f2f725 |  | note | Ref docs - 1200.15 (b) (i) (B)
label | 3051c949-737e-5f17-91d2-d04bc948cd17 |  | note | Acceptance criteria - Clearly mark out lot and extents.
label | 25f3fbd6-318a-5d65-a217-61e8af37ca55 |  | note | • All No-Go Zones must be protected by temporary fencing and signage visible.
label | e9c9eb16-22e5-521a-bc5f-0ef130232142 |  | note | • All fencing of No-Go Zones must be:
label | ecddb32e-7a18-5e98-9fa4-a7143532f8b8 |  | note | a. erected a minimum of 1 metre beyond the boundary of the habitat to be protected, at the Tree Protection Zone or as directed by the Superintendent;
label | 99495e62-1c44-50e3-a545-ba563cb4783e |  | note | b. at minimum, constructed of star picket and paraweb with two wire supports. The star pickets must be 1.3m in height, installed to a height of 1m above ground level and the paraweb must be installed to ensure a minimum 30cm gap is available between the bottom of the fence and existing ground to allow for fauna movement;
label | a255df34-f2a2-559a-b045-2a60203e192a |  | note | c. communicated by signage installed on the temporary fencing at intervals no less than 10 metres apart stating ‘Environmental No-Go Zone – no unauthorised access’;
label | ab6a4518-209c-5efe-a7cc-1e738598fe04 |  | note | d. installed prior to commencement of works in the immediate area, in accordance with the relevant approved SEP; and
label | 568faa27-ea5e-5522-bef7-dc75982fd353 |  | note | e. retained in place for the duration of construction activities.
button | a2ec6a87-7d84-5ed9-bab7-5201a648016d |  | button | Has all of the above been completed? | Yes, No, N/A
label | 7f7c9a1b-c030-5997-9f37-8956a46d8830 |  | note | Freq - Prior to start of works
label | 9c7638ba-17e3-58a3-af91-d967e4e51e98 |  | note | Key - R
label | 067a77d9-060a-5143-8e55-8390c0ede22c |  | note | Resp - SE
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | b489b33a-e894-50f7-8c1c-b138239e478a |  | button | Lot map | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 1.2 - Works required inside a No-Go Zone
label | 688d3eca-247d-5a7a-b7b8-acf90a952cce |  | note | Ref docs - 1200.15 (b) (i) (B)
label | fde1cadf-b659-5684-bfc1-d3340246aa53 |  | note | Acceptance criteria - No works are to occur inside any No-Go Zones, except for where the following process is followed:
label | f732ba0c-e9fd-5929-8e92-7c4091da8c37 |  | note | • Before commencement, where works have potential to impact flora and fauna protected by a No Go Zone, the Superintendent has been provided a report to the requirements of 1200.15 (b) (i) (B) for approval 5 days before the proposed Delivery Activities and it has been approved by the Superintendent.
button | f04de08a-0d34-5f7f-9f75-010c0a684c1a |  | button | Has all of the above been completed? | Yes, No, N/A
label | 28124040-ea02-55df-9758-54259c361318 |  | note | Freq - Prior to start of works
label | 4164726a-ef54-5049-9e7b-ce07d6c2dd95 |  | note | Key - H
label | e12ed4c0-a438-59c1-86cf-80df686a891c |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - MRPV Vegetation Removal Permit
label | 7a32c4b3-012d-5891-8c3f-6e4e4dcc2985 |  | note | Ref docs - Vegetation Removal Permit / PS3020.07 (a) (ii)
label | 8eada7fd-3d79-5a74-9c08-5df5768ef2a7 |  | note | Acceptance criteria - Sign off by the Project and MRPV Environmental Representatives. This is to be reviewed by the Superintendent prior to removal and provided to Environmental team
button | 91c9385b-5359-5c43-a9da-ef3460a5a3a4 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 1e81eec6-8f15-5f5c-96a7-05ff41dfdfab |  | note | Freq - Prior to start of works
label | 134cdc22-d059-503f-95b4-726cd717a2f7 |  | note | Key - H
label | 949dfb55-f788-516a-bea0-33cd437f9916 |  | note | Resp - SE
label | 930838fc-ee73-52da-a4f3-110030ccbd87 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 1.3.1 - Environmental Permit
button | 367059b9-87d4-5293-8214-cc1b1896b2e4 |  | button | Environmental permit | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 1.4 - Design Documents Required
label | ddb00bbb-e7ab-57f2-81b0-8425fbb29e82 |  | note | Ref docs - 1170.11
label | 59a61109-20b6-57de-aeff-cf5e1ccbd714 |  | note | Acceptance criteria - For site clearing and grubbing, the documents needed are:
label | 2b330eb7-feb5-564a-9a12-44a4d86574ad |  | note | (1) marked up drawings that relate to the design Documents and clearly define the scope of the Enabling Works;
label | 81920bc8-2e13-5fb5-9d30-f6bf93d12b48 |  | note | (2) any relevant Construction Specification for the Enabling Works.
label | 491ba839-26c1-582a-abab-fc2dba44b97b |  | note | (3) a drawing showing environmental approval boundaries, activity areas and no-go zones.
label | ce172a45-eb29-594e-a08d-0831f91bdb8b |  | note | (4) evidence that any required design related Approvals have been obtained; and
label | 184d644a-afa8-5878-babb-4a2dfde0aa17 |  | note | (5) a list of all required Approvals.
button | b6acb5f8-f07e-5526-a319-55cdf6a7dae6 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 669666cd-7ee5-5476-942d-038f2b53a010 |  | note | Freq - Prior to start of works
label | f94b0a48-3c1f-59dc-886f-d98f14684e4d |  | note | Key - R
label | c7ab6282-e9f6-5eb6-bc94-0886ca02e57d |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.5 - Site Environmental Protection Plan
label | 19b113f9-f428-575a-a795-80ceb50f031a |  | note | Acceptance criteria - Site Environmental Protection Plans and Site Erosion Control Plans have been reviewed and approved for works.
button | e6a5fa35-acb7-55af-ac19-2539536068d7 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 49d20439-dafe-5eee-916f-3a2959737bc2 |  | note | Freq - Prior to start of works
label | 74f9980d-823b-549b-bae0-1f0f015353e4 |  | note | Key - R
label | bbf7fb5b-40d0-5ab0-9c52-2712c4822e9e |  | note | Resp - ENV REP
checkpoint-group |  |  | section | 2.0 Pre-Clearing activities
checkpoint-status |  |  | checkpoint | 2.1 - Pre-Clearing Identification
label | f66c08f7-26a3-517d-ae71-f8951f49cea7 |  | note | Ref docs - 1200.15 (b)(i)(C)
label | 9c6418f7-b248-5d60-b799-c0428e265a01 |  | note | Acceptance criteria - No less than 7 days prior clearing, an ecologist has certified that all habitat trees are clearly identified and marked with flagging tape or survey, consistent with the Design Documents and permits and approvals.
label | 406073f9-3636-543a-87ce-c92a9517220b |  | note | • Any salvageable timber suitable for reuse to be identified and marked for stockpiling, for it to be reused after clearing.
button | 5caee50c-1dbc-59b4-9134-0420fc38c384 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 304ca1c1-bddc-51d7-8579-614c4c345df5 |  | note | Freq - 7 days prior to proposed clearing
label | 330062aa-d495-5ed1-879e-a331e5e98d40 |  | note | Key - H
label | 5529ab32-761a-5984-9cda-c5b862cf7d98 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.2 - On-site inspection
label | cea5e880-ea3b-5e8b-a0cf-4ef27cdbeaca |  | note | Ref docs - 1200.15 (b)(i)(C) (4)
label | 92af811b-f0a9-5f25-80f6-2041775eaec1 |  | note | Acceptance criteria - Prior to removal of vegetation, site inspection to be arranged with the Superintendent and other authorities to confirm the requirements of Sections 1200.15(b)(i)(C)(1) and 1200.15(b)(i)(C)(2) have been achieved.
label | ad722b5e-4838-5ef2-9c69-15b7464a267b |  | note | • All Approvals are in place and the ecologist is always on site, ready to perform further inspections in accordance with Sections 1200.15(b)(i)(C)(3) and 200.15(b)(i)(C)(5).
button | f703935d-b0ce-532b-bf92-62ede504562d |  | button | Has all of the above been completed? | Yes, No, N/A
label | 36b866cc-9670-5900-8449-ff775a11fea8 |  | note | Freq - Prior to clearing
label | 4b0be976-fa55-5a73-bd16-9cb2a8040ce4 |  | note | Key - H
label | a5b589a5-762b-54c6-bece-ffe2e79061d1 |  | note | Resp - SE
label | 0ffbca66-b115-56c7-a6a8-344f4fafb2bd |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Onsite Clearing and Grubbing
checkpoint-status |  |  | checkpoint | 3.1 - Clearing
label | 8134fbe5-5f9c-51f4-bd1e-2285ba293755 |  | note | Ref docs - VR201.04 1200.15 (b)(i)(C) (5)
label | d1885acc-e2cf-5908-b8a8-3421c18841c4 |  | note | Acceptance criteria - Only non-habitat trees can be removed during the first stage of clearing. Habitat trees can then be removed after approvals have been received and a minimum of 24 hours after the removal of non-habitat trees.
label | 594387f3-cff1-5e29-a205-8c94f69f8f87 |  | note | • Prior to commencing of clearing each day, the ecologist appointed should inspect the area for signs of wildlife.
button | a62414e5-2aa4-57ef-9f46-a24733e6905f |  | button | Has all of the above been completed? | Yes, No, N/A
label | 4aa2dad0-7550-59a2-9b40-919a3fc12b34 |  | note | Freq - Each lot
label | 071f9452-f9ef-53f3-99c2-8969f5ddbef9 |  | note | Key - H
label | ac43cedc-ca20-5277-a6c4-84b94bf60f88 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.2 - Grubbing
label | 765705e2-d463-523b-bf79-b23f0f2c2dc1 |  | note | Ref docs - VR201.05
label | 3810f854-6779-5953-ab9d-554d9449e3f9 |  | note | Acceptance criteria - In areas where excavation will be undertaken, all vegetation shall be grubbed as per the requirements of VR 201.05 and early works – subgrade improvement design package
label | dd370420-f1e0-525b-9fb0-3482980c504d |  | note | • Holes resulting from grubbing shall be backfilled with similar material and compacted to same degree as surrounding material.
label | 43af75e3-6205-5bef-b9c0-c92da9f71132 |  | note | Freq - Each Lot
label | a32fc915-ab09-535b-88b4-4d9f9083db34 |  | note | Key - R
label | 942823a9-3770-57c2-8ed8-76b6d4c64c91 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.3 - Clearing at Culvert Sites
label | 17166604-6bf8-5a47-9f4b-549277092086 |  | note | Ref docs - VR201.06
label | 38cd2420-f39d-52ff-880b-d69a58f4dc70 |  | note | Acceptance criteria - Any trees or stumps with 10m of any portion of a proposed culvert having a waterway area greater than 6m^2 shall be cleared and grubbed in accordance with the requirements of VR201.
button | 81f3b80b-3665-5499-8b7d-4b029a1c3143 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b7364ca5-7ef3-5fd9-a367-9c26af473400 |  | note | Freq - Each lot
label | 1c9aa83b-f83f-567a-92a7-7302c41c5b5d |  | note | Key - R
label | b3d7b60a-53ce-548d-9229-0c85a8d738dd |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.4 - Flora and fauna handling and removal
label | 0c8b1649-bc7c-5328-a8c4-e66f8b8cd5af |  | note | Ref docs - 1200.15 (b)(i)(F)
label | 20c690c6-6455-580f-83a5-255e8110b13d |  | note | Acceptance criteria - The Superintendent must be notified if any significant flora and fauna is found, and an ecologist must identify and provide advice on what to do with the found flora or fauna.
label | 41c59073-a4f0-542b-b774-185ac0f50271 |  | note | • The Superintendent must notify Environmental representative of any flora and fauna found.
button | 6558365f-04f5-5525-b8ca-9e3ada2a8c59 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b015d1ac-2a3a-56ce-a752-5179739c3397 |  | note | Freq - Each lot
label | 6666619e-77af-539b-9be1-17089105176c |  | note | Key - I
label | b4508b45-159e-50f2-807f-3125fb7945ff |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Identified habitat
label | a3eaf210-473b-532b-9b97-c7d2ffb028de |  | note | Ref docs - VR201.10 1200.15
label | db02926b-aa92-5b12-a5c3-e8b948bf7818 |  | note | Acceptance criteria - Trees with hollows can only be removed during initial clearing, if hollow is occupied, the section is to be left and cut after clearance from the ecologist and a minimum of 24 hours after removal of non-habitat trees in the area.
button | 4eaa7fc3-187b-5524-8023-442f29334217 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 50ba95ab-ea75-5cd3-8271-fe53b2ea3dd8 |  | note | Freq - Each lot
label | 0fe09c78-873c-5e1c-b893-7946aa42f93f |  | note | Key - I
label | 9529233f-363e-52e5-a5d0-61fbf76aed4f |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Reuse of Material
label | 5ed6226d-b06c-5add-a9fe-05feddd7d5e0 |  | note | Ref docs - 1200.15 (b)(i)(G)
label | 19593e4e-2458-5263-8699-2530c500b7fb |  | note | Acceptance criteria - Seek and adopt where practical reuse opportunities for vegetation felled during the vegetation clearing operations. Reuse may include:
label | 9bb6ebc9-c4d7-59ad-b1e7-68d766c755b3 |  | note | a. retention of sections of a branch/trunk with hollows;
label | 2b188504-37fe-5e54-bc82-0af88263820c |  | note | b. habitat logs on the ground in revegetation sites;
label | 66b7bdcf-916b-57de-a73f-48746ce61f44 |  | note | c. placement as in-stream habitat with the appropriate approval of the relevant Catchment Management Authority; or
label | 63009fc2-485d-513a-97c2-645a99b9c12f |  | note | d. timber for furniture construction
label | d25265f3-e945-5cd5-8707-e2d067632433 |  | note | e. Mulch provided to Council, local schools, or to landscaping facilities
label | e9746773-2157-53de-9d93-5ee8925d70ab |  | note | Update tree removal/retention register
button | c0c4fd5b-50cf-5eee-9858-233bc7904da5 |  | button | Has all of the above been completed? | Yes, No, N/A
label | f25cfa97-395d-5c6a-938e-144f2ff692ce |  | note | Freq - Each lot
label | 51b7f521-36ee-53b7-9930-8dfb665e33b3 |  | note | Key - R
label | c1c1495d-0590-541c-b1c1-16d8fa3d64cc |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.7 - Disposal of Material
label | 22ab1f51-be06-59d3-8723-6a067c3cd4de |  | note | Ref docs - VR201.07 VR177.I2 PS3020.07 (a)
label | 5c8edeb8-5436-5716-b9ad-7eec55c24b3d |  | note | Acceptance criteria - No removal of noxious weeds from the site. Identify and undertake treatment of declared noxious weeds prior to the commencement of any ground disturbing activities.
label | 8ad52fd6-9afe-5a69-8a56-b25741efabe5 |  | note | • The disposal of these materials shall be in accordance with the CEMP and its sub plans
button | 15f8667e-f158-5a0e-b0b5-bb8f79ea6243 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b9bbbd28-46a5-55c2-90e6-b420a0b67e94 |  | note | Freq - Each lot
label | e67357d3-d70a-5557-a6c5-0724d4b43a7b |  | note | Key - R
label | 91f63033-9c44-5f27-99e0-db12236e6a7d |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.8 - Salvage of Vegetation
label | 23549aac-89ad-5bee-b6eb-0969e80f2ae1 |  | note | Ref docs - VR201.11
label | 72147322-28e1-51bc-b978-03f241399063 |  | note | Acceptance criteria - Salvaging any plants as well as collecting cuttings and available seed from areas of native vegetation on site to be completed where applicable
button | e2ce4a55-26c2-5287-aa10-7edb1b48adf0 |  | button | Has all of the above been completed? | Yes, No, N/A
label | ec6acecb-2efe-5060-8553-6bc607710bf8 |  | note | Freq - Each Lot
label | 41cb47bd-0387-50d8-bf7b-8cc6dc6e4fb5 |  | note | Key - R
label | 5e022082-44cf-5f79-8775-0d23395d8ead |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Product Non-Conformance
label | 19c26434-6dc1-59af-bc98-36adc0c0cfcc |  | note | Ref docs - CQMP
label | 9518b3f4-350e-5fcf-84bb-20dc7d9bfd0a |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 414be1e4-dd58-514e-9aa9-3aa236908911 |  | note | Freq - Each lot
label | 95c40cbe-2f04-5cfb-9ea7-46afacf4e933 |  | note | Key - R
label | 346b6282-08c5-5e82-b865-5a52190fbf88 |  | note | Resp - SE
text | 1de4e1b9-6e81-5c1e-937e-83f3b62d4ca2 |  | textbox | NCR No:
boolean | 3d042604-f802-5c13-9d3a-f5a67dd771c1 |  | tickbox | NCR reports
checkpoint-status |  |  | checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
label | ffc76c0f-2b8b-558d-b0d7-dae9d6812bed |  | note | Ref docs - CQMP Lot Records
label | e10d2619-880b-51f6-88de-945be30924e0 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | b2e3f48d-5616-5f85-8bbf-b937b6eacd62 |  | note | Freq - Each lot
label | a5c3681d-7870-5675-a7cf-b69ac24a35a6 |  | note | Key - R
label | d049f055-3bb5-56ce-a1ed-2ee1e25ae8ea |  | note | Resp - SE
boolean | 7f5d42cd-6f2a-5cfd-8273-f23af83651c5 |  | tickbox | Completed Checklist (if applicable) and reports and other compliance records attached.
checkpoint-status |  |  | checkpoint | Works complete
text | b6cae550-0803-5228-a7c2-2435c6ef9d43 |  | textbox | Name:
text | ecebb617-f0b0-50c9-8b17-5f08b95a2bc6 |  | textbox | Position:
text | 70847307-3131-528f-9492-99a9b779b584 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 943bb270-c14d-5aed-b800-5ed14cd21f4c |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 98450938-7c27-5cfd-8229-478e2b9e454b |  | textbox | Lot opened date:
text | 1587c337-cbcb-52c2-a695-d8ae1dbb010e |  | textbox | Lot opened by:
text | 7b2113f2-6c5b-58f1-805a-99576113cde3 |  | textbox | Date lot closed:
button | e9ba59c4-d4ec-5bae-86c0-824b62dca42d |  | button | NCR raised? | Yes, No
text | 1f9aa9aa-a780-5ddf-84b8-794e798a2a83 |  | textbox | NCR Raised Date:
button | cacd7a56-113f-55d9-96e1-c31ce48d6e89 |  | button | NCR closed? | Yes, No
text | 03c3a0e8-336f-51c2-8975-a06451741f1c |  | textbox | NCR Closed Date:
text | 09fcc37d-f227-5c44-a2e3-a13f819dd630 |  | textbox | NCR Number:
text | 45d50461-e0d0-5c5c-84ec-d4fa00da635c |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 16300-P200-SYM-QAC-ITP-0008 Fill Earthworks (Bridge Embankments) |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0008 Fill Earthworks (Bridge Embankments) | b094fd79-7a4e-4ff1-a18e-026a46e28aa8
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Work Lot
label | baeeddcf-41a7-5da4-b323-515ea44a97d1 |  | note | Ref docs - 173.02 204.03 (h) Table 204.142 Quality Management Plan Lot Diagram 1630-P200-SYM-GEO-DPK-0001 5.2.1.4 (Table 43a)
label | b3500013-706f-51e8-b9ff-dbed333d62a0 |  | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works. Lot diagram to be provided clearly marking up extents of lot area. Work Lot open on Teambinder. Lot size with no more than one day’s production or a maximum of 10,000m² for Type B Material. Lot size with no more than one days production or a maximum of 5000m2 for Type A1 & A2 Material. In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
button | fb295979-421c-5e90-87e6-50c14546f08f |  | button | Has all of the above been completed and approved? | Yes, No
label | d10c24f3-0daf-5cd5-9f2a-70c4ec4c9bcc |  | note | Freq - Prior to start of works
label | 1bbd20c9-f001-55d2-b354-22bd94d63a3e |  | note | Key - R
label | cafcbf63-9daf-59d0-98cd-260f2ded237d |  | note | Resp - SE
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 0b566460-90fd-54eb-8493-9e9c9b41c365 |  | button | Lot map | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 1.2 - Fill at Structures
label | dc8f5842-0f0f-53f9-bb3b-d473167933dc |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1103 to 1105
label | 73979f6f-8f03-510d-a7c3-ea6a1ee6f340 |  | note | Acceptance criteria - Material type is determined by reviewing the proximity of the fill layer to the future bridge abutment. As per the relevant drawings, fill may be Type B, A1 or A2 materials.
button | b9e1939c-0136-55ac-baa3-262980ecec34 |  | button | Material type determined: | Type B, Type A1, Type A2
label | eee5a9dc-7780-5380-8c99-cba687033fae |  | note | Freq - Each Lot
label | 611f72f9-f7fb-5334-841f-7233bbbc7ec5 |  | note | Key - H
label | 943e6a6d-f1b4-5078-8f27-aae28847a6ea |  | note | Resp - SE
checkpoint-group |  |  | section | 2.0 Set Out
checkpoint-status |  |  | checkpoint | 2.1 - Set Out Survey Completed
label | 85782c57-ed78-52c6-a981-6830a30f2bb7 |  | note | Ref docs - VR Clause 204.03 (a) IFC Drawings
label | 185fad8d-707c-5d61-bd03-1ef38c3a12b5 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
button | c03d677a-d30d-54ce-822f-39f905a76d9d |  | button | Has all of the above been completed and approved? | Yes, No
label | 7aa7fa3d-6444-51d5-ba40-abb020f773c1 |  | note | Freq - Each Lot
label | b8eb5b82-a77b-5511-aeed-48134aa4281e |  | note | Key - R
label | 9f49ba8a-a6cd-5773-a460-6388e7422f0a |  | note | Resp - SE
checkpoint-no-status |  |  | checkpoint | 2.1.1 - Surveyor Report Reference
button | 30872b16-bc4b-587d-a099-ce2b4ae2d25e |  | button | Surveyor report reference | Yes,No,N/A
checkpoint-group |  |  | section | 3.0 Placement of Type B Material
checkpoint-status |  |  | checkpoint | 3.1 - Initial Testing
label | 037f499f-1e0a-5f82-b085-3fd6ba07f48c |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1004 VR Clause 204.04(c)
label | 4aa87a10-b419-541e-8585-9fe6bec3b6b9 |  | note | Acceptance criteria - Type B: The material is to be meet the following requirements: CBR ≥ 3% Swell < 2.5% Friction Angle ≥ 37° If swell exceeds 2.5%, material shall be classified as expansive. Raise RFI and request approval from Superintendent to use material. Type A structural fill and Type B fill need to be tested to confirm they are able to meet the adopted shear strength parameters.
label | 096c0754-3b46-5492-90ee-1c762cbecbf9 |  | note | Freq - Each Lot
label | 0f9a3470-853c-5e2f-bfc3-e4a3f7308e9d |  | note | Key - R
label | 7fd80c6a-456f-5921-a294-4c8fb827f75c |  | note | Resp - SE
button | 1d440773-bdf0-5e44-8a90-361a259c005b |  | button | Remarks/record - NATA Test Report: CBR and Swell | Yes, No
checkpoint-status |  |  | checkpoint | 3.2 - Underlying Layer Conformance
label | fb6a3b0b-1703-5ba8-9741-ccee7516ebd0 |  | note | Ref docs - VR Clause 204.10(b) Construction Document
label | d3c26377-277a-5521-998e-f7dc906de206 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent. Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor, Any unstable areas detected by test rolling shall be rectified. Note for 1st layer: After subgrade cut to the depths (or after in-situ stabilisation) nominated in Drawing Nos. 1630-P200-SYM-GEO-1102 to 1105 in Appendix A, or as required by DoT document Section 204, perform subgrade proof roll to assess stability. Results of proof roll to be provided to the Superintendent for review and approval in accordance with the requirements of DoT Section 204.
button | 59e344ce-49a8-52b2-be28-56f6ad046968 |  | button | Approval to proceed granted? | Yes, No
label | 65bddd2f-798c-5da5-a5c7-8904c6829506 |  | note | Freq - Each Lot
label | 1a8b7091-9e2d-5bb6-a1d6-1e1155004c84 |  | note | Key - H
label | daf4fe1b-9a29-58f3-badb-814d465e620b |  | note | Resp - SE
label | 923d331b-a583-5487-96e6-00cab7f76071 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Placing Geotextiles (if applicable)
label | dccbc20a-0b74-5104-adbe-d683e4728622 |  | note | Ref docs - VR Clause 210.05 IFC Drawing
label | 9d3303a0-e76e-5261-939c-89d1a9d81653 |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent. Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with imperfections shall not be used. All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
button | 09fdc6e4-bf00-54bf-b27c-88738cb3f3eb |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 086edbbc-46fc-5c59-bb4d-c6acfd60509c |  | note | Freq - Each Lot
label | 38a2ad61-1109-53f8-bdcf-0693a50afe21 |  | note | Key - H
label | 8b74504f-ac42-591d-99a0-bc82486410d3 |  | note | Resp - SE
label | b7376ac5-18f9-5ec3-90a9-53c56b0738e4 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Placing of Fill
label | 68e79fd0-82b2-560b-bd30-cb3289737342 |  | note | Ref docs - VR Clause 204.10(d) 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.4
label | 325aab88-f6c3-5c41-978f-dbd47b06a92c |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm. Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm. Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material. Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones. Placement of fill to full embankment height in lifts of no more than 2.6m per week where monitoring remains within acceptable limits. Hold filling while monitoring settlement and increase in pore pressures. Commence next lift of filling if the measured settlement and excess pore pressures are within acceptable limits.
button | 611c46ff-e0d5-509e-8db4-1a84b8bbccdc |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 8ccda2f4-6be2-5b35-b370-d7fadcfc288b |  | note | Freq - Once, Each Lot
label | 923c9b8c-15cb-5713-be1a-634e77141050 |  | note | Key - W
label | c4a1d893-d7d6-5e16-aa04-a772e631aa34 |  | note | Resp - SE
button | ad8ffc9d-1fa5-5a29-87c1-aa8aa4eb932e |  | button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
checkpoint-status |  |  | checkpoint | 3.5 - Keyed Fill Layers
label | 29f3cc5a-048e-5e9e-9ce7-3274d0389f15 |  | note | Ref docs - VR Clause 204.10(c) 204.10(d)
label | ceded3b1-a0d6-5645-b266-f18ee26373ac |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other. Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | f7514e72-2959-5ea5-8d6f-73caa49265d1 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 53e8f420-453a-50f3-b438-438cfd4764cc |  | note | Freq - Once, Each Lot
label | 4aa30e82-3c78-5310-ac4a-869b0077cec0 |  | note | Key - W
label | bdf063e6-5bb2-535d-95e6-2a3a4f4b85f0 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Test Roll of Type B fill layer
label | 08725ee6-7633-5718-b740-cf0acae5c156 |  | note | Ref docs - VR Clause 204.12 173.03 Construction Document (Test roll Procedure in specification 173.03) 1630-P200-SYM-GEO-DPK-0001 Table 43
label | b5729838-e7f3-5c0e-aaee-eccb6e8b4d50 |  | note | Acceptance criteria - Test Roll in accordance with Section 173. Surface shall withstand test rolling without visible deformation or springing. Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass. Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted. The Contractor shall provide for the Superintendent to be present during all test rolling.
button | 0d71b7eb-b99b-5089-8e4b-899d5f98e13e |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 0e9c01f3-8e9c-5970-96cf-d0af81e59ac9 |  | note | Freq - Each Lot
label | 1ce41327-ffbb-5a6d-85f2-244c079a0de1 |  | note | Key - H
label | 8303747e-fe17-5bac-88d9-289a9646466c |  | note | Resp - SE
label | f3577c9b-dd67-54a0-ad51-39aa94cdd8be |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction Testing
label | ea2267a2-316c-5ef4-86ca-9ee183e6aaba |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) 1630-P200-SYM-GEO-DRG-0004 (table 3).
label | 4def999c-126d-5c5c-8300-93661d11c62c |  | note | Acceptance criteria - Type B: Type B material placed within 400 mm of top of Type B material: 99% (Scale A) Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A) All areas of the job will be considered as scale A. Type B material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204. >70% for any material within 150mm of subgrade. >80% for all material below cut floor level.
button | 7c425cac-2e51-5297-8383-7ac61c5f99a2 |  | button | Have the results been achieved? | Yes, No
label | cbb3fc50-3680-5fb4-bc2f-a97b57b97437 |  | note | Freq - Each Lot
label | c6141978-9092-5d98-ba11-9f221fdc2870 |  | note | Key - R
label | 98038a81-f071-580d-b1f6-ffba6ff405de |  | note | Resp - SE
button | faf46499-12d1-50a4-b5aa-adfd9390f599 |  | button | Remarks/record - ATA Test Report: Compaction | Yes, No
checkpoint-status |  |  | checkpoint | 3.8 - Monitoring of Settlement
label | eb5a928e-1bfb-5263-9bec-daa05fe20882 |  | note | Ref docs - 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.10 Table 33 5.4.2.2.10 Table 34b
label | 8c56ba21-d1ff-5432-8e70-54e6366643eb |  | note | Acceptance criteria - The rate of filling lifts and effect on settlement, lateral displacement and excess pore water pressure to be monitored. The ratio of change in maximum lateral movement to change in maximum settlement should be calculate at the competition of each lift. A minimum of two readings are to be taken immediately post installation and immediately prior to the commencement of embankment construction from the settlement plates, extensometers, survey prisms on culverts, inclinometers, and standpipes. During the construction phase measurements are to be taken when the fill height reaches 1.0m and then every 0.5m of fill after (TBC). During the hold period measurements are to be taken twice weekly and monthly until practical completion is reached.
label | 2310cec2-619d-5253-9a52-e7af482ba99c |  | note | Vibrating Wire Piezometers readings are to be taken for at least one week prior to commencement of construction. Continuous readings are to be taken during the construction stages with data sent to the logger on 6 hourly intervals. Survey prisms installed on bridge abutments are to have baseline readings taken immediately post installation. Following that readings are to be taken weekly for two months, two weekly for the following six months and monthly following that until practical completion is reached. Are monitoring results within the allowable limits stipulated in Table 34b (where applicable for this lot)?
button | 5b3138c6-52b2-5095-a2dd-6ca87387607d |  | button | Approval to proceed granted? | Yes, No
label | 8fd94d0b-dee7-5341-92a4-c01dfe9c6fc0 |  | note | Freq - Each Lot
label | fc9ae3c8-47df-50c6-98bd-3f0d67263249 |  | note | Key - R
label | 73916675-a39c-5c46-b5fa-8b586be9905a |  | note | Resp - SE
label | 25fa1044-b75c-5141-aaf0-b89713f2d3a8 |  | note | SI Key - H
button | a300aefa-c3b7-559c-86df-3223448fe3a1 |  | button | Remarks/record - Monitoring Checklist | Yes, No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Placement of Type A material (Type A1 and A2)
checkpoint-no-status |  |  | checkpoint | 4.0.1 - Incoming Material Docket
button | 8042dd2c-0d34-5eaa-b1ab-cb433bc3479a |  | button | Incoming material docket | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 4.1 - Initial Testing
label | fbd21e7e-4028-5f79-844e-f1b84bc15e7b |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1004 VR Clause 204.04(c)
label | f2e2113d-1c22-545f-a26a-9f0d028b6261 |  | note | Acceptance criteria - Type A1: The material is to be meet the following requirements: CBR ≥ 6% Swell < 1.5% (1.0% for verge material) Friction Angle ≥ 37° Type A2: The material is to be meet the following requirements: CBR ≥6% Swell < 1.5% (1.0% for verge material) Friction Angle ≥ 32° Drained Cohesion ≥ 6KPA Type A structural fill and Type B fill need to be tested to confirm they are able to meet the adopted shear strength parameters.
label | 779aa915-8b99-574b-8830-72b2d47727eb |  | note | Freq - Each Lot
label | 03917bb0-d9c3-56b2-97ab-8450c6e2dd17 |  | note | Key - R
label | 8f0dbc6d-177c-5594-8b9c-c5220655a0eb |  | note | Resp - SE
button | 0693a0b4-7e53-53ad-a398-2a8072fc8e86 |  | button | Remarks/record - NATA Test Report: CBR and Swell | Yes, No
checkpoint-status |  |  | checkpoint | 4.2 - Underlying Layer Conformance
label | 99a782de-c684-51e0-82de-fb70a3e90de0 |  | note | Ref docs - VR Clause 204.10(b) Construction Work Pack (Placement of fill material)
label | 63a8fe1d-3c60-55b3-a1b6-99c8516dde04 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent. Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor, Any unstable areas detected by test rolling shall be rectified. Note for 1st layer: After subgrade cut to the depths (or after in-situ stabilisation) nominated in Drawing Nos. 1630-P200-SYM-GEO-1102 to 1105 in Appendix A, or as required by DoT document Section 204 dated December 2015, perform subgrade proof roll to assess stability. Results of proof roll to be provided to the Superintendent for review and approval in accordance with the requirements of DoT Section 204.
button | e7e1c75e-f3bd-5b68-a226-0d8ea3ef5d1c |  | button | Approval to proceed granted? | Yes, No
label | 82e1ee0e-1b9b-5289-8a09-708823adf3cc |  | note | Freq - Each lot
label | 0bd8b0ff-7a10-5a43-8a87-aa821d3a1d28 |  | note | Key - H
label | e9d91340-2688-5d1f-a648-80111df275c3 |  | note | Resp - SE
label | d6e6613c-e108-5d27-8243-257236843719 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Placing Subsurface Drainage
label | 8865d1c2-3b8c-53a7-9180-952c6031c1df |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1102
label | 768a8d68-9454-59cb-b33e-47804b79b1b7 |  | note | Acceptance criteria - Have specified drainage materials been placed at the base of excavation as per drawing 1630-P200-SYM-GEO-1102?
button | 95715c8d-3654-5e9e-ac45-a41b803a05a0 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | c7f137cd-d4a6-5460-919f-67a55374c0c0 |  | note | Freq - Each Lot
label | 54a0baf6-4a39-5afc-a074-0093a4211f3b |  | note | Key - H
label | 5731dcaf-d2ff-5921-b22a-1a324773b184 |  | note | Resp - SE
label | 6f5361bc-7356-5c09-b784-531c857690fc |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Placing of Geotextiles (If applicable)
label | 5beb25b3-6dff-5144-a1af-d36b135bfd6c |  | note | Ref docs - VR Clause 210.05 IFC Drawing
label | d922261b-1b13-5972-86e3-7135459d194e |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval from the relevant Surveillance Officer. Geotextile shall be placed to the limits as shown on IFC Drawings without punctures or tears. If these occur, they shall be rectified, or the entire roll of geotextile replaced prior to covering. Geotextiles in subsurface drains shall be placed to conform to the approximate shape of the excavation and fully envelop the drainage material. All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
button | a7070955-73a4-5528-99a9-03478af814bc |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 34a82f5d-f281-5fbc-a0d2-94b2458a0239 |  | note | Freq - Each lot
label | 7bbfce29-d517-5044-aa96-d6ca32e9aca5 |  | note | Key - H
label | e25819d6-383c-5e61-b85a-80dc8f93b180 |  | note | Resp - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 - Placing of Fill
label | 576dad6d-ed75-5e02-ad80-e94abc4c8672 |  | note | Ref docs - VR Clause 204.10(d) 1630-P200-SYM-GEO-RPT-0001 5.2.1.3.1 Table 43
label | ad84aad3-37e5-5d3b-b153-4bee28826990 |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm. Visual Inspection for maximum particle dimension Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than H3:1V, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be not less than 1 m. Placement of fill to full embankment height in lifts of no more than 2.6m per week where monitoring remains within acceptable limits. Hold filling while monitoring settlement and increase in pore pressures. Commence next lift of filling if the measured settlement and excess pore pressures are within acceptable limits.
button | d74bbc54-5720-5d09-a2fc-2957ec9ad545 |  | button | Has all the above been completed per standard and approved? | Yes, No
label | 86d9d439-2ae1-52fa-8864-e4f78d53b7e9 |  | note | Freq - Each lot
label | 3a5da9d3-086f-550c-bd6f-a4d0fbe83d4e |  | note | Key - R
label | 56a9f366-2230-5c38-a1dd-80ccfc9c6571 |  | note | Resp - SE
button | 8532109c-e70a-58ff-a180-63e585a15633 |  | button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
checkpoint-status |  |  | checkpoint | 4.7 - Keyed Fill Layers
label | 1b7c88b9-2e90-56d1-9668-32bad8f1e2d1 |  | note | Ref docs - VR Clause 204.10(c) 204.10(d)
label | a62a8e96-7b87-5ab1-b290-0864810f9c6f |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other. Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | 2896cca6-b5ce-5509-84d0-d929a0bbc259 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 9182a054-3f48-5bf0-ac41-ac010fb90930 |  | note | Freq - Once, Each Lot
label | 08111cc2-16c0-50e6-b0dd-21457dd004e0 |  | note | Key - W
label | 5047887f-45b4-5bb9-832c-88691aed8c05 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.8 - Test Roll of Type A fill layer
label | 26cab5da-18ef-5103-b4d2-e65cb7eef4be |  | note | Ref docs - VR Clause 204.12 173.03 Construction Document (Test roll Procedure in specification 173.03) 1630-P200-SYM-GEO-DPK-0001 Table 43
label | fbc3b14d-715a-55e6-9b1f-d8f6ea5a5dba |  | note | Acceptance criteria - Test Roll in accordance with Section 173. Surface shall withstand test rolling without visible deformation or springing. Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass. Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted. The Contractor shall provide for the Superintendent to be present during all test rolling.
button | 57efeebc-e897-52bd-93b6-5f672739a5fb |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 4bd5fb2d-cc78-5583-9312-91cd3adf8150 |  | note | Freq - Each lot
label | e0763b59-94b9-50a0-b6f9-345398b11a47 |  | note | Key - H
label | 4d69a58a-34c3-53fb-8b88-d4ab50ba894f |  | note | Resp - SE
label | 00c4c0c2-e395-5927-8ad7-4e2b638ed17d |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 4.8.1 - Proof roll if applicable
button | 11a93d5f-0e31-5a34-81a0-601433075af3 |  | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
text | f35f30c1-c3b2-572b-85c2-b9f453adea2a |  | textbox | Chainage
checkpoint-status |  |  | checkpoint | 4.9 - Compaction Testing
label | be975b40-af83-5fa2-8e7e-13966a145243 |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) 1630-P200-SYM-GEO-DRG-0004 (table 3).
label | ef950e19-77e9-5b6c-b0ae-d2e0a7126171 |  | note | Acceptance criteria - Type A1: All Type A material: 99% (Scale A) All areas of the job will be considered as scale A Type A1 material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204. Type A2: All Type A material: 99% (Scale A) All areas of the job will be considered as scale A Type A2 material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204.
label | e77b42ab-b468-591a-b449-0809f1fd0742 |  | note | Freq - Each Lot
label | 5031f8e7-0c7e-5262-b8b1-02094c074457 |  | note | Key - R
label | f494d407-dbf9-53a1-ab94-ef67aeaddc15 |  | note | Resp - SE
button | ffc5132c-f7ef-56d5-bc64-264ebe9e67b9 |  | button | Remarks/record - NATA Test Report: Compaction | Yes, No
checkpoint-status |  |  | checkpoint | 4.10 - Fill at Structures (if applicable)
label | 6831449e-3d14-5504-8104-22249941fa9d |  | note | Ref docs - VR Clause 204.11 (b) Table 204.111 Construction Work Pack
label | 01662495-eddc-5af6-84b7-f3d8b55b391b |  | note | Acceptance criteria - No Fill to be placed within 3 m of structure until the foundation is reviewed by the relevant Surveillance Officer. Culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality. | Yes, No
button | 1664bd7d-79b0-51f9-87dc-eef8d5d052fa |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 16fffd0c-c5a9-57e7-8c6e-d48850c6c870 |  | note | Freq - Each Lot
label | 9cc0edf5-d5f3-5c86-bc3f-c307379ec5ce |  | note | Key - H
label | 59a3d26d-e5a9-5618-a5b5-05f9b0d2521d |  | note | Resp - SE
label | 7d2e113a-00bb-565a-84d4-746d8ea118fa |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.11 - Fill within 300 mm of structures (if applicable)
label | 1fbcc455-8d70-51d9-b875-0fae6a5048a3 |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | 2fdc0347-b9be-52ed-976d-1acf013e4a7e |  | note | Acceptance criteria - Use of geo-composite drainage material or Permeable Fill in accordance with 204.04(f). Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111. The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
button | bfa24cf1-f626-568a-a856-d9edbd35d513 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 43377108-b5fc-5708-ac2a-79804ca9076b |  | note | Freq - Each Lot
label | c47b2ec7-1c97-564e-baf0-4c13a29c8a99 |  | note | Key - R
label | 51e47b72-12b6-5987-b224-7fb39c82104e |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.12 - Fill Material against Concrete Structures (if applicable)
label | 3c0ca7c4-82c7-5d3c-82f1-54091f2cfa64 |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | c7e606c0-067d-511a-b5f3-c2928b953a8d |  | note | Acceptance criteria - No material shall be placed against concrete within 14 days of casting.
label | 3a44c6eb-98d0-5af8-862a-ea7033481081 |  | note | Has all of the above been completed per standard?
label | dd3c5264-5e3d-50b3-b166-848fee617c0e |  | note | Freq - Each Lot
label | c5017994-257b-5094-b320-5662a9199c9f |  | note | Key - R
label | 46cbb0ad-8246-50a7-8fdd-877be25878f9 |  | note | Resp - SE
button | 490f3ef5-8204-5e6c-b1af-7a0a6b449ed6 |  | button | Remarks/record - Concrete Pour Recorded | Yes, No
button | e59d747c-3149-5a2e-b1b5-b6d02c01d1e1 |  | button | NATA Test Reports: Compressive Strength | Yes, No
checkpoint-status |  |  | checkpoint | Monitoring of Settlement
label | 629f9a01-f70c-519c-baa7-b685cf28cf27 |  | note | Ref docs - 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.10 Table 33 5.4.2.2.10 Table 34b
label | 32ad9037-9bbe-5160-bc9a-fd25f6fed795 |  | note | Acceptance criteria - The rate of filling lifts and effect on settlement, lateral displacement and excess pore water pressure to be monitored. The ratio of change in maximum lateral movement to change in maximum settlement should be calculate at the competition of each lift. A minimum of two readings are to be taken immediately post installation and immediately prior to the commencement of embankment construction from the settlement plates, extensometers, survey prisms on culverts, inclinometers, and standpipes. During the construction phase measurements are to be taken when the fill height reaches 1.0m and then every 0.5m of fill after (TBC). During the hold period measurements are to be taken twice weekly and monthly until practical completion is reached.
label | b4015614-6468-51f0-be44-601807054371 |  | note | Vibrating Wire Piezometers readings are to be taken for at least one week prior to commencement of construction. Continuous readings are to be taken during the construction stages with data sent to the logger on 6 hourly intervals. Survey prisms installed on bridge abutments are to have baseline readings taken immediately post installation. Following that readings are to be taken weekly for two months, two weekly for the following six months and monthly following that until practical completion is reached. Are monitoring results within the allowable limits stipulated in Table 34b (where applicable for this lot)?
button | bea09a98-752c-5bfb-9959-175460ed24cc |  | button | Approval to proceed granted? | Yes, No
label | 7ad3d2be-c211-5910-affc-7d2b10fc8b5b |  | note | Freq - Each Lot
label | 3ffb358d-02f4-5251-b178-10a3e69a1eb3 |  | note | Key - R
label | 3b775001-0951-5995-b0ad-13df7e431563 |  | note | Resp - SE
label | faff4b79-09d3-5b0d-9d5e-f73aa01be478 |  | note | SI Key - H
button | c6b8c84f-bbf9-5f1d-9d06-5154e952e703 |  | button | Remarks/record - Monitoring Checklist | Yes, No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.0 Geotechnical Analysis (and Material Testing)
checkpoint-status |  |  | checkpoint | 5.1 - Post Compaction Grading/Maximum Particle Dimension
label | 3c0a14ff-108f-5151-abc8-c4f61d8525d1 |  | note | Ref docs - VR Clause Table 204.041
label | 048abbed-a911-577f-9094-ebada79344f8 |  | note | Acceptance criteria - Type A: Sieve 75.0mm – 100% passing by mass, Sieve 4.75mm – 40 - 80% passing by mass, Sieve 0.075mm – 10 - 40% passing by mass. Type B: Maximum Particle Distribution (MPD) ≤ 150 mm within 400 mm of Top of Type B. or MPD ≤ 400mm at depths greater than 400 mm below the top of Type B material.
button | c879ab91-29f5-52a8-8633-4e35933de44e |  | button | Have the results been achieved? | Yes, No
label | 07061943-5d0d-524f-9bd5-56e0f0c37792 |  | note | Freq - Each Lot
label | d801191e-8de7-5333-a3f3-0d5a863090fa |  | note | Key - R
label | 3d2f15f3-e996-5513-98fc-4638527613de |  | note | Resp - SE
label | 62c497d0-260d-5202-9273-578fbda236f1 |  | note | Remarks/record - NATA Test Report: Grading Visual Inspections for Maximum Particle Dimension
checkpoint-status |  |  | checkpoint | 5.2 - LL and PI Testing
label | a6b76dd0-6a0a-5750-9120-0342ab149f2a |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d)
label | 4a32a77e-b144-5c3e-bc70-38c598201db2 |  | note | Acceptance criteria - Type A: PI: 6 - 25, PI x % Passing 0.425mm: 1000 Max. LL and comparison of PI against LL, (identification of silt) is required for Type A2 Material. Type B: LL and comparison of PI against LL, (identification of silt) is required for Type B Material. Initial testing is 1 Test per 2 lots.
button | 6d55f089-e699-5eed-9c3b-f5c64a074e1b |  | button | Have the results been achieved? | Yes, No
label | 91b56f81-c7af-59b7-8514-a0dd616effab |  | note | Freq - Each Lot
label | e264b5cd-c50e-5b45-a1f0-b038fbf1de91 |  | note | Key - R
label | ee0b7b0f-54ec-5c01-a975-3ac88abf4e01 |  | note | Resp - SE
button | fe436c03-06ca-5403-9bb5-d713999dd30b |  | button | Remarks/record - NATA Test Report: LL, PI | Yes, No
checkpoint-status |  |  | checkpoint | 5.3 - Reduced Frequency Post compaction testing of initial lots.
label | 400d6a2f-5679-56f3-836e-c342f63256bf |  | note | Ref docs - VR Clause 204.14 – Table 204.141 RC 500.20
label | 937c3cb2-dea7-5e4a-84bc-af949f28cb74 |  | note | Acceptance criteria - Test initial lot for CBR/Swell. Test initial 3 lots for compaction. Once material and work have achieved the specified requirements in the first test. And; Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142. If Reduced frequency has been granted, the testing can be conducted at the following frequency. 1 test per every 8 lots for CBR/Swell 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing. 1 test per 4 lots of LL and comparison of PI against LL.
button | fe494730-7214-5c10-afcd-23e1f2c2f655 |  | button | Has the criteria been achieved? | Yes, No
label | 531ee94f-379d-5b41-a7f0-b2f1b937988f |  | note | Freq - Each Lot
label | 94d4ce8a-f708-593e-bd6e-f9c3a86d5eff |  | note | Key - R
label | 94e5b8e8-86e7-5975-9b35-7114da3fa858 |  | note | Resp - SE
label | 0b66f1de-b3bb-5099-8d0d-c9d91f67ffa8 |  | note | SI Key - R
checkpoint-group |  |  | section | 6.0 Completion
checkpoint-status |  |  | checkpoint | 6.1 - Conformity with IFC Drawings and Construction Tolerances
label | 737c0b0d-c5de-571d-9be0-99a46701c6f3 |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | 1f6e8487-94cd-598b-84ec-128216bac7ae |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements. Scale A: 80 measurements per lot Mean +5 / -15 mm Max Std Dev. 12 mm
button | a137cb3d-90ff-5000-828d-26f0565dcf54 |  | button | Does the final product conform to the above criteria? | Yes, No
label | c6c8aa5b-44c9-5d5c-827a-5c22ff621c41 |  | note | Freq - Each Lot
label | 33ff35bb-f5d7-5e3b-bd0a-139461b1bada |  | note | Key - R
label | 869f5576-2195-53cf-90e9-278d0349e38e |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 6.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 3b197c80-e2da-5e6b-a1fe-87e654aca5b5 |  | note | Ref docs - VR Clause 204.15
label | b228fc07-8c7d-5ebd-af73-04aa4eb7d0dc |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | ec249345-1ad8-5cc5-a415-7a95ef9a746c |  | button | Does the final product conform to the above criteria? | Yes, No
label | 3dabf341-8c3d-5eb9-a30a-24adb77cef84 |  | note | Freq - Each Lot
label | 9d8f779c-a933-530e-ab2d-15bff7a5774c |  | note | Key - R
label | c6982f69-adb0-5d50-b124-e874ca3c2077 |  | note | Resp - SE
checkpoint-group |  |  | section | 7.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 7.1 - Test Reports
label | 71d9ea9b-319b-51fc-a33d-afa159828aaf |  | note | Ref docs - DoT Specs
label | 625e9e14-3917-5b1d-905b-0a6e9542d411 |  | note | Acceptance criteria - All Test reports received and reviewed
label | 44e2374e-cda0-5cf1-bd5b-239af1969b3b |  | note | Freq - Each Lot
label | 635d1e25-3f41-56a6-a5e4-cf6196756f76 |  | note | Key - R
label | 28b11944-9860-5341-b674-f06fb0696c01 |  | note | Resp - PE
label | 9df17621-a5ef-545a-9f8d-dcfdbe9a8448 |  | note | Remarks/record - NATA Endorsed Test Reports
checkpoint-status |  |  | checkpoint | 7.2 - Product Non-Conformance
label | 65fb0df3-3755-5975-8723-de50dc8cb571 |  | note | Ref docs - QMP
label | 8e03c6e3-68ba-5630-bc1d-2aa9c5e58523 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 68401126-7f25-5fa6-a8d8-2c6ffec79ddd |  | note | Freq - Each Lot
label | 6662df44-853f-5879-bf61-87123c081173 |  | note | Key - R
label | 37ff0ed3-9f40-525d-9884-64a29a3f51af |  | note | Resp - PE
label | 23aedcba-3e90-5043-a530-8eb9d697ee13 |  | note | Remarks/record - NCR reports
checkpoint-status |  |  | checkpoint | Works complete
text | 55ec85e7-4583-5a67-bd6b-f62cdd59511d |  | textbox | Name:
text | fb09414a-c887-5063-869f-979213ab45e8 |  | textbox | Position:
text | ef52321a-4a40-57e3-a43e-1fbcdd44377e |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 89ed1556-1e8c-59d9-b238-b6bb9d4b4f9b |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 5f4e99cb-3ba8-5a36-8a02-b88fe56d2007 |  | textbox | Lot opened date:
text | e12ef08a-866c-5190-8a56-d0fc30ac4917 |  | textbox | Lot opened by:
text | e411320c-1721-57d0-bef2-d1cd1c488429 |  | textbox | Date lot closed:
button | d78c3bd4-015b-5d95-85d2-ac724b08bd93 |  | button | NCR raised? | Yes, No
text | f2ede038-cdb7-5627-8e66-bc1610634d46 |  | textbox | NCR Raised Date:
button | 9030722d-5794-50a3-888b-ac8ededc6caf |  | button | NCR closed? | Yes, No
text | 9caff87c-c343-56e6-a610-e258e941fa36 |  | textbox | NCR Closed Date:
text | 760be6f9-a430-5f89-901f-fe9840c720ae |  | textbox | NCR Number:
text | 155dd65e-be97-5c87-9596-015c0afd6c04 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0011 |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0011 Stormwater Drainage Installation | ccc57c69-be54-489e-a816-5f790a03cd1b
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Relevant permits acquired
label | 3e3ce95f-8bf8-5295-bc59-4cc85cbd240b |  | note | Ref docs - SMP
label | c336aa15-5a15-5e79-bd8e-d8a82bfa0b4b |  | note | Acceptance Criteria - DBYD
boolean | 7e103913-b86b-55de-9ff4-e67c042b47b5 |  | tickbox | Permit to Work
boolean | 0abf54bc-0745-51a4-9ac4-f18f5eeccdac |  | tickbox | Penetration Permit
boolean | 0ebdef58-1950-5bd6-b0d2-cf519363d9b8 |  | tickbox | Working at Heights
boolean | c29c96eb-9838-51fa-8ea9-1a8e9d022d31 |  | tickbox | Lifting Permit
boolean | 590dbf08-40df-5f1d-9b73-b9f5736f5cce |  | tickbox | VESI Permit
boolean | bbf85ca0-09a5-50ec-8932-dc541f7d7f1e |  | tickbox | Excavation Permit
button | 9b592494-3a68-5fd0-838e-ca1deed3dc80 |  | button | Have any/all of the above permits been acquired/completed and signed off? | Yes, No, N/A
label | 593ed7e9-f28a-5f6d-9be7-9353dc4daeec |  | note | Frequency - Prior to start of works
label | 9f54d782-febe-5149-b304-fb719c07fdb2 |  | note | Symal Key - H
label | 41097e65-1df6-583d-b4f7-694a244f3faf |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 1.2 - Define Work Lot
label | b150e568-f8ca-563c-8d4b-0a88b7873ae2 |  | note | Ref docs - VR Clause 173.02 701.20 701.10 IFC Drawings QMP
label | 379a9a3f-e109-534c-8d67-5ac896097a54 |  | note | Acceptance Criteria - Survey boundaries clearly define the Underground Drainage Construction works. Lot shall be defined from pit to pit (or endwall, where applicable).
button | 654218f7-9f60-5f2d-96d0-56038a1cbfff |  | button | Has all of the above been completed and approved? | Yes, No
label | 5dca0676-55b6-5115-8ea6-98890dcc13ae |  | note | Frequency - Prior to start of works
label | f587a715-125f-5c08-ac5d-f190727e0b95 |  | note | Symal Key - R
label | f85973c0-1f45-5fe9-8ec3-b6501f94d047 |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 1.3 - Conformity with Drawings
label | fb6ccb51-c664-58c1-8150-59545667968e |  | note | Ref docs - VR Clause 701.10
label | 7fdb66ff-c6aa-5e20-b3b8-361574703792 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
button | f7acedbb-67cc-5ed4-a91a-ef861924293b |  | button | Approval to proceed? | Yes, No
label | a7539811-bfca-5cae-9e18-f921ac37f5c9 |  | note | Frequency - Prior to start of works
label | 2694c475-8d30-5438-987f-9e1da313204a |  | note | Symal Key - H
label | 4bdbc060-f784-5083-8864-2eef7f7e6f7d |  | note | Responsibility - SE
label | cab3915b-1931-52d7-ab4e-62c5d1c947ea |  | note | Superintendent - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Acceptance of Box Culverts
label | 0a05cd57-1c7a-5d62-813e-8aa0bb6c0dd7 |  | note | Ref docs - VR Clause 619.22 IFC Drawings
label | da46cf08-4d9e-570e-b9c1-40d5343d37e8 |  | note | Acceptance Criteria - Complies with specified requirements and free of defects and to drawing dimensions. Box culverts shall be accepted on the basis of full compliance with the requirements of this section and AS 1597.1. Documentation supporting the following quality requirements shall be submitted for review by the Superintendent upon transport and delivery of units to site: (a) visual inspection. (b) dimensional measurements. (c) measurements of clear cover to steel reinforcement. (d) concrete compressive strength test results. (e) proof load test results. (f) ultimate load test results.
button | 8f6e3fb1-54dc-541b-b2b0-b9a4d3da607e |  | button | Has all of the above been checked for compliance and approved? | Yes, No, N/A
label | 9aed9d59-50d6-5f62-8c5e-9bcae9e23063 |  | note | Frequency - Prior to start of works
label | 1bf8e45f-444a-5c89-9789-fa8753148422 |  | note | Symal Key - I
label | 30aad421-f295-5e91-8253-9e541009156e |  | note | Responsibility - SE
label | 7cbfdd7f-a51f-54fe-970a-77494c6935e6 |  | note | Superintendent - R
button | f6421d1a-1692-549f-b629-731d0bb5981e |  | button | Remarks/record - Manufacturing Process Records | Yes, No, N/A
button | 7a3b3594-8a5f-536d-93c4-9846cd064bf2 |  | button | Manufactures Compliance Certificate | Yes, No, N/A
checkpoint-status |  |  | checkpoint | 1.5 - Acceptance of Precast Reinforced Concrete Pipes
label | 0b92e4b7-d21e-5bda-8183-579faece015b |  | note | Ref docs - VR Clause 701.05 VR 610 IFC Drawing
label | ff4c98f8-07f0-574b-86ac-059a53b0d978 |  | note | Acceptance Criteria - Precast reinforced concrete shall be of the required sizes and load classes as shown on the drawings. Rubber ring joints shall comply with the requirements of AS 1646. Aggregates for precast reinforced concrete pipes shall comply with the requirements of Section 610 Any steel reinforced concrete pipes that have cracks wider than 0.2 mm or are damaged prior to laying and backfilling shall be rejected.
button | 881dd912-726a-5904-9f0b-1e7af7d27f64 |  | button | Has all of the above been checked for compliance and approved? | Yes, No, N/A
label | c6e6b180-dde9-5ef1-8796-5215e12ecf2b |  | note | Frequency - Prior to start of works
label | 7b883aed-b03b-5972-8676-bb67769c04ca |  | note | Symal Key - I
label | da4f008e-69c8-538f-9ad9-db245c170f09 |  | note | Responsibility - SE
button | 4597c725-dd2b-58a7-a19f-d3d667d2e8a1 |  | button | Remarks/record - Manufacturing Process Records | Yes, No, N/A
text | c5e61072-8cf5-5de0-87ef-102070a142a4 |  | textbox | RFI NUMBER:
checkpoint-status |  |  | checkpoint | 1.6 - Repairs to damaged pipes and box culverts
label | 817a3ca8-1655-54c1-b00d-1274a8ea5858 |  | note | Ref docs - VR Clause 701.31
label | 126fa51a-6e40-582f-9a6d-7da27cd565a7 |  | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance: · cracks wider than 0.5 mm · spalling of concrete · exposed reinforcement · joints that are not fully engaged. Any pipes with defects greater than the following limits shall be removed and replaced: · longitudinal cracks greater than 2 mm · circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm · circumferential cracks around part of the circumference with width greater than 4 mm · penetrations with area greater than 400 mm2 · pipe joints that are separated. Other types of pipes which exhibit defects or are otherwise damaged prior to laying and backfilling shall be rejected. Box culverts which do not comply with the requirements of clause 619.14 prior to laying and backfilling shall be rejected and removed from the site. The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans. No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 1163769b-62f1-5ac1-9c19-2265a042990f |  | note | Frequency - Each lot
label | 1d38de52-6c87-5b60-962e-4c4f42f550ea |  | note | Symal Key - H
label | 59a401fc-f6aa-5e07-8f92-ccebacfd3823 |  | note | Responsibility - SE
label | ed1db58f-d896-5150-ac3a-181b7da111eb |  | note | Superintendent - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Bedding and Backfill Materials
label | 4fefd570-dd00-5186-b3e2-4e48a3e4f4da |  | note | Ref docs - VR Clause 701.09(d) Table 701.091 Table 701.092
label | 860c6137-1602-5612-9255-3080b267358c |  | note | Acceptance Criteria - Materials used for bedding and selected/ordinary backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
button | 9820b0b6-2bda-529a-bd5e-a04ab3aad11b |  | button | Has all of the above been checked for compliance and approved? | Yes, No, N/A
label | 372fca06-cc3c-59f3-9315-e233644f4aee |  | note | Frequency - Prior to start of works
label | b1a3c738-afa4-59e2-b833-39f55802d870 |  | note | Symal Key - R
label | bb4ee23f-c1a0-5ac1-8cd0-306f5fa31b77 |  | note | Responsibility - SE
button | 15102dff-1b06-5688-840f-363466bf4852 |  | button | Remarks/record - Bedding and Backfill Material Conformance | Yes, No, N/A
button | f6b2613c-7478-53e7-b4ef-a76081f05f73 |  | button | NATA Test Report: Grading and PI. | Yes, No, N/A
checkpoint-group |  |  | section | 2.0 Excavation
checkpoint-status |  |  | checkpoint | 2.1 - Excavation of Trench
label | 16fd4093-fa6d-5e73-b618-56fff83fe2fd |  | note | Ref docs - VR Clause 701.15 Table 701.151 701.08
label | 95e04f64-ceba-5896-8314-cb5bcf3e8008 |  | note | Acceptance Criteria - Excavate to required depth which shall also include excavation necessary to prepare the culvert/pit foundation & provide the full specified depth of culvert/ pit bedding. Maintain trench width clearances as per table 701.151.
button | 1fd0fc04-214d-5c05-b134-169e09c663f0 |  | button | Has all of the above been completed? | Yes, No, N/A
label | d7ab89eb-f776-51c7-97fc-fe9a20a5d3ab |  | note | Frequency - Each lot
label | f2067392-be01-5f32-a700-fd8613719e7b |  | note | Symal Key - I
label | ab159ed6-7a21-5783-a11e-604bc5bec22a |  | note | Responsibility - SE
checkpoint-group |  |  | section | 3.0 Bedding
checkpoint-status |  |  | checkpoint | 3.1 - Bedding – Layer Thickness
label | 9ff8cca5-1d22-5c02-90e0-9ebd5e7aa40d |  | note | Ref docs - VR Clause 701.16
label | e04600b9-ee12-51cd-983c-0fea97b63b9f |  | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench or where the pipe/culvert is to be placed without trenching to a width 0.8 m greater than the overall width of the culvert or pipe. Bedding to be the compacted thickness of 100 mm where D < 1500 mm 200 mm where D ≥ 1500 mm (D = Pipe Diameter/Culvert Width)
button | a649dc24-9c03-5052-9116-2b2d1a6ec62d |  | button | Has the above been completed? | Yes, No, N/A
label | 66811e2c-d66e-5d83-9d74-1fa57d6d878e |  | note | Frequency - Each lot
label | 671db894-c338-5a21-929d-bd466a7a367e |  | note | Symal Key - R
label | 8c7eb5d9-4644-5b8b-a6ad-f989d21820a6 |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 3.2 - Bedding Material - Compaction
label | ea2f9a9d-c894-5b92-bdb7-a6ea3b73a987 |  | note | Ref docs - VR Clause 701.20
label | 253d1729-f8df-556e-8b30-16357f8357aa |  | note | Acceptance Criteria - Compact bedding to refusal using handheld mechanical equipment. If expansive (Swell greater than 2.5%) material is utilised as bedding material, then it shall be tested for its swell properties and have the following criteria met. · Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
button | 435f758d-6452-54a8-90a0-e30971606bc7 |  | button | Has the above been completed? | Yes, No, N/A
label | 6e70bb5f-296d-5d3d-9a69-4be8b1fe07cc |  | note | Frequency - Each lot
label | 768206c5-53a1-5bd3-b1e5-67eb6164b25a |  | note | Symal Key - I
label | 1414b3ab-550d-57bf-a15f-7d8cff0fcbfe |  | note | Responsibility - SE
button | e499b68f-fdb3-5595-a8a0-f63d56c487c7 |  | button | Remarks/record - NATA Test Report: Swell | Yes, No, N/A
checkpoint-group |  |  | section | 4.0 Installation of Pipes
checkpoint-status |  |  | checkpoint | 4.1 - Laying of Pipes
label | 70eaa458-1ed8-562c-87c3-0ca08b6c3964 |  | note | Ref docs - VR Clause 701.17 (a) 701.17 (b)
label | 30d24b65-e6f0-5499-83da-5e75604bb075 |  | note | Acceptance Criteria - Laying of Pipes shall not commence until it is verified that pipe bedding complies with the specified lines and levels and compaction requirements.
button | d605a5e8-ed54-5cc0-83d2-1511436d4a35 |  | button | Approval to proceed? | Yes, No, N/A
label | 84163be0-15a0-5c2a-832f-9ba519bf26de |  | note | Laying of pipes shall commence from the downstream end. Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered. The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
button | 8512786e-39a8-5f59-94ed-f851c88b27fe |  | button | Has all of the above been completed correctly and to a high standard? | Yes, No
label | b2ee439a-c08e-5267-9776-e59fbfc3167c |  | note | Frequency - Each lot
label | b030ec9e-519b-5c8d-82db-b56bde38fe01 |  | note | Symal Key - R
label | f381fefe-527f-5bb5-ac4e-7bb8098b60d6 |  | note | Responsibility - SE
label | 1657b275-d6aa-5b74-b778-7624b1ec46a4 |  | note | Superintendent - I
button | 0b4414b8-f8b9-5bd7-97bd-7f9190190830 |  | button | Remarks/record - NATA Test Report: Compaction | Yes, No, N/A
button | 19bc0469-9e9f-5ea9-980a-3670de0c4722 |  | button | Survey Conformance Report | Yes, No, N/A
checkpoint-status |  |  | checkpoint | 4.2 - As-built Survey
label | 6e12c65b-5ddf-576c-9314-05cc301bc800 |  | note | Ref docs - VR Clause 701.10
label | 2c897431-7284-50e3-9237-56e591900c3a |  | note | Acceptance Criteria - The location and grade of each run of underground drainage shall be verified by a survey certificate prior to backfilling the underground drainage. Invert level of pipes at pits ±50 mm Departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250.
button | 77921ba9-68a7-539b-8279-605f95af3eb3 |  | button | Has the above been completed? | Yes, No, N/A
label | 328d684f-32ec-59f0-aa27-46c6664f1257 |  | note | Frequency - Each lot
label | 7640bd2a-db5f-545d-9de8-1ba89ddc5e68 |  | note | Symal Key - R I
label | 48604a72-b4c7-58b5-bc0c-9a9d74c646bd |  | note | Responsibility - SE
button | 4bf43727-044e-5157-af6f-950f8d5407da |  | button | Remarks/record - Survey Conformance Report | Yes, No, N/A
checkpoint-status |  |  | checkpoint | 4.3 - Jointing and Lifting Holes
label | 9547b334-e5e8-5d7c-aa02-e36272a0d1db |  | note | Ref docs - VR Clause 701.18
label | b9b3ebfd-7ca0-51c7-ac3c-896a43168417 |  | note | Acceptance Criteria - All interlocking joint reinforced concrete pipes shall be mortar jointed or wrapped with a 200 mm wide external joint rubber band. External rubber bands shall be manufactured from natural rubber and have a minimum tensile strength of 18 MPa and a minimum elongation of 400% at break. Rubber ring joint pipes shall be jointed with rubber rings. Ensure rubber rings are clean prior to installation. Verify joints by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket against the values specified by the manufacturer. Where lifting holes are provided, the pipes shall be laid with the hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
button | a0ed39f0-9c59-5dd9-a971-4fae27aeb952 |  | button | Has the above been completed? | Yes, No, N/A
label | a19ccfb7-7bd9-5f7c-9d82-de6479f4e919 |  | note | Frequency - Each lot
label | df50412d-69d7-51f7-a338-2bb8deb7567f |  | note | Symal Key - W
label | 4f26b960-2868-54c7-8159-302b6f70b204 |  | note | Responsibility - SE
button | 0ed3d00c-d355-561f-9982-e8b2e86346e4 |  | button | Remarks/record - Visual Inspection: Joint Overlap | Yes, No, N/A
checkpoint-group |  |  | section | 5.0 Installation of Box Culverts
checkpoint-status |  |  | checkpoint | 5.1 - Laying Box Culverts
label | c69de127-104a-5c88-b77f-185ce33ffdb7 |  | note | Ref docs - VR Clause 701.17 (a) (c) (d)
label | bba0f3e4-e937-546b-9068-e49f13f9066d |  | note | Acceptance Criteria - Consecutive sections of box culverts shall be firmly butted together. The top sections shall match to the bottom sections and shall not be lapped over adjoining bottom section. The contact areas between the top and bottom sections shall be mortared.
label | 81a35443-0121-55ae-8cbc-53704d0c2c6f |  | note | Frequency - Each lot
label | 5a14df36-f74a-54e5-9b34-e8a74ce03560 |  | note | Symal Key - R
label | 9a341a59-0cc5-50fb-9b57-b520513d0e37 |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 5.2 - Mortar
label | 1967c5a8-dc31-5b26-a8f1-51ad72c705d9 |  | note | Ref docs - VR Clause 701.09(f) VR610.32
label | 28915878-94fd-513e-9aac-5ed79b3dab29 |  | note | Acceptance Criteria - Mortar used in the laying of box culverts sections shall comply with the following requirements: - Shrinkage compensating proprietary product. - Min 28-day compressive strength not less than 40 MPa. - Cementitious grouts shall be min Type C Class dual shrinkage compensating. Testing requirements: - Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Following (2 x 7-day cubes, 1 x 28-day cube).
button | c6b1d890-da5f-5fe2-a505-e5041ae7cc36 |  | button | Has the above been completed? | Yes, No, N/A
label | 853dabe2-5567-583c-920c-08d22493d437 |  | note | Frequency - Each lot
label | 566f126a-2626-5a28-84a1-49bb978da407 |  | note | Symal Key - R
label | 59726324-ddd6-5662-a710-1583466a0d0b |  | note | Responsibility - SE
button | 832c10df-9dbd-5f7b-b2f6-054a9b20b60e |  | button | Remarks/record - Technical Data Sheet | Yes, No
checkpoint-group |  |  | section | 6.0 Completion of Works and Backfilling
checkpoint-status |  |  | checkpoint | 6.1 - Backfill Underground Drainage
label | 1ac722dd-1787-5dce-8eb5-21f0e3f442be |  | note | Ref docs - VR Clause 701.19
label | 93a60095-9f2b-51c1-b968-f38d39960304 |  | note | Acceptance Criteria - Place and compact backfill material in max loose layer thickness of 150 mm. (i) Under area to be paved: Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material. Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material. (ii) Under area not to be paved: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
button | e44ace2a-cc18-58ea-a48d-b6e07e09cc0e |  | button | Has all of the above been completed? | Yes, No, N/A
label | 8e2b3b88-1c67-56cf-9997-b8e07ce20ce6 |  | note | Frequency - Each lot
label | f71855bf-2828-5499-aa33-333118453646 |  | note | Symal Key - R I
label | b2e8b369-3ac0-5535-9529-83137cb7f6f9 |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 6.2 - Backfill with Cement Stabilised Sand
label | 9a277b18-0627-5097-ba58-153324320713 |  | note | Ref docs - VR Clause 701.19 (c)
label | 2564b59f-a640-5c35-b8d1-feb169dbf727 |  | note | Acceptance Criteria - Culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
button | d5dc4df8-cdae-5d81-985f-d21be2f8cdb3 |  | button | Has the above been completed? | Yes, No, N/A
label | 437bf655-cc9a-5421-9971-4fe700f082cf |  | note | Frequency - Each lot
label | 1fac3d64-5433-5235-b55e-5ed59645b84e |  | note | Symal Key - H
label | 4b6759fb-8fda-54b4-a08c-7424f33403ae |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 6.3 - Compaction: Backfill
label | 60cee991-aa0a-5c29-867e-9afba152f6d4 |  | note | Ref docs - VR Clause 701.20
label | 901db299-582e-5544-a517-6b5719213cc0 |  | note | Acceptance Criteria - One lot is to be raised for backfill for a culvert length (between adjacent pits or end-walls). 3 tests required per layer and a minimum of 20% of all layers for each culvert shall be tested. Material nominal size 40 mm or less after compaction: Mean density ratio not less than 97%. Material nominal size greater than 40 mm after compaction: Submit RFI compacted using a grading, mixing, watering, and rolling procedure that has been trialled, tested and proven.
button | ed42dcd9-17af-51d1-adc8-c85a6879022d |  | button | Has the above been completed? | Yes, No, N/A
label | 68971648-630e-5786-9271-6d9e95cef325 |  | note | Frequency - Each lot
label | a6a8fe40-450b-557a-941b-13b91ea7546e |  | note | Symal Key - R
label | 7e668821-e967-5a75-8bcd-60b567d4ce0a |  | note | Responsibility - SE
label | a737edb7-22c6-543b-b31b-709d990840db |  | note | Superintendent - R
button | 1a8e9a97-d23a-5cd4-a330-ebcd529ab0c3 |  | button | Remarks/record - NATA Test Report: Compaction and Moisture Content | Yes, No
checkpoint-status |  |  | checkpoint | 6.4 - Construction Loading on Culverts
label | c7770f86-1b28-57f7-9409-dc300eb5aa3d |  | note | Ref docs - VR Clause 701.14 Table 701.141
label | 15c42cc7-4dd7-54ca-8a06-ddd1ebc0d766 |  | note | Acceptance Criteria - Construction Traffic shall not be allowed until the minimum cover achieved as per table 701.141
label | 67f3662b-6d3f-5651-8ba2-29c9bc22b8cd |  | note | Frequency - Each lot
label | ac6dcdd4-57ed-5997-bd1e-13d1cd8d4ed2 |  | note | Symal Key - S
label | c769462e-69e8-51b9-a14c-e98123771a5e |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 6.5 - Testing – Backfill Material
label | d52ea478-b888-506e-aaf4-1a358f494d7d |  | note | Ref docs - VR Clause 701.29
label | 6e68582e-2617-5a3c-9f1b-7e019421c2d6 |  | note | Acceptance Criteria - Grading and Plasticity Index– one test per 1000 tonnes or part thereof.
button | a8d4e477-8fe2-58d9-8d16-0e54585d63d8 |  | button | Has the above been completed? | Yes, No, N/A
label | 09b45919-3825-5243-b0bd-a353825d34c2 |  | note | Frequency - Each lot
label | 571e0dc4-eb6d-5239-a8af-fa2f8c1eedbd |  | note | Symal Key - R
label | f78c92cd-c946-521c-a5c3-08eddab13b5e |  | note | Responsibility - SE
button | d6f21c61-3f28-57b7-b33a-fb5122a9c6ab |  | button | Remarks/record - NATA Test Report: Grading and PI | Yes, No, N/A
checkpoint-status |  |  | checkpoint | 6.6 - Existing Pipes Inspection
label | 2500650b-cbba-593e-afe9-3b2cb3a93dda |  | note | Ref docs - 1630-P200-SYM-CVD-DRG-0003
label | eda908f9-dcc3-54da-a2cd-8901ceb9ebe2 |  | note | Acceptance Criteria - Where existing pipes are to be retained, Symal are to undertake CCTV to confirm that pipes are in a satisfactory condition and clear of silt and debris. If necessary, the existing pipe and culverts are to be replaced.
label | 16885002-aa2c-58b9-be34-7f7aa8adc0f6 |  | note | Frequency - Each lot
label | 37bbeed7-0f2d-5633-a571-4a30bef783ce |  | note | Symal Key - R
label | ff8c88c0-76ad-56c3-8c20-8c5222d2e656 |  | note | Responsibility - SE
checkpoint-status |  |  | checkpoint | 6.7 - CCTV Inspection
label | f2bc0632-501e-5951-be77-7b80496d6f8d |  | note | Ref docs - 701.3
label | ad7c3558-c42a-54d7-9471-ffe9e9962695 |  | note | Acceptance Criteria - All drainage lines constructed shall be visually inspected using CCTV by an independent testing organization for the full length between pits after completion of earthworks to subgrade level and before commencement of pavement construction. Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia. Upload to the work lot, the report and the CCTV footage. The report shall include a summary of the location of any defects detected by the survey. The lot diagram shall clearly identify the length of drainage pipes for which the CCTV footage was inspected
button | 4e9c5a0a-284b-569b-ab10-a5476bf38c1c |  | button | Has the above been completed? | Yes, No, N/A
label | edd73e40-92c1-5bcf-b269-0273fb46f018 |  | note | Frequency - Each lot
label | 72d5d6d9-8615-5d80-b3e9-50e92c5c1041 |  | note | Symal Key - H
label | db3f966d-ef04-54cb-a489-bb285c74b0b6 |  | note | Responsibility - SE
label | 0efd2075-e802-5bb4-a818-7f6f9584637c |  | note | Superintendent - H
button | b6497061-db96-598a-af3a-e0c71b7c851e |  | button | Remarks/record - CCTV Inspection Report | Yes, No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.8 - Flushing of culverts
label | de7d5d74-e310-5597-9186-ae6b50c7e8fb |  | note | Ref docs - 701.28
label | 2dad93d9-e35f-5f3d-bb7a-ad02fb11f89e |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order
button | dfb7da26-e04f-5358-92ef-1dcec7c46d4e |  | button | Has the above been completed? | Yes, No, N/A
label | fc681951-1739-5dca-906e-9b4de584da09 |  | note | Frequency - Each lot
label | 6d0062d4-2352-5346-8b3d-97254f62ccf9 |  | note | Symal Key - W
label | 8bd3f642-58ea-5e1c-91a7-e7e0d8a870b6 |  | note | Responsibility - SE
checkpoint-group |  |  | section | 7.0 Close-Out
checkpoint-status |  |  | checkpoint | 7.1 - Test Reports
label | ae5e8e2a-8c9e-551d-b72d-55ea41210bbc |  | note | Acceptance Criteria - All Test reports received and reviewed
label | 01e310d2-804e-5c4d-9f7f-8999aa9d5309 |  | note | Frequency - Each lot
label | 7dc6c953-a2b8-5993-bd12-0b02b7227787 |  | note | Symal Key - R
label | c59e6fea-a63b-514c-b798-b2d016d3773a |  | note | Responsibility - SE
label | ea993db2-a585-57bc-8b21-0c23de5b24a0 |  | note | Remarks/record - NATA Endorsed Test Reports
checkpoint-status |  |  | checkpoint | 7.2 - Product Non-Conformance
label | ad92ef92-0c27-54cf-bc74-e38737df25a8 |  | note | Ref docs - QMP
label | a4318a47-dd46-57a5-9084-c571f819b501 |  | note | Acceptance Criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 88f92d79-2cad-5341-92c5-30c13f834b32 |  | note | Frequency - Each lot
label | 7c6091af-8aa0-5f42-a29a-6334aed66aa9 |  | note | Symal Key - R
label | ee909513-f5ce-597d-98b3-f3f5b9a8e892 |  | note | Responsibility - SE
label | b73746b1-adfc-503c-81bc-9b7b18ea9b30 |  | note | Remarks/record - NCR No___________ NCR reports
checkpoint-status |  |  | checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
label | 74d8a171-f66b-53fc-bf90-d590bff6af61 |  | note | Ref docs - CQMP Lot Records
label | 8a6a1a10-e5b6-5e83-816f-fb2992e388f4 |  | note | Acceptance Criteria - All above criteria met, and records identified attached.
label | 53687fb8-c622-5e58-88cf-664c3b647873 |  | note | Frequency - Each lot
label | ec378c0c-a587-514e-9ec3-d379afe9b1ec |  | note | Symal Key - R
label | 83c8edb3-f86b-5450-ad90-384f739ac113 |  | note | Responsibility - SE
label | 094b45f0-982f-5aaf-9314-d16ac70cfc5c |  | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping | e9007ad5-8686-4cfd-9689-41b829945f13
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Commencement of Work
label | 354d4795-24bc-5065-8ceb-48d5e3a49155 |  | note | Ref docs - VR Clause 160.C1 General condition of Contract
label | 3604b9c5-db0f-5d37-a313-662a65afb029 |  | note | Acceptance criteria - Works shall not commence on site before the following documents have been submitted:
label | a2f3cb45-2f2e-558f-87ca-453e0f657632 |  | note | a. Evidence of public liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
label | b51d1b8c-0fe0-5d99-988d-5917794f9d27 |  | note | b. Third party property damage insurance in accordance with Clause 160.G1
label | 3cbaafe7-b65f-5a84-bc10-df42fc0ce6fd |  | note | c. Health and Safety Management Plan
label | a8777f84-cd15-5f8b-8fed-a7c578cf98ab |  | note | d. Construction Environmental Management Plan
label | cf0d5e50-678a-5153-8ffd-8e63e15a55b2 |  | note | e. Traffic Management Strategy and Traffic Management Plans for the initial works
text | 746ebbb4-4050-5c7c-8aab-a3fcc36b41fc |  | textbox | CHAINAGE FROM
text | e8c3a184-a8f4-5272-82a3-11f5dea72b87 |  | textbox | CHAINAGE TO
button | 845c6684-e4f9-5b0f-96c7-708a92b78f54 |  | button | Has all of the above been completed and approved? | Yes, No, N/A
label | 20dac91e-ef6e-5e5e-8ffa-37400f1d0c16 |  | note | Freq - Once (Pre-Start)
label | fe244820-2108-5934-ab99-c1a8cb1ff05d |  | note | Key - H
label | 3d7c06fa-ab1a-5a17-a992-73a2cc6cb403 |  | note | Resp - SE
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 7a23205e-ea04-5fa3-a339-47099e0014fe |  | button | Lot map | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 1.2 - Safety
label | ab550148-a0da-5865-99b3-d3e81ed2fbb7 |  | note | Ensure that the following items have been actioned:
label | 858b8e46-6323-5fe7-a78a-8195315895fa |  | note | – SWMS if applicable
label | 802b698e-9f4f-585f-b64c-44224b503f97 |  | note | – Plant Pre-start Inspection
label | aee3ad6f-2789-54a5-beb7-2ae34e363e63 |  | note | – Service locations identified
label | d6d6148a-cec1-5c75-b757-64ca8569ac01 |  | note | – Traffic Management Plans (if required)
label | 53102884-5190-5c72-a305-f4f39aa0d7eb |  | note | – All staff inducted
label | 467d9bbd-b7af-54df-a720-1e52b06a19a2 |  | note | Ref docs - SMP
label | 6813e853-7c23-5fad-a934-c334791f559b |  | note | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
label | e8eaa971-6a14-516e-a927-f2a9f7730503 |  | note | • Plant inspections completed and entered.
label | 13dfd283-88d5-5589-b85c-87703defbfb2 |  | note | • TSA training completed. Pre-work briefings completed.
label | 9e6322b5-8a22-5416-8f48-9187111411cd |  | note | • Service Diagrams available and services located.
button | 3401e531-3b6a-53c1-844e-9a977d104998 |  | button | Has all of the above been completed and approved? | Yes, No, N/A
label | 7dd98b5c-d093-5144-b283-b8ac082aefc0 |  | note | Freq - Once (Pre-Start)
label | 38691c0e-e2fa-509d-b301-d94c743604b2 |  | note | Key - H
label | eb6f0e05-79c8-54f9-b15f-8ae740922568 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - Survey Set-out and TBM’s
label | c34585a1-238d-5da7-8dfd-537d2b57c11b |  | note | Ref docs - IFC Drawing
label | f913eb0e-f647-5bba-9aa8-9446a18c6acc |  | note | Acceptance criteria - Record existing and established TBMs. Survey set out including frame, benchmark, and recovery points in place.
button | 3af33cda-3a1b-5e28-a1fd-4225d5b71fd7 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 6519fc63-0e60-5cff-af9b-3840ea887760 |  | note | Freq - Prior to start of Works
label | 66258eb7-fd9d-5092-9b65-23c89f706a84 |  | note | Key - H
label | f3c38956-1ef6-5604-a24c-1983d15461ab |  | note | Resp - SE SV
checkpoint-no-status |  |  | checkpoint | 1.3.1 - Surveyor Report Reference
button | 09f688dd-aa34-5f4f-8cbc-ac625aef672f |  | button | Surveyor report reference | Yes,No,N/A
checkpoint-group |  |  | section | 2.0 Construction
checkpoint-no-status |  |  | checkpoint | 2.0.1 - Incoming Material Docket
button | 03a4e44f-00e7-590a-964e-4a5cf4e4d3b4 |  | button | Incoming material docket | Yes,No,N/A
checkpoint-status |  |  | checkpoint | 2.1 - Topsoil Stripping
label | b78056f9-eb0a-5953-b395-d43fab4429df |  | note | Ref docs - VR Clause 204.05
label | d4271cca-3256-59a3-a32d-4c9a5f196de4 |  | note | Acceptance criteria - Topsoil is to be stripped to an appropriate depth removing surface topsoil in a way to leave the surface evenly graded and free draining.
label | 4f018ea4-fbff-5c2f-a722-eb4288acda14 |  | note | • Topsoil to be reused onsite is to be stockpiled in an agreed location. All stockpiles shall be maintained in a neat, well-shaped state capable of shedding water.
button | 45a75409-28f4-56a0-99fb-520c552a9c37 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 7e4bce7f-f710-50ec-9fac-f027c0f60c90 |  | note | Freq - Each Lot
label | 8fda29b4-19e6-5859-b55b-dfa2005a36f1 |  | note | Key - R
label | d01857fa-f4df-5ae3-a305-843bef5f790e |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.2 - Site Excavation
label | 3dbca08e-003d-5324-adf5-0c8ea834c548 |  | note | Ref docs - VR Clause 204.06
label | 26145cf0-a388-5b28-bb51-e7b5aca2fa02 |  | note | Acceptance criteria - Prior and during excavation work, the Superintendent will be notified to inspect all material encountered for material classification, subject to verification by laboratory testing.
label | 4da4d0d2-4596-5db3-88a2-de1794556e17 |  | note | • The areas of rock subgrade shall be presented to the Superintendent for acceptance.
button | 11ff03e0-5769-5659-8555-fa91069a1d5c |  | button | Has all of the above been completed? | Yes, No, N/A
label | 8bbcd9ee-fac7-5547-851c-99d46787a713 |  | note | Freq - Each lot & Each possession
label | c9c30a26-d7ea-5272-8bdf-6dcc3c20cb89 |  | note | Key - H I S
label | 69ab45c6-0d80-5d75-914b-74d5750af34a |  | note | Resp - SE
label | 2ca9c33b-0b10-5043-a676-00b29b77b27a |  | note | SI Key - H
button | f140015f-9544-5a17-acbf-c61c6962d731 |  | button | NATA Test Reports (as required): | Yes, No
label | 1eeb59c8-7cb9-5cb0-b222-fad81728a2b3 |  | note | – CBR and Swell
label | 3e19371f-2051-5b89-8b7d-b5c082dc5e72 |  | note | – PI
label | b547beb7-6f63-5981-ace3-f27a7017d5f5 |  | note | – Permeability
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Groundwater / Seepage (if applicable)
label | 71e5f216-2ecc-5d84-842c-f6a2ac75ff92 |  | note | Ref docs - VR Clause 204.06 (h)
label | d7503594-bcb2-5ad7-a828-3b3fd3b71809 |  | note | Acceptance criteria - If groundwater or seepage is encountered, notify the Superintendent, and create a course of proposed action.
label | 4d8cc251-9c73-5622-bbc3-5c2224d5b4ce |  | note | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
button | 8fbc0d1b-cea8-58ca-a282-ffd65476b0e3 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 43e8fa9a-3acb-52d6-9c1c-d09bec99a386 |  | note | Freq - Each lot & Each possession
label | 8dde038c-78af-589e-843f-02cfcbd813a7 |  | note | Key - H I S
label | 7d8fb756-d231-5a81-8cc0-11f22a3054a0 |  | note | Resp - SE
label | 1d4e1dea-25a1-55fc-b1f5-75b147ced990 |  | note | SI Key - H
text | 71f126af-dbb5-5d0e-a81e-c4bae4b69a51 |  | textbox | Dewatering Permit No.:
button | 36b9c9ca-1e9e-5fd6-97cd-f50e04e32803 |  | button | Written Approval from Authorities | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Treatment of Unsuitable Materials (if applicable)
label | 6e5ebc13-ebdb-5975-b7f3-c00e48e4fb90 |  | note | Ref docs - VR Clause 204.07 (d)
label | 4c386842-4811-5f84-82fc-1a56ee50cf06 |  | note | Acceptance criteria - If unsuitable material is encountered, submit proposal for in-situ treatment or excavation and replacement with conforming material.
button | c999ed12-ea6d-51b4-b60f-583d0bd2e54e |  | button | Has all of the above been completed? | Yes, No, N/A
label | 00e7c125-26f5-5fbf-9ca4-c1acf6226440 |  | note | Freq - Each lot & Each possession
label | 94792577-2bb8-5a86-b8ec-3e497604eabb |  | note | Key - H
label | 8aad049c-99a1-51fb-b5a9-1b74159378d4 |  | note | Resp - SE
label | b589bb22-544c-5af5-b12e-1530b0e05944 |  | note | SI Key - H
button | 91fc756b-208f-594d-a1ad-c52a8b917225 |  | button | Survey Report (Extent of Area) | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Treatment of Cut / Rock Subgrade
checkpoint-status |  |  | checkpoint | 3.1 - Treatment of Rock Subgrade
label | dc46f4b8-3f7f-50a3-96fb-35a3211330b0 |  | note | Ref docs - VR Clause 204.06 (f)
label | cfd6d02c-6f33-5584-a11f-7ace2d67d67b |  | note | Acceptance criteria - Where rock exists in a cut below subgrade level but within the designed capping or selected material layer:
label | c2df1d1f-3a42-5db2-96ea-162d40546085 |  | note | • Excavate minimum 150 mm below subgrade level in all areas on which pavement is to be placed.
label | 8c02cdf2-f17c-502a-be42-aed6f00afbbc |  | note | • Remove loose material and soil from the rock floor.
label | 674927fe-90ce-524f-8824-85cfb305ffa4 |  | note | • Any resulting depressions lower than 150 mm below subgrade level shall be cleaned of loose material and backfilled with 20 mm Class 3, 3% cement treated crushed rock and compacted as specified.
label | 719f4a96-b270-510c-9f4f-d35d8b04f122 |  | note | ○ Present the above to Superintendent for inspection.
label | b5bcad0f-4589-5ff7-8f23-0b4282dc02bc |  | note | ○ Contractor is to submit details of any necessary adjustments to the subsurface drainage design, including transverse subsurface drainage at all interfaces to the Superintendent for inspection and review.
button | 73479a87-bdf1-52bb-857d-d3c85d9c1426 |  | button | Has all of the above been completed? | Yes, No, N/A
label | f425aa4b-24b9-5544-a64a-9a5784477d35 |  | note | Freq - Each lot & Each possession
label | e7a44e25-8613-5538-a8b7-f99f4214f978 |  | note | Key - H W S
label | 45af8726-8d29-58ba-966a-713b42c2caa0 |  | note | Resp - SE
label | 13aca8c9-2d27-50df-8239-4077197e6400 |  | note | SI Key - H
button | defeafc4-308c-58f0-9355-502284218a09 |  | button | Evidence of VicRoads Registered Mix | Yes,No
button | a04b5e9c-55e7-5571-be53-98d640a71176 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Regulating Layer for Rock Subgrade
label | e53644c0-6d45-5e79-861b-0b04ee49d2b9 |  | note | Ref docs - VR Clause 204.06
label | e2bd0d62-8680-552e-a466-bf615aa7814e |  | note | Acceptance criteria - Following inspection of rock subgrade by Superintendent, place 150 mm regulating layer of Class 4, 20 mm Crushed to subgrade level in lieu of the specified capping or selected material.
button | d0c31cfb-3e79-58f4-901d-21b3e64bc8b1 |  | button | Has all of the above been completed? | Yes, No, N/A
label | e7c25b1e-c2d2-5f8a-a416-663bb3fcd878 |  | note | Freq - Each lot & Each possession
label | a8085c19-1495-599b-8707-612a219a19aa |  | note | Key - W S
label | abf77ff0-fb0c-5b8a-b6f8-bf1fb1404819 |  | note | Resp - SE
button | e74dfb76-bfac-5a95-9f1d-e178756c5065 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
checkpoint-status |  |  | checkpoint | 3.3 - Testing In-situ Material in Cuts
label | d19e9362-2436-5eda-ae14-ede3d36d21d7 |  | note | Ref docs - VR Clause 204.07 PS3020.05 (c)
label | 95eb85db-9635-5592-9cc1-d069d0d51eaa |  | note | Acceptance criteria - Undertake 1 Lot test initially to determine Assigned CBR and % swell for in-situ material in cuts within 400 mm below capping layer.
label | 52b3800a-aa7b-5ee2-aa3a-c7f196ed4b55 |  | note | • Where the assigned CBR and % swell conform to the requirements of Cl. 204.04, seek the Superintendents ’s approval for minimum frequency of testing.
label | f1f02e00-9f19-5fc3-8c4f-c1bd673cddad |  | note | • Assigned CBR must be equal to or greater than 2.5% and must be no more than 10%.
label | e053a484-9e84-5867-8c77-46baf3f19112 |  | note | • Assigned percent swell must be less than 2.5%
label | 121ff1b6-5ce9-5c25-92fc-2f4e85cdb1fb |  | note | • Where Superintendent approves minimum testing frequency, proceed to conduct 1 single CBR and % swell test to confirm Assigned CBR and swell every 4 lots.
label | 8f7e6ba2-7a09-5f72-a268-279d9c46ed42 |  | note | • Where unsuitable material is encountered on site, the contractor shall submit proposed treatment plan to the superintendent for evaluation.
button | 1f310865-f0a2-52a5-b9ed-5efd69f1e4de |  | button | Has all of the above been completed? | Yes, No, N/A
label | dd19ff20-4c7e-5d4a-823c-347e77f704d1 |  | note | Freq - Each lot & Each possession
label | f170c8e9-9499-5195-9231-865b5afabea1 |  | note | Key - W S
label | 8eef8029-68cd-56b8-ba0d-9eba64294b96 |  | note | Resp - SE
button | bb76e712-5fea-51b3-8e86-c3431ca52423 |  | button | NATA Test Report: CBR and Swell | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Treatment of Cut (if applicable)
label | 13c7d6eb-566e-5ef5-bb11-40514a98c06b |  | note | Ref docs - VR Clause 204.06 (e)(ii) 204.10 (b) 204.12
label | 263ff6d1-d670-512e-8edf-ef5704dd79f2 |  | note | Acceptance criteria - The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm.
label | 188662a4-b8b1-5771-90ee-cea6ff90ca0f |  | note | • Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with Type B material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
button | f41ef56a-f579-5fc9-8fb5-67f5e62d5d07 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 419ed413-bd9e-513b-9b3c-2991b7a7eb06 |  | note | Freq - Each lot & Each possession
label | 4c934a84-3d28-534b-a5e5-0d3bfdfc260e |  | note | Key - W S
label | 7c0c504e-9ce1-5648-a1f2-2d83830fa3e5 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Compaction and Moisture Requirements (material of nominal size < 40 mm)
label | 4c0558d5-2dbf-5e33-ab3f-9e01534fef0c |  | note | Ref docs - VR Clause 204.13 (para 1) 204.13 (b) 204.15
label | 3702e6a1-eeee-50c3-a15a-d8364f238983 |  | note | Acceptance criteria - Undertake 6 tests per lot (except for small lots).
label | 309dbdf3-8fbd-55b6-a17d-f48bc67df3b5 |  | note | • Ripped and re-compacted material below CFL: minimum CDR 99% (Scale A)
label | 3667c525-8d48-50ab-8bf2-e05dea9f1d10 |  | note | • Top 150 mm of areas where fill is to be constructed: minimum CDR 97% (Scale A)
label | 9b2aa876-1447-5483-8302-1e4033166390 |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer above.
label | ba086768-31c2-586b-ab0c-c1a2512ae333 |  | note | • The moisture ratio shall be determined using the material which passes the 37.5 mm sieve, where the material contains less than 20% oversize material. If the material contains more than 20% oversize material, the moisture ratio shall be determined using an alternative method in accordance with the appropriate test method or Code of Practice.
button | a00c3d9c-a330-5e2d-8552-a6a903d9b73e |  | button | Has all of the above been completed? | Yes, No, N/A
label | 6d090dd2-21ba-5777-bd0d-ac8bd55d2bbf |  | note | Freq - Each lot & Each possession
label | c96f9750-b33f-5913-b71c-aa56b3318804 |  | note | Key - W S
label | fc8c429f-b71a-5759-a225-a5e156c3bfe1 |  | note | Resp - SE
button | a7baaf89-94d3-5839-bb11-92b0bb04e593 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
checkpoint-status |  |  | checkpoint | 3.6 - Compaction and Moisture Requirements (material of nominal size > 40 mm)
label | e5713da6-0202-59df-af38-1c0a212b7f4d |  | note | Ref docs - VR Clause 204.13 204.15
label | 6cf35207-f719-54ef-b24b-3f022973a7d6 |  | note | Acceptance criteria - All fill material and material below the Cut Floor Level shall be compacted at minimum moisture ratio of 80%. Place and compact material in accordance with approved procedure.
label | 534cd735-9926-5ca2-9608-4c4c2083f12a |  | note | • Any unstable areas detected by test rolling shall be rectified. Where unstable areas exceed 20% of the area being test rolled, the whole of the area shall be ripped, re compacted as specified above, and re-presented for test rolling.
button | 81f8a26a-fe89-5a8b-a9ca-f2341f7935fa |  | button | Has all of the above been completed? | Yes, No, N/A
label | 2e18ad7f-1650-55a5-b7f3-65dd92bf69db |  | note | Freq - Each lot & Each possession
label | f4e77a1f-07b9-52c0-9e3b-423c7293c460 |  | note | Key - W S
label | 158c3fef-8bbc-5cc5-a262-e3092516f966 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.7 - Surface Level Conformity – Fills and Prepared Surfaces
label | 517b58a4-cd13-5202-8843-6f3b7574a963 |  | note | Ref docs - VR Clause 204.03 (a),(b),(c),(d),(e),(f),(g),(i),(j) & (K)204.15
label | 02c6bd54-5239-5c37-aad6-a14a6cb8337e |  | note | • VR Clause 204.12
label | cfb65c17-b056-5982-829b-cc270e587283 |  | note | Acceptance criteria - Where capping and/or selected material is to be placed above the Cut Floor Level to subgrade level, the level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
label | fbf2949c-b9e7-54dd-af5e-7e3808610224 |  | note | • Where capping and/or selected material is not required, the Cut Floor Level shall be prepared to the appropriate tolerance for the subgrade. (See figure 1)
button | f016296c-c9bd-5b5d-81ef-1bec01e06269 |  | button | Has all of the above been completed? | Yes, No, N/A
label | caa8cc8a-1fdb-5daa-8da8-9452cc75dd47 |  | note | Freq - Each lot & Each possession
label | 7564ccc7-b44d-5cfe-b858-b2ac681a997b |  | note | Key - I S
label | bbbfc94f-2aab-592f-b3c8-54ee7d519da1 |  | note | Resp - SE
button | 35b12cf9-d6c0-5325-b11e-3655abe375c3 |  | button | Survey Conformance Report | Yes,No
label | 20ebf3e3-187e-5847-8a80-e4664a75c3f0 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | ff889095-5a80-596a-a74b-79eb81ad4af3 |  | note | Figure 1.
label | 6a8f1ba9-79e5-5c88-895c-c9da96f415b2 |  | note | Table 204.031 Minimum Number of Level Measurements and Tolerances
label | 10a3701e-7be7-5be0-90e7-afaaf9e3788b |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 6ad71462-cf0c-5bc3-a17c-90ab6eee099c |  | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̄ Range (mm) ¦¦ Tolerance: Maximum S (mm)
label | 4d49f4e8-d7cf-5442-9426-aecb66c4a12a |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | ac3dd7ba-e12c-5f27-9962-f711f8795fcf |  | note | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
label | e5d5aea4-adcf-5f14-bc61-7f0cf0f51121 |  | note | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
label | 3f744d3b-386b-5cea-811d-03e65d832e8f |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | c05453e2-8510-56b5-a1eb-923c899e0ef1 |  | note | Notes:
label | 33378fdf-1b0e-5fd7-8cdb-a743c5ed8561 |  | note | 1. x̄ is the mean value of all level readings taken in the lot
label | 16c761b7-d084-5b00-9c03-a81db5facd61 |  | note | 2. S is the standard deviation of all level readings taken in the lot
label | 1c6d8b14-6eb4-5370-82d4-acb374136121 |  | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
checkpoint-status |  |  | checkpoint | 3.8 - Test Rolling
label | 2df1ed7a-3f9e-58de-b541-ecf8f1e8736a |  | note | Ref docs - VR Clause 204.12
label | faa97184-a15a-5b06-8759-5d9da28419c4 |  | note | Acceptance criteria - Test Roll in accordance with Section 173.
label | ed057fd5-5646-5b6a-9feb-760dff8e743f |  | note | • The Contractor shall provide for the Superintendent to be present during all test rolling.
label | 6ae69317-d944-5705-8af1-20894256f4a4 |  | note | • Surface shall withstand test rolling without visible deformation or springing.
button | eef470b0-9d49-5204-8b25-964221af9fb7 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 97ded3ae-34a4-5064-88ae-58153bfec0cf |  | note | Freq - Each lot & Each possession
label | 74e0d21d-c552-5dd5-8465-4f0fecfcd990 |  | note | Key - W S
label | e140ed56-b79d-53b2-af93-0280d4428121 |  | note | Resp - SE
label | d6c70eda-971c-5781-873d-f941dc7d37e5 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 3.8.1 - Proof roll if applicable
button | 9af9148c-76ed-5486-a207-1cac2fa80380 |  | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
text | d8a339f5-31c1-52e8-8467-959132686604 |  | textbox | Chainage
checkpoint-status |  |  | checkpoint | 3.9 - Maintenance of Cut Floor Level
label | 7759a58f-fb5b-5c17-a11a-775b50759477 |  | note | Ref docs - VR Clause 204.15
label | 9c3afb80-a414-5352-8f93-ea14a15ec8c4 |  | note | Acceptance criteria - Visual inspection to confirm that surface is produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | 50431e93-6315-5693-893f-b29e79663935 |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
button | 75d270ab-b993-55cd-9ce6-4d9a0ba6fd7a |  | button | Has all of the above been completed? | Yes, No, N/A
label | 939d98dd-c561-5ca7-8265-ec96bf4ad7fc |  | note | Freq - Each lot & Each possession
label | 2891a4a3-aaee-5713-80c0-1d501857cb12 |  | note | Key - W S
label | 331b886e-9a67-5851-bce8-308e774caabe |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Test Reports
label | b190ccef-1ea1-5964-b59e-b33ae19a291e |  | note | Ref docs - VIC Roads Specifications
button | 34232b75-da6c-53e2-aa25-51ae3844ab67 |  | button | Acceptance criteria - All Test reports received and Reviewed. | Yes, No, N/A
label | 530678c3-b60d-5b84-9051-7a5f5e02cf74 |  | note | Freq - Each lot
label | 81302774-d031-5f9e-a3af-dfadc79a9982 |  | note | Key - R
label | 43cb3c08-fa9a-598c-948a-863187ae379b |  | note | Resp - SE
button | 34b18927-742a-556e-a974-7efc3474d1ce |  | button | NATA Endorsed Test Reports | Yes,No
checkpoint-status |  |  | checkpoint | 4.2 - Product Non-Conformance
label | 440ede72-b716-5c21-b481-e8ce125fb51d |  | note | Ref docs - CQMP
button | 544e2d5c-6070-56a9-b017-a94410256f62 |  | button | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable) | Yes, No, N/A
label | d272dd55-8d73-5999-b921-4232ad0bd0ae |  | note | Freq - Each lot
label | f12d9070-98c4-5e5e-a9e5-d393f6675078 |  | note | Key - R
label | a2764a93-086b-5613-9770-d9e227ba285c |  | note | Resp - SE
text | 406a12de-d985-508a-acf6-f29296fe8f43 |  | textbox | NCR No:
button | 25b65892-8b52-5646-87e1-0abb1a91f2ce |  | button | NCR reports | Yes,No
checkpoint-status |  |  | checkpoint | Works complete
text | 8e6f2020-9965-51d1-adb2-8ae0a80cefde |  | textbox | Name:
text | 7bed400d-0a9e-59d7-9ad4-87b46aac7d68 |  | textbox | Position:
text | 7a803878-0079-5057-8bbb-6262cf2fae33 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | a74f3555-06d7-5e38-8363-7f4c430d1281 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 5e2ef7f6-7cf3-5492-a301-2380d87e28c6 |  | textbox | Lot opened date:
text | 113a78f1-49dd-5b7d-90ff-ad2a466ffac1 |  | textbox | Lot opened by:
text | 1d89c42d-b4aa-546e-8b47-a1e3dae6a789 |  | textbox | Date lot closed:
button | 8f7af5ee-580c-5db9-8da3-3c219248d580 |  | button | NCR raised? | Yes, No
text | cc62c50c-2687-59ae-b65d-2ae43f6fc644 |  | textbox | NCR Raised Date:
button | db18f11e-7363-5103-ba2c-1b689f2ec717 |  | button | NCR closed? | Yes, No
text | d90f20cc-4751-599d-adcc-736c7d28a653 |  | textbox | NCR Closed Date:
text | a1372e54-146a-5b52-a4c8-18ce7642526e |  | textbox | NCR Number:
text | 3019cb63-4553-5dfe-b0af-5ae8eda01a0b |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0013 Subsurface Drainage |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0013 Subsurface Drainage | f2d3d3ba-04aa-4fb7-88d1-d230b4fdf57e
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Procedure for method of compaction and placement of no fines concrete filter material
label | f91c4160-0901-5ff0-84dc-a01402165585 |  | note | Ref docs - VR702.09
label | baf26de6-f23c-5528-ab0f-0aeb0cb4c2fe |  | note | Acceptance criteria - The method of compaction shall be in accordance with the Contractor’s quality procedures and shall be submitted for review by the Superintendent.
label | 7c40b4fa-1629-59a8-96a7-88137761989f |  | note | Freq - Prior to start of works
label | a819febb-b549-5ecc-bdf0-1472f4aed0fd |  | note | Key - H
label | f51c384c-1295-527c-94f7-74760bb6bc44 |  | note | Resp - SE
label | c7f819e0-781f-53a1-b6b5-003f52b7bf2c |  | note | SI Key - R
label | 8580071f-66d5-53ab-9a24-aefce84bfb87 |  | note | Remarks/record - As per approved Construction Document
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 47ea718a-9139-5084-860d-d61fe2a4b303 |  | button | Lot map | Yes,No,N/A
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | c6c85b1f-bd88-5b7d-ab61-320bb0242f3a |  | button | Environmental permit | Yes,No,N/A
checkpoint-group |  |  | section | 2.0 Materials
checkpoint-status |  |  | checkpoint | 2.1 - Supply of Pipes & Geocomposite Drains
label | 8f7feb94-1e20-503f-80a9-464aabb7aa7a |  | note | Ref docs - VR702.04 PS3030.05 IFC Drawings
label | cf4f7680-b046-5462-bd22-538d537a9831 |  | note | Acceptance criteria - All subsurface drainage pipes supplied shall be Category 1 (Class 1000)
label | 273d6d78-1063-5fbf-bbbb-59ed1dfbdce5 |  | note | • Perforation size must be a maximum width of 1.5 mm and a minimum length of 150 mm per m2
label | ac1cebec-1090-5106-8541-42a4bd3543c0 |  | note | • Plastic pipes and geocomposite drains shall be handled appropriately to reduce sunlight exposure during delivery, storage, and installation.
label | 614cbcd9-5e0e-5a02-aaf7-ed818f827c33 |  | note | Freq - Each Lot
label | ce6a6110-e5a7-5ad4-8143-0e600ede901a |  | note | Key - R I
label | 0b5476dc-1756-5c17-b07a-6565e21cdd00 |  | note | Resp - SE
button | 97e5a096-2c3a-5d9c-a980-ccc89c03ee38 |  | button | Remarks/record - Manufactures Compliance Certificates (AS2439) | Yes,No
checkpoint-status |  |  | checkpoint | 2.2 - Supply of Pits & Flushout Risers
label | ec9d882f-aaaa-579c-a3f6-e5370a651b6d |  | note | Ref docs - SD1631 SD1611 PS3030.5 IFC Drawings
label | 151e6603-94c4-5a87-8b11-ba064be9a25f |  | note | Acceptance criteria - Flushout risers for geocomposite drains shall consist of a preformed riser fitting, or a pipe of diameter not less than 100 mm.
label | 3ae307c4-e1e8-5a40-8e2d-9760a3071c98 |  | note | • Flushout risers shall have surface fittings as shown on the drawings.
label | 77b32c0c-1d36-5a2d-9a66-e5198ee404f7 |  | note | • Pits shall be supplied in accordance to SD1611.
label | 38168700-4b13-534f-affe-b942331ae85d |  | note | Freq - Each Lot
label | 114cc5da-9d61-51c0-94d4-65f9a4d2e2c8 |  | note | Key - R
label | 683e20dc-f300-5288-82a7-d63a2f4e6daa |  | note | Resp - SE
button | 07491c3d-4a88-5428-a91a-5330a038a49c |  | button | Remarks/record - Supplier Compliance Certificate | Yes,No
checkpoint-status |  |  | checkpoint | 2.3 - Granular Filter Material – Sand
label | 3811133f-0710-5ad4-9f62-2440cd05d933 |  | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
label | 1a2aaf02-1b0c-534a-ac5f-b810c5b7abcf |  | note | Acceptance criteria - Granular filter material must meet the below requirements:
label | 971b6d87-a765-5b8a-8084-12ad0e12e63f |  | note | • Grading: As per Table 702.051,
label | f3242474-0e4c-52cb-91c3-a2b386631e93 |  | note | • pH: 6.0 – 10.0.
label | 3c9df138-e52c-5e6d-918c-b33d8a3e3c2f |  | note | • For glass fines: be thoroughly washed and retested prior to use, where the measured Total Dissolved Solids (TDS) of the granular filter material exceeds 1500 mg/L.
label | af0da553-1d01-5b9f-8e68-f87b83693fa3 |  | note | ○ pH and total dissolved solids (glass fines only) must be tested at a rate of one test per 5000 tonnes of product.
label | 88af118c-2df4-5ab4-81ac-6b8df59be9ef |  | note | Freq - Each Lot
label | d358e849-b700-59e5-940e-36d5c7a3096b |  | note | Key - R
label | 9567219c-eff3-5084-8596-0b2350b26097 |  | note | Resp - SE
label | 07528748-56e8-59fc-b9c0-24769d992cb7 |  | note | SI Key - R
button | 60df4f2c-a2a9-5302-91dd-4b443ad6ca57 |  | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
button | d68c2f31-bd15-5a6c-bbf2-8ab7b63b93ec |  | button | Remarks/record - NATA Test Report: Grading | Yes,No
checkpoint-status |  |  | checkpoint | 2.4 - Granular Filter Material – Crushed Rock
label | 09176e86-dd31-58a6-91c3-638a86822827 |  | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
label | 2f29afd7-ab07-5300-9835-e5cb85f0166f |  | note | Acceptance criteria - Granular filter material must meet the below requirements:
label | faa1e1c3-dc3c-5a53-a82b-ec80e7a4ab5b |  | note | • Grading: As per Table 702.051,
label | 3d822aad-c10d-511e-9cc2-274c2598bb03 |  | note | • Unsound Rock Content: < 5% by mass,
label | 558bc1b8-7c21-5d47-8b37-b6471d434a2c |  | note | • pH: 6.0 – 10.0.
label | e2a27c78-4276-55c8-823a-9933b4caae98 |  | note | ○ Crushed Rock Components: The percentage by mass of unsound and marginal rock in that fraction of an aggregate retained on a 4.75 mm AS sieve shall not exceed the values specified in Table 702.052.
label | 85cc2d29-e21b-5167-91d2-0d6dda96d518 |  | note | ○ Granular filter material must be tested for grading, unsound rock content on each production day or at a rate of one test per 500 tonnes of material as per Table 702.131.
label | 52502764-001a-5415-874c-a6c4c2d4d3a9 |  | note | Freq - Each Lot
label | c58d5326-9211-5273-b4e8-bd72094ec365 |  | note | Key - R
label | 3bacf34b-b730-5897-a716-4c4f7810985d |  | note | Resp - SE
label | 145d03e5-0484-5c17-b0ff-b3338c8d3351 |  | note | SI Key - R
button | 5dae040e-c748-5b49-99f6-49b0ffba19df |  | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
button | 904bb841-333b-5335-a8f5-b6c3dfd0a15d |  | button | Remarks/record - NATA Test Report: Grading | Yes,No
checkpoint-status |  |  | checkpoint | 2.5 - Granular Filter Material – No Fines
label | c8221dc3-b527-5ab6-b679-6fa0e0e68227 |  | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
label | f645cf26-faf8-5e49-bf10-24b898b5aa57 |  | note | Acceptance criteria - Granular filter material must meet the below requirements:
label | 655ae7c5-03c0-5013-a36a-a14518988859 |  | note | • Grading: As per Table 702.051,
label | 4369bf76-c723-591f-92f6-5b460a1ca42c |  | note | • Unsound Rock Content: < 5% by mass,
label | 36e349d0-ad0b-50cd-887a-1b7dc700bb8c |  | note | • pH: 6.0 – 10.0.
label | 7fdf8164-4230-5e22-8547-2fc64c48c1f1 |  | note | ○ No fines concrete shall consist of B4 filter as defined in Table 702.051 and mixed with 4.0% by mass of cement and 3.5% by mass of water in a mixing plant.
label | a37d3119-0e1e-5974-9442-1b2c46224f1d |  | note | ○ Granular filter material must be tested for grading, unsound rock content on each production day or at a rate of one test per 500 tonnes of material as per Table 702.131.
label | 992b1f2a-8a17-56df-9683-7fddad9acbe1 |  | note | Freq - Each Lot
label | d91f44ec-dd2c-5517-92b7-1e2f3d9e3df8 |  | note | Key - R
label | 3c49ec8e-2bd4-5adf-9fbf-f24783c33ba0 |  | note | Resp - SE
label | d69c2e96-659a-5b1c-ac6a-c1525d4f4661 |  | note | SI Key - R
button | e4a24350-e40f-5bc5-88a1-63111416f486 |  | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
button | 5c8c87f9-545c-542d-bee3-679123d090a9 |  | button | Remarks/record - NATA Test Report: Grading | Yes,No
checkpoint-status |  |  | checkpoint | 2.6 - Geotextile Filters
label | c3a6be97-0579-50bd-9b72-d47682cca111 |  | note | Ref docs - VR702.06 Table 702.061
label | ac0ef425-9491-543e-9d83-3c542cb681a4 |  | note | Acceptance criteria - Geotextile filter shall consist of a fabric manufactured from synthetic fibres of a long-chain polymer such as polypropylene, polyethylene, polyester or similar material and shall be stabilised against deterioration due to ultraviolet light.
label | f2df2df4-f8c1-55eb-811e-28a56c7309c0 |  | note | • The geotextile shall be free from defects or flaws which significantly affect its physical and/or filtering properties.
label | 580ad5ff-e4bf-58c0-84cb-b3d39b75265f |  | note | • A geotextile filter may be non-woven or knitted fabric and shall comply with the requirements of Table 702.061 relevant to the geotextile filter type specified in clause 702.12.
label | efda487c-7a9e-5e78-8490-521fc56b2282 |  | note | Freq - Each Lot
label | 5c522407-8aab-5258-ad15-4176c21becc4 |  | note | Key - R
label | fb8d4874-42d2-5c63-9286-4bb92c7ca5ab |  | note | Resp - SE
button | 69e30fae-1e79-5946-bca0-9deba2d8acf1 |  | button | Remarks/record - Manufactures Compliance Certificates | Yes,No
checkpoint-group |  |  | section | 3.0 Installation of Subsoil Drainage
checkpoint-status |  |  | checkpoint | 3.1 - Excavation of Trench
label | 7bd9f9d0-c738-50b6-8134-ea48c0b64d18 |  | note | Ref docs - VR702.08 VR702.09
label | 59693f08-14d9-52b7-b868-f19c105e1005 |  | note | Acceptance criteria - Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile
label | b7a0263d-0c14-5c12-84ec-85e544ae7a6e |  | note | • Trench base shall not be more than 50mm below the specified level of invert of the pipe.
label | 5ae1fde6-c02b-59dd-ab3d-add57cf912ae |  | note | • The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations.
label | fd41dc9b-8f15-5e81-9a58-9a0423cb30f5 |  | note | • Subsurface drainage pipes or geocomposite drains shall be laid to the depths or levels shown on the drawings. The top of any subsurface drainage pipe shall be at least 200 mm below subgrade.
label | 6d91e3cf-9858-5531-8866-57e3e859ea0f |  | note | Freq - Each Lot
label | 89749f10-a14e-5114-a627-c63c8e6758ea |  | note | Key - S
label | e6b1b70e-b0bf-586d-ac3c-a74a7af0de38 |  | note | Resp - SE
label | 1a0fa295-08a4-5441-856d-f331b8dd4004 |  | note | SI Key - I
checkpoint-status |  |  | checkpoint | 3.2 - Excavation of Trench in Expansive Material
label | 36ebc5e6-44e5-57f7-89c6-85aef457d46c |  | note | Ref docs - PS3030.07 (b)
label | 2539ff39-cf33-541e-84fc-c43a021c6e18 |  | note | Acceptance criteria - Subsurface drainages laid in expansive materials with swell ≥2.5% shall conform to the following requirements:
label | e86ed7cd-919a-5968-b417-0a185f2eedaa |  | note | • Pipes shall not come into contact with material.
label | 357e4d7c-199d-51d8-9df5-078839accc88 |  | note | • At least 100mm of capping materials provided below the floor of the subsurface drainage trench.
label | 0ec4b5a0-d9d2-5018-9ccb-f79e7a778fc9 |  | note | Freq - Each Lot
label | 4944e6d4-903e-5d2a-8b80-87b35bbb86df |  | note | Key - I
label | 83ea4b76-4cbc-5e61-b7ac-d1ff492d4c11 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.3 - Placement of Bedding
label | 4619c392-f4f4-563e-ad61-13b47e6888be |  | note | Ref docs - VR702.09
label | 71b8d399-22b2-5b59-bb6c-50cd521898d4 |  | note | Acceptance criteria - A bedding of granular filter material of thickness between 25 mm and 50 mm shall be placed across the bottom of the trench. The bedding shall be tamped and screeded or graded to level. Bedding is not required for geocomposite drains.
label | 1aea52bf-ab14-5a51-bb08-174f980f4833 |  | note | Freq - Each Lot
label | d1fd14e3-15cf-556f-b21d-603e33490153 |  | note | Key - H
label | 56718f78-4ed8-5b98-b388-0cc39341615a |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.4 - Construction – Pipe and Geocomposite Installation
label | 640b623a-18fe-5036-9a3c-d79a417332c1 |  | note | Ref docs - VR702.09 702.03
label | 22d4f3a1-7df1-5571-8dc4-58da82d3367a |  | note | Acceptance criteria - The grade of pipes or geocomposite drains shall be not flatter than 1 in 250.
label | 92d3920d-1ef9-536b-a744-3bdc643e2bd9 |  | note | • Pipes shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the openings in the lower half of the pipe.
label | 4a3a04dc-9119-5826-a93d-18a3b2d33fc2 |  | note | • The minimum width of geotextile used for wrapping shall be 450 mm.
label | 3a18cfc0-2363-53e0-9039-65ed15fc4d98 |  | note | • Lap joints in geotextile used as first stage filters shall consist of an overlap of not less than 900 mm longitudinally and 150 mm transversely. Lap joints in geotextile used as second stage filters shall consist of an overlap of not less than 300 mm.
label | 5dc695c8-7277-5219-88d8-601bedec6f21 |  | note | Freq - Each Lot
label | e5977556-0fed-5fa6-89f2-7edfca848cf1 |  | note | Key - S
label | 960f5792-99fb-52c9-84cf-7aa09d35a30d |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Construction – Access points and Inspection Openings
label | 88c7d12c-694d-5bad-9137-47d947e7f75f |  | note | Ref docs - VR702.10 IFC Drawing
label | 03ab2281-19a2-5318-9168-08142fa539e5 |  | note | Acceptance criteria - Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located minimum 100 mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100 m and 150 m intervals unless noted otherwise on drawings.
label | 9434db44-af8a-5f1c-91c0-d365c259d7a1 |  | note | Freq - Each Lot
label | c0bc77e5-0398-571e-a636-95651ff05829 |  | note | Key - R I
label | 6434209d-949a-5dd4-a3a8-ff001f141861 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Construction – S1 Pit, Batter Outlet & Flush Out Riser Installation
label | 97e6b5ce-212c-50b0-851d-b0a8cb219cdd |  | note | Ref docs - VR702.10 SD1611 IFC Drawings PS3030.05
label | 83acf61d-16ac-5572-bbb6-ff8fc03b21b7 |  | note | Acceptance criteria - Flushout risers for drainage pipes shall have the same diameter as the pipe.
label | b67903ae-0ce6-5e72-94d3-4a4c74742166 |  | note | • Flushout risers for geocomposite drains shall consist of a preformed riser fitting, or a pipe of diameter not less than 100 mm.
label | 644b19b8-00f0-5050-bb83-ef8f9158b8ab |  | note | • Flushout risers shall be installed in accordance to SD1631.
label | 3ed2cc6c-620c-5c52-ba33-91534094a228 |  | note | • Pits shall be installed in accordance to SD1611.
label | a45d8c32-220a-56c9-99a7-b74e9e97b207 |  | note | • Pits deeper than 1m shall be fitted with step irons.
label | 80c5a124-76f6-56de-b599-bc0f5d89d843 |  | note | • Batter outlets into a swale must maintain min. 200mm clearance to the invert of the swale.
label | a59eb6cc-7c95-5ad9-8a17-88405ba259d4 |  | note | Freq - Each Lot
label | 12742cf6-a07f-58d5-9155-00a8e8293a0e |  | note | Key - R I
label | db61ae89-269d-56b8-b13c-ee11e102599c |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.7 - Inspection of Drainage Lines & Pits
label | 55f7f2c5-a08b-5dfc-ac6e-3df9c9df9df9 |  | note | Ref docs - PS3030.07 (iv)
label | f953710e-fca7-519d-8e21-97f6c2730cfa |  | note | Acceptance criteria - The superintendent must inspect subsoil drainage trenches, subsoil drainage lines, and associated pits, endwalls and risers, prior to the commencement of backfilling
label | 86832d77-623b-5f6b-87a9-b6677a4b12ab |  | note | Freq - Each Lot
label | eb506233-9ac2-5b02-be31-28c3bc7815f9 |  | note | Key - H
label | fc4e10fd-e8d6-570d-a34b-c364965e2fa0 |  | note | Resp - SE
label | 7627a78c-0f51-52e5-935f-dcf76510f065 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Construction – Granular Filter Backfill
label | d173159f-d06b-5b96-92b7-ea83a8ce2f2e |  | note | Ref docs - VR702.09(g), Approved procedure in Construction Document - Drainage
label | 442dd08f-a2f3-5796-85c3-b30d6e0bb83e |  | note | Acceptance criteria - Material shall be placed moist and compacted in layers not exceeding 300 mm. Material shall be compacted with minimal disturbance to pipes, geocomposite drains, geotextiles and trench walls.
label | a9148e6e-3beb-5399-9e15-70c6acf1fa10 |  | note | • The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Superintendent.
label | 2dcf837b-3bde-5dc2-bbfa-3d2de5159829 |  | note | Freq - Each Lot
label | 89bc7873-f56b-5872-b69b-1153b18a7268 |  | note | Key - H
label | eeeecb47-e895-5d1e-99ae-adab1babf10f |  | note | Resp - SE
label | c1cb9778-e45f-563d-a042-5b8b07155991 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Construction – Granular Filter Backfill (No Fines)
label | 2072a448-e3f9-5a31-b5ca-9e19c2b26ca9 |  | note | Ref docs - VR702.09(g), Approved procedure in Construction Document – Drainage
label | 0f1b448f-0228-511f-84a7-837ff37ff37b |  | note | Acceptance criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
label | 7fcd070c-39ea-56a6-b0ef-2274a6ffa241 |  | note | • Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
label | 8b131465-ab7c-5e4d-83fb-f063837f51eb |  | note | Freq - Each Lot
label | 215b8604-b8db-5534-b02e-ebb68e963a48 |  | note | Key - H
label | 1bdafb71-abb4-5d6d-818a-300a60a66cb9 |  | note | Resp - SE
label | a81da753-6320-52da-a355-de68779ffc02 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Flushing of Subsoil Lines Flushed after Completion of Flushers, Outlets
label | 953a5cbb-8349-5e39-9042-4d803aa17ab1 |  | note | Ref docs - VR Clause 702.09 (h)
label | 07b39d41-7e5f-56dd-bffb-b34e313c7c1a |  | note | Acceptance criteria - Subsoil Lines Flushed to ensure Drainage Lines are free from obstruction.
label | 698100be-8a9d-5139-8767-864369e947b6 |  | note | • Location, Date & Time for subsoil line recorded on lot map.
label | d0c1e9e7-5fa9-5b34-a298-8f2d86f1a17b |  | note | • The flushing test shall be witnessed by a representative nominated by the Superintendent.
label | b85f5998-6ec3-570f-b3c5-4fc19aca9ab0 |  | note | Freq - Each Lot
label | 92bed01e-f772-55bc-85b8-ebe282a07b51 |  | note | Key - R
label | 3604ea2a-9d1a-591d-93f9-10c32b0c6e20 |  | note | Resp - SE
label | 184ce42a-684e-5459-a54e-52926cb989b6 |  | note | SI Key - W
checkpoint-status |  |  | checkpoint | 4.2 - Inspection of Subsurface Drainage Lines
label | b7e3b1ce-a873-5bba-8162-8e666cf7e7e9 |  | note | Ref docs - DoT Clause 702.09(i)
label | 9536df01-d8fc-58fc-a61e-0770a774c8b9 |  | note | Acceptance criteria - All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television
label | bfc087df-b2d0-50f6-8b10-2ad780631d49 |  | note | • (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | f93d71b7-43ac-5dad-8932-55f49d2612eb |  | note | • The report shall be provided to the Superintendent, with a copy of the CCTV record including any video recordings and a summary of the location of any waste construction materials, obstructions and defects detected by the survey.
label | c1d7a9b8-efba-5b26-8a2f-71501b79c513 |  | note | • Any sections of damaged or deformed subsurface drainage pipe shall be removed and replaced. A further CCTV survey shall be undertaken to verify that the damaged or deformed subsurface drainage pipes have been replaced and are defects free.
label | 58c2ad75-7e0a-53a6-988f-665f8e88ebea |  | note | • Placement of Asphalt shall not proceed until the CCTV inspection and flushing test has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage line has been verified by the superintendent.
label | e02bb468-4e29-5d0e-83c0-50e27df55e59 |  | note | Freq - Each Lot
label | 82078bef-9e64-5ede-bc2c-333011a712ab |  | note | Key - H
label | be6019c5-5539-5af0-b230-cd9e0d33f962 |  | note | Resp - SE
label | 255aa015-f272-53c8-b41e-e21c1295692f |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - As built
label | 14911955-1a54-575f-a05f-1141b5e948f1 |  | note | Ref docs - DoT Clause 702.03
label | aee2fc8c-9e05-5d50-8de2-6ff808ddc91f |  | note | Acceptance criteria - Subsurface drains to be constructed true to line, level and depth, as shown on the drawings.
label | f16a35b3-b8d9-5d02-934a-e59a1efac3f5 |  | note | • The invert of the subsurface drainage to be < 25 mm from the specified level and not more than 50 mm from the specified line.
label | e581257d-15d3-5db1-bd84-8a4b38636448 |  | note | • Grade < 10mm in any 3m length or lead to ponding of water within the drainage pipe.
label | 935a5baa-5625-5e37-b445-b57fb147ff2e |  | note | • Changes to design shall be recorded.
label | daaac9b5-5f46-55bb-878f-50a727c980b6 |  | note | Freq - Each Lot
label | 8bdb13ba-d1da-5ce5-809a-b4fc7f060842 |  | note | Key - H
label | ec629d6f-8558-5e66-b944-1e1b07e0709b |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.4 - Product Non-Conformance
label | e2a54873-2016-5acb-ac85-a68fc99f48a4 |  | note | Ref docs - CQMP
label | d20b3537-49c2-507a-a9ac-3d6dde75ea5b |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 19a0207c-729a-5575-a06b-ef1d9ba76281 |  | note | Freq - Each Lot
label | 903bf4b5-fa73-5e5b-a424-50f307c39790 |  | note | Key - R
label | 7e5a2076-fabd-55e2-a470-b22c6ab8c33c |  | note | Resp - SE
button | dc40bfc9-fa82-51da-bea9-4fc996016e04 |  | button | Remarks/record - NCR | Yes,No
text | fe1dabd7-951f-53a8-b600-7784d85088aa |  | textbox | NCR No:
checkpoint-status |  |  | checkpoint | Works complete
text | f608ec89-1391-59ce-b38c-450a52b83682 |  | textbox | Name:
text | ed9ecff7-796d-513b-b39a-19956b1345a7 |  | textbox | Position:
text | bb53acb1-963e-59db-b2b1-874863abeb51 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 96db63d1-1903-55a9-8088-1a4f5c8b7f17 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 0d59c59c-1c87-5b0e-b99d-dcd94fafe97e |  | textbox | Lot opened date:
text | 54aea8b7-9409-5209-8fea-9eafa6c209ed |  | textbox | Lot opened by:
text | c0229246-fe9c-5558-a665-edb05b39755d |  | textbox | Date lot closed:
button | 1b814b65-477b-5b10-9b79-4b38619cae71 |  | button | NCR raised? | Yes, No
text | 9319d810-ad00-544e-8e4c-e434fa828e7c |  | textbox | NCR Raised Date:
button | 42a47ca8-bffe-508a-bcee-1247f5bce91e |  | button | NCR closed? | Yes, No
text | 1382810a-e71a-5a31-b3b0-caa5aa9c52c7 |  | textbox | NCR Closed Date:
text | 2d7aeabd-4ae5-5e05-836a-82aae30c94f1 |  | textbox | NCR Number:
text | 6340ecaa-30c1-552e-8c9c-4f345db39de3 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP