## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP-013-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0013 - Structural Concrete | 5210e9b4-9ed2-48fd-a6c7-3f29aa61738c
checkpoint-group | 1 - Referenced Documentation
checkpoint-status | Referenced Documentation
label | Document Title: ITP-013-AX-LOT-XXX - Description
label | ITP Description: Structural Concrete
label | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0013
label | Revision Number: 00
label | Revision Date: 26/05/2022
label | ITP created by: Omar El-Khub
label | ITP approved for use by: Babak Rudd
label | 1.1 VicRoads Section 204 Dec 2015
label | 1.2 VicRoads Section 602 Oct 2007
label | 1.3 VicRoads Section 610 Feb 2020
label | 1.4 VicRoads Section 611 Nov 2018
label | 1.5 VicRoads Section 613 Jun 2017
label | 1.6 VicRoads Section 614 Jun 2017
label | 1.7 AS5100
label | 1.8 AS3810
checkpoint-group | 2 - Preliminaries - Materials
checkpoint-status | 2.1 - Concrete mix design
label | Frequency - Each Mix, not less than 4 weeks prior to the placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Ensure all mix designs have been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | Concrete Mix is Registered with VicRoads.
label | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.07(b)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved Mix design
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 2.2 - Reinforcement Certification
label | Frequency - Once for each supplier, 14 days of award of contract
label | - - - - - - - - -
label | Acceptance Criteria - Ensure the manufacturer and supplier of the steel reinforcement is in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance submitted to superintendent within 14 days of contract award.
label | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g. 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.611.04
label | Cl.611.05(a)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - ACRS Certificate of Approval.
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 2.3 - Bar Chairs/Aspros Certification
label | Frequency - Once for each supplier, 14 days of award of contract
label | - - - - - - - - -
label | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.26 (a)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved bar chairs and aspros
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 2.4 - Evaporative Retardant
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.17 (f)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved evaporative retardant
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 2.5 - Curing Compound
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.23 (b)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved curing compound
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-group | 3 - Preliminary Works
checkpoint-status | 3.1 - Concrete Placement and Compaction Work Method Statements
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to MRPV
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.18 (a) (i)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved WMS
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 3.2 - Concrete Sampling and Testing Procedure
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to MRPV
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.18 (a) (v)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved procedure
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | Minutes of this meeting to be submitted to MRPV
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.18 (a) (iv)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved quality requirements
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | Frequency - Once, 2 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to MRPV.
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.17
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved procedure
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 3.5 - Curing Methodology (for Concrete and Grout)
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Curing methodology/procedure to be submitted for review to MRPV.
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.23 (a)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved methodology
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 3.6 - Concrete Drilling Procedure
label | Frequency - Where applicable, once, 2 days prior to drilling
label | - - - - - - - - -
label | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | The planned locations and drilling procedure shall be submitted for review to MRPV.
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.46
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved drilling location and procedure
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-group | 4 - Pre-construction activities
checkpoint-status | 4.1 - Check that IFC drawings are being used
label | Frequency - Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria - Issued For Construction (IFC) and latest available revision on TeamBinder is used
label | - - - - - - - - -
label | Reference Documents - Project Drawings / Drawing Register
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Latest Revision Drawings
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer / Site Foreman
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 4.2 - Survey set out works
label | Frequency - Prior to Work Commencement
label | - - - - - - - - -
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used
label | - - - - - - - - -
label | Reference Documents - Project Spec.
label | Cl.1190.06
label | - - - - - - - - -
label | Inspection / Test Method - Site inspection
label | - - - - - - - - -
label | Record of conformity - Survey records & pegs on the ground This ITP Signed off
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Site Engineer, Foreman & Surveyor
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 4.3 - Excavation Permit issued
label | Frequency - Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
label | - - - - - - - - -
label | Reference Documents - Excavation Permit
label | - - - - - - - - -
label | Inspection / Test Method - Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity - Excavation Permit #
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 4.4 - Excavation Inspection
label | Frequency - Where applicable, prior to placing blinding concrete
label | - - - - - - - - -
label | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.602.03
label | - - - - - - - - -
label | Inspection / Test Method - Site inspection
label | - - - - - - - - -
label | Record of conformity - Superintendent approval
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Site Engineer/ Project Engineer
label | - - - - - - - - -
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 5 - Construction Activities - Formwork
checkpoint-status | 5.1 - Formwork Design and Construction
label | Frequency - Each Pour/ Type of element
label | - - - - - - - - -
label | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.614.04
label | CI.614.05
label | Cl.614.06
label | Table 614.041
label | - - - - - - - - -
label | Inspection / Test Method - Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity - Proof Engineering Certificate approved This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | Frequency - Each element (where greater than 2m)
label | - - - - - - - - -
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres
label | All other concrete members
label | Any member for which self-compacting concrete is proposed.
label | Attach: Attachment A
label | Attach: Attachment B
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.614.08
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | Visual
label | Measure
label | - - - - - - - - -
label | Record of conformity - ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Temporary Works Designer
label | Proof Engineer
label | SE/PE/SPE
label | - - - - - - - - -
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | Frequency - Each element (where 2m or less)
label | - - - - - - - - -
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
label | Attach: Attachment C
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.614.08
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | Visual
label | Measure
label | - - - - - - - - -
label | Record of conformity - ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | PE/SPE
label | - - - - - - - - -
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.4 - Reinforcement Placement
label | Frequency - Each Structure
label | - - - - - - - - -
label | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | Projecting reinforcement is the correct length and location.
label | Splice lengths achieve the minimum length and are in contact for this length.
label | The reinforcement surface condition is free from dirt, debris and damage.
label | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec 611.06
label | 611.09
label | 611.1
label | 611.11
label | 611.12
label | - - - - - - - - -
label | Inspection / Test Method - Measure
label | Visual
label | - - - - - - - - -
label | Record of conformity - This ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Foreman
label | SE/PE/SPE
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 5.5 - Pre-pour Survey
label | Frequency - Prior to concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | Erected formwork within the tolerance as Cl.610.36.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.47
label | Table.610.471
label | Table.610.472
label | Table.610.473
label | Table.610.474
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed/
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Site Engineer/ Surveyor/Foreman
label | - - - - - - - - -
date | Date Completed:
checkpoint-group | 6 - Construction Activities - Concrete Pour
checkpoint-status | 6.1 - Construction Joint Preparation
label | Frequency - Each concrete pour, prior placing concrete (As required)
label | - - - - - - - - -
label | Acceptance Criteria - Construction joint preparation in accordance with CL.610.20
label | Existing concrete to be roughened by removing all laitance and sufficient mortar to expose the coarse aggregate to a depth of 3mm.
label | All surfaces should be cleaned, moistened with water with any excess removed immediately prior to placing concrete.
label | Joints shall be at the locations specified on the drawings
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.20
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.2 - Cast-in Items
label | Frequency - Where applicable, each element
label | - - - - - - - - -
label | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | ii. Running dimensions of a group of the above = ±6mm
label | iii. Ducts and conduit location = ±12mm
label | iv. Diameter of ducts and conduits = ±3mm
label | - - - - - - - - -
label | Reference Documents - VicRoads spec.
label | Cl.610.47 (a)
label | AS3180.1 Table 3.3.6.2
label | - - - - - - - - -
label | Inspection / Test Method - Site inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer/ Foreman
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.3 - Pre-pour Inspection
label | Frequency - Each element
label | - - - - - - - - -
label | Acceptance Criteria - Evidence that the forms, reinforcement and cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority.
label | All foreign material has been completely removed from the forms.
label | - - - - - - - - -
label | Reference Documents - IFC Drawings VicRoads Spec. 610.18 (a) (ii) & (iii)
label | - - - - - - - - -
label | Inspection / Test Method - Measure, Visual
label | - - - - - - - - -
label | Record of conformity - ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Superintendent
label | - - - - - - - - -
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 6.4 - Weather Conditions & Evaporation Limits
label | Frequency - Prior to concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Unless otherwise approved by the superintendent, the following conditions must be satisfied when placing concrete:
label | a) The temperature of concrete, measured immediately prior to placing, shall not be less than 10⁰ C or greater than 32⁰ C
label | b) Concrete shall not be placed if the air temperature is greater than 35⁰ C or less than 5⁰ C.
label | c) Concrete shall not be placed during rain or when rain appears imminent. Freshly placed concrete shall be protected from the rain
label | d) Rate of evaporation < 0.50 kg/m2/hr. If not, additional controls initiated as per 610.17. Refer to concrete pour record
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. CI.610.17
label | - - - - - - - - -
label | Inspection / Test Method - Visual Inspection
label | Concrete Pour Record
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | Concrete Pour Record
label | Concrete Dockets
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer/ Foreman
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.5 - Concrete Testing - Sampling Frequency
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 0m³ to 10m³ = 1 sample
label | 10m³ to 25m³ = 2 samples
label | 25m³ to 50m³ = 3 samples
label | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | For each additional 50m³ and additional sample shall be taken.
label | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.16 (b)
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | Concrete Pour Record
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.6 - Concrete Testing - Slump
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Slump testing tolerances =
label | <60mm = ±10mm
label | ≥60mm to ≤80mm = ±15mm
label | >80mm to ≤110mm = ±20mm
label | >110mm to ≤150mm = ±30mm
label | >150mm = ±40mm
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.16 (c)
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.7 - Concrete Testing - Spread, Passability & Viscosity
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Spread range = 550mm to 750mm
label | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | Passability = ≤10mm (aggregate height differential)
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.13 (b)
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.8 - Concrete Testing - Compressive Strength Cylinders
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - Site Sampling and Testing Procedure
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.9 - Supply & Discharge Rates
label | Frequency - Prior to concrete pour (each load)
label | - - - - - - - - -
label | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | No water is to be added once discharge commences.
label | Maximum time between batching trucks is 25 minutes.
label | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | Concrete is not dropped freely from a height exceeding 2m.
label | Concrete is not moved horizontally by use of vibrators.
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.13 (a) & (e )
label | - - - - - - - - -
label | Inspection / Test Method - Visual Inspection
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer/ Foreman
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 6.10 - Surface Finishes
label | Frequency - Each element
label | - - - - - - - - -
label | Acceptance Criteria - Surface finish as per IFC drawings.
label | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.31
label | Cl.610.20
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-group | 7 - Post-pour Details and Inspection
checkpoint-status | 7.1 - Thermal Differential Monitoring
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | Only applicable if the element has:
label | i. the smallest sectional dimension exceeding 500mm
label | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | Attach: Thermal Monitoring Report
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.22
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Temperature data acquired and proposed control measures to reduce differential temperature submitted to Superintendent for review (if applicable)
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | Subcontractor
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 7.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Where IFC drawings do not nominate minimum strength development for removal of formwork, refer to Table 610.251.
label | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.25 (b)
label | Table 610.251
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 7.3 - Surface Inspection - Cracks
label | Frequency - Each element
label | - - - - - - - - -
label | Acceptance Criteria - Repair procedure submitted to the Superintendent. Repair undertaken in accordance with VicRoads Section 687.
label | Cracks investigated and if greater than specified in the table 610.241, an NCR raised. Notwithstanding the requirements of this clause the acceptable crack width at the concrete surface of precast pre-stressed concrete elements shall not exceed 0.1 mm.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.24 (a)
label | Table 610.241
label | Section 687
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Superintendent approval (if applicable)
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 7.4 - Early Age Compressive Strength Test Results - Placement of Fill Against Concrete
label | Frequency - Each Pour
label | - - - - - - - - -
label | Acceptance Criteria - No fill is to be placed against concrete within 14 days of casting in accordance with the requirements of Clause 204.11 of Section 204. Proposed placement prior to 14 days from casting shall comply with the early application of loading requirements of Clause 610.16(l) or maturity testing requirements of Clause 610.16(m).
label | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | CI.610.35 Cl.204.11(b)
label | Table 204.111
label | Cl.610.16(m)
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Holdpoint released
label | This ITP signed
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Site Engineer/ Superintendent
label | - - - - - - - - -
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 7.5 - Compressive Strength Result
label | Frequency - Each Specimen
label | - - - - - - - - -
label | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Attach: Compressive Strength Test Results
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | CI.610.16 (g)
label | Table 610.051
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | - - - - - - - - -
label | Record of conformity - Concrete Test Result
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 7.6 - Post Pour Concrete Cover
label | Frequency - Every 25m2 or part thereof.
label | - - - - - - - - -
label | Acceptance Criteria - Concrete cover meter check one 3m² test area for every 25m² exterior surface area.
label | Minimum 10 no. measurements recorded in each area.
label | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | Attach: cover meter Check Record
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.34
label | IFC drawings
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | 7.7 - Prepare As Built Drawings
label | Frequency - Prior to lot closure
label | - - - - - - - - -
label | Acceptance Criteria - As-built survey completed and drawings (IFC Mark up Drawings) prepared for the lot and copy of the drawings kept in the files
label | The tolerances listed in Tables 610.471, 610.472, 610.473 and 610.474 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
label | - - - - - - - - -
label | Reference Documents - IFC Project Drawings
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - As-built survey and drawings
label | This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
date | Date Completed:
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
date | Work Completed On