## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-006 - Concrete Pavements and Crossovers REV1 | itp |  |  |  | Yes | CC0394 - ITP-006 - Concrete Pavements and Crossovers REV1 | 40d3e093-effd-43df-ae2f-6f443fdd9aeb
section | Lot Conformance.
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | AUTHORITY HOLDPOINT
section | 1.0 Planning
checkpoint | 1.1 - Determine Lot Size
label | Acceptance criteria - Day’s Productivity
button | Acceptance | Yes,No,N/A
label | • See Work Lot Map
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Work lot map attached
checkpoint | 1.2 - Survey Set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the work area been set out for line and level?
label | • Preceding pavement layer has been picked up and confirmed within tolerance.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
checkpoint | 1.3 - Confirm Pavement Type
label | Ref docs - IFC Drawings
label | Acceptance criteria - Confirm pavement type/s within the work lot, and the concrete pavement depth associated.
label | Acceptance
text | Pavement Type:
text | Pavement Depth:
label | Key - H
label | Resp - SE
checkpoint | 1.4 - Confirm Concrete Strength & Colour Required
label | Ref docs - IFC Drawings
label | Acceptance criteria - Confirm correct concrete mix in use prior to commencement of pour.
label | Acceptance
text | Concrete mix:
text | Strength:
text | Slump:
text | Aggregate size:
label | Key - H
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Docket attached
boolean | Pre-pour inspection checklist
section | 2.0 Construction
checkpoint | 2.1 - Preparation of Subgrade and Base Pavement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Subgrade trimmed and compacted prior to prior to placement of successive pavement layers.
label | • Subbase placed and compacted to the correct line and level. Confirm compaction and tolerance prior to commencement.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | QA for preceding pavement layers complete
checkpoint | 2.2 - Install Reinforcement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Reinforcement installed as per IFC Drawings, City of Casey Standard Drawings and Specifications.
label | • Symal to confirm prior to commencement of pour.
button | Acceptance | Yes,No,N/A
label | RJE Key - H
label | Resp - Client
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Pre-pour inspection checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Concrete Pour
label | Ref docs - IFC Drawings
label | Acceptance criteria - Confirm via delivery dockets that concrete is in accordance with that listed above.
label | • Contractor shall place concrete to avoid segregation. The placing of concrete in a section shall be carried on continuously until that section is completed.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Docket attached
checkpoint | 2.4 - Jointing
label | Ref docs - IFC Drawings, City of Casey Specification
label | Acceptance criteria - All jointing/saw cutting completed in accordance with IFC Drawings and relevant Specification.
label | • Joint placement to be confirmed on site.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint | 2.5 - Concrete Testing
label | Ref docs - IFC Drawings
label | Acceptance criteria - 1 sample to be taken per 50m3 placed.
label | • 3 cylinders to be taken per sample.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
section | 3.0 Conformance Check
checkpoint | 3.1 - Finish
label | Ref docs - IFC Drawings
label | Acceptance criteria - Confirm finish is in accordance with IFC Drawing and Casey City Council specification
label | Acceptance
text | Finish Type:
label | Key - S
label | Resp - SE
checkpoint | 3.2 - Visual Inspection
label | Ref docs - IFC Drawings
label | Acceptance criteria - Do not cover or conceal work until it has been inspected by Symal.
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp - SE
checkpoint | 3.3 - As-Builts
label | Ref docs - IFC Drawings
label | Acceptance criteria - As-built survey of work lot attached.
label | • All points within tolerance.
button | Acceptance | Yes,No,N/A
label | RJE Key - H
label | Resp - Client
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | As-Built Attached
holdpoint | AUTHORITY HOLDPOINT