## EW-ITP-104
Earthworks Materials Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0104 - Rev 2
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Earthworks Materials
4.01.01 | Principal-supplied Structural Fill | The Principal shall be responsible for strength, weathering, crushing, abrasion and any laboratory testing to confirm that the Principal-supplied aggregate meets the design or for quality control. No other Structural fill is to be used unless approved by the Engineer. | PS 15.4.2 | Principal Supplied Source and Production Properties Tests | Prior to use | HP | ENG
4.01.02 | Structural Fill Density Tests | The Contractor shall carrying out laboratory tests by an IANZ accredited Laboratory to determine the maximum laboratory dry density at the optimum water content (OWC) of the fill aggregate used and the Solid Density. The tests shall be undertaken on material that is representative of that used in construction and a grading for the material tested shall be supplied with the results | PS 15.5.4 | IANZ MDD, OMC, SD, PSD | Prior to use | HP | ENG
4.01.03 | Principal-supplied Structural Fill - MSE | The Principal shall provide a separate stockpile for material to be used as fill for the MSE structure and the stockpile shall be located within 5km of the site. The Principal shall undertake any tests required to confirm the properties of the Principal-supplied Structural Fill for the MSE structure. The Contractor may assume such material is deemed to comply. | PS 15.4.2 | Principal Supplied Source and Production Properties Tests | Prior to use | HP | ENG
4.01.04 | Structural Fill - Compaction Characteristics | The Contractor is required to carry out compaction testing by Test 4.2.1, NZS 4402:1986 to determine the compaction characteristics for each type and mix of material used in filling. | PS 15.4.2 | Test Report | Prior to use for each Structural Fill to be used | HP | ENG
4.01.05 | Site Won and Contractor Supplied Structural Fill - Not Expected to be Used | Any site won or Imported material considered as Structural Fill shall be verified by the Contractor and approved by the Engineer prior to use within the works | PS 15.4.2 | IANZ Test Reports | Prior to use | HP | ENG
4.01.06 | Type A Bulk Fill - Grading | Type A Bulk Fill (AP100 All IN) Ganular soils not meeting the fill type requirements of this specification may be used for this purpose with a Maximum particle size <100mm | C262 | PSD / Visual Screening | Prior to use | I | PE
4.01.07 | Type A Bulk Fill - Density Tests | The Contractor shall carrying out laboratory tests by an IANZ accredited Laboratory to determine the maximum laboratory dry density at the optimum water content (OWC) of the fill aggregate used. | PS 15.5.4 | IANZ MDD & OMC | Prior to use | HP | ENG
4.01.08 | Type B Bulk Fill - Grading | Non granular and granular soils not meeting the fill type requirements of this specification may be used for this purpose with a Maximum particle size <300mm | PS 15.4.3 | PSD / Visual Screening | Prior to use | I | PE
4.01.09 | Talus Fill | Where Talus fill material contains rocks greater than 300mm diameter then these shall be removed from the talus materials, stockpiled and reclassified as rock fill. | PS 15.4.5 | PSD / Visual Screening | Prior to use | I | PE
4.02 | Rip Rap Materials
4.02.01 | Principal-supplied Rip Rap | Rock Fill is required for use in the scour blanket as rip rap construction. This shall be predominantly be supplied by the Principal (see 24.1). | PS 15.4.4 | Principal Supplied Source and Production Properties Tests | Prior to use | HP | ENG
4.02.02 | Site Won Rip Rap - Size | Rock Fill for scour protection is specified in terms of D50 (millimetres). This represents the rock size that 50% of the material must exceed. The dimension of any rock shall not exceed its narrowest dimension by more than a factor of three. | PS 15.4.4 | Hand Grading | Prior to use | I | PE
4.02.03 | Site Won Rip Rap - Density | Shall have a uniform density with an average specific gravity of no less than 2.65g/cm 3 . | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.02.04 | Site Won Rip Rap - Soundness of Rock | The rocks shall be sound and durable, being resistant to abrasion and free from cracks, laminations, seams, weak cleavages or other defects that would tend to increase unduly the likelihood of destruction of individual rocks by normal handling or weathering. | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.02.05 | Site Won Rip Rap - Broken faces | The rock shall be angular in form with broken faces over at least 2/3 of its surface. | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.02.06 | Site Won Rip Rap - Weathering Grade | The rock is to have minimal weathering, being rock of Grade I and II of the weathering term for the field description of rock provided in the 2005 “Guidelines for the field classification and description of soil and rock for engineering purposes”, NZ Geotechnical Society. | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.03 | Geogrid / geofabric requirements Materials
4.03.01 | Geogrid and Geofabric | Where required by the design drawings geogrids or geofabrics shall be sourced from a reputable supplier and laid, inspected and verified in accordance with the manufacturer’s specifications. | PS 15.4.7 | Datasheet | Prior to use | R | PE