## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2676-DOW-ITP-CV-0104-Earthworks Materials | itp |  |  |  | Yes | DS2676-DOW-ITP-CV-0104-Earthworks Materials Rev 0 | c224f9ec-2c32-46e7-b772-1b9d1e03cc8c
section | 4.01 Earthworks Materials
checkpoint | 4.01.01 Principal-supplied Structural Fill
label | Acceptance / Conformance Criteria - The Principal shall be responsible for strength, weathering, crushing, abrasion and any laboratory testing to confirm that the Principal-supplied aggregate meets the design or for quality control. No other Structural fill is to be used unless approved by the Engineer.
label | Standard / Specification - PS 15.4.2
label | Verifying Document - Principal Supplied Source and Production Properties Tests
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.02 Structural Fill Density Tests
label | Acceptance / Conformance Criteria - The Contractor shall carrying out laboratory tests by an IANZ accredited Laboratory to determine the maximum laboratory dry density at the optimum water content (OWC) of the fill aggregate used and the Solid Density. The tests shall be undertaken on material that is representative of that used in construction and a grading for the material tested shall be supplied with the results
label | Standard / Specification - PS 15.5.4
label | Verifying Document - IANZ MDD, OMC, SD, PSD
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.03 Principal-supplied Structural Fill - MSE
label | Acceptance / Conformance Criteria - The Principal shall provide a separate stockpile for material to be used as fill for the MSE structure and the stockpile shall be located within 5km of the site. The Principal shall undertake any tests required to confirm the properties of the Principal-supplied Structural Fill for the MSE structure. The Contractor may assume such material is deemed to comply.
label | Standard / Specification - PS 15.4.2
label | Verifying Document - Principal Supplied Source and Production Properties Tests
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.04 Structural Fill - Compaction Characteristics
label | Acceptance / Conformance Criteria - The Contractor is required to carry out compaction testing by Test 4.2.1, NZS 4402:1986 to determine the compaction characteristics for each type and mix of material used in filling.
label | Standard / Specification - PS 15.4.2
label | Verifying Document - Test Report
label | Frequency - Prior to use for each Structural Fill to be used
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.05 Site Won and Contractor Supplied Structural Fill - Not Expected to be Used
label | Acceptance / Conformance Criteria - Any site won or Imported material considered as Structural Fill shall be verified by the Contractor and approved by the Engineer prior to use within the works
label | Standard / Specification - PS 15.4.2
label | Verifying Document - IANZ Test Reports
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.06 Type A Bulk Fill - Grading
label | Acceptance / Conformance Criteria - Type A Bulk Fill (AP100 All IN) Ganular soils not meeting the fill type requirements of this specification may be used for this purpose with a Maximum particle size <100mm
label | Standard / Specification - C262
label | Verifying Document - PSD / Visual Screening
label | Frequency - Prior to use
label | Activity - I
label | By - PE
checkpoint | 4.01.07 Type A Bulk Fill - Density Tests
label | Acceptance / Conformance Criteria - The Contractor shall carrying out laboratory tests by an IANZ accredited Laboratory to determine the maximum laboratory dry density at the optimum water content (OWC) of the fill aggregate used.
label | Standard / Specification - PS 15.5.4
label | Verifying Document - IANZ MDD & OMC
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.08 Type B Bulk Fill - Grading
label | Acceptance / Conformance Criteria - Non granular and granular soils not meeting the fill type requirements of this specification may be used for this purpose with a Maximum particle size <300mm
label | Standard / Specification - PS 15.4.3
label | Verifying Document - PSD / Visual Screening
label | Frequency - Prior to use
label | Activity - I
label | By - PE
checkpoint | 4.01.09 Talus Fill
label | Acceptance / Conformance Criteria - Where Talus fill material contains rocks greater than 300mm diameter then these shall be removed from the talus materials, stockpiled and reclassified as rock fill.
label | Standard / Specification - PS 15.4.5
label | Verifying Document - PSD / Visual Screening
label | Frequency - Prior to use
label | Activity - I
label | By - PE
section | 4.02 Rip Rap Materials
checkpoint | 4.02.01 Principal-supplied Rip Rap
label | Acceptance / Conformance Criteria - Rock Fill is required for use in the scour blanket as rip rap construction. This shall be predominantly be supplied by the Principal (see 24.1).
label | Standard / Specification - PS 15.4.4
label | Verifying Document - Principal Supplied Source and Production Properties Tests
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02.02 Site Won Rip Rap - Size
label | Acceptance / Conformance Criteria - Rock Fill for scour protection is specified in terms of D50 (millimetres). This represents the rock size that 50% of the material must exceed. The dimension of any rock shall not exceed its narrowest dimension by more than a factor of three.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - Hand Grading
label | Frequency - Prior to use
label | Activity - I
label | By - PE
checkpoint | 4.02.03 Site Won Rip Rap - Density
label | Acceptance / Conformance Criteria - Shall have a uniform density with an average specific gravity of no less than 2.65g/cm 3 .
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.02.04 Site Won Rip Rap - Soundness of Rock
label | Acceptance / Conformance Criteria - The rocks shall be sound and durable, being resistant to abrasion and free from cracks, laminations, seams, weak cleavages or other defects that would tend to increase unduly the likelihood of destruction of individual rocks by normal handling or weathering.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.02.05 Site Won Rip Rap - Broken faces
label | Acceptance / Conformance Criteria - The rock shall be angular in form with broken faces over at least 2/3 of its surface.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.02.06 Site Won Rip Rap - Weathering Grade
label | Acceptance / Conformance Criteria - The rock is to have minimal weathering, being rock of Grade I and II of the weathering term for the field description of rock provided in the 2005 “Guidelines for the field classification and description of soil and rock for engineering purposes”, NZ Geotechnical Society.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
section | 4.03 Geogrid / geofabric requirements Materials
checkpoint | 4.03.01 Geogrid and Geofabric
label | Acceptance / Conformance Criteria - Where required by the design drawings geogrids or geofabrics shall be sourced from a reputable supplier and laid, inspected and verified in accordance with the manufacturer’s specifications.
label | Standard / Specification - PS 15.4.7
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE