## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Greensborough Stage 1 - ITP-008 - Stormwater Drainage - Greensborough Stg 1
| Scope |  |  | Greensborough Stage 1 | ITP - 008 Stormwater Drainage - Greensborough Stg 1
Rows
|  | Greensborough Stage 1 - ITP-008 Stormwater Drainage - Greensborough Stg 1 | dynamic | ITP - 008 Stormwater Drainage - Greensborough Stg 1 | Greensborough Stage 1
Columns
|  | Preliminary Works |  | Preliminary Works
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | 1.3 Precast Materials acceptance |  | 1.3 Precast Materials acceptance
|  | 1.4 Precast Pipe & Culvert Compliance |  | 1.4 Precast Pipe & Culvert Compliance
|  | 1.5 Precast Drainage Pit Compliance |  | 1.5 Precast Drainage Pit Compliance
|  | 1.6 Bedding material classification |  | 1.6 Bedding material classification
|  | 1.7 Backfill material Classification |  | 1.7 Backfill material Classification
|  | 1.8 Mortar material classification |  | 1.8 Mortar material classification
|  | Construction Works |  | Construction Works
|  | 2.1 Excavation Permit |  | 2.1 Excavation Permit
|  | 2.2 Set out drainage |  | 2.2 Set out drainage
|  | 2.3 Excacation (pipes) |  | 2.3 Excacation (pipes)
|  | 2.4 Excacation (pits) |  | 2.4 Excacation (pits)
|  | 2.5 Compact base of trench |  | 2.5 Compact base of trench
|  | 2.6 Place bedding material & compact |  | 2.6 Place bedding material & compact
|  | 2.7 Place pipes & precast pits |  | 2.7 Place pipes & precast pits
|  | 2.8 Jointing pipe sections |  | 2.8 Jointing pipe sections
|  | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits |  | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
|  | 2.10 Survey of laid pipe or pit |  | 2.10 Survey of laid pipe or pit
|  | 2.11 Haunching & compaction of bedding material |  | 2.11 Haunching & compaction of bedding material
|  | 2.12 Place & compact backfill material over pipes |  | 2.12 Place & compact backfill material over pipes
|  | 2.13 Place & compact backfill material around pits |  | 2.13 Place & compact backfill material around pits
|  | 2.14 Backfilling with cement stabilised sand |  | 2.14 Backfilling with cement stabilised sand
|  | 2.15 Install step irons |  | 2.15 Install step irons
|  | 2.16 Pit base shaped with concrete to match pipe invert |  | 2.16 Pit base shaped with concrete to match pipe invert
|  | 2.17 Place pit covers |  | 2.17 Place pit covers
|  | 2.18 Repairs to damaged pipes and box culverts |  | 2.18 Repairs to damaged pipes and box culverts
|  | Testing & Completion |  | Testing & Completion
|  | 3.1 Compaction and moisture content of backfill & bedding material |  | 3.1 Compaction and moisture content of backfill & bedding material
|  | 3.2 CCTV inspection |  | 3.2 CCTV inspection
|  | 3.3 Cleaning of pipes |  | 3.3 Cleaning of pipes
|  | Final Inspection |  | Final Inspection
Greensborough Stage 1 - ITP-012 - Hot Mix Asphalt - Greensborough
| Scope |  |  | Greensborough Stage 1 | ITP-012 - Hot Mix Asphalt - Greensborough
Rows
|  | Greensborough Stage 1 - ITP-012 - Hot Mix Asphalt - Greensborough | dynamic | ITP-012 - Hot Mix Asphalt - Greensborough | Greensborough Stage 1
Columns
|  | Construction Works |  | Construction Works
|  | 1.1 Submission of Mix Design |  | 1.1 Submission of Mix Design
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | 1.3 Site Inspection and Base Condition |  | 1.3 Site Inspection and Base Condition
|  | 1.4 Ambient Conditions for Placing |  | 1.4 Ambient Conditions for Placing
|  | 1.5 Planning of Joints |  | 1.5 Planning of Joints
|  | 1.6 Longitudinal Joints with existing Pavement |  | 1.6 Longitudinal Joints with existing Pavement
|  | 1.7 Lot Size |  | 1.7 Lot Size
|  | Asphalt Placement works |  | Asphalt Placement works
|  | 2.1 Tack Coat |  | 2.1 Tack Coat
|  | 2.2 Commencement of Placing |  | 2.2 Commencement of Placing
|  | 2.3 Mix Design Confirmation |  | 2.3 Mix Design Confirmation
|  | 2.4 Delivery of Mix |  | 2.4 Delivery of Mix
|  | 2.5 Traceability |  | 2.5 Traceability
|  | 2.6 Layer Thickness and Level Control |  | 2.6 Layer Thickness and Level Control
|  | 2.7 Paver Stoppages |  | 2.7 Paver Stoppages
|  | 2.8 Surface Finish of Wearing Course |  | 2.8 Surface Finish of Wearing Course
|  | 2.9 Height Relative Kerb and Channel |  | 2.9 Height Relative Kerb and Channel
|  | 2.10 Alignment of layers not placed against concrete edge |  | 2.10 Alignment of layers not placed against concrete edge
|  | 2.11 Width of layers not placed against concrete edge |  | 2.11 Width of layers not placed against concrete edge
|  | Testing |  | Testing
|  | 3.1 Compaction |  | 3.1 Compaction
|  | 3.2 Level Conformance |  | 3.2 Level Conformance
|  | Final Inspection |  | Final Inspection
Greensborough Stage 1 - ITP-015 - Kerb and Channel - Greensborough
| Scope |  |  | Greensborough Stage 1 | ITP-015 - Kerb and Channel - Greensborough
Rows
|  | Greensborough Stage 1 - ITP-015 - Kerb and Channel - Greensborough | dynamic | ITP-015 - Kerb and Channel - Greensborough | Greensborough Stage 1
Columns
|  | Preliminary Works |  | Preliminary Works
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | Construction Works |  | Construction Works
|  | 2.1 Setting Out |  | 2.1 Setting Out
|  | 2.2 Temporary Drainage Provisions |  | 2.2 Temporary Drainage Provisions
|  | 2.3 Bedding |  | 2.3 Bedding
|  | 2.4 Pre-concrete check |  | 2.4 Pre-concrete check
|  | 2.5 Concrete Placement |  | 2.5 Concrete Placement
|  | 2.6 Finish Surfaces |  | 2.6 Finish Surfaces
|  | 2.7 Tolerances |  | 2.7 Tolerances
|  | 2.8 Joints |  | 2.8 Joints
|  | 2.9 Backfilling |  | 2.9 Backfilling
|  | Completion |  | Completion
|  | 3.1 Survey data captured for as-built purposes |  | 3.1 Survey data captured for as-built purposes
|  | Final Inspection |  | Final Inspection
Greensborough Stage 1 - ITP-025 - Structural Concrete Construction - Greensborough
| Scope |  |  | Greensborough Stage 1 | ITP-025 - Structural Concrete Construction - Greensborough
Rows
|  | Greensborough Stage 1 - ITP-025 - Structural Concrete Construction - Greensborough | dynamic | ITP-025 - Structural Concrete Construction - Greensborough | Greensborough Stage 1
Columns
|  | Design and Submissions |  | Design and Submissions
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | 1.3 Approval of mix design |  | 1.3 Approval of mix design
|  | 1.4 Reinforcement schedule |  | 1.4 Reinforcement schedule
|  | Construction/Erection of Formwork |  | Construction/Erection of Formwork
|  | 2.1 Excavation |  | 2.1 Excavation
|  | 2.2 Construction Methodology |  | 2.2 Construction Methodology
|  | Pre-Pour Planning and Inspection |  | Pre-Pour Planning and Inspection
|  | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete |  | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
|  | 3.2 Formwork levels and position |  | 3.2 Formwork levels and position
|  | 3.3 Location of splices |  | 3.3 Location of splices
|  | 3.4 Cleaning formwork |  | 3.4 Cleaning formwork
|  | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments |  | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
|  | 3.6 Reinforcement assembly of piles |  | 3.6 Reinforcement assembly of piles
|  | 3.7 Monitoring weather |  | 3.7 Monitoring weather
|  | Placing and Finishing Concrete |  | Placing and Finishing Concrete
|  | 4.1 Carry out sampling of concrete |  | 4.1 Carry out sampling of concrete
|  | 4.2 Discharge time |  | 4.2 Discharge time
|  | 4.3 Methodology of placement (structural) |  | 4.3 Methodology of placement (structural)
|  | Post-Pour Details and Inspection |  | Post-Pour Details and Inspection
|  | 5.1 Curing |  | 5.1 Curing
|  | 5.2 Formwork removal |  | 5.2 Formwork removal
|  | 5.3 Positional tolerance and dimensions of concrete members and piles |  | 5.3 Positional tolerance and dimensions of concrete members and piles
|  | 5.4 Concrete Sampling and Testing |  | 5.4 Concrete Sampling and Testing
|  | 5.5 As Built Drawings |  | 5.5 As Built Drawings
|  | Final Inspection |  | Final Inspection
Greensborough Stage 2 - ITP-008 - Stormwater Drainage - Greensborough
| Scope |  |  | Greensborough Stage 2 | ITP-008 - Stormwater Drainage - Greensborough
Rows
|  | Greensborough Stage 2 - ITP-008 - Stormwater Drainage - Greensborough | dynamic | ITP-008 - Stormwater Drainage - Greensborough | Greensborough Stage 2
Columns
|  | Preliminary Works |  | Preliminary Works
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | 1.3 Precast Materials acceptance |  | 1.3 Precast Materials acceptance
|  | 1.4 Precast Pipe & Culvert Compliance |  | 1.4 Precast Pipe & Culvert Compliance
|  | 1.5 Precast Drainage Pit Compliance |  | 1.5 Precast Drainage Pit Compliance
|  | 1.6 Bedding material classification |  | 1.6 Bedding material classification
|  | 1.7 Backfill material Classification |  | 1.7 Backfill material Classification
|  | 1.8 Mortar material classification |  | 1.8 Mortar material classification
|  | Construction Works |  | Construction Works
|  | 2.1 Excavation Permit |  | 2.1 Excavation Permit
|  | 2.2 Set out drainage |  | 2.2 Set out drainage
|  | 2.3 Excacation (pipes) |  | 2.3 Excacation (pipes)
|  | 2.4 Excacation (pits) |  | 2.4 Excacation (pits)
|  | 2.5 Compact base of trench |  | 2.5 Compact base of trench
|  | 2.6 Place bedding material & compact |  | 2.6 Place bedding material & compact
|  | 2.7 Place pipes & precast pits |  | 2.7 Place pipes & precast pits
|  | 2.8 Jointing pipe sections |  | 2.8 Jointing pipe sections
|  | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits |  | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
|  | 2.10 Survey of laid pipe or pit |  | 2.10 Survey of laid pipe or pit
|  | 2.11 Haunching & compaction of bedding material |  | 2.11 Haunching & compaction of bedding material
|  | 2.12 Place & compact backfill material over pipes |  | 2.12 Place & compact backfill material over pipes
|  | 2.13 Place & compact backfill material around pits |  | 2.13 Place & compact backfill material around pits
|  | 2.14 Backfilling with cement stabilised sand |  | 2.14 Backfilling with cement stabilised sand
|  | 2.15 Install step irons |  | 2.15 Install step irons
|  | 2.16 Pit base shaped with concrete to match pipe invert |  | 2.16 Pit base shaped with concrete to match pipe invert
|  | 2.17 Place pit covers |  | 2.17 Place pit covers
|  | 2.18 Repairs to damaged pipes and box culverts |  | 2.18 Repairs to damaged pipes and box culverts
|  | Testing & Completion |  | Testing & Completion
|  | 3.1 Compaction and moisture content of backfill & bedding material |  | 3.1 Compaction and moisture content of backfill & bedding material
|  | 3.2 CCTV inspection |  | 3.2 CCTV inspection
|  | 3.3 Cleaning of pipes |  | 3.3 Cleaning of pipes
|  | Final Inspection |  | Final Inspection
Greensborough Stage 2 - ITP-012 - Hot Mix Asphalt
| Scope |  |  | Greensborough Stage 2 | ITP - 012 - Hot Mix Asphalt
Rows
|  | Greensborough Stage 2 - ITP-012 - Hot Mix Asphalt | dynamic | ITP - 012 - Hot Mix Asphalt | Greensborough Stage 2
Columns
|  | Construction Works |  | Construction Works
|  | 1.1 Submission of Mix Design |  | 1.1 Submission of Mix Design
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | 1.3 Site Inspection and Base Condition |  | 1.3 Site Inspection and Base Condition
|  | 1.4 Ambient Conditions for Placing |  | 1.4 Ambient Conditions for Placing
|  | 1.5 Planning of Joints |  | 1.5 Planning of Joints
|  | 1.6 Longitudinal Joints with existing Pavement |  | 1.6 Longitudinal Joints with existing Pavement
|  | 1.7 Lot Size |  | 1.7 Lot Size
|  | Asphalt Placement works |  | Asphalt Placement works
|  | 2.1 Tack Coat |  | 2.1 Tack Coat
|  | 2.2 Commencement of Placing |  | 2.2 Commencement of Placing
|  | 2.3 Mix Design Confirmation |  | 2.3 Mix Design Confirmation
|  | 2.4 Delivery of Mix |  | 2.4 Delivery of Mix
|  | 2.5 Traceability |  | 2.5 Traceability
|  | 2.6 Layer Thickness and Level Control |  | 2.6 Layer Thickness and Level Control
|  | 2.7 Paver Stoppages |  | 2.7 Paver Stoppages
|  | 2.8 Surface Finish of Wearing Course |  | 2.8 Surface Finish of Wearing Course
|  | 2.9 Height Relative Kerb and Channel |  | 2.9 Height Relative Kerb and Channel
|  | 2.10 Alignment of layers not placed against concrete edge |  | 2.10 Alignment of layers not placed against concrete edge
|  | 2.11 Width of layers not placed against concrete edge |  | 2.11 Width of layers not placed against concrete edge
|  | Testing |  | Testing
|  | 3.1 Compaction |  | 3.1 Compaction
|  | 3.2 Level Conformance |  | 3.2 Level Conformance
|  | Final Inspection |  | Final Inspection
Greensborough Stage 2 - ITP-013 - Concrete Paving
| Scope |  |  | Greensborough Stage 2 | ITP-013 - Concrete Paving
Rows
|  | Greensborough Stage 2 - ITP-013 - Concrete Paving | dynamic | ITP-013 - Concrete Paving | Greensborough Stage 2
Columns
|  | Preliminary Works |  | Preliminary Works
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | 1.3 Submission & Approval of Concrete Mix Design |  | 1.3 Submission & Approval of Concrete Mix Design
|  | Construction Works |  | Construction Works
|  | 2.1 Setting Out |  | 2.1 Setting Out
|  | 2.2 Excavation Permit |  | 2.2 Excavation Permit
|  | 2.3 Excavation |  | 2.3 Excavation
|  | 2.4 Bedding |  | 2.4 Bedding
|  | 2.5 Formwork |  | 2.5 Formwork
|  | 2.6 Reinforcement |  | 2.6 Reinforcement
|  | 2.7 Concrete Placement |  | 2.7 Concrete Placement
|  | 2.8 Surface Finish |  | 2.8 Surface Finish
|  | 2.9 Pram Crossings |  | 2.9 Pram Crossings
|  | 2.10 Joints |  | 2.10 Joints
|  | 2.11 Protection of concrete |  | 2.11 Protection of concrete
|  | 2.12 Curing |  | 2.12 Curing
|  | 2.13 Ambient Weather |  | 2.13 Ambient Weather
|  | Completion |  | Completion
|  | 3.1 Carry out sampling of concrete - strength and consistency |  | 3.1 Carry out sampling of concrete - strength and consistency
|  | 3.2 Tolerances |  | 3.2 Tolerances
|  | 3.3 Backfilling |  | 3.3 Backfilling
|  | Final Inspection |  | Final Inspection
Greensborough Stage 2 - ITP-015 - Kerb and Channel
| Scope |  |  | Greensborough Stage 2 | ITP - 015 - Kerb and Channel
Rows
|  | Greensborough Stage 2 - ITP-015 - Kerb and Channel | dynamic | ITP - 015 - Kerb and Channel | Greensborough Stage 2
Columns
|  | Preliminary Works |  | Preliminary Works
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | Construction Works |  | Construction Works
|  | 2.1 Setting Out |  | 2.1 Setting Out
|  | 2.2 Temporary Drainage Provisions |  | 2.2 Temporary Drainage Provisions
|  | 2.3 Bedding |  | 2.3 Bedding
|  | 2.4 Pre-concrete check |  | 2.4 Pre-concrete check
|  | 2.5 Concrete Placement |  | 2.5 Concrete Placement
|  | 2.6 Finish Surfaces |  | 2.6 Finish Surfaces
|  | 2.7 Tolerances |  | 2.7 Tolerances
|  | 2.8 Joints |  | 2.8 Joints
|  | 2.9 Backfilling |  | 2.9 Backfilling
|  | Completion |  | Completion
|  | 3.1 Survey data captured for as-built purposes |  | 3.1 Survey data captured for as-built purposes
|  | Final Inspection |  | Final Inspection
Greensborough Stage 2 - ITP-025 - Structural Concrete
| Scope |  |  | Greensborough Stage 2 | ITP - 025 - Structural Concrete
Rows
|  | Greensborough Stage 2 - ITP-025 - Structural Concrete | dynamic | ITP - 025 - Structural Concrete | Greensborough Stage 2
Columns
|  | Design and Submissions |  | Design and Submissions
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls
|  | 1.3 Approval of mix design |  | 1.3 Approval of mix design
|  | 1.4 Reinforcement schedule |  | 1.4 Reinforcement schedule
|  | Construction/Erection of Formwork |  | Construction/Erection of Formwork
|  | 2.1 Excavation |  | 2.1 Excavation
|  | 2.2 Construction Methodology |  | 2.2 Construction Methodology
|  | Pre-Pour Planning and Inspection |  | Pre-Pour Planning and Inspection
|  | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete |  | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
|  | 3.2 Formwork levels and position |  | 3.2 Formwork levels and position
|  | 3.3 Location of splices |  | 3.3 Location of splices
|  | 3.4 Cleaning formwork |  | 3.4 Cleaning formwork
|  | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments |  | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
|  | 3.6 Reinforcement assembly of piles |  | 3.6 Reinforcement assembly of piles
|  | 3.7 Monitoring weather |  | 3.7 Monitoring weather
|  | Placing and Finishing Concrete |  | Placing and Finishing Concrete
|  | 4.1 Carry out sampling of concrete |  | 4.1 Carry out sampling of concrete
|  | 4.2 Discharge time |  | 4.2 Discharge time
|  | 4.3 Methodology of placement (structural) |  | 4.3 Methodology of placement (structural)
|  | Post-Pour Details and Inspection |  | Post-Pour Details and Inspection
|  | 5.1 Curing |  | 5.1 Curing
|  | 5.2 Formwork removal |  | 5.2 Formwork removal
|  | 5.3 Positional tolerance and dimensions of concrete members and piles |  | 5.3 Positional tolerance and dimensions of concrete members and piles
|  | 5.4 Concrete Sampling and Testing |  | 5.4 Concrete Sampling and Testing
|  | 5.5 As Built Drawings |  | 5.5 As Built Drawings
|  | Final Inspection |  | Final Inspection