## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-254-CIV-Hopkins-Unbound Flexible Pavement | itp |  |  |  |  | ITP-254-CIV-Hopkins-Unbound Flexible Pavement Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-254-CIV-Hopkins-Unbound Flexible Pavement
label | ITP Description: Hopkins-Unbound Flexible Pavement
label | Discipline (e.g. CIV/STR/RAIL): 254-CIV
label | Revision Number: 0
label | Revision Date: 24/04/2025
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - Reference Documents: IFC Drawings
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 173 (10/9/2008)
label | 1.3 - Non Dependent
label | Reference - VicRoads Section 304 (13/8/13)
label | 1.4 - Non Dependent
label | Reference - VicRoads Section 801 (19/07/18)
label | 1.5 - Non Dependent
label | Reference - VicRoads Section 812 (13/07/16)
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Crushed Rock Mix Design
label | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
label | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Material conformance as per Table 812.121
label | Category - HP
label | Responsibility - NA
label | Verifying Documents - TeamBinder Material Approval Number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documentation
checkpoint | 3.1 - Subgrade Preparation
label | Reference - 304.04
label | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
textbox | Reference: Subgrade Preparation/Type fill Lot Number:
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - Underlying layer Lot number
date | Date Completed:
checkpoint | 3.2 - Select Scale
label | Reference - Project Requirement Specifications, IFC Drawings
label | Acceptance Criteria - Specify site specific scale:
textbox | Enter: Site Specific Scale (A, B or C)
label | Method - Document Review
label | Frequency - Prior to Commencement, Each lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-out and Lot size
label | Reference - IFC Drawings Section 304.06
label | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
label | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | Method - Survey, Document Review, Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Surveyor, SE
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Crushed Rock Delivery Dockets
label | Reference - 304.04
label | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
label | ○ ATTACH: Delivery Docket(s)
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Attached Docket, Sign ITP
date | Date Completed:
checkpoint | 5.2 - Placement of Material
label | Reference - Section 304.03, Section 304.06, Section 304.08
label | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | ○ At no location shall water pond on the surface of any pavement layer.
label | Method - Visual and Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.3 - Construction - Jointing
label | Reference - Section 304.07
label | Acceptance Criteria - The layout of joints shall conform to the following requirements:
label | (a) material shall be spread in such a manner as to minimize the number of joints;
label | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | Method - Visual and Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.4 - Compaction test (Frequency)
label | Reference - 304 .11 (b)
label | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | — Scales A and B: 6 samples
label | — Scale C: 3 Samples
label | — Pass: Tested
label | — NA: Not Tested
label | Method - Visual
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
label | Reference - 304.11 (c )
label | Acceptance Criteria - SCALE A:
label | — The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
label | Compaction:
label | —Lower Subbase: none
label | —Upper Subbase: 1 in 4
label | —Base: 1 in 2
label | PI:
label | —Upper Subbase and Lower Base: 1 (two samples) in 8
label | —Upper Base: 1 (two samples) in 4
label | SCALE B:
label | —the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | SCALE C:
label | —Post compaction grading and PI testing is not required (CHOOSE NA)
label | Method - Visual
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.6 - Proof Roll
label | Reference - Section 304.08
label | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | Method - Visual
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Protection of compacted layer
label | Reference - Section 304.09
label | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Compaction Testing (results)
label | Reference - Section 173, Section 304.08 Table 304.081
label | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
label | Scale A:
label | — Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
label | — Base Layer CDR ≥ 100%
label | Scale B:
label | — Subbase Layer CDR ≥ 97%
label | — Base Layer CDR ≥ 98%
label | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | Scale C:
label | — Mean Value of Density Ratio (3 tests):
label | — Subbase Layers >98%
label | — Base Layers >100%
label | ○ ATTACH: Compaction Test Results
label | Method - Document Review
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Compaction Test Rersults
date | Date Completed:
checkpoint | 6.2 - Post Compaction Materials Testing (Results)
label | Reference - Section 304.10, Section 304.11 RC 500.02
label | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | 20mm Class 3:
label | Grading
label | ○ 26.5mm 100%
label | ○ 19.0mm 95-100%
label | ○ 13.2mm 75-95%
label | ○ 9.5mm 60-90%
label | ○ 4.75mm 42-76%
label | ○ 2.36mm 28-61%
label | ○ 0.425mm 14-29%
label | ○ 0.075mm 6-14%
label | — PI between 0 to 10
label | 20mm Class 4:
label | Grading
label | ○ 26.5mm 100%
label | ○ 4.75mm 42-76%
label | ○ 0.425mm 10-28%
label | ○ 0.075mm 2-14%
label | — PI between 0 to 20
label | — PI x % passing 0.425 mm sieve (max) 450
label | Scale C: Post compaction material testing is not required (Choose NA)
label | Method - Document Review
label | Frequency - Each Lot Where applicable
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Compaction Test Rersults
date | Date Completed:
checkpoint | 6.3 - Survey As-Built - Surface Level
label | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
label | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
label | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | Scale A: A minimum of 80 measurements per lot
label | — Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
label | — Base: mean range ±5mm, maximum Standard Deviation of 8mm
label | Scale B: A minimum of 40 measurements per lot
label | — Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | — Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | Scale C:
label | — Lower Subbase (mm) +15/ -25
label | — Upper Subbase (mm) +10/ -25
label | — Base (mm) +/-15
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/Surveyor
label | Verifying Documents - Survey Conformance Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP