## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
| Scope |  |  | QA
Rows
|  | Civil | dynamic | QA | Civil
|  | Hydraulics - New | dynamic | QA | Hydraulics | New
|  | Hydraulics - Thermostatic Mixing Valves | dynamic | QA | Hydraulics | Thermostatic Mixing Valves
|  | Decommissioning / Demolition | dynamic | QA | Decommissioning / Demolition
|  | Misc Issues | dynamic | QA | Misc Issues
|  | Variations | dynamic | QA | Variations
|  | Haz Mat | dynamic | QA | Haz Mat
Columns
|  | QA |  | QA
CCTV Checksheet
| Scope |  |  | QA
Rows
|  | Hydraulics - Investigation | grouping | Hydraulics - Investigation
|  | CCTV Joel 07/08/24 2x sewers |  | QA | Hydraulics | Investigation | CCTV Joel 07/08/24 2x sewers
|  | CCTV BG sewer delapidation |  | QA | Hydraulics | Investigation | CCTV BG sewer delapidation
|  | CCTV BG sewer dilapidation |  | QA | Hydraulics | Investigation | CCTV BG sewer dilapidation
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | CCTV Completed & Attached |  | CCTV Completed & Attached
|  | Drains clear, free of obstructions & in acceptable condition | Drains clear, free of obstructions & in acceptable condition | CCTV Completed & Attached
|  | If No, explain why | If No the above explain why | CCTV Completed & Attached
|  | Final sign off - CCTV completed |  | Final sign off - CCTV completed, Pass when satisfied to proceed (Any issues please comment & Add photos below)
Cold Water BG
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 01 - Zone 5 - Pump Line BG (PL) - Pump Line from Sump Pit 1 |  | QA | Hydraulics | New | Level 01 | Zone 5 | Pump Line BG (PL) | Pump Line from Sump Pit 1
|  | Level 01 - Zone 5 - Pump Line BG (PL) - Pump Line from Sump Pit 2 |  | QA | Hydraulics | New | Level 01 | Zone 5 | Pump Line BG (PL) | Pump Line from Sump Pit 2
|  | Level 01 - Zone 5 - Pump Line BG (PL) - Pump Line from Sump Pit 3 |  | QA | Hydraulics | New | Level 01 | Zone 5 | Pump Line BG (PL) | Pump Line from Sump Pit 3
|  | Level 01 - Zone 5 - Cold Water BG (CW) |  | QA | Hydraulics | New | Level 01 | Zone 5 | Cold Water BG (CW)
|  | Level 05 - Zone 4 - Cold Water BG (CW) - Grid (ZB-ZC, Z3-Z6) |  | QA | Hydraulics | New | Level 05 | Zone 4 | Cold Water BG (CW) | Grid (ZB-ZC, Z3-Z6)
|  | Level 05 - Zone 4 - Cold Water BG (CW) - Grid (AB-ZB, Z3-Z6) |  | QA | Hydraulics | New | Level 05 | Zone 4 | Cold Water BG (CW) | Grid (AB-ZB, Z3-Z6)
|  | Level 05 - Zone 4 - Non-Potable Cold Water BG (NPCW) - |  | QA | Hydraulics | New | Level 05 | Zone 4 | Non-Potable Cold Water BG (NPCW)
|  | Level 05 - Zone 5 - Pump Line AG (PL) |  | QA | Hydraulics | New | Level 05 | Zone 5 | Pump Line AG (PL)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, Z3-Z1) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, Z3-Z1)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, Z1-02) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, Z1-02)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 02-04) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 02-04)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 04-06) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 04-06)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 06-08) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 06-08)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZD, 08-09) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZD, 08-09)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 02-04) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 02-04)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (AA-ZA, Z3-Z1) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (AA-ZA, Z3-Z1)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (AA-ZA, Z1-02) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (AA-ZA, Z1-02)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (AA-ZA, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (AA-ZA, 02-03)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZA-ZB, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZA-ZB, 02-03)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 02-04) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 02-04)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 04-06) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 04-06)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 06-08) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 06-08)
|  | Level 05 - Zone 5 - 150mm Cold Water BG (CW) - Grid (ZB-ZC, 08-09) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 150mm Cold Water BG (CW) | Grid (ZB-ZC, 08-09)
|  | Level 05 - Zone 5 - 100mm Cold Water BG (CW) - Grid (AA-ZA, 02-04) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Cold Water BG (CW) | Grid (AA-ZA, 02-04)
|  | Level 05 - Zone 5 - 100mm Cold Water BG (CW) - Grid (AA-ZA, 04-07) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Cold Water BG (CW) | Grid (AA-ZA, 04-07)
|  | Level 05 - Zone 5 - 50mm Cold Water BG (CW) - Grid (ZB-ZC, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 50mm Cold Water BG (CW) | Grid (ZB-ZC, 02-03)
|  | Level 05 - Zone 5 - 50mm Cold Water BG (CW) - Grid (ZA-ZB, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 50mm Cold Water BG (CW) | Grid (ZA-ZB, 02-03)
|  | Level 05 - Zone 5 - 50mm Cold Water BG (CW) - Grid (AA-ZA, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 50mm Cold Water BG (CW) | Grid (AA-ZA, 02-03)
|  | Level 05 - Zone 5 - 50mm Cold Water BG (CW) - Grid (AA-ZA, 03-05) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 50mm Cold Water BG (CW) | Grid (AA-ZA, 03-05)
|  | Level 05 - Zone 5 - 50mm Cold Water BG (CW) - Grid (AA-ZA, 05-07) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 50mm Cold Water BG (CW) | Grid (AA-ZA, 05-07)
|  | Level 05 - Zone 5 - 20mm Cold Water BG (CW) - Grid (AA-ZA, 06-08) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 20mm Cold Water BG (CW) | Grid (AA-ZA, 06-08)
|  | Level 05 - Zone 5 - 20mm Cold Water BG (CW) - Grid (AA-ZA, 08-09) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 20mm Cold Water BG (CW) | Grid (AA-ZA, 08-09)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (ZB-ZC, Z3-Z1) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (ZB-ZC, Z3-Z1)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (ZB-ZC, Z1-02) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (ZB-ZC, Z1-02)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (ZB-ZC, 02-04) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (ZB-ZC, 02-04)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (ZB-ZC, 04-06) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (ZB-ZC, 04-06)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (ZB-ZC, 06-08) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (ZB-ZC, 06-08)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (ZB-ZC, 08-09) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (ZB-ZC, 08-09)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (ZA-ZB, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (ZA-ZB, 02-03)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (AA-ZA, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (AA-ZA, 02-03)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (AA-ZA, 02-04) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (AA-ZA, 02-04)
|  | Level 05 - Zone 5 - 100mm Non-Potable Cold Water BG (NPCW) - Grid (AA-ZA, 04-07) |  | QA | Hydraulics | New | Level 05 | Zone 5 | 100mm Non-Potable Cold Water BG (NPCW) | Grid (AA-ZA, 04-07)
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Correct material as per sample register |  | Correct material as per sample register
|  | Bedding material installed correctly |  | Bedding material installed correctly
|  | Fittings & joints correctly installed to manufacturer's requirements |  | Fittings & joints correctly installed to manufacturer's requirements
|  | Satisfactory welding/pressing of copper pipe |  | Satisfactory welding/pressing of copper pipe
|  | Witness marks visible |  | Witness marks visible
|  | Pipework layed correctly & to AS 3500 |  | Pipework layed correctly and to AS 3500
|  | Inspection & Testing Prior to Concealment to AS 3500 |  | Inspection and Testing Prior to Concealment to AS 3500
|  | Seal open ends with caps & high light to avoid damage |  | Seal open ends with caps & high light to avoid damage
|  | Identification of services via I.D tape |  | Identification of services via I.D tape
|  | Backfill & compaction to specification in 300mm layers |  | Backfill & compaction to specification in 300mm layers
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Cold Water Checklist
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 5 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 02 | Zone 5 | Cold Water AG (CW)
|  | Level 02 - Zone 6 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Cold Water AG (CW)
|  | Level 02 - Zone 6 - Pump Line & Vent (PL) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Pump Line & Vent (PL)
|  | Level 03 - Zone 1 - Pump Line (PL) |  | QA | Hydraulics | New | Level 03 | Zone 1 | Pump Line (PL)
|  | Level 03 - Zone 1 - Grid (AD-AE, 6-7) - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 03 | Zone 1 | Grid (AD-AE, 6-7) | Cold Water AG (CW)
|  | Level 03 - Zone 1 - Grid (AD-AE, 7-8) - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 03 | Zone 1 | Grid (AD-AE, 7-8) | Cold Water AG (CW)
|  | Level 03 - Zone 2 - Pump Line (PL) |  | QA | Hydraulics | New | Level 03 | Zone 2 | Pump Line (PL)
|  | Level 04 - Zone 1 - Pump Line (PL) |  | QA | Hydraulics | New | Level 04 | Zone 1 | Pump Line (PL)
|  | Level 04 - Zone 1 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 04 | Zone 1 | Cold Water AG (CW)
|  | Level 04 - Zone 5 - Grid (AA-ZA, 4-5) - Pump Line 1 (PL) |  | QA | Hydraulics | New | Level 04 | Zone 5 | Grid (AA-ZA, 4-5) | Pump Line 1 (PL)
|  | Level 04 - Zone 5 - Grid (AA-ZA, 4-5) - Pump Line 2 (PL) |  | QA | Hydraulics | New | Level 04 | Zone 5 | Grid (AA-ZA, 4-5) | Pump Line 2 (PL)
|  | Level 04 - Zone 6 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 04 | Zone 6 | Cold Water AG (CW)
|  | Level 05 - Zone 1 - Grid (AA-AD, 6-7) - Pump Line (PL) |  | QA | Hydraulics | New | Level 05 | Zone 1 | Grid (AA-AD, 6-7) | Pump Line (PL)
|  | Level 05 - Zone 1 - Grid (AC-AD, 7-8) - Pump Line (PL) |  | QA | Hydraulics | New | Level 05 | Zone 1 | Grid (AC-AD, 7-8) | Pump Line (PL)
|  | Level 05 - Zone 2 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 05 | Zone 2 | Cold Water AG (CW)
|  | Level 05 - Zone 6 - 150mm Cold Water AG (CW) - Grid (ZC-ZD, 09-11) |  | QA | Hydraulics | New | Level 05 | Zone 6 | 150mm Cold Water AG (CW) | Grid (ZC-ZD, 09-11)
|  | Level 05 - Zone 6 - 150mm Cold Water AG (CW) - Grid (ZB-ZD, 11-12) |  | QA | Hydraulics | New | Level 05 | Zone 6 | 150mm Cold Water AG (CW) | Grid (ZB-ZD, 11-12)
|  | Level 05 - Zone 6 - 150mm Cold Water AG (CW) - Grid (ZB-ZC, 09-11) |  | QA | Hydraulics | New | Level 05 | Zone 6 | 150mm Cold Water AG (CW) | Grid (ZB-ZC, 09-11)
|  | Level 05 - Zone 6 - 100mm Non-Potable Cold Water AG (NPCW) - Grid (ZB-ZD, 11-12) |  | QA | Hydraulics | New | Level 05 | Zone 6 | 100mm Non-Potable Cold Water AG (NPCW) | Grid (ZB-ZD, 11-12)
|  | Level 05 - Zone 6 - 100mm Non-Potable Cold Water AG (NPCW) - Grid (ZB-ZC, 09-11) |  | QA | Hydraulics | New | Level 05 | Zone 6 | 100mm Non-Potable Cold Water AG (NPCW) | Grid (ZB-ZC, 09-11)
|  | Level 05A - Zone 1 - Pump Line AG (PL) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Pump Line AG (PL)
|  | Level 05A - Zone 1 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Cold Water AG (CW)
|  | Level 05A - Zone 1 - Non-Potable Cold Water AG (NPCW) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Non-Potable Cold Water AG (NPCW)
|  | Level 05A - Zone 2 - Pump Line AG (PL) |  | QA | Hydraulics | New | Level 05A | Zone 2 | Pump Line AG (PL)
|  | Level 05A - Zone 2 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 05A | Zone 2 | Cold Water AG (CW)
|  | Level 05A - Zone 6 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Cold Water AG (CW)
|  | Level 05A - Zone 6 - Non-Potable Cold Water AG (NPCW) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Non-Potable Cold Water AG (NPCW)
|  | Level 06 - Zone 2 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Cold Water AG (CW)
|  | Level 06 - Zone 5 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 06 | Zone 5 | Cold Water AG (CW)
|  | Level 06 - Zone 6 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 06 | Zone 6 | Cold Water AG (CW)
|  | Level 07 - Zone 2 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 07 | Zone 2 | Cold Water AG (CW)
|  | Level 10 - Zone 2 - Cold Water AG (CW) |  | QA | Hydraulics | New | Level 10 | Zone 2 | Cold Water AG (CW)
|  | Misc Issues | grouping | Misc Issues
|  | Cold Water freeze and pipe alter |  | QA | Misc Issues | Cold Water freeze and pipe alter
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Material type (as per sample submission) |  | Material type (as per sample submission)
|  | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6) |  | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
|  | Welding/pressfit/push fit (as per AS 3500.1) |  | Welding / pressfit / push fit (as per AS 3500.1)
|  | Support & fixings (acoustic/seismic/water hammer) |  | Support & fixings (acoustic / seismic / water hammer)
|  | Pipework installation (as per AS 3500.1) |  | Pipework installation (as per AS 3500.1)
|  | Check no cross connection |  | Check no cross connection
|  | Pressure test (1500kpa pressure test) |  | Pressure test (1500kpa pressure test)
|  | 3rd Party Inspection |  | 3rd Party Inspection (Including the below as applicable)
|  | Name | Name | 3rd Party Inspection (Including the below as applicable)
|  | Company | Company | 3rd Party Inspection (Including the below as applicable)
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Commissioning Pump / Macerator Station
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 01 - Zone 1 - Pump Station - Commissioning Pump / Macerator Station |  | QA | Hydraulics | New | Level 01 | Zone 1 | Pump Station | Commissioning Pump / Macerator Station
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Pump Station - Commissioning Pump / Macerator Station |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Pump Station | Commissioning Pump / Macerator Station
|  | Level 02 - Zone 6 - Pump Station (ZA-ZB, 14-15) - Commissioning Pump / Macerator Station |  | QA | Hydraulics | New | Level 02 | Zone 6 | Pump Station (ZA-ZB, 14-15) | Commissioning Pump / Macerator Station
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Condition as when it was installed (report any changes) |  | Condition as when it was installed (report any changes)
|  | Control panel installed |  | Control panel installed
|  | Electrical wiring connected between pumps, controller & level sensing system installed correctly |  | Electrical wiring connected between pumps, controller & level sensing system installed correctly
|  | Connected to BMS |  | Connected to BMS
|  | Connected to power supply |  | Connected to power supply
|  | BMS faults in working order |  | BMS faults in working order (specify faults)
|  | High level alarm in working order |  | High level alarm in working order
|  | Supplier commissioning sheet |  | Supplier commissioning sheet
|  | Area clean | Area clean | Supplier commissioning sheet
Decommissioning / Demolition
| Scope |  |  | QA | Decommissioning / Demolition
Rows
|  | Level 01 | dynamic | Decommissioning / Demolition | Level 01
|  | Level 02 | dynamic | Decommissioning / Demolition | Level 02
|  | Level 03 | dynamic | Decommissioning / Demolition | Level 03
|  | Level 05 | dynamic | Decommissioning / Demolition | Level 05
|  | Level 07 | dynamic | Decommissioning / Demolition | Level 07
Columns
|  | Employee trained for task |  | Employee trained for task
|  | Drawing & revision number(s) | Drawing & revision number(s) | Employee trained for task
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Service/object to be decommissioned/demolished located |  | Service / object to be decommissioned / demolished located
|  | Identify & locate any dependant & affected areas/stakeholders/items |  | Identify and locate any dependant and affected areas/stakeholders/items
|  | Locate & identify any hazards that may occur when decommissioning/demolishing |  | Locate and identify any hazards that may occur when decommissioning / demolishing
|  | Service/object locked out for decommissioning/demolition |  | Service / object locked out for decommissioning / demolition
|  | Service/object isolated & ready for safe decommissioning/demolition |  | Service / object isolated and ready for safe decommissioning / demolition
|  | Service/object isolated safely decommissioned/demolished |  | Service / object isolated safely decommissioned / demolished (testing if applicable)
|  | Clean |  | Clean
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Fire Collars
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 1 |  | QA | Hydraulics | New | Level 02 | Zone 1 | Fire Collars
|  | Level 02 - Zone 2 |  | QA | Hydraulics | New | Level 02 | Zone 2 | Fire Collars
|  | Level 02 - Zone 3 |  | QA | Hydraulics | New | Level 02 | Zone 3 | Fire Collars
|  | Level 03 - Zone 1 |  | QA | Hydraulics | New | Level 03 | Zone 1 | Fire Collars
|  | Level 03 - Zone 2 |  | QA | Hydraulics | New | Level 03 | Zone 2 | Fire Collars
|  | Level 03 - Zone 5 |  | QA | Hydraulics | New | Level 03 | Zone 5 | Fire Collars
|  | Level 03 - Zone 6 |  | QA | Hydraulics | New | Level 03 | Zone 6 | Fire Collars
|  | Level 04 - Zone 1 |  | QA | Hydraulics | New | Level 04 | Zone 1 | Fire Collars
|  | Level 04 - Zone 2 |  | QA | Hydraulics | New | Level 04 | Zone 2 | Fire Collars
|  | Level 04 - Zone 5 |  | QA | Hydraulics | New | Level 04 | Zone 5 | Fire Collars
|  | Level 05 - Zone 1 |  | QA | Hydraulics | New | Level 05 | Zone 1 | Fire Collars
|  | Level 05 - Zone 2 |  | QA | Hydraulics | New | Level 05 | Zone 2 | Fire Collars
|  | Level 05 - Zone 6 |  | QA | Hydraulics | New | Level 05 | Zone 6 | Fire Collars
|  | Level 05A - Zone 1 |  | QA | Hydraulics | New | Level 05A | Zone 1 | Fire Collars
|  | Level 05A - Zone 2 |  | QA | Hydraulics | New | Level 05A | Zone 2 | Fire Collars
|  | Level 05A - Zone 5 |  | QA | Hydraulics | New | Level 05A | Zone 5 | Fire Collars
|  | Level 05A - Zone 6 |  | QA | Hydraulics | New | Level 05A | Zone 6 | Fire Collars
|  | Level 06 - Zone 1 |  | QA | Hydraulics | New | Level 06 | Zone 1 | Fire Collars
|  | Level 06 - Zone 2 |  | QA | Hydraulics | New | Level 06 | Zone 2 | Fire Collars
|  | Level 06 - Zone 4 |  | QA | Hydraulics | New | Level 06 | Zone 4 | Fire Collars
|  | Level 06 - Zone 5 |  | QA | Hydraulics | New | Level 06 | Zone 5 | Fire Collars
|  | Level 06 - Zone 6 |  | QA | Hydraulics | New | Level 06 | Zone 6 | Fire Collars
|  | Level 07 - Zone 1 |  | QA | Hydraulics | New | Level 07 | Zone 1 | Fire Collars
|  | Level 07 - Zone 2 |  | QA | Hydraulics | New | Level 07 | Zone 2 | Fire Collars
|  | Level 07 - Zone 5 |  | QA | Hydraulics | New | Level 07 | Zone 5 | Fire Collars
|  | Level 07 - Zone 6 |  | QA | Hydraulics | New | Level 07 | Zone 6 | Fire Collars
|  | Level 08 - Zone 1 |  | QA | Hydraulics | New | Level 08 | Zone 1 | Fire Collars
|  | Level 10 - Zone 2 |  | QA | Hydraulics | New | Level 10 | Zone 2 | Fire Collars
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Installation as per manufacturer's requirements |  | Installation as per manufacturer's requirements
|  | Correct fire collar location (as per drawing) |  | Correct fire collar location (as per drawing)
|  | Location | Location | Correct fire collar location (as per drawing)
|  | Fire tags as per fire matrix installed |  | Fire tags as per fire matrix installed
|  | Structurally correct (Engineers Approval required) |  | Structurally correct (Engineers Approval required)
|  | Engineers Approval attached | Engineers Approval attached | Structurally correct (Engineers Approval required)
|  | Fire sealant installed correctly |  | Fire sealant installed correctly
|  | Final Inspection - 3rd Party |  | Final Inspection - 3rd Party (Including the below as applicable)
|  | Name | Name | Final Inspection - 3rd Party (Including the below as applicable)
|  | Company | Company | Final Inspection - 3rd Party (Including the below as applicable)
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Fix 1 Checklist
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 1 - Grid (AA-AE, 07-09) - Toilet (02.504) + Cleaner's Sink, Drinking Fountain & Paint Collection Tank |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AA-AE, 07-09) | Toilet (02.504) + Cleaner's Sink, Drinking Fountain & Paint Collection Tank | Fix 1 Checklist
|  | Level 02 - Zone 1 - Grid (AD-AE, 08-09) - Scenery Dock (02.040) |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AD-AE, 08-09) | Scenery Dock (02.040) | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Drinking Fountain (AC-AD, 13-14) drink fountain West |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Drinking Fountain (AC-AD, 13-14) drink fountain West | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - UD WC (02.537) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | UD WC (02.537) | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Quick change |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Quick change | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Amenities West |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Amenities West | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AD-AL, 11-12) - Grid (AD-AE, 11-12) cleaners sink West |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Grid (AD-AE, 11-12) cleaners sink West | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AD-AL, 11-12) - Grid (AJ-AL, 11-12) cleaners sink East |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Grid (AJ-AL, 11-12) cleaners sink East | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AD-AL, 11-12) - Waynes World |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Waynes World | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AL-AN, 14-16) - Drinking Fountain (AL-AM, 13-14) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | Drinking Fountain (AL-AM, 13-14) | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AL-AN, 14-16) - Ensuite (02.572) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | Ensuite (02.572) | Fix 1 Checklist
|  | Level 02 - Zone 2 - Grid (AL-AN, 14-16) - UD WC (02.570) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | UD WC (02.570) | Fix 1 Checklist
|  | Level 02 - Zone 3 - Wardrobe Kitchenette (02.582A) |  | QA | Hydraulics | New | Level 02 | Zone 3 | Wardrobe Kitchenette (02.582A) | Fix 1 Checklist
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - Dressing Room (02.522) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Dressing Room (02.522)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - WC1 (ZA-ZB, 13-14) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | WC1 (ZA-ZB, 13-14)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - Ensuite (02.524) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Ensuite (02.524)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - Ensuite (02.523) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Ensuite (02.523)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - Crew Stand By Room (02.532) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Crew Stand By Room (02.532)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - Room (AA-ZA, 13-14) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Room (AA-ZA, 13-14)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - WC2 (AA-ZA, 14-15) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | WC2 (AA-ZA, 14-15)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - Kitchen (AA-ZA, 14-15) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Kitchen (AA-ZA, 14-15)
|  | Level 02 - Zone 6 - Corridor & Performer BOH Spaces (Cold Shell) - Sound Lock (02.526) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Sound Lock (02.526)
|  | Level 03 - Zone 2 - UD WC (03.518) |  | QA | Hydraulics | New | Level 03 | Zone 2 | UD WC (03.518) | Fix 1 Checklist
|  | Level 03 - Zone 2 - Female Amenities (03.517) |  | QA | Hydraulics | New | Level 03 | Zone 2 | Female Amenities (03.517) | Fix 1 Checklist
|  | Level 03 - Zone 2 - UD Ambulant (03.541) |  | QA | Hydraulics | New | Level 03 | Zone 2 | UD Ambulant (03.541) | Fix 1 Checklist
|  | Level 03 - Zone 6 - Male Amenities (03.516) |  | QA | Hydraulics | New | Level 03 | Zone 6 | Male Amenities (03.516) | Fix 1 Checklist
|  | Level 05 - Zone 6 - Female Amenities (05.532) |  | QA | Hydraulics | New | Level 05 | Zone 6 | Female Amenities (05.532) | Fix 1 Checklist
|  | Level 05 - Zone 6 - UD WC (05.533) |  | QA | Hydraulics | New | Level 05 | Zone 6 | UD WC (05.533) | Fix 1 Checklist
|  | Level 05 - Zone 6 - UD Ambulant (05.534) |  | QA | Hydraulics | New | Level 05 | Zone 6 | UD Ambulant (05.534) | Fix 1 Checklist
|  | Level 05 - Zone 6 - All Gender Inclusive (05.537) |  | QA | Hydraulics | New | Level 05 | Zone 6 | All Gender Inclusive (05.537) | Fix 1 Checklist
|  | Level 05 - Zone 6 - Male Amenities (05.535) |  | QA | Hydraulics | New | Level 05 | Zone 6 | Male Amenities (05.535) | Fix 1 Checklist
|  | Level 05A - Zone 1 - WC (05.523) |  | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.523) | Fix 1 Checklist
|  | Level 05A - Zone 1 - WC (05.544) |  | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.544) | Fix 1 Checklist
|  | Level 05A - Zone 1 - WC (05.545) |  | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.545) | Fix 1 Checklist
|  | Level 05A - Zone 2 - Dock Manager's Office (05.515) |  | QA | Hydraulics | New | Level 05A | Zone 2 | Dock Manager's Office (05.515) | Fix 1 Checklist
|  | Level 05A - Zone 6 - Grid (AA-ZA, 15-16) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Grid (AA-ZA, 15-16) | Fix 1 Checklist
|  | Level 06 - Zone 1 - Stage Door Entry (06.501) |  | QA | Hydraulics | New | Level 06 | Zone 1 | Stage Door Entry (06.501) | Fix 1 Checklist
Columns
|  | Sewer AG - Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual) | Sewer AG
|  | Sewer AG - Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point) | Sewer AG
|  | Sewer AG - Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below) | Sewer AG
|  | Sewer AG - Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below) | Sewer AG
|  | Sewer AG - Grades, fittings & joints installed to standards |  | Grades, fittings & joints installed to standards | Sewer AG
|  | Sewer AG - Fixings & seismic support to standards |  | Fixings & seismic support to standards | Sewer AG
|  | Sewer AG - Expansion joints per floor installed correctly & clipped |  | Expansion joints per floor installed correctly & clipped | Sewer AG
|  | Sewer AG - Pipe risers sealed per floor & capped off to prevent damage |  | Pipe risers sealed per floor & capped off to prevent damage | Sewer AG
|  | Sewer AG - Correct invert level (As per Standards) |  | Correct invert level (As per Standards) | Sewer AG
|  | Sewer AG - Vents & AAV installed (As per Standards) |  | Vents and AAV installed (As per Standards) | Sewer AG
|  | Sewer AG - Acoustic lagging installed to acoustic spec. |  | Acoustic lagging installed to acoustic specification | Sewer AG
|  | Sewer AG - Pipework water tested to 15Kpa |  | Pipework water tested to 15Kpa | Sewer AG
|  | Sewer AG - Identifications of services |  | Identifications of services | Sewer AG
|  | Sewer AG - Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Sewer AG
|  | Sewer AG - Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Sewer AG
|  | Stormwater AG - Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual) | Stormwater AG
|  | Stormwater AG - Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point) | Stormwater AG
|  | Stormwater AG - Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below) | Stormwater AG
|  | Stormwater AG - Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below) | Stormwater AG
|  | Stormwater AG - Grades (as per AS:3500) |  | Grades (as per AS:3500) | Stormwater AG
|  | Stormwater AG - Location (as per hydraulic drawing) |  | Location (as per hydraulic drawing) | Stormwater AG
|  | Stormwater AG - Location | Location | Location (as per hydraulic drawing) | Stormwater AG
|  | Stormwater AG - Fixings - Securely fixed (As per Standards) |  | Fixings - Securely fixed (As per Standards) | Stormwater AG
|  | Stormwater AG - Fittings Joints ETC (as per AS 3500) |  | Fittings Joints ETC (as per AS 3500) | Stormwater AG
|  | Stormwater AG - Inspection prior to closure |  | Inspection prior to closure | Stormwater AG
|  | Stormwater AG - Operation of pumps (Commissioning report) |  | Operation of pumps (Commissioning report) if Applicable | Stormwater AG
|  | Stormwater AG - Test water & discharge requirements are met |  | Test water and discharge requirements are met | Stormwater AG
|  | Stormwater AG - Correct invert level AS per AS 3500 |  | Correct invert level AS per AS 3500 | Stormwater AG
|  | Stormwater AG - Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Stormwater AG
|  | Stormwater AG - Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Stormwater AG
|  | Rough In - Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual) | Rough In
|  | Rough In - Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point) | Rough In
|  | Rough In - Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below) | Rough In
|  | Rough In - Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below) | Rough In
|  | Rough In - Material type (as per sample submission) |  | Material type (as per sample submission) | Rough In
|  | Rough In - Pipework installation checked against standards (as per AS 3500.1) |  | Pipework installation checked against standards (as per AS 3500.1) | Rough In
|  | Rough In - Welding/pressfit/push fit/witness marks (as per AS 3500.1) |  | Welding / pressfit / push fit / witness marks (as per AS 3500.1) | Rough In
|  | Rough In - Support & fixings checked (acoustic/seismic/water hammer/silicone) |  | Support & fixings checked (acoustic / seismic / water hammer/ silicone) | Rough In
|  | Rough In - Check for no cross connection |  | Check for no cross connection | Rough In
|  | Rough In - Heights double checked before room sign off as per sample submission |  | Heights double checked before room sign off as per sample submission | Rough In
|  | Rough In - Pipe risers water sealed per floor & capped off to prevent damage |  | Pipe risers water sealed per floor and capped off to prevent damage | Rough In
|  | Rough In - Correct sewer ventilation |  | Correct sewer ventilation | Rough In
|  | Rough In - Pressure test water lines to (1500kpa) |  | Pressure test water lines to (1500kpa) | Rough In
|  | Rough In - Identification of services |  | Identification of services | Rough In
|  | Rough In - Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Rough In
|  | Rough In - Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Rough In
|  | Rainwater - Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual) | Rainwater
|  | Rainwater - Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point) | Rainwater
|  | Rainwater - Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below) | Rainwater
|  | Rainwater - Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below) | Rainwater
|  | Rainwater - Material type as per approved sample submission |  | Material type as per approved sample submission | Rainwater
|  | Rainwater - Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6) |  | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6) | Rainwater
|  | Rainwater - Welding/pressfit/push fit (as per AS 3500.1) |  | Welding / pressfit / push fit (as per AS 3500.1) | Rainwater
|  | Rainwater - Support & fixings (acoustic/seismic/water hammer) |  | Support & fixings (acoustic / seismic / water hammer) | Rainwater
|  | Rainwater - Pipework Installation (as per AS 3500.1) |  | Pipework Installation (as per AS 3500.1) | Rainwater
|  | Rainwater - Check no cross connection |  | Check no cross connection | Rainwater
|  | Rainwater - Pressure test (1500kpa pressure test) |  | Pressure test (1500kpa pressure test) | Rainwater
|  | Rainwater - Identifications of services |  | Identifications of services | Rainwater
|  | Rainwater - Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Rainwater
|  | Rainwater - Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Rainwater
Fix 2 Checklist
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 1 - Grid (AA-AE, 07-09) - Toilet (02.504) + Cleaner's Sink, Drinking Fountain & Paint Collection Tank |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AA-AE, 07-09) | Toilet (02.504) + Cleaner's Sink, Drinking Fountain & Paint Collection Tank | Fix 2 checklist
|  | Level 02 - Zone 1 - Grid (AD-AE, 08-09) - Scenery Dock (02.040) |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AD-AE, 08-09) | Scenery Dock (02.040) | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Drinking Fountain (AC-AD, 13-14) drink fountain West |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Drinking Fountain (AC-AD, 13-14) drink fountain West | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - UD WC (02.537) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | UD WC (02.537) | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Quick change |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Quick change | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Amenities West |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Amenities West | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AD-AL, 11-12) - Grid (AD-AE, 11-12) cleaners sink West |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Grid (AD-AE, 11-12) cleaners sink West | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AD-AL, 11-12) - Grid (AJ-AL, 11-12) cleaners sink East |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Grid (AJ-AL, 11-12) cleaners sink East | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AD-AL, 11-12) - Waynes World |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Waynes World | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AL-AN, 14-16) - Drinking Fountain (AL-AM, 13-14) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | Drinking Fountain (AL-AM, 13-14) | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AL-AN, 14-16) - Ensuite (02.572) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | Ensuite (02.572) | Fix 2 checklist
|  | Level 02 - Zone 2 - Grid (AL-AN, 14-16) - UD WC (02.570) |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | UD WC (02.570) | Fix 2 checklist
|  | Level 02 - Zone 3 - Wardrobe Kitchenette (02.582A) |  | QA | Hydraulics | New | Level 02 | Zone 3 | Wardrobe Kitchenette (02.582A) | Fix 2 checklist
|  | Level 03 - Zone 2 - UD WC (03.518) |  | QA | Hydraulics | New | Level 03 | Zone 2 | UD WC (03.518) | Fix 2 checklist
|  | Level 03 - Zone 2 - Female Amenities (03.517) |  | QA | Hydraulics | New | Level 03 | Zone 2 | Female Amenities (03.517) | Fix 2 checklist
|  | Level 03 - Zone 2 - UD Ambulant (03.541) |  | QA | Hydraulics | New | Level 03 | Zone 2 | UD Ambulant (03.541) | Fix 2 checklist
|  | Level 03 - Zone 6 - Male Amenities (03.516) |  | QA | Hydraulics | New | Level 03 | Zone 6 | Male Amenities (03.516) | Fix 2 checklist
|  | Level 05 - Zone 6 - Female Amenities (05.532) |  | QA | Hydraulics | New | Level 05 | Zone 6 | Female Amenities (05.532) | Fix 2 checklist
|  | Level 05 - Zone 6 - UD WC (05.533) |  | QA | Hydraulics | New | Level 05 | Zone 6 | UD WC (05.533) | Fix 2 checklist
|  | Level 05 - Zone 6 - UD Ambulant (05.534) |  | QA | Hydraulics | New | Level 05 | Zone 6 | UD Ambulant (05.534) | Fix 2 checklist
|  | Level 05 - Zone 6 - All Gender Inclusive (05.537) |  | QA | Hydraulics | New | Level 05 | Zone 6 | All Gender Inclusive (05.537) | Fix 2 checklist
|  | Level 05 - Zone 6 - Male Amenities (05.535) |  | QA | Hydraulics | New | Level 05 | Zone 6 | Male Amenities (05.535) | Fix 2 checklist
|  | Level 05A - Zone 1 - WC (05.523) |  | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.523) | Fix 2 checklist
|  | Level 05A - Zone 1 - WC (05.544) |  | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.544) | Fix 2 checklist
|  | Level 05A - Zone 1 - WC (05.545) |  | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.545) | Fix 2 checklist
|  | Level 05A - Zone 2 - Dock Manager's Office (05.515) |  | QA | Hydraulics | New | Level 05A | Zone 2 | Dock Manager's Office (05.515) | Fix 2 checklist
|  | Level 05A - Zone 6 - Grid (AA-ZA, 15-16) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Grid (AA-ZA, 15-16) | Fix 2 checklist
|  | Level 06 - Zone 1 - Stage Door Entry (06.501) |  | QA | Hydraulics | New | Level 06 | Zone 1 | Stage Door Entry (06.501) | Fix 2 checklist
Columns
|  | Fixtures - Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual) | Fixtures
|  | Fixtures - Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point) | Fixtures
|  | Fixtures - Correct product (samples provided) |  | Correct product (samples provided) | Fixtures
|  | Fixtures - Check products for imperfections |  | Check products for imperfections | Fixtures
|  | Fixtures - Location & fixings (as per drawings & manufacturer guidelines) |  | Location & fixings (as per drawings & manufacturer guidelines) | Fixtures
|  | Fixtures - Silicone seals are acceptable standard |  | Silicone seals are acceptable standard (as applicable) | Fixtures
|  | Fixtures - Operation of all fixtures, taps & points of demand |  | Operation of all fixtures, taps & points of demand | Fixtures
|  | Fixtures - Final fit off inspection on all items |  | Final fit off inspection on all items | Fixtures
|  | Fixtures - Inspection date | Inspection date | Final fit off inspection on all items | Fixtures
|  | Fixtures - Items protected until commissioning |  | Items protected until commissioning (Attach photos below) | Fixtures
|  | Fixtures - Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Fixtures
|  | Commissioning - Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual) | Commissioning
|  | Commissioning - Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point) | Commissioning
|  | Commissioning - Check products for imperfections |  | Check products for imperfections | Commissioning
|  | Commissioning - Fixtures location & fixings all correct (as per drawings & samples) |  | Fixtures location & fixings all correct (as per drawings & samples) | Commissioning
|  | Commissioning - Clean out all strainers/aerators |  | Clean out all strainers / aerators | Commissioning
|  | Commissioning - Check for no cross connections/leaks/access to isolation valves |  | Check for no cross connections / leaks / access to isolation valves | Commissioning
|  | Commissioning - Floor wastes (clear of debris & draining correctly) |  | Floor wastes (clear of debris & draining correctly) | Commissioning
|  | Commissioning - Quality of silicone seals to fixtures acceptable |  | Quality of silicone seals to fixtures acceptable | Commissioning
|  | Commissioning - Hot water tempering valve set to 50c (+/- 5c) & DDA thermostatic mixing valve set to 42 degrees. |  | Hot water tempering valve set to 50c (+/- 5c) & DDA thermostatic mixing valve set to 42 degrees. | Commissioning
|  | Commissioning - Water pressure acceptable 350Kpa to 500 Kpa |  | Water pressure acceptable 350Kpa to 500 Kpa | Commissioning
|  | Commissioning - Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Commissioning
|  | Commissioning - Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below) | Commissioning
Gas
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 05A - Zone 6 |  | QA | Hydraulics | New | Level 05A | Zone 6 | Gas AG
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Material type as per approved sample submission |  | Material type as per approved sample submission
|  | Welding, press fittings, witness marks visually checked |  | Welding, press fittings, witness marks visually checked
|  | Supports & fixings to ESV & WPD standards |  | Supports & fixings to ESV and WPD standards
|  | Pipework installations to ESV standards |  | Pipework installations to ESV standards
|  | Penetrations, fire protection, wall sealant installed to the BCA requirements |  | Penetrations, fire protection, wall sealant installed to the BCA requirements
|  | Witness marks/labels/tiger tape/kpa signage |  | Witness marks / labels / tiger tape / kpa signage
|  | Pressure test (as per AS/NZS 5601.1) |  | Pressure test (as per AS/NZS 5601.1)
|  | Test appliances (as per AS/NZS 5601.1) |  | Test appliances (as per AS/NZS 5601.1)
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Gas BG
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 05 - Zone 4 |  | QA | Hydraulics | New | Level 05 | Zone 4 | Gas BG
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Correct material as per sample register |  | Correct material as per sample register
|  | Bedding material installed correctly |  | Bedding material installed correctly
|  | Fittings & joints correctly installed to manufacturer's requirements |  | Fittings & joints correctly installed to manufacturer's requirements
|  | Witness marks visible |  | Witness marks visible
|  | Pipework layed correctly & to AS 5601.1 |  | Pipework layed correctly and to AS 5601.1
|  | Inspection & Testing Prior to Concealment to AS 5601.1 (ESV start works notice) |  | Inspection and Testing Prior to Concealment to AS 5601.1 (ESV start works notice)
|  | Seal open ends with caps & high light to avoid damage |  | Seal open ends with caps & high light to avoid damage
|  | Identification of services via I.D tape |  | Identification of services via I.D tape
|  | Backfill & compaction to specification in 300mm layers |  | Backfill & compaction to specification in 300mm layers
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean & As-Built Markup | Area clean and As-Built Markup | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Greasy AG
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 5 - Greasy Waste AG (GW) |  | QA | Hydraulics | New | Level 02 | Zone 5 | Greasy Waste AG (GW)
|  | Level 05A - Zone 1 - Greasy Waste AG (GW) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Greasy Waste AG (GW)
|  | Level 05A - Zone 6 - Greasy Waste AG (GW) - Stack 1 (AA-AB, 16-17) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Greasy Waste AG (GW) | Stack 1 (AA-AB, 16-17)
|  | Level 05A - Zone 6 - Greasy Waste AG (GW) - Stack 2 (AA-AB, 16-17) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Greasy Waste AG (GW) | Stack 2 (AA-AB, 16-17)
|  | Level 06 - Zone 2 - Greasy Waste AG (GW) - Grid (AA-AC, 14-19) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Greasy Waste AG (GW) | Grid (AA-AC, 14-19)
|  | Level 06 - Zone 2 - Greasy Waste AG (GW) - Grid (AC-AJ, 19-22) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Greasy Waste AG (GW) | Grid (AC-AJ, 19-22)
|  | Misc Issues | grouping | Misc Issues
|  | MAPT Greasy AG lv 5 A leak |  | QA | Misc Issues | MAPT Greasy AG lv 5 A leak
|  | level 5a leak Greasy AG |  | QA | Misc Issues | level 5a leak Greasy AG
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Correct material as per sample register |  | Correct material as per sample register
|  | Grades, fittings & joints installed to standards including witness marks |  | Grades, fittings & joints installed to standards including witness marks
|  | Fixings & seismic support to code requirements |  | Fixings & seismic support to code requirements
|  | Expansion joints per floor installed correctly & clipped |  | Expansion joints per floor installed correctly & clipped
|  | Pipe risers sealed per floor & capped off to prevent damage |  | Pipe risers sealed per floor & capped off to prevent damage
|  | Correct ventilation installed including AAV |  | Correct ventilation installed including AAV
|  | Acoustic lagging installed to acoustic specification |  | Acoustic lagging installed to acoustic specification
|  | Testing to 15KPA with air or full water test |  | Testing to 15KPA with air or full water test
|  | Identifications of services |  | Identifications of services
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Greasy BG
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 01 - Zone 5 - Greasy Waste BG (GW) |  | QA | Hydraulics | New | Level 01 | Zone 5 | Greasy Waste BG (GW)
|  | Level 02 - Zone 5 - Greasy Waste BG (GW) |  | QA | Hydraulics | New | Level 02 | Zone 5 | Greasy Waste BG (GW)
|  | Level 02 - Zone 6 - Greasy Waste BG (GW) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Greasy Waste BG (GW)
|  | Level 05 - Zone 6 - GIT 1 - Greasy Waste BG (GW) |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 1 | Greasy Waste BG (GW)
|  | Level 05 - Zone 6 - GIT 2 - Greasy Waste BG (GW) |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 2 | Greasy Waste BG (GW)
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Latest specifications & standards nominated in ITP |  | Latest specifications and standards nominated in ITP
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register |  | Correct approved materials as per sample register
|  | Excavation undertaken & no issues |  | Excavation undertaken & no issues (Any issues comment below)
|  | Pipe bedding material comply (as per AS 3500) |  | Pipe bedding material comply (as per AS 3500)
|  | Grades, fittings & joints installed to standards |  | Grades, fittings & joints installed to standards
|  | Pipe clean out via water flush |  | Pipe clean out via water flush
|  | Inspection & Testing Prior to Concealment to AS 3500.2 section 13 |  | Inspection & Testing Prior to Concealment to AS 3500.2 section 13
|  | Builder sign off prior concealment |  | Builder sign off prior concealment
|  | Seal open ends with caps & high light to avoid damage |  | Seal open ends with caps & high light to avoid damage
|  | Backfill & Compaction of Material (As per Specification/Geotechnical report) |  | Backfill & Compaction of Material (As per Specification / Geotechnical report)
|  | CCTV on completion & record results |  | CCTV on completion & record results
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Hot Water
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 6 - Hot Water AG (HWF & HWR) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Hot Water AG (HWF & HWR)
|  | Level 03 - Zone 1 - Grid (AD-AE, 6-7) - Hot Water AG (HWF & HWR) |  | QA | Hydraulics | New | Level 03 | Zone 1 | Grid (AD-AE, 6-7) | Hot Water AG (HWF & HWR)
|  | Level 03 - Zone 1 - Grid (AD-AE, 7-8) - Hot Water AG (HWF & HWR) |  | QA | Hydraulics | New | Level 03 | Zone 1 | Grid (AD-AE, 7-8) | Hot Water AG (HWF & HWR)
|  | Level 03 - Zone 2 - Hot Water AG (HWF & HWR) |  | QA | Hydraulics | New | Level 03 | Zone 2 | Hot Water AG (HWF & HWR)
|  | Level 04 - Zone 1 - Hot Water (HWF) - Hot Water Line 1 |  | QA | Hydraulics | New | Level 04 | Zone 1 | Hot Water (HWF) | Hot Water Line 1
|  | Level 04 - Zone 1 - Hot Water (HWF) - Hot Water Line 2 |  | QA | Hydraulics | New | Level 04 | Zone 1 | Hot Water (HWF) | Hot Water Line 2
|  | Level 05A - Zone 1 - Hot Water (HWF) - Grid (AE-AB, 04-05) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Hot Water (HWF) | Grid (AE-AB, 04-05)
|  | Level 05A - Zone 1 - Hot Water (HWF) - Grid (AE-AA, 06-08) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Hot Water (HWF) | Grid (AE-AA, 06-08)
|  | Level 05A - Zone 2 - Hot Water (HWR) |  | QA | Hydraulics | New | Level 05A | Zone 2 | Hot Water (HWR)
|  | Level 06 - Zone 5 - Hot Water (HW) |  | QA | Hydraulics | New | Level 06 | Zone 5 | Hot Water (HW)
|  | Level 06 - Zone 6 - Hot Water (HW) |  | QA | Hydraulics | New | Level 06 | Zone 6 | Hot Water (HW)
|  | Hydraulics - Hot Water freeze isolations | grouping | Hydraulics - Hot Water freeze isolations
|  | Hot Water freeze isolations |  | QA | Hydraulics | Hot Water freeze isolations
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Material type (as per sample submission) |  | Material type (as per sample submission)
|  | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6) |  | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
|  | Welding/pressfit/push fit (as per AS 3500.1) |  | Welding / pressfit / push fit (as per AS 3500.1)
|  | Support & fixings (acoustic/seismic/water hammer) |  | Support & fixings (acoustic / seismic / water hammer)
|  | Pipework installation (as per AS 3500.1) |  | Pipework installation (as per AS 3500.1)
|  | Check no cross connection |  | Check no cross connection
|  | Pressure test (1500kpa pressure test) |  | Pressure test (1500kpa pressure test)
|  | 3rd Party Inspection |  | 3rd Party Inspection (Including the below as applicable)
|  | Name | Name | 3rd Party Inspection (Including the below as applicable)
|  | Company | Company | 3rd Party Inspection (Including the below as applicable)
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
In Ground Tank
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 05 - Zone 6 - GIT 1 |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 1 | GIT
|  | Level 05 - Zone 6 - GIT 2 |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 2 | GIT
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Latest specifications & standards nominated in ITP |  | Latest specifications and standards nominated in ITP
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register |  | Correct approved materials as per sample register
|  | Manufacturer's Quality |  | Manufacturer's Quality
|  | Tank Excavation |  | Tank Excavation
|  | Tank Installation & correct invert levels (as per AS 3500.1 Section 8) |  | Tank Installation & correct invert levels (as per AS 3500.1 Section 8)
|  | Builder sign off prior concealment |  | Builder sign off prior concealment
|  | Backfilling (as per AS 3500.3 Section 6.2.11) |  | Backfilling (as per AS 3500.3 Section 6.2.11)
|  | Compaction of Material (As per Specification/Geotechnical report) |  | Compaction of Material (As per Specification / Geotechnical report)
|  | Clean & Flush |  | Clean and Flush
|  | Inspection Prior to Closure |  | Inspection Prior to Closure
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Leak Detection System
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 01 - Zone 5 |  | QA | Hydraulics | New | Level 01 | Zone 5 | Leak Detection System
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Latest specifications & standards |  | Latest specifications and standards
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register | Correct approved materials as per sample register | Setout & alignment as per latest available drawing (include revision below)
|  | Manufacturer's quality |  | Manufacturer's quality
|  | Correct connections |  | Correct connections
|  | Simulate water leak from the furthest detection points to trigger alarm |  | Simulate water leak from the furthest detection points to trigger alarm
|  | System functioning correctly? |  | System functioning correctly?
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Pit
| Scope |  |  | QA
Rows
|  | Civil - Pits | grouping | Civil - Pits
|  | Pit 1.1 |  | QA | Civil | Pits | Pit 1.1
|  | Pit 1.2 |  | QA | Civil | Pits | Pit 1.2
|  | Pit 1.3 (GPT) |  | QA | Civil | Pits | Pit 1.3 (GPT)
|  | Pit 1.4/EX.3 |  | QA | Civil | Pits | Pit 1.4/EX.3
|  | Pit 2.1 |  | QA | Civil | Pits | Pit 2.1
|  | Pit 2.2 |  | QA | Civil | Pits | Pit 2.2
|  | Pit 2.3 |  | QA | Civil | Pits | Pit 2.3
|  | Pit 2.4 |  | QA | Civil | Pits | Pit 2.4
|  | Pit 2.5 |  | QA | Civil | Pits | Pit 2.5
|  | Pit 2.6 |  | QA | Civil | Pits | Pit 2.6
|  | Pit 2.7 |  | QA | Civil | Pits | Pit 2.7
|  | Pit 3.2 |  | QA | Civil | Pits | Pit 3.2
|  | Civil - Sewer Maintenance Shafts | grouping | Civil - Sewer Maintenance Shafts
|  | Sewer Maintenance Shaft 01-2 |  | QA | Civil | Sewer Maintenance Shafts | Sewer Maintenance Shaft 01-2
|  | Sewer Maintenance Shaft 01-3 |  | QA | Civil | Sewer Maintenance Shafts | Sewer Maintenance Shaft 01-3
|  | Sewer Maintenance Shaft 01-4 |  | QA | Civil | Sewer Maintenance Shafts | Sewer Maintenance Shaft 01-4
|  | Sewer Maintenance Shaft 01-5 |  | QA | Civil | Sewer Maintenance Shafts | Sewer Maintenance Shaft 01-5
|  | Sewer Maintenance Shaft 01-6 |  | QA | Civil | Sewer Maintenance Shafts | Sewer Maintenance Shaft 01-6
|  | Sewer Maintenance Shaft 01-7 |  | QA | Civil | Sewer Maintenance Shafts | Sewer Maintenance Shaft 01-7
|  | Sewer Maintenance Shaft 01-8 |  | QA | Civil | Sewer Maintenance Shafts | Sewer Maintenance Shaft 01-8
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Latest specifications & standards nominated in ITP |  | Latest specifications and standards nominated in ITP
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register | Correct approved materials as per sample register | Setout & alignment as per latest available drawing (include revision below)
|  | Manufacturer's Quality |  | Manufacturer's Quality
|  | Pit Excavation |  | Pit Excavation
|  | Pit Installation & correct invert levels (as per AS 3500.3 Section 7.5) |  | Pit Installation & correct invert levels (as per AS 3500.3 Section 7.5)
|  | Builder sign off prior concealment |  | Builder sign off prior concealment
|  | Backfilling (as per AS 3500.3 Section 6.2.11) |  | Backfilling (as per AS 3500.3 Section 6.2.11)
|  | Compaction of Material (As per Specification/Geotechnical report) |  | Compaction of Material (As per Specification / Geotechnical report)
|  | Clean & Flush |  | Clean and Flush
|  | Inspection Prior to Closure |  | Inspection Prior to Closure
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Pump / Macerator Station
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 01 - Zone 1 - Pump Station |  | QA | Hydraulics | New | Level 01 | Zone 1 | Pump Station | Pump / Macerator Station
|  | Level 02 - Zone 6 - Pump Station (ZA-ZB, 14-15) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Pump Station (ZA-ZB, 14-15) | Pump / Macerator Station
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Latest specifications & standards |  | Latest specifications and standards
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register | Correct approved materials as per sample register | Setout & alignment as per latest available drawing (include revision below)
|  | Manufacturer's quality |  | Manufacturer's quality
|  | Pump installed correctly |  | Pump installed correctly
|  | Correct invert levels |  | Correct invert levels
|  | All valves installed correctly |  | All valves installed correctly
|  | Pressure transducer installed correctly |  | Pressure transducer installed correctly
|  | Correct ventilation |  | Correct ventilation
|  | Clean |  | Clean
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Pump / Macerator Station Above Ground
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 2 - Grid (AA-AD, 14-16) - Pump Station |  | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Pump Station | Pump / Macerator Station Above Ground
Columns
|  | Employee trained for task and reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Latest specifications and standards |  | Latest specifications and standards
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register | Correct approved materials as per sample register | Setout & alignment as per latest available drawing (include revision below)
|  | Manufacturer's quality |  | Manufacturer's quality
|  | Pump installed correctly |  | Pump installed correctly
|  | Correct invert levels |  | Correct invert levels
|  | All valves installed correctly |  | All valves installed correctly
|  | Pressure transducer installed correctly |  | Pressure transducer installed correctly
|  | Correct ventilation |  | Correct ventilation
|  | Clean |  | Clean
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Rainwater
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 05 - Zone 2 - Non-Potable Cold Water (NPCW) |  | QA | Hydraulics | New | Level 05 | Zone 2 | Non-Potable Cold Water (NPCW)
|  | Level 06 - Zone 2 - Non-Potable Cold Water (NPCW) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Non-Potable Cold Water (NPCW)
|  | Level 06 - Zone 5 - Non-Potable Cold Water (NPCW) |  | QA | Hydraulics | New | Level 06 | Zone 5 | Non-Potable Cold Water (NPCW)
|  | Level 06 - Zone 6 - Non-Potable Cold Water (NPCW) |  | QA | Hydraulics | New | Level 06 | Zone 6 | Non-Potable Cold Water (NPCW)
|  | Level 07 - Zone 2 - Non-Potable Cold Water (NPCW) |  | QA | Hydraulics | New | Level 07 | Zone 2 | Non-Potable Cold Water (NPCW)
|  | Level 10 - Zone 2 - Non-Potable Cold Water (NPCW) |  | QA | Hydraulics | New | Level 10 | Zone 2 | Non-Potable Cold Water (NPCW)
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Material type as per approved sample submission |  | Material type as per approved sample submission
|  | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6) |  | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
|  | Welding/pressfit/push fit (as per AS 3500.1) |  | Welding / pressfit / push fit (as per AS 3500.1)
|  | Support & fixings (acoustic/seismic/water hammer) |  | Support & fixings (acoustic / seismic / water hammer)
|  | Pipework Installation (as per AS 3500.1) |  | Pipework Installation (as per AS 3500.1)
|  | Check no cross connection |  | Check no cross connection
|  | Pressure test (1500kpa pressure test) |  | Pressure test (1500kpa pressure test)
|  | Identifications of services |  | Identifications of services
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Rough In Checklist
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 1 - Grid (AA-AE, 07-09) - Pump Line (PL) |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AA-AE, 07-09) | Pump Line (PL)
Columns
Sanitary
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 1 - Grid (AA-AE, 07-09) - Sanitary Drainage (SS) |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AA-AE, 07-09) | Sanitary Drainage (SS)
|  | Level 02 - Zone 1 - Grid (AA-AE, 07-09) - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AA-AE, 07-09) | Chamber Vent (CHV)
|  | Level 02 - Zone 6 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Chamber Vent (CHV)
|  | Level 03 - Zone 1 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 03 | Zone 1 | Chamber Vent (CHV)
|  | Level 03 - Zone 5 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 03 | Zone 5 | Chamber Vent (CHV)
|  | Level 03 - Zone 6 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 03 | Zone 6 | Chamber Vent (CHV)
|  | Level 03 - Zone 6 - Space Theatre Function Space (Cold Shell) - Planting Room (03.522) - Sanitary Service AG (SS) |  | QA | Hydraulics | New | Level 03 | Zone 6 | Space Theatre Function Space (Cold Shell) | Planting Room (03.522) | Sanitary Service AG (SS)
|  | Level 04 - Zone 1 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 04 | Zone 1 | Chamber Vent (CHV)
|  | Level 04 - Zone 2 - Vent Pipe (VP) |  | QA | Hydraulics | New | Level 04 | Zone 2 | Vent Pipe (VP)
|  | Level 04 - Zone 2 - Mechanical Condensate Drainage |  | QA | Hydraulics | New | Level 04 | Zone 2 | Mechanical Condensate Drainage
|  | Level 05 - Zone 1 - Grid (AA-AD, 6-7) - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 05 | Zone 1 | Grid (AA-AD, 6-7) | Chamber Vent (CHV)
|  | Level 05 - Zone 2 - Vent Pipe (VP) |  | QA | Hydraulics | New | Level 05 | Zone 2 | Vent Pipe (VP)
|  | Level 05 - Zone 6 - 50mm Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 05 | Zone 6 | 50mm Chamber Vent (CHV)
|  | Level 05 - Zone 6 - GIT 1 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 1 | Chamber Vent (CHV)
|  | Level 05 - Zone 6 - GIT 2 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 2 | Chamber Vent (CHV)
|  | Level 05A - Zone 1 - Sanitary Drainage AG (SS) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Sanitary Drainage AG (SS)
|  | Level 05A - Zone 2 - Sanitary Drainage (SS) |  | QA | Hydraulics | New | Level 05A | Zone 2 | Sanitary Drainage (SS)
|  | Level 05A - Zone 5 - Chamber Vent (CHV) - Grid (AA-ZA, 01-02) |  | QA | Hydraulics | New | Level 05A | Zone 5 | Chamber Vent (CHV) | Grid (AA-ZA, 01-02)
|  | Level 07 - Zone 2 - Sanitary Drainage - Grid (AA-AE, 08-11) |  | QA | Hydraulics | New | Level 07 | Zone 2 | Sanitary Drainage | Grid (AA-AE, 08-11)
|  | Level 07 - Zone 2 - Sanitary Drainage - Grid (AA-AC, 17-19) |  | QA | Hydraulics | New | Level 07 | Zone 2 | Sanitary Drainage | Grid (AA-AC, 17-19)
|  | Level 08 - Zone 1 - Chamber Vent (CHV) |  | QA | Hydraulics | New | Level 08 | Zone 1 | Chamber Vent (CHV)
Columns
Service Log - Thermostatic Mixing Valves (TMV)
| Scope |  |  | QA
Rows
|  | Hydraulics - Thermostatic Mixing Valves | grouping | Hydraulics - Thermostatic Mixing Valves
|  | Level 02 - Zone 1 - Toilet (02.504) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 02 | Zone 1 | Toilet (02.504)
|  | Level 02 - Zone 1 - UD WC (02.537) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 02 | Zone 1 | UD WC (02.537)
|  | Level 02 - Zone 1 - Ensuite (02.572) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 02 | Zone 1 | Ensuite (02.572)
|  | Level 02 - Zone 1 - UD WC (02.570) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 02 | Zone 1 | UD WC (02.570)
|  | Level 03 - Zone 2 - UD Ambulant (03.541) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 03 | Zone 2 | UD Ambulant (03.541)
|  | Level 03 - Zone 2 - Female Amenities (03.517) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 03 | Zone 2 | Female Amenities (03.517)
|  | Level 03 - Zone 2 - UD WC (03.518) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 03 | Zone 2 | UD WC (03.518)
|  | Level 03 - Zone 6 - Male Amenities (03.516) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 03 | Zone 6 | Male Amenities (03.516)
|  | Level 05 - Zone 5 - Female Amenities (05.532) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 05 | Zone 5 | Female Amenities (05.532)
|  | Level 05 - Zone 5 - UD WC (05.533) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 05 | Zone 5 | UD WC (05.533)
|  | Level 05 - Zone 5 - UD Ambulant (05.534) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 05 | Zone 5 | UD Ambulant (05.534)
|  | Level 05 - Zone 5 - All Gender Inclusive (05.537) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 05 | Zone 5 | All Gender Inclusive (05.537)
|  | Level 05 - Zone 5 - Male Amenities (05.535) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 05 | Zone 5 | Male Amenities (05.535)
|  | Level 05A - Zone 1 - WC (05.523) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 05A | Zone 1 | WC (05.523)
|  | Level 06 - Zone 5 - UD Toilet (06.503) |  | QA | Hydraulics | Thermostatic Mixing Valves | Level 06 | Zone 5 | UD Toilet (06.503)
Columns
Sewer AG
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 05 - Zone 2 - Sewer AG (SS) |  | QA | Hydraulics | New | Level 05 | Zone 2 | Sewer AG (SS)
|  | Level 05A - Zone 5 - Sanitary Drainage (AG) - Grid (AA-ZA, 04-05) |  | QA | Hydraulics | New | Level 05A | Zone 5 | Sanitary Drainage (AG) | Grid (AA-ZA, 04-05)
|  | Level 05A - Zone 6 - Sanitary Drainage AG (SS) - Grid (ZA-ZB, 09-10) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Sanitary Drainage AG (SS) | Grid (ZA-ZB, 09-10)
|  | Level 05A - Zone 6 - Sanitary Drainage AG (SS) - Grid (ZA-ZB, 11-12) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Sanitary Drainage AG (SS) | Grid (ZA-ZB, 11-12)
Columns
Sewer BG
| Scope |  |  | QA
Rows
|  | Civil - Sewer Drains | grouping | Civil - Sewer Drains
|  | Section 01-2 - 01-3 |  | QA | Civil | Sewer Drains | Section 01-2 - 01-3
|  | Section 01-3 - Building |  | QA | Civil | Sewer Drains | Section 01-3 - Building
|  | Section 01-3 - 01-4 |  | QA | Civil | Sewer Drains | Section 01-3 - 01-4
|  | Section 01-4 - 01-5 |  | QA | Civil | Sewer Drains | Section 01-4 - 01-5
|  | Section 01-5 - 01-6 |  | QA | Civil | Sewer Drains | Section 01-5 - 01-6
|  | Section 01-6 - 01-7 |  | QA | Civil | Sewer Drains | Section 01-6 - 01-7
|  | Section 01-7 - Building |  | QA | Civil | Sewer Drains | Section 01-7 - Building
|  | Section 01-7 - 01-8 |  | QA | Civil | Sewer Drains | Section 01-7 - 01-8
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 6 - Sewer BG (SS) |  | QA | Hydraulics | New | Level 02 | Zone 6 | Sewer BG (SS)
|  | Level 05 - Zone 4 - Sewer BG |  | QA | Hydraulics | New | Level 05 | Zone 4 | Sewer BG
|  | Level 05 - Zone 6 - GIT 1 - Sewer BG (SS) |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 1 | Sewer BG (SS)
|  | Level 05 - Zone 6 - GIT 2 - Sewer BG (SS) |  | QA | Hydraulics | New | Level 05 | Zone 6 | GIT 2 | Sewer BG (SS)
Columns
Slab Penetrations Template
| Scope |  |  | QA
Rows
|  | Civil | grouping | Civil
|  | Civil |  | QA | Civil | Slab Penetrations Template
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 06 - Zone 4 - Level 6 zone 4 deck - Lv 6 zone 4 |  | QA | Hydraulics | New | Level 06 | Zone 4 | Level 6 zone 4 deck | Lv 6 zone 4
|  | Level 06 - Zone 4 - Level 6 zone 4 deck - Level 6 zone 4 pour 1 |  | QA | Hydraulics | New | Level 06 | Zone 4 | Level 6 zone 4 deck | Level 6 zone 4 pour 1
|  | Level 06 - Zone 4 - Level 6 zone 4 deck - Level 6 zone 4 pour 2 |  | QA | Hydraulics | New | Level 06 | Zone 4 | Level 6 zone 4 deck | Level 6 zone 4 pour 2
Columns
Storage Tanks
| Scope |  |  | QA
Rows
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 02 - Zone 1 - Grid (AA-AE, 07-09) - Paint Collection Tank |  | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AA-AE, 07-09) | Paint Collection Tank
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Latest specifications & standards |  | Latest specifications and standards
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register | Correct approved materials as per sample register | Setout & alignment as per latest available drawing (include revision below)
|  | Manufacturer's quality |  | Manufacturer's quality
|  | Connections & valves properly installed & tested for leaks |  | Connections and valves properly installed and tested for leaks
|  | Access equipment installed as per AS1657 |  | Access equipment installed as per AS1657
|  | Level sensor installed & working correctly |  | Level sensor installed and working correctly
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Stormwater AG
| Scope |  |  | QA
Rows
|  | Civil | grouping | Civil
|  | AG stormwater drains - Stormwater AG zone 5 |  | QA | Civil | AG stormwater drains | Stormwater AG zone 5
|  | AG stormwater drains - Stormwater AG zone 4 |  | QA | Civil | AG stormwater drains | Stormwater AG zone 4
|  | Hydraulics - New | grouping | Hydraulics - New
|  | Level 05 - Zone 4 - Stormwater AG (SW) - Downpipe 1 (DP) (AA-ZA, Z4-Z5) |  | QA | Hydraulics | New | Level 05 | Zone 4 | Stormwater AG (SW) | Downpipe 1 (DP) (AA-ZA, Z4-Z5)
|  | Level 05 - Zone 4 - Stormwater AG (SW) - Downpipe 2 (DP) (ZA-ZB, Z5-Z6) |  | QA | Hydraulics | New | Level 05 | Zone 4 | Stormwater AG (SW) | Downpipe 2 (DP) (ZA-ZB, Z5-Z6)
|  | Level 05 - Zone 4 - Stormwater AG (SW) - Downpipe 3 (DP) (ZC-ZD, Z4-Z5) |  | QA | Hydraulics | New | Level 05 | Zone 4 | Stormwater AG (SW) | Downpipe 3 (DP) (ZC-ZD, Z4-Z5)
|  | Level 05 - Zone 4 - Stormwater AG (SW) - Downpipe 3 (DP) (ZC-ZD, Z5-Z6) |  | QA | Hydraulics | New | Level 05 | Zone 4 | Stormwater AG (SW) | Downpipe 3 (DP) (ZC-ZD, Z5-Z6)
|  | Level 05 - Zone 5 - Stormwater AG (SW) - Downpipe 1 (DP) (ZA-ZB, 01-Z1) |  | QA | Hydraulics | New | Level 05 | Zone 5 | Stormwater AG (SW) | Downpipe 1 (DP) (ZA-ZB, 01-Z1)
|  | Level 05 - Zone 5 - Stormwater AG (SW) - Downpipe 2 (DP) (ZA-ZB, 01-Z1) |  | QA | Hydraulics | New | Level 05 | Zone 5 | Stormwater AG (SW) | Downpipe 2 (DP) (ZA-ZB, 01-Z1)
|  | Level 05 - Zone 5 - Stormwater AG (SW) - Downpipe 3 (DP) (ZA-ZB, 02-03) |  | QA | Hydraulics | New | Level 05 | Zone 5 | Stormwater AG (SW) | Downpipe 3 (DP) (ZA-ZB, 02-03)
|  | Level 05 - Zone 5 - Stormwater AG (SW) - Downpipe 4 (DP) (ZB-ZC, 03-04) |  | QA | Hydraulics | New | Level 05 | Zone 5 | Stormwater AG (SW) | Downpipe 4 (DP) (ZB-ZC, 03-04)
|  | Level 05A - Zone 1 - Stormwater AG (SW) - Grid (AC-AD, 04-05) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Stormwater AG (SW) | Grid (AC-AD, 04-05)
|  | Level 05A - Zone 1 - Stormwater AG (SW) - Grid (AA-AD, 04-08) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Stormwater AG (SW) | Grid (AA-AD, 04-08)
|  | Level 05A - Zone 5 - Stormwater AG (SW) - Downpipe 1 (DP) (ZB-ZC, 02-03) |  | QA | Hydraulics | New | Level 05A | Zone 5 | Stormwater AG (SW) | Downpipe 1 (DP) (ZB-ZC, 02-03)
|  | Level 05A - Zone 5 - Stormwater AG (SW) - Downpipe 1 (DP) (ZB-ZC, 03-04) |  | QA | Hydraulics | New | Level 05A | Zone 5 | Stormwater AG (SW) | Downpipe 1 (DP) (ZB-ZC, 03-04)
|  | Level 05A - Zone 5 - Stormwater AG (SW) - Overflow 1 (OF) (AA-ZA, 07-08) |  | QA | Hydraulics | New | Level 05A | Zone 5 | Stormwater AG (SW) | Overflow 1 (OF) (AA-ZA, 07-08)
|  | Level 05A - Zone 5 - Stormwater AG (SW) - Overflow 2 (OF) (AA-ZA, 08-09) |  | QA | Hydraulics | New | Level 05A | Zone 5 | Stormwater AG (SW) | Overflow 2 (OF) (AA-ZA, 08-09)
|  | Level 05A - Zone 5 - Stormwater AG (SW) - Overflow 3 (OF) (AA-ZA, 08-09) |  | QA | Hydraulics | New | Level 05A | Zone 5 | Stormwater AG (SW) | Overflow 3 (OF) (AA-ZA, 08-09)
|  | Level 05A - Zone 6 - Stormwater AG (SW) - Overflow 1 (ZA, 13) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Stormwater AG (SW) | Overflow 1 (ZA, 13)
|  | Level 05A - Zone 6 - Stormwater AG (SW) - Overflow 2 (ZA, 15) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Stormwater AG (SW) | Overflow 2 (ZA, 15)
|  | Level 05A - Zone 6 - Stormwater AG (SW) - Overflow 3 (AA-ZA, 18-19) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Stormwater AG (SW) | Overflow 3 (AA-ZA, 18-19)
|  | Level 05A - Zone 6 - Stormwater AG (SW) - Downpipe 1 (AB-ZA, 16-17) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Stormwater AG (SW) | Downpipe 1 (AB-ZA, 16-17)
|  | Level 05A - Zone 6 - Stormwater AG (SW) - Downpipe 2 (AB-ZA, 16-17) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Stormwater AG (SW) | Downpipe 2 (AB-ZA, 16-17)
|  | Level 05A - Zone 6 - Stormwater AG (SW) - Downpipe 3 (AA-ZA, 18-19) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Stormwater AG (SW) | Downpipe 3 (AA-ZA, 18-19)
|  | Level 06 - Zone 1 - Sanitary Drainage (AG) - Grid (AA-AD, 03-06) |  | QA | Hydraulics | New | Level 06 | Zone 1 | Sanitary Drainage (AG) | Grid (AA-AD, 03-06)
|  | Level 06 - Zone 1 - Sanitary Drainage (AG) - Grid (AA-AD, 06-09) |  | QA | Hydraulics | New | Level 06 | Zone 1 | Sanitary Drainage (AG) | Grid (AA-AD, 06-09)
|  | Level 06 - Zone 2 - Stormwater AG (SW) - Grid (AA-AC, 09-11) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Stormwater AG (SW) | Grid (AA-AC, 09-11)
|  | Level 06 - Zone 2 - Stormwater AG (SW) - Grid (AA-AC, 14-19) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Stormwater AG (SW) | Grid (AA-AC, 14-19)
|  | Level 06 - Zone 2 - Stormwater AG (SW) - Grid (AC-AJ, 19-22) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Stormwater AG (SW) | Grid (AC-AJ, 19-22)
|  | Level 06 - Zone 4 - Stormwater AG (SW) - Grid (AA-ZA, Z5-Z6) |  | QA | Hydraulics | New | Level 06 | Zone 4 | Stormwater AG (SW) | Grid (AA-ZA, Z5-Z6)
|  | Level 06 - Zone 4 - Stormwater AG (SW) - Grid (ZB-ZC, Z3-Z4) |  | QA | Hydraulics | New | Level 06 | Zone 4 | Stormwater AG (SW) | Grid (ZB-ZC, Z3-Z4)
|  | Level 06 - Zone 4 - Stormwater AG (SW) - Grid (AA-ZA, Z3-Z4) |  | QA | Hydraulics | New | Level 06 | Zone 4 | Stormwater AG (SW) | Grid (AA-ZA, Z3-Z4)
|  | Level 06 - Zone 5 - Stormwater AG (SW) - Grid (ZA-ZC, Z3-02) |  | QA | Hydraulics | New | Level 06 | Zone 5 | Stormwater AG (SW) | Grid (ZA-ZC, Z3-02)
|  | Level 06 - Zone 5 - Stormwater AG (SW) - Grid (ZA-ZC, Z3-02) |  | QA | Hydraulics | New | Level 06 | Zone 5 | Stormwater AG (SW) | Grid (ZA-ZC, Z3-02)
|  | Level 06 - Zone 6 - Stormwater AG (SW) |  | QA | Hydraulics | New | Level 06 | Zone 6 | Stormwater AG (SW)
|  | Level 07 - Zone 1 - Stormwater AG (SW) |  | QA | Hydraulics | New | Level 07 | Zone 1 | Stormwater AG (SW)
|  | Level 07 - Zone 2 - Stormwater AG (SW) - Grid (AA-AE, 08-11) |  | QA | Hydraulics | New | Level 07 | Zone 2 | Stormwater AG (SW) | Grid (AA-AE, 08-11)
|  | Level 07 - Zone 2 - Stormwater AG (SW) - Grid (AA-AE, 18-22) |  | QA | Hydraulics | New | Level 07 | Zone 2 | Stormwater AG (SW) | Grid (AA-AE, 18-22)
|  | Level 07 - Zone 2 - Stormwater AG (SW) - Grid (AJ-AE, 19-22) |  | QA | Hydraulics | New | Level 07 | Zone 2 | Stormwater AG (SW) | Grid (AJ-AE, 19-22)
|  | Level 07 - Zone 5 - Stormwater AG (SW) |  | QA | Hydraulics | New | Level 07 | Zone 5 | Stormwater AG (SW)
|  | Level 07 - Zone 6 - Stormwater AG (SW) |  | QA | Hydraulics | New | Level 07 | Zone 6 | Stormwater AG (SW)
|  | Level 08 - Zone 1 - Stormwater AG (SW) |  | QA | Hydraulics | New | Level 08 | Zone 1 | Stormwater AG (SW)
|  | Level 10 - Zone 2 - Stormwater AG (SW) |  | QA | Hydraulics | New | Level 10 | Zone 2 | Stormwater AG (SW)
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | Setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per drawing (include revision below)
|  | Grades (as per AS:3500) |  | Grades (as per AS:3500)
|  | Location (as per hydraulic drawing) |  | Location (as per hydraulic drawing)
|  | Location | Location | Location (as per hydraulic drawing)
|  | Fixings - Securely fixed (As per Standards) |  | Fixings - Securely fixed (As per Standards)
|  | Fittings Joints ETC (as per AS 3500) |  | Fittings Joints ETC (as per AS 3500)
|  | Inspection prior to closure |  | Inspection prior to closure
|  | Operation of pumps (Commissioning report) |  | Operation of pumps (Commissioning report) if Applicable
|  | Test water & discharge requirements are met |  | Test water and discharge requirements are met
|  | Correct invert level AS per AS 3500 |  | Correct invert level AS per AS 3500
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
Stormwater BG
| Scope |  |  | QA
Rows
|  | Civil | grouping | Civil
|  | Stormwater Drains - Section 4.1 - 4.2 |  | QA | Civil | Stormwater Drains | Section 4.1 - 4.2
|  | Stormwater Drains - Section 1.1 - 1.2 |  | QA | Civil | Stormwater Drains | Section 1.1 - 1.2
|  | Stormwater Drains - Section 1.2 - 1.3 |  | QA | Civil | Stormwater Drains | Section 1.2 - 1.3
|  | Stormwater Drains - Section GPT 525 Pipe - Building |  | QA | Civil | Stormwater Drains | Section GPT 525 Pipe - Building
|  | Stormwater Drains - Section 1.3 - 1.4/EX.3 |  | QA | Civil | Stormwater Drains | Section 1.3 - 1.4/EX.3
|  | Stormwater Drains - Section 1.4 - 2.1 |  | QA | Civil | Stormwater Drains | Section 1.4 - 2.1
|  | Stormwater Drains - Section 2.1 - 2.2 |  | QA | Civil | Stormwater Drains | Section 2.1 - 2.2
|  | Stormwater Drains - Section 2.1 - Building |  | QA | Civil | Stormwater Drains | Section 2.1 - Building
|  | Stormwater Drains - Section 2.2 - 2.3 |  | QA | Civil | Stormwater Drains | Section 2.2 - 2.3
|  | Stormwater Drains - Section 2.2 - Building |  | QA | Civil | Stormwater Drains | Section 2.2 - Building
|  | Stormwater Drains - Section 2.3 - 2.4 |  | QA | Civil | Stormwater Drains | Section 2.3 - 2.4
|  | Stormwater Drains - Section 2.4 - 2.5 |  | QA | Civil | Stormwater Drains | Section 2.4 - 2.5
|  | Stormwater Drains - Section 2.5 - 3.2 |  | QA | Civil | Stormwater Drains | Section 2.5 - 3.2
|  | Stormwater Drains - Section 2.5 - Building |  | QA | Civil | Stormwater Drains | Section 2.5 - Building
|  | Stormwater Drains - Section 2.5 - 2.6 |  | QA | Civil | Stormwater Drains | Section 2.5 - 2.6
|  | Stormwater Drains - Section 2.6 - 2.7 |  | QA | Civil | Stormwater Drains | Section 2.6 - 2.7
|  | Stormwater Drains - Section 2.6 - Buiding |  | QA | Civil | Stormwater Drains | Section 2.6 - Buiding
|  | Stormwater BG Kavanagh St stage 1 - |  | QA | Civil | Stormwater BG Kavanagh St stage 1
|  | Stormwater BG Southern end Kav St - |  | QA | Civil | Stormwater BG Southern end Kav St
Columns
|  | Employee trained for task & reviewed installation instructions |  | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | Notify and gain permit from principal contractor / client for inspection (hold point)
|  | Latest specifications & standards nominated in ITP |  | Latest specifications and standards nominated in ITP
|  | Setout & alignment as per latest available drawing |  | Setout & alignment as per latest available drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | Setout & alignment as per latest available drawing (include revision below)
|  | Correct approved materials as per sample register |  | Correct approved materials as per sample register
|  | Excavation undertaken & no issues |  | Excavation undertaken & no issues (Any issues comment below)
|  | Pipe bedding material (as per AS 500) |  | Pipe bedding material (as per AS 500)
|  | Grades, fittings & joints installed to standards |  | Grades, fittings & joints installed to standards
|  | Pipe clean out via water flush |  | Pipe clean out via water flush
|  | Inspection & Testing Prior to Concealment to AS 3500.2 section 13 |  | Inspection and Testing Prior to Concealment to AS 3500.2 section 13
|  | Builder sign off prior concealment |  | Builder sign off prior concealment
|  | Seal open ends with caps & high light to avoid damage |  | Seal open ends with caps & high light to avoid damage
|  | Backfill & Compaction of Material (As per Specification/Geotechnical report) |  | Backfill & Compaction of Material (As per Specification / Geotechnical report)
|  | CCTV on completion & record results |  | CCTV on completion & record results (If applicable)
|  | Final sign off |  | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
|  | Area clean | Area clean | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)