## EW-ITP-104
Earthworks Materials Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0104 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Earthworks Materials
4.01.01 | Principal-supplied Structural Fill | The Principal shall be responsible for strength, weathering, crushing, abrasion and any laboratory testing to confirm that the Principal-supplied aggregate meets the design or for quality control. No other Structural fill is to be used unless approved by the Engineer. | PS 15.4.2 | Principal Supplied Source and Production Properties Tests | Prior to use | HP | ENG
4.01.02 | Structural Fill Density Tests | The Contractor shall carrying out laboratory tests by an IANZ accredited Laboratory to determine the maximum laboratory dry density at the optimum water content (OWC) of the fill aggregate used and the Solid Density. The tests shall be undertaken on material that is representative of that used in construction and a grading for the material tested shall be supplied with the results | PS 15.5.4 | IANZ MDD, OMC, SD, PSD | Prior to use | HP | ENG
4.01.03 | Principal-supplied Structural Fill - MSE | The Principal shall provide a separate stockpile for material to be used as fill for the MSE structure and the stockpile shall be located within 5km of the site. The Principal shall undertake any tests required to confirm the properties of the Principal-supplied Structural Fill for the MSE structure. The Contractor may assume such material is deemed to comply. | PS 15.4.2 | Principal Supplied Source and Production Properties Tests | Prior to use | HP | ENG
4.01.04 | Structural Fill - Compaction Characteristics | The Contractor is required to carry out compaction testing by Test 4.2.1, NZS 4402:1986 to determine the compaction characteristics for each type and mix of material used in filling. | PS 15.4.2 | Test Report | Prior to use for each Structural Fill to be used | HP | ENG
4.01.05 | Site Won and Contractor Supplied Structural Fill - Not Expected to be Used | Any site won or Imported material considered as Structural Fill shall be verified by the Contractor and approved by the Engineer prior to use within the works | PS 15.4.2 | IANZ Test Reports | Prior to use | HP | ENG
4.01.06 | General Bulk Fill – Non Structural | Non granular and granular soils not meeting the fill type requirements of this specification may be used for this purpose with a Maximum particle size <300mm | PS 15.4.3 | PSD / Visual Screening | Prior to use | I | PE
4.01.07 | Talus Fill | Where Talus fill material contains rocks greater than 300mm diameter then these shall be removed from the talus materials, stockpiled and reclassified as rock fill. | PS 15.4.5 | PSD / Visual Screening | Prior to use | I | PE
4.02 | Rip Rap Materials
4.02.01 | Principal-supplied Rip Rap | Rock Fill is required for use in the scour blanket as rip rap construction. This shall be predominantly be supplied by the Principal (see 24.1). | PS 15.4.4 | Principal Supplied Source and Production Properties Tests | Prior to use | HP | ENG
4.02.02 | Site Won Rip Rap - Size | Rock Fill for scour protection is specified in terms of D50 (millimetres). This represents the rock size that 50% of the material must exceed. The dimension of any rock shall not exceed its narrowest dimension by more than a factor of three. | PS 15.4.4 | Hand Grading | Prior to use | I | PE
4.02.03 | Site Won Rip Rap - Density | Shall have a uniform density with an average specific gravity of no less than 2.65g/cm 3 . | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.02.04 | Site Won Rip Rap - Soundness of Rock | The rocks shall be sound and durable, being resistant to abrasion and free from cracks, laminations, seams, weak cleavages or other defects that would tend to increase unduly the likelihood of destruction of individual rocks by normal handling or weathering. | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.02.05 | Site Won Rip Rap - Broken faces | The rock shall be angular in form with broken faces over at least 2/3 of its surface. | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.02.06 | Site Won Rip Rap - Weathering Grade | The rock is to have minimal weathering, being rock of Grade I and II of the weathering term for the field description of rock provided in the 2005 “Guidelines for the field classification and description of soil and rock for engineering purposes”, NZ Geotechnical Society. | PS 15.4.4 | IANZ Lab Test Report | Prior to use | R | PE
4.03 | Geogrid / geofabric requirements Materials
4.03.01 | Geogrid and Geofabric | Where required by the design drawings geogrids or geofabrics shall be sourced from a reputable supplier and laid, inspected and verified in accordance with the manufacturer’s specifications. | PS 15.4.7 | Datasheet | Prior to use | R | PE

## RD-ITP-105
Roading Materials Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0105 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.15 | TNZ M/4 - AP40 Material Approval
4.15.01 | Principal-supplied stockpiles | The Principal shall provide stockpiles with material suitable for use as Basecourse within 5km the site. The Principal shall undertake any tests required to confirm the suitability as Basecourse material. | PS 17.4.1 | Stockpile Location | Prior to use | HP | ENG
4.15.02 | Principal-supplied Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | 10,000m3 | HP | ENG
4.15.03 | Principal-supplied Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | TNZ M/4: 2006 - 4 NZS 4407 : 1991 | IANZ Lab Reports |  | HP | ENG
4.15.04 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE
4.16 | TNZ M/3 Notes - AP65 Subbase Material Approval
4.16.01 | Principal-supplied stockpiles | The Principal shall provide stockpiles with material suitable for use as Subbase within 5km of the site. The Principal shall undertake any tests required to confirm the suitability as Subbase material. | PS 17.3.1 | Stockpile Location | Prior to use | HP | ENG
4.16.02 | Principal-supplied Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | TNZ M/3 Notes : 1986 TNZ M/4: 2006 PS 17.3.2.2 | IANZ Lab Reports | 10,000m3 | HP | ENG
4.16.03 | Principal-supplied Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | TNZ M/3 Notes : 1986 TNZ M/4: 2006 PS 17.3.2.2 | IANZ Lab Reports |  | HP | ENG
4.16.04 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE
4.17 | TNZ B/02:2005 Material Approval
4.17.01 | Running Course Material Approval | The running course shall have a crushing resistance of not less than 130 kN It shall be free from all non-mineral matter. The grading of the running course shall be conforming. | TNZ B/02: 2005 - 10.2 | IANZ Lab Reports |  | HP | ENG
4.18 | Sealing Chip Supply Materials
4.18.01 | Sealing Chip - Source Property Tests and Sampling | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV | TNZ M/6: 2019 - 4 | IANZ Lab Reports | Before Supply and Every 10,000m3 Thereafter | R | SE
4.18.02 | Sealing Chip - Production Property Test Sampling | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6 | TNZ M/6: 2019 - 5 | IANZ Lab Reports | Every 500m3 | R | SE
4.19 | Bitumen Supply Materials
4.19.01 | Bitumen - Quality Testing | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01. | NZTA M01: 2022 - 6 | IANZ Lab Reports | One test per grade supplied | R | SE
4.19.02 | Bitumen - Supply Testing | The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05. | NZTA Q05: 2022 - 6.2 | IANZ Lab Reports | Every 200 tonnes supplied. | R | SE
4.2 | NZTA M10 2020 - Dense Graded Asphaltic Concrete Materials
4.2.01 | Coarse Aggregate - Property Tests and Sampling | The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution | NZTA M10:2020 - 2.1 | IANZ Lab Reports | Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne. | H | PE
4.2.02 | Fine Aggregate - Property Tests and Sampling | The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution | NZTA M10:2020 - 2.1. | IANZ Lab Reports | Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne. | H | PE
4.2.03 | Mineral Filler | Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt. | NZTA M10:2020 - 2.2 ASTM D242 | IANZ Lab Reports | Prior to use | H | PE
4.2.04 | Bitumen | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification. | NZTA M10:2020 - 2.3.1 NZTA M01-A | IANZ Lab Reports | Prior to use | H | PE
4.2.05 | Mix Design Approval | The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use. | NZTA M10:2020 - 3.1 , 3.6 | Approved Mix Design | Prior to Use | HP | ENG
4.21 | Road Marking Materials
4.21.01 | Paint Approval | The paint to be used for roading marking shall be on "LIST OF M07 APPROVED PRODUCTS" | PS 18.1.3.4 | Datasheet and M7 List | Prior to use | R | SE
4.21.02 | Sprayer Certification | The Sprayer is to have a current T8 certificate | PS 18.1.3.4 | T8 Certificate | Prior to use | R | SE
4.22 | Traffic Sign Materials
4.22.01 | Traffic Sign Post | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.22.02 | Traffic Signs | All signs shall be completed in accordance wit NZTA P/24: Performance Based Specification for Traffic Signs | 18.2.1.3 | Datasheet and P24 List | Prior to use | R | SE
4.22.03 | Large Sign Posts | All signs larger than 4.5m2 and more than two posts shall have posts with breakaway bases and hinges, unless protected by safety barrier and more than 600mm behind the barrier. All other signs shall have posts complying with NZTA P/24 and the RSMA standard, | 18.2.1.4 | Datasheet and P24 List | Prior to use | R | SE
4.22.04 | Normal Sign Posts | All other signs shall have posts complying with NZTA P/24 and the RSMA standard, unless protected by safety barrier and more than 600mm behind the barrier. | 18.2.1.4 | Datasheet and P24 List | Prior to use | R | SE
4.22.05 | Support and Posts | Supports and posts for signs shall only be constructed of structural aluminium or steel. Refer to Clause 15.1 (b) & (c) of the RSMA Standard. All steel shall be hot-dipped galvanised after fabrication to CES 306. | 18.2.3.1 | Datasheet and P24 List | Prior to use | R | SE

## SW-ITP-106
Stormwater Materials Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0106 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.04 | Stormwater Drainage Materials
4.04.01 | PVC Pipes | PVC shall be Class SN8 or higher unless specified otherwise | 16.7.3.1 | Datasheet | Prior to use | R | PE
4.04.02 | Corrugated steel, Aluminium, and profiled-wall PE | Corrugated steel or aluminium pipes and profiled-wall PE need to be approved by the Engineer | 16.7.3.1 | Datasheet | Prior to use | HP | ENG
4.04.03 | Concrete Pipes | Concrete pipes shall be a minimum of Class 4 unless specified | 16.7.3.1 | Datasheet | Prior to use | R | PE
4.04.04 | Concrete pipe Embedment | Bedding and haunching material shall either conform to the grading limits of AS/NZS 3725 Table 6 or complies with the compaction requirements of Table 16.7 below or Section 16.7.3.5, and does not exceed the maximum particle size stated in AS/NZS 3725. Alternatively Low fines may be used. Testing shall include PSD, MDD (VH Cohesiveless), Fines etc. | 16.7.3.2 | IANZ Test Results | Prior to use | R | PE
4.04.05 | Concrete pipe Embedment - Compaction Fraction | Bedding and haunching material must be tested for compaction fraction as per AS/NZS3725 to determine the target Minimum Dry Density required for insitu compaction. | 16.7.3.2 | IANZ Test Results | Prior to use | R | PE
4.04.06 | Buried flexible pipe embedment | Bedding and haunching material for flexible pipes shall conform to AS/NZS 2566.2 except where Low Fines is used. Testing shall include PSD, MDD (VH Cohesiveless), Fines etc. | 16.7.3.3 | IANZ Test Results | Prior to use | HP | ENG
4.04.07 | Geotextile Wrapped Subsoil Drain Aggregate | The granular aggregate subsoil material may be as specified in NZTA F/6 or alternatively a free draining angular material free from fines and not exceeding 19mm maximum particle size where used for sub-soil pipe embedment e.g. 7mm drainage chip. The Engineer can advise on which materials are considered appropriate for use. | 16.7.3.4 | IANZ Test Results | Prior to use | HP | ENG
4.04.08 | Low fines | ‘Low fines’ material may be used for embedment (e.g. drainage chip) for both concrete and flexible pipes subject to complying with the specification. A Compaction Fraction shall be completed to determin compaction requirmenets. | 16.7.3.5 | IANZ Test Results | Prior to use | R | PE
4.04.09 | Manholes | Manholes shall be a minimum of DN1050. Manhole cover slabs and risers shall be rated to HN-HO-72, as specified in NZTA P46, where subject to vehicle loads. This shall include all areas accessible to vehicles including access ramps, shallow berms and car parking areas | 16.9.1.1 | Datasheet | Prior to use | R | PE
4.04.10 | Manhole Steps | Manholes shall include Grade 316 SS or plastic encapsulated step rungs complying with AS 1657:2018 located to avoid any connected pipes. The manhole cover slab shall have an eccentric opening rotated to align with the step rungs | 16.9.1.1 | Datasheet | Prior to use | R | PE
4.04.11 | Sumps / Catch-Pits Lids | The grate and frame shall be hinged cast or ductile iron with 675 x 450 mm clear opening at all locations unless specified otherwise on the drawing. The grate and frame shall be rated Class D to AS 3996 or higher. | 16.10.1 | Datasheet | Prior to use | R | PE
4.04.12 | Geo-textiles | Geo-textiles for all drainage separation purposes shall be a non-woven needle-punched fabrication in accordance with NZTA specification F/7. | 16.11.1 PS 15.4.7 | Datasheet | Prior to use | R | PE

## IC-ITP-107
Insitu Structure and Concrete Materials Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0107 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.09 | Insitu Mix Designs
4.09.01 | Concrete Plant | The Concrete Plant shall have a Current Certificate of Audit | PS 27.4.1 | Certificate of Audit to NZS 3104:2003 | With Mix Design and Upon Revalidation | HP | ENG
4.09.02 | Concrete Aggregate Reactivity Testing | When required, the Concrete producer is to confirm the proposed aggregates are non-reactive as defined in clause 6.1 of CCANZ TR3. | PS 27.4.2.3 | Supplier Statement | With Mix Designs Submissions | HP | ENG
4.09.03 | Insitu Concrete Handling and Placing | The contractor shall submit the proposed handling and placing methods, sequence and timing of pours and location on construction joints for the Engineer's consent before concrete placing commences | 27.4.5.1 | Approved Method | Before Concrete Placing Commences | HP | ENG
4.09.04 | Insitu stitch in torsion beam Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.09.05 | Insitu Stitches between hollowcore roof beams Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.09.06 | Other insitu stitches and insitu snow wall Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.09.07 | Kerb and channel Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.1 | Insitu Concrete Materials
4.10.01 | Dry Pack Mortar | Dry pack mortar where specified on the drawings shall consist of a sand/cement mix in the loose volume proportions of one part of cement to two parts of well drained Class A (coarse) plastering sand or concrete sand complying with NZS 3103 and NZS 3121 respectively. | PS 27.4.3.7 | Datasheets | Prior to use | R | PE
4.10.02 | Fibre Reinforcement | The following proprietary fibres and doses shall be used: • iNFORCE Microforce19 polypropylene fibres – 1.8 kg/m3 • iNFORCE Ultrafiber500 cellulose fibres – 1.8 kg/m3 | PS 21.7.4 | Datasheets | With Mix Designs Submissions | R | PE
4.10.03 | Reinforcement Supplier | The contractor shall provide the name of reinforcement supplier before delivering any reinforcement | PS 27.7 | Supplier Details | Before delivering any reinforcement | R | PE
4.10.04 | Reinforcement | Reinforcing bars and mesh shall comply with AS/NZS4671:2001. Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of any work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work. | PS 27.7.1 / 27.7.9 | Mill Certs | At least one week before incorporating these materials. | R | PE
4.10.05 | Bar Bending Schedules | The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars. | PS 27.7.8 | Bar Bending Schedules | At least 14 days before the start of placing the corresponding reinforcing bars. | HP | ENG
4.10.06 | TPI Inspector approval | The Contractor shall supply the details of the proposed Third Party Inspector to the engineer prior to welding | PS 27.7.6 | TPI Details and Qualifications | Prior to Welding | HP | ENG
4.10.07 | Welding of Reinforcement | The welding shall be inspected by the Contractor’s Third Party Inspector who shall meet the “Qualifications of Inspectors” requirements of AS/NZS 1554.3 Clause 10.2. Inspections of the welding shall be in accordance with AS/NZS 1554.3. | PS 27.7.6 | TPI Report | Prior to be encased. 100% Visual, 10% Ultrasonic, and 10% of Fillet by Magnetic. | HP | ENG
4.10.08 | Mechanical couplers and anchors in reinforced concrete | Mechanical couplers and anchors for the jointing of reinforcing steel shall satisfy the requirements of NZS 3101 clauses 8.7.5 and 8.9.1.3, and ISO 15835-1 Steels for the reinforcement of concrete. Only steel Reidbar components meeting the above requirements shall be accepted. | PS 27.7.12.1 | System Certification or Batch Verification. | Prior to use | R | PE
4.10.09 | Joint Sealing and Waterproofing | Where so indicated on the Drawings, joints are to be sealed using Sikaflex 11FC or similar approved equivalent. | PS 27.8 | Datasheet | Prior to use | R | PE
4.10.10 | Compressible Filler | Compressible filler board shall be a closed polyethylene board complying with the requirements of DTp Specification for Highway Works series 1000. Details of the material proposed to be used shall submitted to the Designer at least 1 week prior to installation, for acceptance. | PS 27.8.3 | Datasheet | At least 1 week prior to installation, for acceptance. | R | PE
4.10.11 | Interfaces with bitumen | At all interfaces with bitumen-based materials the sealant shall be separated using high strength multilaminate modified bitumen tape or approved equivalent on top of aluminium tape C126(sticky side-up). | PS 27.8.4 | Datasheet | Prior to use | R | PE
4.10.12 | Permeant Formwork Certification Compressible Filler) | Design details, construction drawings and a formwork certificate (PF-T-442) shall be supplied to the Engineer prior to the formwork assembly and at least 14 days prior to concreting of the component, for review, for all permanent formwork proposed to be used. | PS 27.5.3.5 | PF-T-442 Certificate | Prior to Pour | HP | ENG
4.10.13 | Membrane Curing | The use of membrane curing shall be subject to the written consent of the Engineer, following the submission of full details of the method proposed (including details of the curing compound where applicable) and the area of proposed use. | PS 27.4.8.2 | Post Pour | Prior to use | HP | ENG
4.11 | Special Provisions Relating to Pumped Concrete
4.11.01 | Pumping Equipment | Concrete pumping equipment shall be of a proven type able to deliver the specified concrete and distances and heights required. Pumping equipment that relies on compressed air to move the concrete through the pipeline shall not be used. The pump shall be located as near as practicable to the placement area. | PS 27B1.2 | Equipment Details | Prior to use | R | PE
4.11.02 | Concrete Materials | Concrete mixes for pumping shall have a plastic consistency and provision shall be made for the elimination of oversized particles in the concrete by finish screening or by the careful selection of aggregates. | PS 27B1.4 | Mix Design | Submitted least 14 days in advance of concrete supply | HP | ENG
4.12 | Falsework Requirements
4.12.01 | Falsework Design | The Contractor shall provide the Engineer with a summary of the falsework requirements for the works and the proposed design requirements and quality controls to ensure the design of the falsework is fit for purpose. In developing these proposals, the Contractor shall refer to the best practice guidelines referenced by the Temporary Works Forum NZ | PS 27.5.2 | Falsework Design | Prior to Fabrication | HP | ENG
4.12.02 | Falsework Engineer | The Contractor shall appoint a Falsework Engineer for the design of the falsework and preparation of the falsework drawings and specification. The person appointed shall be competent and experienced in falsework design and, for "special" and "conventional" falsework, shall also be a registered engineer. | PS 27.5.2 | Notice | Prior to Fabrication | HP | ENG
4.12.03 | Falsework Programme | The Contractor shall supply to the Engineer at least one week prior to the programmed start of construction of the falsework a completed Falsework Design Certificate on form PF-T-440 (attached in Appendix 27A). All subsequent modifications to the original design shall be likewise certified by the engineer, and by the independent checker for "special" falsework. | PS 27.5.2 | PF-T-440 | At least one week prior to the programmed start of construction | HP | ENG
4.12.04 | Falsework Site Register | The Contractor shall provide, at the site for the Engineer's inspection, a register containing the completed Falsework Design and Inspection Certificates. The Engineer shall have access to these documents at all times. | PS 27.5.2.4 | Register | Ongoing | R | PE
4.13 | Avalanche Shelter Structures
4.13.01 | Concrete, Mortar and Grout | Mortar and grout, whether cementitious or epoxy, used for bedding precast units or bearings against the concrete shall have a compressive strength at 28 days of not less than the specified concrete strength of the concrete elements being bedded against unless specified otherwise. | PS 21.3.1 | Datasheets | Prior to use | R | PE
4.13.02 | Proprietary grout approval | Details of any proprietary grout shall be submitted to the Engineer for approval 5 days in advance of any construction works using such material. | PS 21.3.1 | Datasheets | 5 days in advance of any construction works using such material. | HP | ENG
4.13.03 | Epoxy mortar | Epoxy mortar shall be a proprietary product from a recognised manufacturer and shall be subject to the acceptance of the Engineer as suitable for the particular application. | PS 21.3.1 | Datasheets | Prior to use | HP | ENG
4.13.04 | Patch repair mortar | Patch repair mortar, wherever it may be used, shall be a proprietary product from a recognised manufacturer, and subject to the acceptance of the Engineer as suitable for the particular application. | PS 21.3.1 | Datasheets | Prior to use | HP | ENG
4.13.05 | Bolts, Nuts and Washers | The Contractor shall submit test reports or test certificates for all bolts nuts and washers, prepared by a laboratory accredited by signatories to the International Accreditation Cooperation (ILAC) Mutual Recognition Agreement (MRA) on behalf of the manufacturer, as evidence of compliance with the relevant material supply standard specified. | PS 21.3.3 | Test reports or Test certificates | at least one week before the programmed commencement of any work incorporating these materials. | HP | ENG
4.13.06 | Elastomeric Strip Bearings | All elastomeric bearing strips shall comply with AS 5100.4 IRHD 60. | 21.3.5.1 | Datasheets | Prior to use | R | PE
4.13.07 | Expansion Joints | Compression Board to be approved and compression seal WaboXPE Seal (XPE 3000) or similar approved equivalent in accordance with the Manufacturer’s written instructions | 21.3.6 | Datasheets | Prior to use | R | PE
4.13.08 | Cast-In Sleeving | Cast-in sleeving, unless specified or shown on the drawings as otherwise, shall be rigid uPVC pipe complying with AS/NZS 1260, or other acceptable standard, and of the size shown on the drawings. | 21.3.7 | Datasheets | Prior to use | R | PE
4.13.09 | Services Ducts | Ducting for services shall be uPVC ducting of the nominal bore diameter shown on the drawings and complying with AS/NZS 2053.1, AS/NZS 2053.2 and AS/NZS 2053.4 as applicable. | 21.3.8 | Datasheets | Prior to use | R | PE
4.13.10 | Precast Bedding Material | Where precast units are to be placed on granular material, the bedding material shall consist of PAP 7, all in crushed hard aggregate, well graded from coarse to fine, durable and free of nonmineral matter. | 21.5.1.2 | PSD | Prior to use | R | PE
4.13.11 | Temporary Works | The Contractor shall provide the Engineer with a summary of the temporary works required for the works and the proposed design requirements and quality controls to ensure the design of the temporary works is fit for purpose | 21.5.2 | Temporary Works Summary | Prior to use | HP | ENG
4.14 | Anti Graffiti Guard
4.14.01 | Permanent Anti Graffiti Guard | Permanent (not sacrificial) anti graffiti coatings shall be applied to the exposed faces of all concrete surfaces including barriers, piers and abutments. The coatings shall have a design life of not less than 10 years. The coating shall be either on the Waka Kotahi list of prequalified formulations or prequalified by the Contractor for inclusion on the Waka Kotahi list. | PS 14.3.1 | Datasheet and on Waka Kotahi S10 List | Prior to use | HP | ENG
4.14.02 | Anti-Graffiti Label Approval | A self-adhesive label shall indicate all areas of anti-graffiti coatings on site. at least two weeks prior to the applicable works, the Contractor shall submit details of the label to the Engineer for approval. | PS 21.7.1.3 | Label Details | at least two weeks prior to the applicable work | HP | ENG
4.14.03 | Anti-Graffiti Product and Approval | The Contractor shall prepare a test panel to demonstrate that the above appearance requirements have been met to the satisfaction of the Engineer. | 21.7.1.1 | Notice | Prior to production use | HP | ENG

## LS-ITP-108
Landscaping Materials Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0108 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.25 | Landscaping Materials
4.25.01 | Topsoil | All topsoil and associated weathered/organic material obtained from on-site stripping shall be retained and stockpiled for future use within the Project area. | PS 25.7.3 | Site Notes | Prior to use | R | PE
4.25.02 | Fertilisers | The relocated plant material shall be top-dressed with a controlled, slow release fertiliser such as ‘Nutricote’ or ‘Osmocote Plus's of composition 12:8:6 (N:P:K) or similar. Nitrogen is likely to be the most deficient mineral in the local topsoil/avalanche debris substrate. | PS 25.8.2 | Datasheet | Prior to use | R | PE

## MSE-ITP-109
MSE Wall Design Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0109 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.23 | Mechanically Stabilised Earth (MSE) Wall Design
4.23.01 | MSE Wall Design | Design of and preparation of detailed specifications and drawings for the manufacture and erection of the MSE wall shall be the responsibility of the Contractor. The MSE wall designer shall provide a Producer Statement for Design (PS1) | PS 22.4.1 PS 22.4.4 | Design, Spec, Drawings, and PS1 | Prior to commencing construction of the MSE Wall | HP | ENG
4.23.02 | MSE Design Review Engineer Approval | The name and qualifications of the design review company shall be submitted to the Engineer for approval prior to commencing the review. | PS 22.4.3 | Review Engineer Approval | Prior to commencing the review. | HP | ENG
4.23.03 | MSE Design Review | The Contractor shall engage an independent reviewer to undertake peer review of the MSE wall design. The independent reviewer shall provide a Producer Statement for Design Review (PS2) | PS 22.4.3 | PS2 | Prior to commencing construction of the MSE Wall | HP | ENG
4.23.04 | Method Statement and ITP | The Contractor shall prepare and submit a Construction Methodology and an Inspection Test Plan (ITP) for the MSE wall for Waka Kotahi and Engineer’s approval prior to construction. The ITP shall include all quality control testing required during construction as specified by the MSE wall designer | PS 22.4.5 | Method Statement and ITP | Prior to commencing construction of the MSE Wall | HP | ENG |  |  | MSE Wall ITP to be incorporated into this ITP below.
4.24 | MSE Wall Sample Panel
4.24.01 | MSE Wall Sample Panel | Prior to the commencement of the permanent work, the Contractor shall produce one sample panel of similar dimensions and construction to the proposed final panels. | PS 22.16.5 | 3m Visal Inspection by Engineer | Prior to the commencement of the permanent work | HP | ENG