## 110 - ITP
Existing Shelter Deconstruction Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0110 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 13 – CONSTRUCTION ACTIVITY – EXISTING SHELTER DECONSTRUCTION
13.01 | Existing Shelter Deconstruction
13.01.01 | Inspection | The Contractor shall inspect the existing shelter and undertake investigation works necessary to ensure their methodology is suitable. | PS 23.1 | Report | Prior to Works | HP | ENG
13.01.02 | Methodology for deconstruction | The Contractor shall confirm their methodology for deconstruction at least 20 working days before work starts. | PS 23.1.6 | Methodology | 20 working days before work starts. | HP | ENG
13.01.03 | Heritage investigation of Rubble | The debris from the demolition shall be placed in a dedicated stockpile within the adjacent carpark area to allow further heritage investigation without impeding progress on the shelter demolition and construction. | PS 23.1.7 | Site Notes | During Works | R | PE

## 111 - ITP
Existing Plant Room Relocation Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0111 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 15 – CONSTRUCTION ACTIVITY – EXISTING PLANT ROOM RELOCATION
15.01 | Plant Room Relocation
15.01.01 | Foundation Preparation | The foundation preparation for the relocated passageway units shall comprise of 200mm minimum of compacted hardfill and 20mm nominal screed sand bedding and conform with the drawings | PS 26.2 | Site Records | Each Location | I | PE
15.01.02 | Connection details | The passageway units are temporarily connected with longitudinal RB32 bar in non-grouted Drossbach ducts formed in the precast units and anchored at the ends with RB32 flange nuts and washers. New longer RB32 galvanised bars shall be used to connect the passageway units together in their permanent location. The washer plates and flange nuts may be salvaged and reused from the temporary passageway. The permanent anchors shall have their ducts grouted with denso tape wrapped around the bars for 300mm each side of a joint between precast units. | PS 26.3 | Site Records | Each Connection | I | PE
15.01.03 | Waterproofing | The outside face of the joints between precast units shall be sealed with Sikablackseal-1 sealant, the face then waterproofed with 2 coats of Sika Black seal elastic liquid applied waterproofing membrane and the joint then further sealed with 150mm wide strip of Sika Multiseal tape | PS 26.4 | Site Records | Each Joint | I | PE
15.01.04 | Subsoil drains | Subsoil drains shall be provided along the base of each side of the relocated passageway units. These shall be installed at a level to drain away from the new avalanche shelter and shall connect into the subsoil drains constructed as part of the plant room construction. The subsoil drain detail is shown on the above referenced plant room drawings. | PS 26.5 | Site Records | Each Drain | I | PE
15.01.05 | New holes for future proofing ducts | Two holes shall be cored in the roof of the passageway unit closest to the new avalanche shelter to accommodate the two 100 diameter future proofing ducts shown on drawing C 291. The Contractor shall undertake a cover meter survey to confirm locations of existing reinforcement in the units prior to coring. The interface between the ducts and precast units shall be waterproofed using a detail agreed with the Engineer | PS 26.6 | Site Records | Each Hole | I | PE