## 116 - ITP
Roading Pavement - Subgrade to Basecourse Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0116
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 7 – CONSTRUCTION ACTIVITY – ROADING
7.01 | Subgrade and Undercut
7.01.01 | Bulk Fill Embankments | The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Bulk Fill Embankments 12%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered. | PS 17.2.1 PS 17.2.2 | Scala Results | 10m intervals along each lane or widening with a minimum of 5 tests | I | SE
7.01.02 | Insitu Cut | The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Insitu Cut 12%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered. | PS 17.2.1 PS 17.2.2 | Scala Results | 10m intervals along each lane or widening with a minimum of 5 tests | I | SE
7.01.03 | Insitu pavements | The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Insitu pavements 5%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered. | PS 17.2.1 PS 17.2.2 | Scala Results | 10m intervals along each lane or widening with a minimum of 5 tests | I | SE
7.01.04 | Unsealed Roads | The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Unsealed Roads 5%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered. | PS 17.2.1 PS 17.2.2 | Scala Results | 10m intervals along each lane or widening with a minimum of 5 tests | I | SE
7.02 | Subbase
7.02.01 | Overlay Sites Plateau Density Tests | The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC. | TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 | HP | ENG
7.02.02 | Sub-basecourse Pavement Layer Compaction | Mean Value ≥ 95 Minimum Value ≥ 92 | TNZ B/02: 2005-7.6 PS 17.3.4 | NDM Report | Min 5 Tests per lot 1000m2 max lot size | HP | ENG
7.02.03 | Sub-basecourse Layer thickness. | The Sub-basecourse shall be monitored for Layer thickness. | TNZ B/02:2005 -7.5 PS 17.3.4 | Survey / Level Checks | 1 test per 20m | W | SV / PE
7.02.04 | Material Placement | The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout | TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Continuous monitoring. | I | SV / PE
7.03 | Basecourse
7.03.01 | Overlay Sites Plateau Density Tests | The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC. | TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 | HP | ENG
7.03.02 | Basecourse Pavement Layer Compaction | Mean Value ≥ 98 Minimum Value ≥ 95 | TNZ B/02: 2005 - 7.6 | NDM Report | Min 5 Tests per lot 1000m2 max lot size | HP | ENG
7.03.03 | Basecourse Layer thickness. | The Basecourse shall be monitored for Layer thickness. | TNZ B/02: 2005 - 7.5 | Survey / Level Checks | 1 test per 20m | W | SV / PE
7.03.04 | Additional Rolling | Further to Clause 7.5 of TNZ B/2 if it is not possible to ensure that at least 1,000 vehicles pass evenly over each unsealed lane the Contractor shall allow for carrying out 30 passes evenly spread per lane of a 2 axle truck with the twin tyred rear axle loaded to 10 tonnes. | PS 17.4.5 | Site Records | Prior to sealing | W | PE
7.03.05 | Finished Surface Shape Approval | The Contractor shall agree details with the Engineer including the road profile of the semi-temporary surface, cross falls and temporary details at the kerbs to control drainage until the final surfacing is placed. | 17.8.1 | Approval | Prior to sealing | HP | ENG
7.03.06 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | TNZ B/02: 2005 - 7.7 PS 17.4.5 | Survey / Straight edge Report | Prior to sealing | HP | ENG
7.03.07 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | TNZ B/02: 2005 - 7.7 PS 17.4.5 | Survey | Prior to sealing | HP | ENG
7.03.08 | Running Course | If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface. | TNZ B/02: 2005 - 10.1 | Site Notes | Prior to sealing | S | SUP
7.03.09 | Benkelman beam tests | The Contractor shall record the deflections of the finished basecourse after compaction, but before sealing by Benkelman Beam Deflection testing in terms of TNZ T/1. Tests shall be performed at 10m intervals in each wheel track in both lanes. Test results shall be reported to the Engineer prior to sealing. (95 percentile = 0.8mm / Max = 1mm) | PS 17.5.1 PS 17.5.2 Table 17.5 | Beam Report | at 10m intervals in each wheel track in both lanes | HP | ENG
7.03.10 | Preselling Requirements | Degree of Saturation (DOS) requirements for this site are DOS less than 60% prior to seal with the preparation of the surface for sealing shall be in accordance with TNZ B/2 and TNZ P/3. | PS 17.6.2 PS 17.6.1 | Test Report | Prior to sealing | HP | ENG
7.03.11 | Surface Finish post sweeping | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | TNZ B/02: 2005 -7.8 PS 17.4.5 | Photos | Prior to sealing | HP | ENG
7.03.12 | Pre Sealing Notice | The Contractor shall give the Engineer 48 hours prior notice that the surface is ready for inspection and shall not undertake any surfacing until the surface preparation has been accepted by the Engineer. | 17.6.3 | Approval | 48 hours prior notice to sealing | HP | ENG

## 117 - ITP
Roading Surfacing - Chipseal Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0117
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 8 – CONSTRUCTION ACTIVITY – CHIPSEALING
8.01 | Chipsealing General
8.01.01 | Sealing Procedure | Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, P4, P17, and Q/1. | M/1, M/6, M/13, P/3, P4, P17, and Q/1. | Methodology / Construction Pack | Prior to Sealing | R | SE
8.01.02 | Seal Design / Binder application rate | The sealing design including binder application rate to suit the surface conditions shall be approved by the Design Engineer prior to sealing. | TNZ P3 TNZ P4 | Approved Seal Design | Prior to Sealing | HP | ENG
8.01.03 | Adhesion Agents | When used, Adhesion agents must be approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents. | TNZ M13 | Binder Aggregate Adhesion Test | Each Adhesion Agent & Dosage Rate for a Particular Chip Source | R | SE
8.01.04 | Sprayer Certification | The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc. | TNZ P3 TNZ P4 | E2 Cert | Each Sprayer | R | SE
8.02 | First Coat Sealing
8.02.01 | Preselling Requirements | The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%. | TNZ B02 | NDM Report | Min 5 Tests Per Lot 1000m2 Max Lot Size | HP | ENG
8.02.02 | PreSeal inspection | The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site. | TNZ P3 TNZ B02 | Hold Point Release | Prior to Sealing | W | ENG
8.02.03 | Spray Temperature | The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC. | TNZ P3 | Site Notes | Prior to Seal | I | SE
8.02.04 | Binder Sampling | A minimum of two samples per bitumen distributor load shall be taken. The first of these samples shall be taken at the end of the initial spray run and the other immediately before the final spray run. Bitumen to be tested on Engineers instruction. | TNZ P3 | Site Notes | Each Worksite | I | SE
8.02.05 | Quantity of Binder Sprayed | The quantity of binder sprayed in any spray run, measured by dipstick reading, shall not vary from the amount directed by more than 50 litres plus 4% of the amount directed. | TNZ P3 | Site Notes | Every Spray Run | I | SE
8.02.06 | Chip Application | All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying. | TNZ P3 | Site Notes | Every Spray Run | I | SE
8.02.07 | Surplus Chip Removal | Surplus chips shall be removed from the sealed surface prior to the removal of the temporary speed restriction signs. | TNZ P3 | Site Notes | 24 hours of Completion of any Section of Seal. | R | SE
8.02.08 | Post Seal Inspections | The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed. | TNZ P3 | Engineers Acceptance | Prior to TM Removal and After Final Sweeping | HP | ENG
8.02.09 | Chipseal Repairs | The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used. | TNZ P3 | Approved Repair Methodology | Prior to Repairs | HP | ENG
8.02.10 | NAASRA - Chipseal Surfacing | The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. No 20m reading in any lane shall exceed 70 NAASRA counts/km for chipseal surface. | PS 14.1.4.1 PS 17.7 NZTA M10:2020 - 10 | Test Report | Prior to sealing | HP | ENG

## 118 - ITP
Roading Surfacing - Asphalt Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0118
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 9 – CONSTRUCTION ACTIVITY – ASPHALT SURFACING
9.01 | Construction Activity - NZTA M10 - Specification for dense-graded asphaltic concrete
9.01.01 | Construction Trail | Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. Asphalt manufactured in the production trial can also be used in the construction trial if it meets the requirements of the specification. | NZTA M10:2020 - 7 | Test Results | As Required, two days before the site work is due to commence. | I | PE
9.01.02 | Paving Plan | The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement. | NZTA M10:2020 - 8, 9 | Construction Work Pack | 7 days prior to construction of the asphalt pavement. | HP | ENG
9.01.03 | Preparation of Area to be Paved | The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected. | NZTA M10:2020 - 9 | Site Notes | Pre Seal | I | PE
9.01.04 | Protection of Services | The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures | NZTA M10:2020 | Environmental Inspections | Daily | R | SE
9.01.05 | Ambient Conditions for Placing | Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, | NZTA M10:2020 | Site Notes | Pre Seal | H | SE
9.01.06 | Tack Coating | Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. | NZTA M10:2020 - 9 | Site Notes | Prior to Paving | I | PE
9.01.07 | Asphalt Production Conformance | Conforming Grading and Binder content by mass | NZTA M10:2020 -Table 3.1 & 5.1 | Test Results | 1 per 200T Min 3 tests per mix | I | PE
9.01.08 | Core Thickness | The layer thickness determined from measurements on the cores shall be -0 mm to +10 mm of the specified thickness | NZTA M10:2020 | Lab Report | min 8 per lot (day) (1 for every 300 m²) | R | SE
9.01.09 | Mat Density | 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot | ASTM D5361 NZTA M10:2020 - 9 | Cores | min 8 per lot (day) (1 for every 300 m²) | R | PE
9.01.10 | Joint Density | 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot | NZTA M10:2020 - 9 | Cores | min 3 per lot (day) (1 per 100 m of joint) | R | PE
9.01.11 | Density Testing | The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2 | NZTA M10:2020 - 9 | Lab Report | within 24 hours of them being cut from the pavement | I | PE
9.01.12 | NDM Density | NDMs are to be completed at the time of pacing to ensure compile when cores are taken | NZTA M10:2020 - 9 | IANZ Lab Report | min 8 per lot (day) | I | PE
9.01.13 | Transverse truth of the surface | The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge. | NZTA M10:2020 - 9 | Site Notes | Post Seal | I | SE
9.01.14 | Finished Pavement Level, Alignment, and Thickness | The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements. | NZTA M10:2020 - 10 | Survey | Continuous thought construction | I | SE
9.01.15 | NAASRA - Asphalt Surfacing | The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements as per TM7003. No 20m reading in any lane shall exceed 60 NAASRA counts/km for an asphaltic concrete surface. | PS 14.1.4.2 PS 17.7 NZTA M10:2020 - 10 TM7003 | Test Report | Prior to End of Defects | HP | ENG
9.01.16 | Skid Resistance | The surfacing shall meet the requirements specified in the Waka Kotahi Specification T10 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments. | PS 14.2 PS 17.7 | Test Report | Prior to End of Defects | HP | ENG

## 119 - ITP
Roading Furniture and Marking Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0119
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 7 – CONSTRUCTION ACTIVITY – ROADING
7.04 | Road marking
7.04.01 | Setting out the new road markings | Setting out the new road markings following resurfacing and Carrying out pavement marking within 48 hours of sealing. | PS 18.1 | Programme | within 48 hours of sealing. | HP | ENG
7.04.02 | Dry film thickness Inspection | The dry film thickness of each layer shall be as specified in Clause 13.1 of NZTA P/22. | PS 18.1.3.4 | Thickness Checks | During Painting | I | SE
7.05 | Traffic signs
7.05.01 | Sign Positions | The sign locations shown on the drawings are indicative only (New and Relocated). Actual positions will be fixed on site jointly between the Engineer and the Contractor. The Contractor shall supply all pegs, paint etc necessary to achieve this. This operation shall be carried out before the manufacture of the signs and their supports. | 18.2.4.1 | Survey | Prior to install | HP | ENG
7.05.02 | Relocated signs | All relocated signs shall be in the same condition as prior to uplift and relocation. | 18.2.5.2 | Condition Records | Prior to Relocation | I | SE
7.05.03 | Pre-Pour Inspection | Complete a comprehensive pre-pour inspection and obtain approval (Inspection or Verbal) from the Engineer prior to pouring. | PS 27.6.1 | Signed Pre-Pour | 24 hours prior to the casting of any unit | HP | ENG
7.05.04 | Delivery Dockets | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, admixtures and quality, mixing time, water added during batching and maximum aggregate size. | PS 27.7.11 PS 27.4.3.6 | Dockets / Bag Details | Each Pour | R | PE

## 120 - ITP
Road Opening Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0120
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 7 – CONSTRUCTION ACTIVITY – ROADING
7.06 | Road Opening
7.06.01 | Pre-Opening Safety Review | Prior to opening the Works for use by the general travelling public, a pre-opening safety review will be undertaken by the Engineer and the Principal’s Road Safety Audit team, to approve the removal of any temporary works, speed limits and traffic management. | PS 7.5.1 | Safety Review | Prior to opening the Works | HP | ENG
7.06.02 | Post Construction Safety Audit | Prior to the issue of Practical Completion, a post construction safety audit must be completed by the Engineer and the Principal’s Road Safety Audit team. | PS 7.5.2 | Safety Audit | Prior to the issue of Practical Completion | HP | ENG