## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | DS2676-DOW-ITP-CV-0001-Precast Unit (Pre, Post, Delivery) | itp |  |  |  | Yes | DS2676-DOW-ITP-CV-0001-Precast Unit (Pre, Post, Delivery) Rev B | 316e33fb-0f08-4df3-bed4-63699dc1b212
checkpoint-group |  |  | section | 5.01 Concrete Pour
checkpoint-status |  |  | checkpoint | General Details
label | 77cff223-d242-55bb-ae73-0de39b287700 |  | note | Verifying Document - Site Records
text | ca7a47e3-3987-549e-8dc1-e587c9281069 |  | textbox | Item Name
date | 3df081fd-7eec-52c4-b66f-2d02b6fdcce3 |  | date | Pre Pour Date
text | cb157378-b4ab-587d-8dac-0362e286a5e2 |  | textbox | Concrete Strength (mPa)
text | 29dc6c5a-d135-5fe1-8971-71abc2014969 |  | textbox | Volume (m3)
text | ac8849ed-3775-5152-a17e-4d0f9e4f438c |  | textbox | Mix Design
text | b00621ea-1408-5893-b576-6c5c89e3a254 |  | textbox | Additives
checkpoint-status |  |  | checkpoint | 5.01.01 - Reinforcement Pre Pour Inspection
label | 485b3c54-339b-5240-ab17-758a676045ad |  | note | Acceptance / Conformance Criteria - Complete a comprehensive Reinforcing inspetion including: Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Anchor embedmen, Steel coating, Bar Spacing, Cover, Steel condition / clean, Starter positions, Anchor position etc.
label | 2609f67f-ff11-58b1-ac15-71fc5064488f |  | note | Standard / Specification - PS 27.7.10
label | 3c4f6831-55b1-570b-8c16-7242e227a7e4 |  | note | Verifying Document - Site Records
label | 15583a32-bbf6-5b31-8d06-b06529820fe6 |  | note | Frequency - Each Pour
label | 3f787f14-06ec-5d58-b5b1-0e6cd44fc3f6 |  | note | Activity - R
label | 2f525a81-843f-5cca-a50a-1673a9f1feb2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | Formwork has been checked and conforms to the drawings included:
label | ec750cd7-9ecd-5ac0-a1af-d2916fb3678b |  | note | Acceptance / Conformance Criteria - Overall location, Straightness , Bracing & supports , Grout tightness , Cleanliness , Surface finish, Construction joints (position and preparation), Rebate , Contraction joints , Penetrations , Plan dimensions , Formwork oiled , Pour thickness , Angle fillet , Diagonals , Divi nuts tight etc.
label | 0658bb95-4267-536b-8a6d-4bd34898ce1f |  | note | Verifying Document - Site Records
checkpoint-status |  |  | checkpoint | 5.01.02 - Pre-Pour Inspection
label | a09a12e8-6c76-56b3-8e75-b28b93b726d3 |  | note | Acceptance / Conformance Criteria - Complete a comprehensive pre-pour inspection and obtain approval (Inspection or Verbal) from the Engineer prior to pouring. Sign as WP when WSP not inspecting unit and note in comments.
label | 66744cc2-0a83-58e0-bbe3-0042941b4aa9 |  | note | Standard / Specification - PS 27.6.1
label | 5958ee2a-6a33-5934-b02a-afa41d3282c7 |  | note | Verifying Document - Signed Pre-Pour
label | cec3a5fa-d936-5a38-ba39-b47d2617c4a1 |  | note | Frequency - 24 hours’ Notice prior to the casting of any unit
label | 705aa9ff-bf31-535b-afef-ad5b3b4d193e |  | note | Activity - HP / W
label | 81b274eb-d23a-580c-9dba-c8de1ce13614 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Items to be rectified prior to pour
checkpoint-status |  |  | checkpoint | 5.01.03 - Delivery Dockets
label | 8f70f2ce-a9de-5759-905c-6a155eaf1b4e |  | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | 6a744022-b76a-579a-a698-db81be7872f0 |  | note | Standard / Specification - PS 27.7.11
label | a7e20c2e-3f3a-5d16-99db-e38e77cdbb9b |  | note | Verifying Document - Dockets
label | 9d36dd0d-8551-5b58-a5c7-1b54e63dd074 |  | note | Frequency - Each Pour
label | cde6a9fe-08a6-54a0-bf97-f63f0b2efa27 |  | note | Activity - R
label | c70e8390-68a0-59ec-b170-0d381b90c6e3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.01.04 - Slump Testing
label | 2a91eda7-03f5-522d-b7ab-b2db82b9d0f8 |  | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor. Slump that that exceeds the tolerance limit in NZS 3109 cl 9.4.2 shall be liable to rejection.
label | dee41927-3272-5f36-9130-d67ddabbddcf |  | note | Standard / Specification - PS 27.4.4.4
label | f365ce8a-47f0-5488-9867-9178d2c1b20d |  | note | Verifying Document - Site Records
label | 13f53ce7-b82b-56f8-a4f2-481d51f5ac55 |  | note | Frequency - Each Pour
label | ff9dbeed-f857-500f-a7b4-a560ddcdb021 |  | note | Activity - R
label | 6619f7d1-2281-56d5-a515-c8ffd63bf281 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.01.05 - Compression Testing
label | 8022ef4f-8008-5b64-96f6-267f86b2ae2e |  | note | Acceptance / Conformance Criteria - For repetitive small pours undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 day compressive strength in an approved laboratory.
label | cd997cee-0c0b-5815-bab2-d469935926b5 |  | note | Standard / Specification - PS 27.4.4.3
label | d00d0c69-c52b-5150-b946-e6c6f6e8f21f |  | note | Verifying Document - Test Results
label | abb587bf-5956-5b7b-86db-aeeb2cf68275 |  | note | Frequency - First five pours of any one type, and thereafter shall be made for every fifth pour of that type
label | 2fa03885-97be-521a-8d18-e72b9e8dcfcc |  | note | Activity - R
label | 6b7639de-01a2-5165-88ff-38c37c0e64cd |  | note | By - PE
label | 82c350f8-991a-561e-87b9-c858bad2a7d1 |  | note | Comments / Closeout Details - Four Cylinders if one is needed at 7 days
checkpoint-status |  |  | checkpoint | 5.01.06 - Precast Prestressed Accelerated Concrete Compression Test
label | d5b38b2b-f241-50eb-b11b-ea3c8a9ef389 |  | note | Acceptance / Conformance Criteria - Compression test cylinders, for precast prestressed units subject to accelerated curing by applying heat to the concrete, shall be cast in moulds preheated to the same temperature as the main moulds. After casting the test cylinders shall be placed in a heated enclosure monitored and controlled such that the test cylinder concrete follows the same time - temperature curve as that of the precast units.
label | c507f024-e933-558e-9b58-ffcab1824ec0 |  | note | Standard / Specification - PS 27.4.4.8.2
label | e25f4a61-d2e4-5824-b4ca-6215fbdd6379 |  | note | Verifying Document - Test Results
label | d91b62e0-0bad-5edd-8e93-4d66acfb7f97 |  | note | Frequency - Each Occurrence
label | 1a050cad-d8aa-5b24-9fef-180465b46be3 |  | note | Activity - R
label | 72fd4b4d-00f9-510f-8659-ae12f6394d10 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.01.07 - Air Content Tests for Air Entrained Concrete
label | 4dbd0d93-e408-5c83-8919-1037f2bfcf56 |  | note | Acceptance / Conformance Criteria - Where air content tests for air entrained concrete is required by this specification, unless otherwise directed by the Engineer, each day during the manufacture and placing of concrete, for each 50m3 of concrete or part thereof produced, one sample shall be taken and subjected to air content testing in accordance with section 9 of NZS 3112: Part 1. All Air Entrained concreted to be tested, as per Table 27.2
label | 69cea7f5-3736-5c3d-b1e4-79ebd4dfc74c |  | note | Standard / Specification - PS 27.4.4.7
label | b308c54e-f396-51b4-901f-94ad24a530f7 |  | note | Verifying Document - Test Results
label | 74ad37cc-d215-5e6b-aab1-e14ef7e87ae7 |  | note | Frequency - Each day, one Set per 50m3 (or part thereof) for each mix placed.
label | 94caf86e-bbda-5339-80d6-8ec234e8b0b0 |  | note | Activity - R
label | b79d5081-29db-5547-9b1f-03f399cdead2 |  | note | By - PE
checkpoint-group |  |  | section | 5.02 Post Pour
checkpoint-status |  |  | checkpoint | 5.02.01 - Post Pour Inspection
label | 7acfd6b7-9f62-5e7d-b182-3d3b217260af |  | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, Inserts, Reliefs, Curing, membrane application, and Finish against the drawings.
label | efb2cde7-139b-5c2a-b20e-0b247008eefe |  | note | Standard / Specification - PS 27.6.6.14
label | 1e4a0c68-91bc-5110-bdc1-adccf0453f25 |  | note | Verifying Document - Site Records
label | 190e92f1-46ca-56ef-9a23-ab385f00985c |  | note | Frequency - Each Pour Prior to delviery
label | 3bfb16de-dfa8-5f3f-9b1b-d740f5807d25 |  | note | Activity - R
label | e67b3a53-dd14-553a-ae9b-53f501182642 |  | note | By - PE
checkpoint-status |  |  | checkpoint | Items to be rectified
checkpoint-status |  |  | checkpoint | 5.02.02 - Membrane Curing
label | 692ea41a-e184-51e9-8137-cfac8d03b384 |  | note | Acceptance / Conformance Criteria - The Curing Membrane shall be applied as per the methodology with the approval of the Engineer.
label | 129c59fe-4c8a-5a0d-a55f-076b09100b3d |  | note | Standard / Specification - PS 27.4.8.2
label | 90081544-d0ff-59c7-867d-9638daf87b32 |  | note | Verifying Document - Site Records
label | 337ce60a-9bd1-5b7f-a25f-dc16236b45c8 |  | note | Frequency - Each Occurrence
label | ca11d02d-647e-5d0f-b7c8-c704a6fd30a8 |  | note | Activity - R
label | 968d98b9-b100-585e-afe1-9df8146e88ec |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.02.03 - Stripping and Lifting
label | 5fdeb78c-499b-50d5-a96d-6c47ca8f98c9 |  | note | Acceptance / Conformance Criteria - No formwork shall be stripped or the panel lifted until the minimum strength has been reached as per the drawings and methodology. Alternativly an approved curing time can be used
label | d2eef46c-955b-504c-bc32-8a6f8c853d59 |  | note | Standard / Specification - PS 27.4.4.8.1
label | 271bc28b-7d7b-51bf-9ab3-97e88a29b8aa |  | note | Verifying Document - Schmitt Hammer or Apporved Curing Time
label | 65345801-25b7-5ecc-bb1e-0fd723673ff4 |  | note | Frequency - Prior to Stripping and Lifting
label | e668d855-6bb1-590d-91c0-1ce6482a32fc |  | note | Activity - R
label | 2cf02ce7-6f94-5167-b461-af4620a38dc7 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.02.04 - Defective Concrete Finishes
label | 434ea9da-a8df-5aa3-befa-9fa239adddcf |  | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | 85507041-830f-589e-ac22-f6c124a3857e |  | note | Standard / Specification - PS27.4.9.1 / NZS 3114
label | 18061b5e-a4e4-5227-b572-b339073c02ed |  | note | Verifying Document - NCR
label | a2b52269-8b47-5fad-8847-92326d1e3c3b |  | note | Frequency - Prior to non Minor Repair
label | 4ebc1cf0-c8b1-5b62-8664-20767cbd16e9 |  | note | Activity - HP
label | 8ce44183-2c41-5a9f-9b44-2edf32a9438e |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | McIntosh Precast QA
label | f2c35c11-dcf1-50cf-a4dd-ba11ab53b631 |  | note | Acceptance / Conformance Criteria - Attach McIntosh Precast QA
label | c05c4328-2133-5329-8575-7e73cf78dab8 |  | note | Activity - R
label | aa2685b0-fca3-506e-9224-c4865beea041 |  | note | By - PE
checkpoint-group |  |  | section | 5.04 Delivery
checkpoint-status |  |  | checkpoint | 5.04.01 - Delivery Inspection
label | 037ce71a-6693-5b1f-a241-88c40b0d4dec |  | note | Acceptance / Conformance Criteria - Following delivery, each precast item shall be inspected for conformance and delivery damage.
label | 31bfab36-ada2-5864-b615-c1ee3d79b14c |  | note | Standard / Specification - PS 27.6.6.14
label | a4818edc-94cd-5202-b274-01e4c931c801 |  | note | Verifying Document - Delivery Record
label | cd5123d9-0dbf-5885-8d1f-abc7fb5d064d |  | note | Frequency - Each Delivery
label | 9eaf30ce-db22-5a00-98d2-24b6bc00cb0a |  | note | Activity - R
label | 9cb47f33-88ba-51bc-91c4-e61f90e8cff6 |  | note | By - PE
checkpoint-status |  |  | checkpoint | Items to be rectified
checklist-sectioned |  |  | checklist | DS2676-DOW-ITP-CV-0001-Precast Vapour Blasting | itp |  |  |  | Yes | DS2676-DOW-ITP-CV-0001-Precast Vapour Blasting Rev B | 9a80a806-5888-407b-9022-fc1ca625b1e7
checkpoint-group |  |  | section | 5.03 Urban design feature on fascia panel
checkpoint-status |  |  | checkpoint | 5.03.01 - Vapour Blasting Method Statement
label | 9bc68ee2-b1df-5bee-bc3c-c6d8f2c78737 |  | note | Acceptance / Conformance Criteria - Contractor to provide method statement and shop drawings to landscape architect, cultural artist and Engineer for approval prior to commencing work
label | 9b260c46-1802-5427-8c97-e6ecbaebbbe1 |  | note | Standard / Specification - PS 21.7.2.1
label | 23b4f60b-7f68-523d-850d-cb1ad2e53303 |  | note | Verifying Document - Methodology
label | fecb09a8-5029-52d3-9587-38988d07cf29 |  | note | Frequency - Prior to Commencing Work
label | 687c6db1-d3c4-59a3-9558-02e20b7404d0 |  | note | Activity - HP
label | d3e7d71e-b865-5d58-9c56-526c1406e676 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.03.02 - Blasting depth
label | f66a1a4d-d7d4-59c0-ab4d-c77ec134b9e2 |  | note | Acceptance / Conformance Criteria - Blasting depth not to exceed 5mm in order to avoid compromising reinforcing cover.
label | 276263a8-eaf5-53c6-ba03-7854076622c0 |  | note | Standard / Specification - PS 21.7.2.1
label | 8a71ffe8-4e6d-59bd-9cba-34a31571197d |  | note | Verifying Document - Site Records
label | e427ef6c-4a27-54fd-9d17-82fe3c28477b |  | note | Frequency - Each Panel
label | caaf7bed-d859-511f-a331-4e62cd786869 |  | note | Activity - R
label | 2e470bb7-6bbe-5260-b3e6-e2093e1977f3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.03.03 - Permacolour Application
label | 351ea8ce-83b2-5448-8a7a-65362d07e721 |  | note | Acceptance / Conformance Criteria - Vapour blasted area to have permacolour clear concrete sealer or approved alternative applied within the blasted area only.
label | d7e3df16-9329-5404-8a4f-aa5df595b6c1 |  | note | Standard / Specification - PS 21.7.2.1
label | 2b3b2f3e-540f-502d-bcb3-6cb9df531eb5 |  | note | Verifying Document - Site Records
label | 1744cc78-cac1-580f-900f-6825e128f8ae |  | note | Frequency - Prior to sealing
label | 8f991e8e-b965-5664-bd67-7f7bf8f6c668 |  | note | Activity - R
label | e1ab1761-dcc3-5fec-8ade-babc06ed0865 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.03.04 - Panel Cleaning
label | 30212631-ed4b-5802-8c53-6dc477e8529e |  | note | Acceptance / Conformance Criteria - Prior to sealing of pattern and application of anti-graffiti coating, blasted areas are to be cleared of blasting agent before sealants applied, surface to be washed and free of marks.
label | e7b02489-a152-513d-9520-e39161cb5412 |  | note | Standard / Specification - PS 21.7.2.1
label | 067eaf14-f13b-52c0-8748-4db6b51335b8 |  | note | Verifying Document - Site Records
label | 80abbcaf-195b-5436-9b51-e579fae04737 |  | note | Frequency - Prior to sealing
label | 9f8e7f76-e25c-5204-8aca-801f51a3bdc7 |  | note | Activity - R
label | 5f58cfa2-1e9c-577b-bfe7-739dfe9aa3d5 |  | note | By - PE
checklist-sectioned |  |  | checklist | DS2676-DOW-ITP-CV-0001-Precast Concrete Materials | itp |  |  |  | Yes | DS2676-DOW-ITP-CV-0001-Precast Concrete Materials Rev B | dea2c948-063e-4235-a320-1bbefbdfada8
checkpoint-group |  |  | section | 4.01 Concrete Materials and Approvals
checkpoint-status |  |  | checkpoint | 4.01.01 - Shop Drawing Tolerances
label | 1bdde67f-944e-5ba8-9611-6e485b806429 |  | note | Acceptance / Conformance Criteria - The Contractor shall check all tolerances and clearances between precast elements to ensure a satisfactory fit between all elements and shall notify the Engineer of any locations where tolerances or clearances need to be increased to ensure satisfactory construction procedures.
label | a8309323-0195-51cd-8a08-9376944793ab |  | note | Standard / Specification - PS 27.6.6.2
label | ba3abdb4-4721-5dec-aeb5-380e4ba7c138 |  | note | Verifying Document - Shop Drawings
label | 7d75ce02-5f81-503a-9f73-379eaa748c1e |  | note | Frequency - Prior to Submission to the Engineer
label | 6cd28686-2c79-5171-8b30-c3f5fbcb6896 |  | note | Activity - R
label | 38feaf39-212b-5ffe-928f-a25287acd0fd |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.02 - Shop Drawings
label | d97dd165-e1a4-55b8-906a-e5884f06f170 |  | note | Acceptance / Conformance Criteria - The Contractor shall make available the shop drawings to the Engineer for review, at least 14 days prior to manufacture. Acceptance of the drawings must be obtained from the Engineer prior to the units being cast.
label | 786dd059-c802-53f8-9be6-f098c1f7769b |  | note | Standard / Specification - PS 27.6.6.2
label | 29eaf4f0-7f39-5e83-90db-c5bf8ec13e49 |  | note | Verifying Document - Shop Drawings
label | 02366582-73c4-5f15-b17f-7e650a04bd93 |  | note | Frequency - At least 14 days prior to manufacture.
label | 59b4f601-88bc-51eb-8bb0-e9485aee8b5a |  | note | Activity - HP
label | 470b9894-94d4-5259-beb0-eba4466263f6 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.03 - Lifting Design
label | aee3c65e-6191-5fd6-a0aa-b42f1cf6c62d |  | note | Acceptance / Conformance Criteria - The lifting design specifying the lifting eyes shall be incorporated into the fabrication drawings.
label | 395e47a5-079b-52fb-9f06-98f00ba7e89b |  | note | Standard / Specification - PS 27.6.6.17
label | 19daf731-24b8-5a41-9c9b-3a0c0f051b5b |  | note | Verifying Document - Datasheets
label | 972d90fe-00a4-568d-ab6c-ca7b266e425c |  | note | Frequency - With Shop Drawings
label | 00b701de-65f8-59af-a124-08570fdbdff7 |  | note | Activity - HP
label | a5ef0b19-1d25-5314-9fa8-ebbdbe9b817a |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.04 - Concrete Plant
label | 73e5a699-62b9-5da2-a8d8-ae1fb86adb82 |  | note | Acceptance / Conformance Criteria - The Concrete Plant shall have a Current Certificate of Audit
label | 12b51cbb-34eb-5223-a683-5c33c51aec11 |  | note | Standard / Specification - PS 27.4.1
label | 98d7b93e-367b-5195-9881-83be29744a60 |  | note | Verifying Document - Certificate of Audit to NZS 3104:2003
label | 8dac4525-4f4d-5ae0-a9b7-2d33700df8a6 |  | note | Frequency - With Mix Design and Upon Revalidation
label | 1714e0cf-fc70-5a82-8318-1d636c4ad527 |  | note | Activity - HP
label | a11f511a-3528-5b5b-8e18-24544b48f0b3 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.05 - Concrete Aggregate Reactivity Testing
label | 567ae82b-12b0-5a19-9402-7dda88e230ca |  | note | Acceptance / Conformance Criteria - When required, the Concrete producer is to confirm the proposed aggregates are non-reactive as defined in clause 6.1 of CCANZ TR3.
label | 5c78e8e6-3f08-50b9-a70f-80629240ae7c |  | note | Standard / Specification - PS 27.4.2.3
label | e24c8c7a-8af4-5ff2-8130-8770c7000ae2 |  | note | Verifying Document - Supplier Statement
label | ff488367-7d6f-53be-993b-63324fcba62f |  | note | Frequency - With Mix Designs Submissions
label | fe002878-dbea-5215-91c4-3486b3c1f869 |  | note | Activity - HP
label | 09d7cea2-583e-5557-ba7d-94ff709d2c1e |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.06 - Precast Columns Concrete Mix Design
label | f16f2005-271d-52e6-8a03-094b3761a97d |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | aa4285aa-adc0-59c6-aaf4-0187b78420a1 |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | ae0fcd82-6785-53f0-ae02-5c94a2019b3d |  | note | Verifying Document - Concrete supplier mix designs
label | f52ab44b-8197-558f-9326-b853d0e94c9e |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | 1b7e1cb4-95bf-5396-9477-194bbfbf51f7 |  | note | Activity - HP
label | d4971903-7e69-56ee-88ce-6d8b12faef0e |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.07 - Precast wall Concrete Mix Design
label | ff4a3c6b-18f2-5a63-88ec-dc8eb5567d29 |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | 61431285-2405-57ea-be01-3b24c78286a1 |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | 002c49d9-8334-59be-9e7a-17b2e438fd28 |  | note | Verifying Document - Concrete supplier mix designs
label | bc0e877e-e6ec-5649-b194-9cf9105dcaf5 |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | 0ea96325-5386-5992-bd10-b95687d9b0b8 |  | note | Activity - HP
label | 008060bd-054f-543d-a67d-dfceb1d5d227 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.08 - Link Slab Concrete Mix Design
label | a9e27d9f-515d-528d-a6ec-256e005c0900 |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | e82a70ea-20a8-55fd-8a1c-a581ea620e6f |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | 1d97ab26-c060-57b0-8ddd-de31df708d82 |  | note | Verifying Document - Concrete supplier mix designs
label | 6b8b4fda-b41c-5198-a451-bf5d202a3116 |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | 7e66971f-1dad-5211-b81f-8d102bf54b46 |  | note | Activity - HP
label | 4b4b5d67-bede-53d8-ba9d-15ba307914f5 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.09 - Footing Concrete Mix Design
label | 6fa5924d-5b2e-5f1d-a051-c11da0efb2cc |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | e392fc09-4fe6-5933-adea-a742ff232008 |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | 41a8abc4-e87b-5b50-833c-03df808a40f8 |  | note | Verifying Document - Concrete supplier mix designs
label | 904fb709-eba1-58dc-aa5a-5eb45ef755ac |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | 5fe5601c-8488-5200-98f1-f04ac9ccb6cd |  | note | Activity - HP
label | b60802cb-10b6-5309-8841-6244f4553d51 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.10 - Footing Shear Key Concrete Mix Design
label | bb387e9c-abff-55d4-8665-112c45ac0f24 |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | f6f39ce5-ab1a-587e-9ccd-b6f319db3d3b |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | 8841b5e8-1ccd-5bd2-bf72-28c56b377882 |  | note | Verifying Document - Concrete supplier mix designs
label | dbd067a6-87d6-500a-8f0e-70227d3a974f |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | 2839012b-79de-5ee1-bb18-b80b582d49d3 |  | note | Activity - HP
label | e5acb83e-0ef4-51b9-b941-2efd7b9f6a2f |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.11 - Precast Hollow Core Roof Beams Concrete Mix Design
label | c21ed679-6714-5347-9986-f4f3e5c6937f |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | 4e841a16-8766-58a1-8bac-4a9498cf2324 |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | 3766a350-b77e-5c92-8c45-3966571edddd |  | note | Verifying Document - Concrete supplier mix designs
label | 918567be-4061-5ab3-91bf-4957b0bf64cc |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | d25a37e0-dc19-5131-9ffc-864645b10323 |  | note | Activity - HP
label | 339b9b5d-b663-5840-a6c4-60301de502b7 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.12 - Precast Torsion Beam Concrete Mix Design
label | c54b2d36-e8b6-59b7-acd1-ee22bd5f0c73 |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | fded60bb-3e3c-54c2-a65e-1406b9edf1b8 |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | c99d205b-754a-5237-abf8-9923b6ad2ec1 |  | note | Verifying Document - Concrete supplier mix designs
label | 2de04961-dfe0-5508-9845-c6c73c64496a |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | d0ba85bd-e3bf-53a6-af0b-cdf367fb22c1 |  | note | Activity - HP
label | 046fe8d0-fdc3-52c2-89ee-471925f394bf |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.13 - MSE Approach Wall Panels Concrete Mix Design
label | 336450a5-a6a5-573e-a753-6ecc9fe29f4f |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | b4984d18-557d-5932-986e-29614397929d |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | 5e5574d8-9adf-5d55-855a-af51d4b52683 |  | note | Verifying Document - Concrete supplier mix designs
label | 325f7917-1d9c-526f-9880-d34a11ae01bb |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | aa81dddc-4b27-5341-b572-c087937eb318 |  | note | Activity - HP
label | 16840c5b-59ab-58e9-a21f-34fa19e907fb |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.14 - Precast Facia Panels and Precast Upper Retaining Wall Concrete Mix Design
label | 0d37c67b-91c3-59cd-b1cd-de08d583ae01 |  | note | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | bcc2dc20-0aff-533c-b2a0-238530aa68ca |  | note | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | c79e99c9-c233-5e4d-9ba8-39a11ca7b71b |  | note | Verifying Document - Concrete supplier mix designs
label | 11ccd2ae-6c99-53b5-9ca8-aa0a874976b3 |  | note | Frequency - Submitted least 14 days in advance of concrete supply
label | bc52391b-3971-5993-9e80-5cc4d568e0d8 |  | note | Activity - HP
label | c26d5436-778a-5e41-858c-64297adf5337 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.15 - Reinforcement Supplier
label | c8c9cdad-aa2d-5172-bd45-477a625946ab |  | note | Acceptance / Conformance Criteria - The contractor shall provide the name of reinforcement supplier before delivering any reinforcement
label | ec59f4e1-9cd5-5b2a-b870-8f58d83c8adf |  | note | Standard / Specification - PS 27.7
label | 38d800f3-5b0d-51e1-b327-847d467d4df0 |  | note | Verifying Document - Supplier Details
label | 0399cba5-c621-5637-8df6-ef8d51a05943 |  | note | Frequency - Before delivering any reinforcement
label | 1c7adf98-7372-5ee0-9e28-297575c1a433 |  | note | Activity - R
label | e6d1894b-e605-5053-a00a-fb00d05ec312 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.16 - Reinforcement
label | bd0d2193-ea57-551c-89d5-31cc07ddc4d4 |  | note | Acceptance / Conformance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001. Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of any work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
label | 87b1af61-5da5-5398-b9b9-c4ad9d06943e |  | note | Standard / Specification - PS 27.7.1 / 27.7.9
label | 15f3c1f1-d775-5f37-b865-06b5db1d89a6 |  | note | Verifying Document - Mill Certs
label | 868ead7e-73c0-55db-94c2-db80f0cbb66c |  | note | Frequency - At least one week before incorporating these materials.
label | 3e98eb3a-997c-5742-9bd9-1964862b8ca5 |  | note | Activity - R
label | 120c4abc-808b-5e19-9dee-4d80faba8e33 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.17 - Bar Bending Schedules
label | 8ea80c59-d997-5006-88fb-961c05c1f972 |  | note | Acceptance / Conformance Criteria - The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars.
label | f933285a-7466-5d86-a30b-945ff1f0ed68 |  | note | Standard / Specification - PS 27.7.8
label | c52bcf35-083d-54a9-86b4-6a711d6fe69e |  | note | Verifying Document - Bar Bending Schedules
label | e410b689-e6cc-5054-9af7-b6c5302abe61 |  | note | Frequency - At least 14 days before the start of placing the corresponding reinforcing bars.
label | c81a25e9-360d-58ce-aea1-f3c0ef45d13a |  | note | Activity - HP
label | 6c8123ae-e28f-53e8-a936-8a9c09b10de0 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.18 - ITP Inspector approval
label | ff3e635f-f91a-5893-b63f-ecdff3a8224c |  | note | Acceptance / Conformance Criteria - The Contractor shall supply the details of the proposed Third Party Inspector to the engineer prior to welding
label | 64712f2a-7337-595c-ba5d-13721553597a |  | note | Standard / Specification - PS 27.7.6
label | f9e5ba8c-a1c8-5986-9158-2bf5f7e76fe1 |  | note | Verifying Document - TPI Details and Qualifications
label | f9a0725a-de92-5a83-a98a-bb589236d95a |  | note | Frequency - Prior to Welding
label | 70d1062d-7b39-517a-9e0e-ac883c79db0a |  | note | Activity - HP
label | 614f7b33-ccc9-5c6a-b6b6-9d282e2746ee |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.19 - Welding of Reinforcement
label | 73bcf316-1596-5567-9c6f-8cc0477b0ba3 |  | note | Acceptance / Conformance Criteria - The welding shall be inspected by the Contractor’s Third Party Inspector who shall meet the “Qualifications of Inspectors” requirements of AS/NZS 1554.3 Clause 10.2. Inspections of the welding shall be in accordance with AS/NZS 1554.3.
label | ee30a850-0e69-5625-9e5f-cc5cfdca889a |  | note | Standard / Specification - PS 27.7.6
label | 5800fcb0-3cf8-58b9-961a-77684cc92f7b |  | note | Verifying Document - TPI Report
label | 8abf23b8-d105-513a-8c42-3f23bce34fa3 |  | note | Frequency - Prior to be encased. 100% Visual, 10% Ultrasonic, and 10% of Fillet by Magnetic.
label | edc0c86e-fba4-5383-9bc3-faec1fd91ad1 |  | note | Activity - HP
label | 1735f94c-fae3-5cb0-b436-312a0926be7b |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.20 - Mechanical couplers and anchors in reinforced concrete
label | 1b6bc696-9512-5c6a-9fda-8f5f15d87b88 |  | note | Acceptance / Conformance Criteria - Mechanical couplers and anchors for the jointing of reinforcing steel shall satisfy the requirements of NZS 3101 clauses 8.7.5 and 8.9.1.3, and ISO 15835-1 Steels for the reinforcement of concrete. Only steel Reidbar components meeting the above requirements shall be accepted.
label | 0a5471c2-9f84-5fe8-a115-cfd906cdbf1e |  | note | Standard / Specification - PS 27.7.12.1
label | bea6fa30-ac62-5c0c-b9c5-8ab34ec9c676 |  | note | Verifying Document - System Certification or Batch Verification.
label | 4c703b78-bc0c-5a3d-b6a4-164523d43041 |  | note | Frequency - Prior to use
label | 4a7c329c-a69b-5575-ab29-1782dd2cb78d |  | note | Activity - R
label | 79db27a3-9b1e-5346-8a35-9679adc5661b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.21 - Fibre Reinforcement
label | fecb47bb-a593-5a93-b953-1c004325e0d6 |  | note | Acceptance / Conformance Criteria - The following proprietary fibres and doses shall be used:
label | 806fcde2-b86b-5679-9433-ccd2bc165167 |  | note | ○ iNFORCE Microforce19 polypropolene fibres – 1.8 kg/m3
label | d8dee470-fb7f-598c-afd9-58fd6dbb8273 |  | note | ○ iNFORCE Ultrafiber500 cellulose fibres – 1.8 kg/m3
label | bd48487d-9cc5-5446-af67-091c76d24148 |  | note | Standard / Specification - PS 21.7.4
label | e3bfe745-6398-5100-9451-3f3c994ed6d6 |  | note | Verifying Document - Datasheets
label | c8dc102e-5408-58f9-9010-7ef2e7116998 |  | note | Frequency - With Mix Designs Submissions
label | 73bc56fd-2d2e-5697-a340-974e42be9425 |  | note | Activity - R
label | d44f853a-e868-56cb-b26a-49455f1c9898 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.22 - Void Formers
label | 9e8627e7-2b1e-5838-81c6-abd60d39106c |  | note | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer details of the proposed method of forming the voids, including the method of securing the formers in position.
label | d4d23b15-cced-5a74-bda7-f5b655fb15bd |  | note | Standard / Specification - PS 27.5.3.7
label | 9573be6b-60f1-5933-998a-31df4770c0ac |  | note | Verifying Document - Datasheet and Method
label | c8dfcf16-0238-57e0-a5ea-a8120d75ad75 |  | note | Frequency - Prior to Pour
label | 13703a87-b291-530b-9264-c652fdb1d314 |  | note | Activity - HP
label | 32b36257-58da-5208-acd3-c0f94cdba131 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.23 - Permeant Formwork Certification (Void Formers)
label | d1577d91-6796-5296-bb26-0a9c58c4cda3 |  | note | Acceptance / Conformance Criteria - Design details, construction drawings and a formwork certificate (PF-T-442) shall be supplied to the Engineer prior to the formwork assembly and at least 14 days prior to concreting of the component, for review, for all permanent formwork proposed to be used.
label | 9f5c5d14-6b5d-5bea-9b49-1561cd98700d |  | note | Standard / Specification - PS 27.5.3.5
label | 4f1b83b5-40b0-5fc1-9c2a-6fec07a157e6 |  | note | Verifying Document - PF-T-442 Certificate
label | 067a44da-1031-5799-a180-95c4e3854385 |  | note | Frequency - Prior to Pour
label | c8498e6b-bbcb-553a-ba0c-cbbedc41b880 |  | note | Activity - HP
label | 17660396-ab9d-5182-b0a0-9ccef3eef3e4 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.02 Methodology
checkpoint-status |  |  | checkpoint | 4.02.01 - Precast Methodology Submissions
label | d0378f4a-9200-592d-b8a9-444ba4863f84 |  | note | Acceptance / Conformance Criteria - Details of the proposed method of casting, curing, storing, transportation, and erection shall be submitted to the Engineer before commencing manufacture of the mould and precast units.
label | 92101442-dd72-5a96-becc-1b0ba7e5a2fb |  | note | Standard / Specification - PS 27.6.1, PS 27.6.6.7, PS 21.5.3
label | 459a2e9a-d9c0-5bf5-a37d-2fad15d37786 |  | note | Verifying Document - Methodology and Programme
label | 4d66e850-64c1-5c64-ac20-f2a438995181 |  | note | Frequency - Prior to Precast
label | efe2b2c7-ae1e-5a33-88dd-14569024ca19 |  | note | Activity - HP
label | a7830c41-181e-5dc7-93b2-3d60c77b4347 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.03 Precast Test Pannels
checkpoint-status |  |  | checkpoint | 4.03.01 - Precast Test Panels
label | 82b1c3db-998f-5419-9ddf-cf4d811db475 |  | note | Acceptance / Conformance Criteria - The Contractor shall prepare precast test panels for:
label | 3bd81546-2539-55db-ad42-a12083fc5a51 |  | note | 1. Fascia with sandblasted design, tinted concrete and fibre reinforcement
label | d3bbf3c2-e06e-57ff-8e00-70778137572a |  | note | 2. Column with tinted concrete and fibre reinforcement
label | 90f72244-761e-578f-8ec0-c5a92ce99570 |  | note | 3. MSE Wall
label | 73092b01-ce2a-56db-a183-1681baadd322 |  | note | Standard / Specification - PS 21.5.1.1, PS 22.16.5
label | 27d0ec7c-fbce-54ac-a2bf-8db35212b325 |  | note | Verifying Document - Test Panel Approval
label | bea8e149-efc0-561b-a875-89fea42fe273 |  | note | Frequency - Prior to the commencement of the permanent work
label | fafa4ebf-519b-59b1-bce5-7fd23b38c3c3 |  | note | Activity - HP
label | 93509a07-8be9-53da-97bf-2f553a63f672 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.04 Precast Vapour Blasting Materials
checkpoint-status |  |  | checkpoint | 4.04.01 - Precast Vapour Blasting Test Panel
label | f277abb1-9523-539d-b3cb-556fac00eb82 |  | note | Acceptance / Conformance Criteria - A 1.8x1.8m test panel is to be produced for landscape architect and cultural artist approval prior to construction.
label | c7987d26-25eb-5c47-ace5-5c20bca2a625 |  | note | Standard / Specification - PS 21.7.2.1
label | 07a06778-8c83-5300-a9a2-27effb7cebaa |  | note | Verifying Document - Notice
label | 2cca08c3-4175-5cd9-a757-c77cb15fb9f0 |  | note | Frequency - prior to construction
label | 79d1a26d-1cae-50a3-ab35-33db29613a91 |  | note | Activity - HP
label | fba2e6e2-a998-5007-bdb1-4d3959157126 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.04.02 - Vapour blasted permacolour approval
label | 26dbe176-ea60-5777-9f6f-013df4202b19 |  | note | Acceptance / Conformance Criteria - Vapour blasted area to have permacolour clear concrete sealer or approved alternative.
label | 70bd569c-e084-5056-a072-f3e62f091b3c |  | note | Standard / Specification - PS 21.7.2.1
label | 13cadbc8-2fa5-5ae3-b24a-2e926dd5bc90 |  | note | Verifying Document - Notice
label | 5eb9e291-098a-5eb5-8bb0-a9c2792b2ca4 |  | note | Frequency - prior to use
label | ba33860e-131d-5136-98b3-7cd35056d23f |  | note | Activity - HP
label | 8dd423a5-9fb9-5b36-94ba-617c74f40b25 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT