## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2676-DOW-ITP-CV-0104-Earthworks Materials | itp |  |  |  |  | DS2676-DOW-ITP-CV-0104-Earthworks Materials Rev 0
section | 4.01 Earthworks Materials
checkpoint | 4.01.01 Principal-supplied Structural Fill
label | Acceptance / Conformance Criteria - The Principal shall be responsible for strength, weathering, crushing, abrasion and any laboratory testing to confirm that the Principal-supplied aggregate meets the design or for quality control. No other Structural fill is to be used unless approved by the Engineer.
label | Standard / Specification - PS 15.4.2
label | Verifying Document - Principal Supplied Source and Production Properties Tests
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.02 Structural Fill Density Tests
label | Acceptance / Conformance Criteria - The Contractor shall carrying out laboratory tests by an IANZ accredited Laboratory to determine the maximum laboratory dry density at the optimum water content (OWC) of the fill aggregate used and the Solid Density. The tests shall be undertaken on material that is representative of that used in construction and a grading for the material tested shall be supplied with the results
label | Standard / Specification - PS 15.5.4
label | Verifying Document - IANZ MDD, OMC, SD, PSD
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.03 Principal-supplied Structural Fill - MSE
label | Acceptance / Conformance Criteria - The Principal shall provide a separate stockpile for material to be used as fill for the MSE structure and the stockpile shall be located within 5km of the site. The Principal shall undertake any tests required to confirm the properties of the Principal-supplied Structural Fill for the MSE structure. The Contractor may assume such material is deemed to comply.
label | Standard / Specification - PS 15.4.2
label | Verifying Document - Principal Supplied Source and Production Properties Tests
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.04 Structural Fill - Compaction Characteristics
label | Acceptance / Conformance Criteria - The Contractor is required to carry out compaction testing by Test 4.2.1, NZS 4402:1986 to determine the compaction characteristics for each type and mix of material used in filling.
label | Standard / Specification - PS 15.4.2
label | Verifying Document - Test Report
label | Frequency - Prior to use for each Structural Fill to be used
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.05 Site Won and Contractor Supplied Structural Fill - Not Expected to be Used
label | Acceptance / Conformance Criteria - Any site won or Imported material considered as Structural Fill shall be verified by the Contractor and approved by the Engineer prior to use within the works
label | Standard / Specification - PS 15.4.2
label | Verifying Document - IANZ Test Reports
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.06 General Bulk Fill – Non Structural
label | Acceptance / Conformance Criteria - Non granular and granular soils not meeting the fill type requirements of this specification may be used for this purpose with a Maximum particle size <300mm
label | Standard / Specification - PS 15.4.3
label | Verifying Document - PSD / Visual Screening
label | Frequency - Prior to use
label | Activity - I
label | By - PE
checkpoint | 4.01.07 Talus Fill
label | Acceptance / Conformance Criteria - Where Talus fill material contains rocks greater than 300mm diameter then these shall be removed from the talus materials, stockpiled and reclassified as rock fill.
label | Standard / Specification - PS 15.4.5
label | Verifying Document - PSD / Visual Screening
label | Frequency - Prior to use
label | Activity - I
label | By - PE
section | 4.02 Rip Rap Materials
checkpoint | 4.02.01 Principal-supplied Rip Rap
label | Acceptance / Conformance Criteria - Rock Fill is required for use in the scour blanket as rip rap construction. This shall be predominantly be supplied by the Principal (see 24.1).
label | Standard / Specification - PS 15.4.4
label | Verifying Document - Principal Supplied Source and Production Properties Tests
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02.02 Site Won Rip Rap - Size
label | Acceptance / Conformance Criteria - Rock Fill for scour protection is specified in terms of D50 (millimetres). This represents the rock size that 50% of the material must exceed. The dimension of any rock shall not exceed its narrowest dimension by more than a factor of three.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - Hand Grading
label | Frequency - Prior to use
label | Activity - I
label | By - PE
checkpoint | 4.02.03 Site Won Rip Rap - Density
label | Acceptance / Conformance Criteria - Shall have a uniform density with an average specific gravity of no less than 2.65g/cm 3 .
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.02.04 Site Won Rip Rap - Soundness of Rock
label | Acceptance / Conformance Criteria - The rocks shall be sound and durable, being resistant to abrasion and free from cracks, laminations, seams, weak cleavages or other defects that would tend to increase unduly the likelihood of destruction of individual rocks by normal handling or weathering.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.02.05 Site Won Rip Rap - Broken faces
label | Acceptance / Conformance Criteria - The rock shall be angular in form with broken faces over at least 2/3 of its surface.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.02.06 Site Won Rip Rap - Weathering Grade
label | Acceptance / Conformance Criteria - The rock is to have minimal weathering, being rock of Grade I and II of the weathering term for the field description of rock provided in the 2005 “Guidelines for the field classification and description of soil and rock for engineering purposes”, NZ Geotechnical Society.
label | Standard / Specification - PS 15.4.4
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Prior to use
label | Activity - R
label | By - PE
section | 4.03 Geogrid / geofabric requirements Materials
checkpoint | 4.03.01 Geogrid and Geofabric
label | Acceptance / Conformance Criteria - Where required by the design drawings geogrids or geofabrics shall be sourced from a reputable supplier and laid, inspected and verified in accordance with the manufacturer’s specifications.
label | Standard / Specification - PS 15.4.7
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checklist | DS2676-DOW-ITP-CV-0105-Roading Materials | itp |  |  |  |  | DS2676-DOW-ITP-CV-0105-Roading Materials Rev 0
section | 4.15 TNZ M/4 - AP40 Material Approval
checkpoint | 4.15.01 Principal-supplied stockpiles
label | Acceptance / Conformance Criteria - The Principal shall provide stockpiles with material suitable for use as Basecourse within 5km the site. The Principal shall undertake any tests required to confirm the suitability as Basecourse material.
label | Standard / Specification - PS 17.4.1
label | Verifying Document - Stockpile Location
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.15.02 Principal-supplied Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.15.03 Principal-supplied Production Property Test Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Standard / Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – – –
label | 1m3 to 400m3 ¦¦ 2
label | 400m3 to 1,500m3 ¦¦ 3
label | 1,500m3 to 4,000m3 ¦¦ 4
label | – – – – – – – – – – – – – – –
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.15.04 Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Activity - R
label | By - PE
section | 4.16 TNZ M/3 Notes - AP65 Subbase Material Approval
checkpoint | 4.16.01 Principal-supplied stockpiles
label | Acceptance / Conformance Criteria - The Principal shall provide stockpiles with material suitable for use as Subbase within 5km of the site. The Principal shall undertake any tests required to confirm the suitability as Subbase material.
label | Standard / Specification - PS 17.3.1
label | Verifying Document - Stockpile Location
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.16.02 Principal-supplied Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Standard / Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2006, PS 17.3.2.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.16.03 Principal-supplied Production Property Test Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
label | Standard / Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2006, PS 17.3.2.2
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – – –
label | 1m3 to 400m3 ¦¦ 2
label | 400m3 to 1,500m3 ¦¦ 3
label | 1,500m3 to 4,000m3 ¦¦ 4
label | – – – – – – – – – – – – – – –
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.16.04 Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Activity - R
label | By - PE
section | 4.17 TNZ B/02:2005 Material Approval
checkpoint | 4.17.01 Running Course Material Approval
label | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN It shall be free from all non-mineral matter. The grading of the running course shall be conforming.
label | Standard / Specification - TNZ B/02: 2005 - 10.2
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – – –
label | 1m3 to 400m3 ¦¦ 2
label | 400m3 to 1,500m3 ¦¦ 3
label | 1,500m3 to 4,000m3 ¦¦ 4
label | – – – – – – – – – – – – – – –
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.18 Sealing Chip Supply Materials
checkpoint | 4.18.01 Sealing Chip - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Standard / Specification - TNZ M/6: 2019 - 4
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Activity - R
label | By - SE
checkpoint | 4.18.02 Sealing Chip - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Standard / Specification - TNZ M/6: 2019 - 5
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Activity - R
label | By - SE
section | 4.19 Bitumen Supply Materials
checkpoint | 4.19.01 Bitumen - Quality Testing
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Standard / Specification - NZTA M01: 2022 - 6
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Activity - R
label | By - SE
checkpoint | 4.19.02 Bitumen - Supply Testing
label | Acceptance / Conformance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Standard / Specification - NZTA Q05: 2022 - 6.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Activity - R
label | By - SE
section | 4.20 NZTA M10 2020 - Dense Graded Asphaltic Concrete Materials
checkpoint | 4.20.01 Coarse Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution
label | Standard / Specification - NZTA M10:2020 - 2.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Activity - H
label | By - PE
checkpoint | 4.20.02 Fine Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution
label | Standard / Specification - NZTA M10:2020 - 2.1.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Activity - H
label | By - PE
checkpoint | 4.20.03 Mineral Filler
label | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
label | Standard / Specification - NZTA M10:2020 - 2.2 ASTM D242
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Activity - H
label | By - PE
checkpoint | 4.20.04 Bitumen
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Standard / Specification - NZTA M10:2020 - 2.3.1 NZTA M01-A
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Activity - H
label | By - PE
checkpoint | 4.20.05 Mix Design Approval
label | Acceptance / Conformance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
label | Standard / Specification - NZTA M10:2020 - 3.1 , 3.6
label | Verifying Document - Approved Mix Design
label | Frequency - Prior to Use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.21 Road Marking Materials
checkpoint | 4.21.01 Paint Approval
label | Acceptance / Conformance Criteria - The paint to be used for roading marking shall be on "LIST OF M07 APPROVED PRODUCTS"
label | Standard / Specification - PS 18.1.3.4
label | Verifying Document - Datasheet and M7 List
label | Frequency - Prior to use
label | Activity - R
label | By - SE
checkpoint | 4.21.02 Sprayer Certification
label | Acceptance / Conformance Criteria - The Sprayer is to have a current T8 certificate
label | Standard / Specification - PS 18.1.3.4
label | Verifying Document - T8 Certificate
label | Frequency - Prior to use
label | Activity - R
label | By - SE
section | 4.22 Traffic Sign Materials
checkpoint | 4.22.01 Traffic Sign Post
label | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted least 14 days in advance of concrete supply
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.22.02 Traffic Signs
label | Acceptance / Conformance Criteria - All signs shall be completed in accordance wit NZTA P/24: Performance Based Specification for Traffic Signs
label | Standard / Specification - 18.2.1.3
label | Verifying Document - Datasheet and P24 List
label | Frequency - Prior to use
label | Activity - R
label | By - SE
checkpoint | 4.22.03 Large Sign Posts
label | Acceptance / Conformance Criteria - All signs larger than 4.5m2 and more than two posts shall have posts with breakaway bases and hinges, unless protected by safety barrier and more than 600mm behind the barrier. All other signs shall have posts complying with NZTA P/24 and the RSMA standard,
label | Standard / Specification - 18.2.1.4
label | Verifying Document - Datasheet and P24 List
label | Frequency - Prior to use
label | Activity - R
label | By - SE
checkpoint | 4.22.04 Normal Sign Posts
label | Acceptance / Conformance Criteria - All other signs shall have posts complying with NZTA P/24 and the RSMA standard, unless protected by safety barrier and more than 600mm behind the barrier.
label | Standard / Specification - 18.2.1.4
label | Verifying Document - Datasheet and P24 List
label | Frequency - Prior to use
label | Activity - R
label | By - SE
checkpoint | 4.22.05 Support and Posts
label | Acceptance / Conformance Criteria - Supports and posts for signs shall only be constructed of structural aluminium or steel. Refer to Clause 15.1 (b) & (c) of the RSMA Standard. All steel shall be hot-dipped galvanised after fabrication to CES 306.
label | Standard / Specification - 18.2.3.1
label | Verifying Document - Datasheet and P24 List
label | Frequency - Prior to use
label | Activity - R
label | By - SE
checklist | DS2676-DOW-ITP-CV-0106-Stormwater Materials | itp |  |  |  |  | DS2676-DOW-ITP-CV-0106-Stormwater Materials Rev 0
section | 4.04 Stormwater Drainage Materials
checkpoint | 4.04.01 PVC Pipes
label | Acceptance / Conformance Criteria - PVC shall be Class SN8 or higher unless specified otherwise
label | Standard / Specification - 16.7.3.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.02 Corrugated steel, Aluminium, and profiled-wall PE
label | Acceptance / Conformance Criteria - Corrugated steel or aluminium pipes and profiled-wall PE need to be approved by the Engineer
label | Standard / Specification - 16.7.3.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04.03 Concrete Pipes
label | Acceptance / Conformance Criteria - Concrete pipes shall be a minimum of Class 4 unless specified
label | Standard / Specification - 16.7.3.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.04 Concrete pipe Embedment
label | Acceptance / Conformance Criteria - Bedding and haunching material shall either conform to the grading limits of AS/NZS 3725 Table 6 or complies with the compaction requirements of Table 16.7 below or Section 16.7.3.5, and does not exceed the maximum particle size stated in AS/NZS 3725. Alternatively Low fines may be used. Testing shall include PSD, MDD (VH Cohesiveless), Fines etc.
label | Standard / Specification - 16.7.3.2
label | Verifying Document - IANZ Test Results
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.05 Concrete pipe Embedment - Compaction Fraction
label | Acceptance / Conformance Criteria - Bedding and haunching material must be tested for compaction fraction as per AS/NZS3725 to determine the target Minimum Dry Density required for insitu compaction.
label | Standard / Specification - 16.7.3.2
label | Verifying Document - IANZ Test Results
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.06 Buried flexible pipe embedment
label | Acceptance / Conformance Criteria - Bedding and haunching material for flexible pipes shall conform to AS/NZS 2566.2 except where Low Fines is used. Testing shall include PSD, MDD (VH Cohesiveless), Fines etc.
label | Standard / Specification - 16.7.3.3
label | Verifying Document - IANZ Test Results
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04.07 Geotextile Wrapped Subsoil Drain Aggregate
label | Acceptance / Conformance Criteria - The granular aggregate subsoil material may be as specified in NZTA F/6 or alternatively a free draining angular material free from fines and not exceeding 19mm maximum particle size where used for sub-soil pipe embedment e.g. 7mm drainage chip. The Engineer can advise on which materials are considered appropriate for use.
label | Standard / Specification - 16.7.3.4
label | Verifying Document - IANZ Test Results
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04.08 Low fines
label | Acceptance / Conformance Criteria - ‘Low fines’ material may be used for embedment (e.g. drainage chip) for both concrete and flexible pipes subject to complying with the specification. A Compaction Fraction shall be completed to determin compaction requirmenets.
label | Standard / Specification - 16.7.3.5
label | Verifying Document - IANZ Test Results
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.09 Manholes
label | Acceptance / Conformance Criteria - Manholes shall be a minimum of DN1050. Manhole cover slabs and risers shall be rated to HN-HO-72, as specified in NZTA P46, where subject to vehicle loads. This shall include all areas accessible to vehicles including access ramps, shallow berms and car parking areas
label | Standard / Specification - 16.9.1.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.10 Manhole Steps
label | Acceptance / Conformance Criteria - Manholes shall include Grade 316 SS or plastic encapsulated step rungs complying with AS 1657:2018 located to avoid any connected pipes. The manhole cover slab shall have an eccentric opening rotated to align with the step rungs
label | Standard / Specification - 16.9.1.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.11 Sumps / Catch-Pits Lids
label | Acceptance / Conformance Criteria - The grate and frame shall be hinged cast or ductile iron with 675 x 450 mm clear opening at all locations unless specified otherwise on the drawing. The grate and frame shall be rated Class D to AS 3996 or higher.
label | Standard / Specification - 16.10.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.04.12 Geo-textiles
label | Acceptance / Conformance Criteria - Geo-textiles for all drainage separation purposes shall be a non-woven needle-punched fabrication in accordance with NZTA specification F/7.
label | Standard / Specification - 16.11.1 PS 15.4.7
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checklist | DS2676-DOW-ITP-CV-0107-Insitu Structure and Concrete Materials | itp |  |  |  |  | DS2676-DOW-ITP-CV-0107-Insitu Structure and Concrete Materials Rev 0
section | 4.09 Insitu Mix Designs
checkpoint | 4.09.01 Concrete Plant
label | Acceptance / Conformance Criteria - The Concrete Plant shall have a Current Certificate of Audit
label | Standard / Specification - PS 27.4.1
label | Verifying Document - Certificate of Audit to NZS 3104:2003
label | Frequency - With Mix Design and Upon Revalidation
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.09.02 Concrete Aggregate Reactivity Testing
label | Acceptance / Conformance Criteria - When required, the Concrete producer is to confirm the proposed aggregates are non-reactive as defined in clause 6.1 of CCANZ TR3.
label | Standard / Specification - PS 27.4.2.3
label | Verifying Document - Supplier Statement
label | Frequency - With Mix Designs Submissions
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.09.03 Insitu Concrete Handling and Placing
label | Acceptance / Conformance Criteria - The contractor shall submit the proposed handling and placing methods, sequence and timing of pours and location on construction joints for the Engineer's consent before concrete placing commences
label | Standard / Specification - 27.4.5.1
label | Verifying Document - Approved Method
label | Frequency - Before Concrete Placing Commences
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.09.04 Insitu stitch in torsion beam Concrete Mix Design
label | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted least 14 days in advance of concrete supply
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.09.05 Insitu Stitches between hollowcore roof beams Concrete Mix Design
label | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted least 14 days in advance of concrete supply
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.09.06 Other insitu stitches and insitu snow wall Concrete Mix Design
label | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted least 14 days in advance of concrete supply
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.09.07 Kerb and channel Concrete Mix Design
label | Acceptance / Conformance Criteria - The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Standard / Specification - PS 27.4.3.3 / 27.3.1
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted least 14 days in advance of concrete supply
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.10 Insitu Concrete Materials
checkpoint | 4.10.01 Dry Pack Mortar
label | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall consist of a sand/cement mix in the loose volume proportions of one part of cement to two parts of well drained Class A (coarse) plastering sand or concrete sand complying with NZS 3103 and NZS 3121 respectively.
label | Standard / Specification - PS 27.4.3.7
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.10.02 Fibre Reinforcement
label | Acceptance / Conformance Criteria - The following proprietary fibres and doses shall be used:
label | • iNFORCE Microforce19 polypropylene fibres – 1.8 kg/m3
label | • iNFORCE Ultrafiber500 cellulose fibres – 1.8 kg/m3
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Datasheets
label | Frequency - With Mix Designs Submissions
label | Activity - R
label | By - PE
checkpoint | 4.10.03 Reinforcement Supplier
label | Acceptance / Conformance Criteria - The contractor shall provide the name of reinforcement supplier before delivering any reinforcement
label | Standard / Specification - PS 27.7
label | Verifying Document - Supplier Details
label | Frequency - Before delivering any reinforcement
label | Activity - R
label | By - PE
checkpoint | 4.10.04 Reinforcement
label | Acceptance / Conformance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001. Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of any work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
label | Standard / Specification - PS 27.7.1 / 27.7.9
label | Verifying Document - Mill Certs
label | Frequency - At least one week before incorporating these materials.
label | Activity - R
label | By - PE
checkpoint | 4.10.05 Bar Bending Schedules
label | Acceptance / Conformance Criteria - The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars.
label | Standard / Specification - PS 27.7.8
label | Verifying Document - Bar Bending Schedules
label | Frequency - At least 14 days before the start of placing the corresponding reinforcing bars.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10.06 TPI Inspector approval
label | Acceptance / Conformance Criteria - The Contractor shall supply the details of the proposed Third Party Inspector to the engineer prior to welding
label | Standard / Specification - PS 27.7.6
label | Verifying Document - TPI Details and Qualifications
label | Frequency - Prior to Welding
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10.07 Welding of Reinforcement
label | Acceptance / Conformance Criteria - The welding shall be inspected by the Contractor’s Third Party Inspector who shall meet the “Qualifications of Inspectors” requirements of AS/NZS 1554.3 Clause 10.2. Inspections of the welding shall be in accordance with AS/NZS 1554.3.
label | Standard / Specification - PS 27.7.6
label | Verifying Document - TPI Report
label | Frequency - Prior to be encased. 100% Visual, 10% Ultrasonic, and 10% of Fillet by Magnetic.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10.08 Mechanical couplers and anchors in reinforced concrete
label | Acceptance / Conformance Criteria - Mechanical couplers and anchors for the jointing of reinforcing steel shall satisfy the requirements of NZS 3101 clauses 8.7.5 and 8.9.1.3, and ISO 15835-1 Steels for the reinforcement of concrete. Only steel Reidbar components meeting the above requirements shall be accepted.
label | Standard / Specification - PS 27.7.12.1
label | Verifying Document - System Certification or Batch Verification.
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.10.09 Joint Sealing and Waterproofing
label | Acceptance / Conformance Criteria - Where so indicated on the Drawings, joints are to be sealed using Sikaflex 11FC or similar approved equivalent.
label | Standard / Specification - PS 27.8
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.10.10 Compressible Filler
label | Acceptance / Conformance Criteria - Compressible filler board shall be a closed polyethylene board complying with the requirements of DTp Specification for Highway Works series 1000. Details of the material proposed to be used shall submitted to the Designer at least 1 week prior to installation, for acceptance.
label | Standard / Specification - PS 27.8.3
label | Verifying Document - Datasheet
label | Frequency - At least 1 week prior to installation, for acceptance.
label | Activity - R
label | By - PE
checkpoint | 4.10.11 Interfaces with bitumen
label | Acceptance / Conformance Criteria - At all interfaces with bitumen-based materials the sealant shall be separated using high strength multilaminate modified bitumen tape or approved equivalent on top of aluminium tape C126(sticky side-up).
label | Standard / Specification - PS 27.8.4
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.10.12 Permeant Formwork Certification Compressible Filler)
label | Acceptance / Conformance Criteria - Design details, construction drawings and a formwork certificate (PF-T-442) shall be supplied to the Engineer prior to the formwork assembly and at least 14 days prior to concreting of the component, for review, for all permanent formwork proposed to be used.
label | Standard / Specification - PS 27.5.3.5
label | Verifying Document - PF-T-442 Certificate
label | Frequency - Prior to Pour
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10.13 Membrane Curing
label | Acceptance / Conformance Criteria - The use of membrane curing shall be subject to the written consent of the Engineer, following the submission of full details of the method proposed (including details of the curing compound where applicable) and the area of proposed use.
label | Standard / Specification - PS 27.4.8.2
label | Verifying Document - Post Pour
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.11 Special Provisions Relating to Pumped Concrete
checkpoint | 4.11.01 Pumping Equipment
label | Acceptance / Conformance Criteria - Concrete pumping equipment shall be of a proven type able to deliver the specified concrete and distances and heights required. Pumping equipment that relies on compressed air to move the concrete through the pipeline shall not be used. The pump shall be located as near as practicable to the placement area.
label | Standard / Specification - PS 27B1.2
label | Verifying Document - Equipment Details
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.11.02 Concrete Materials
label | Acceptance / Conformance Criteria - Concrete mixes for pumping shall have a plastic consistency and provision shall be made for the elimination of oversized particles in the concrete by finish screening or by the careful selection of aggregates.
label | Standard / Specification - PS 27B1.4
label | Verifying Document - Mix Design
label | Frequency - Submitted least 14 days in advance of concrete supply
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.12 Falsework Requirements
checkpoint | 4.12.01 Falsework Design
label | Acceptance / Conformance Criteria - The Contractor shall provide the Engineer with a summary of the falsework requirements for the works and the proposed design requirements and quality controls to ensure the design of the falsework is fit for purpose. In developing these proposals, the Contractor shall refer to the best practice guidelines referenced by the Temporary Works Forum NZ
label | Standard / Specification - PS 27.5.2
label | Verifying Document - Falsework Design
label | Frequency - Prior to Fabrication
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.12.02 Falsework Engineer
label | Acceptance / Conformance Criteria - The Contractor shall appoint a Falsework Engineer for the design of the falsework and preparation of the falsework drawings and specification. The person appointed shall be competent and experienced in falsework design and, for "special" and "conventional" falsework, shall also be a registered engineer.
label | Standard / Specification - PS 27.5.2
label | Verifying Document - Notice
label | Frequency - Prior to Fabrication
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.12.03 Falsework Programme
label | Acceptance / Conformance Criteria - The Contractor shall supply to the Engineer at least one week prior to the programmed start of construction of the falsework a completed Falsework Design Certificate on form PF-T-440 (attached in Appendix 27A). All subsequent modifications to the original design shall be likewise certified by the engineer, and by the independent checker for "special" falsework.
label | Standard / Specification - PS 27.5.2
label | Verifying Document - PF-T-440
label | Frequency - At least one week prior to the programmed start of construction
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.12.04 Falsework Site Register
label | Acceptance / Conformance Criteria - The Contractor shall provide, at the site for the Engineer's inspection, a register containing the completed Falsework Design and Inspection Certificates. The Engineer shall have access to these documents at all times.
label | Standard / Specification - PS 27.5.2.4
label | Verifying Document - Register
label | Frequency - Ongoing
label | Activity - R
label | By - PE
section | 4.13 Avalanche Shelter Structures
checkpoint | 4.13.01 Concrete, Mortar and Grout
label | Acceptance / Conformance Criteria - Mortar and grout, whether cementitious or epoxy, used for bedding precast units or bearings against the concrete shall have a compressive strength at 28 days of not less than the specified concrete strength of the concrete elements being bedded against unless specified otherwise.
label | Standard / Specification - PS 21.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.13.02 Proprietary grout approval
label | Acceptance / Conformance Criteria - Details of any proprietary grout shall be submitted to the Engineer for approval 5 days in advance of any construction works using such material.
label | Standard / Specification - PS 21.3.1
label | Verifying Document - Datasheets
label | Frequency - 5 days in advance of any construction works using such material.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.13.03 Epoxy mortar
label | Acceptance / Conformance Criteria - Epoxy mortar shall be a proprietary product from a recognised manufacturer and shall be subject to the acceptance of the Engineer as suitable for the particular application.
label | Standard / Specification - PS 21.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.13.04 Patch repair mortar
label | Acceptance / Conformance Criteria - Patch repair mortar, wherever it may be used, shall be a proprietary product from a recognised manufacturer, and subject to the acceptance of the Engineer as suitable for the particular application.
label | Standard / Specification - PS 21.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.13.05 Bolts, Nuts and Washers
label | Acceptance / Conformance Criteria - The Contractor shall submit test reports or test certificates for all bolts nuts and washers, prepared by a laboratory accredited by signatories to the International Accreditation Cooperation (ILAC) Mutual Recognition Agreement (MRA) on behalf of the manufacturer, as evidence of compliance with the relevant material supply standard specified.
label | Standard / Specification - PS 21.3.3
label | Verifying Document - Test reports or Test certificates
label | Frequency - at least one week before the programmed commencement of any work incorporating these materials.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.13.06 Elastomeric Strip Bearings
label | Acceptance / Conformance Criteria - All elastomeric bearing strips shall comply with AS 5100.4 IRHD 60.
label | Standard / Specification - 21.3.5.1
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.13.07 Expansion Joints
label | Acceptance / Conformance Criteria - Compression Board to be approved and compression seal WaboXPE Seal (XPE 3000) or similar approved equivalent in accordance with the Manufacturer’s written instructions
label | Standard / Specification - 21.3.6
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.13.08 Cast-In Sleeving
label | Acceptance / Conformance Criteria - Cast-in sleeving, unless specified or shown on the drawings as otherwise, shall be rigid uPVC pipe complying with AS/NZS 1260, or other acceptable standard, and of the size shown on the drawings.
label | Standard / Specification - 21.3.7
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.13.09 Services Ducts
label | Acceptance / Conformance Criteria - Ducting for services shall be uPVC ducting of the nominal bore diameter shown on the drawings and complying with AS/NZS 2053.1, AS/NZS 2053.2 and AS/NZS 2053.4 as applicable.
label | Standard / Specification - 21.3.8
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.13.10 Precast Bedding Material
label | Acceptance / Conformance Criteria - Where precast units are to be placed on granular material, the bedding material shall consist of PAP 7, all in crushed hard aggregate, well graded from coarse to fine, durable and free of nonmineral matter.
label | Standard / Specification - 21.5.1.2
label | Verifying Document - PSD
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.13.11 Temporary Works
label | Acceptance / Conformance Criteria - The Contractor shall provide the Engineer with a summary of the temporary works required for the works and the proposed design requirements and quality controls to ensure the design of the temporary works is fit for purpose
label | Standard / Specification - 21.5.2
label | Verifying Document - Temporary Works Summary
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.14 Anti Graffiti Guard
checkpoint | 4.14.01 Permanent Anti Graffiti Guard
label | Acceptance / Conformance Criteria - Permanent (not sacrificial) anti graffiti coatings shall be applied to the exposed faces of all concrete surfaces including barriers, piers and abutments. The coatings shall have a design life of not less than 10 years. The coating shall be either on the Waka Kotahi list of prequalified formulations or prequalified by the Contractor for inclusion on the Waka Kotahi list.
label | Standard / Specification - PS 14.3.1
label | Verifying Document - Datasheet and on Waka Kotahi S10 List
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.14.02 Anti-Graffiti Label Approval
label | Acceptance / Conformance Criteria - A self-adhesive label shall indicate all areas of anti-graffiti coatings on site. at least two weeks prior to the applicable works, the Contractor shall submit details of the label to the Engineer for approval.
label | Standard / Specification - PS 21.7.1.3
label | Verifying Document - Label Details
label | Frequency - at least two weeks prior to the applicable work
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.14.03 Anti-Graffiti Product and Approval
label | Acceptance / Conformance Criteria - The Contractor shall prepare a test panel to demonstrate that the above appearance requirements have been met to the satisfaction of the Engineer.
label | Standard / Specification - 21.7.1.1
label | Verifying Document - Notice
label | Frequency - Prior to production use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2676-DOW-ITP-CV-0108-Landscaping Materials | itp |  |  |  |  | DS2676-DOW-ITP-CV-0108-Landscaping Materials Rev 0
section | 4.25 Landscaping Materials
checkpoint | 4.25.01 Topsoil
label | Acceptance / Conformance Criteria - All topsoil and associated weathered/organic material obtained from on-site stripping shall be retained and stockpiled for future use within the Project area.
label | Standard / Specification - PS 25.7.3
label | Verifying Document - Site Notes
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checkpoint | 4.25.02 Fertilisers
label | Acceptance / Conformance Criteria - The relocated plant material shall be top-dressed with a controlled, slow release fertiliser such as ‘Nutricote’ or ‘Osmocote Plus's of composition 12:8:6 (N:P:K) or similar. Nitrogen is likely to be the most deficient mineral in the local topsoil/avalanche debris substrate.
label | Standard / Specification - PS 25.8.2
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Activity - R
label | By - PE
checklist | DS2676-DOW-ITP-CV-0109-MSE Wall Design | itp |  |  |  |  | DS2676-DOW-ITP-CV-0109-MSE Wall Design Rev 0
section | 4.23 Mechanically Stabilised Earth (MSE) Wall Design
checkpoint | 4.23.01 MSE Wall Design
label | Acceptance / Conformance Criteria - Design of and preparation of detailed specifications and drawings for the manufacture and erection of the MSE wall shall be the responsibility of the Contractor. The MSE wall designer shall provide a Producer Statement for Design (PS1)
label | Standard / Specification - PS 22.4.1, PS 22.4.4
label | Verifying Document - Design, Spec, Drawings, and PS1
label | Frequency - Prior to commencing construction of the MSE Wall
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.23.02 MSE Design Review Engineer Approval
label | Acceptance / Conformance Criteria - The name and qualifications of the design review company shall be submitted to the Engineer for approval prior to commencing the review.
label | Standard / Specification - PS 22.4.3
label | Verifying Document - Review Engineer Approval
label | Frequency - Prior to commencing the review.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.23.03 MSE Design Review
label | Acceptance / Conformance Criteria - The Contractor shall engage an independent reviewer to undertake peer review of the MSE wall design. The independent reviewer shall provide a Producer Statement for Design Review (PS2)
label | Standard / Specification - PS 22.4.3
label | Verifying Document - PS2
label | Frequency - Prior to commencing construction of the MSE Wall
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.23.04 Method Statement and ITP
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a Construction Methodology and an Inspection Test Plan (ITP) for the MSE wall for Waka Kotahi and Engineer’s approval prior to construction. The ITP shall include all quality control testing required during construction as specified by the MSE wall designer
label | Standard / Specification - PS 22.4.5
label | Verifying Document - Method Statement and ITP
label | Frequency - Prior to commencing construction of the MSE Wall
label | Activity - HP
label | By - ENG
label | Comments / Closeout Details - MSE Wall ITP to be incorporated into this ITP below.
holdpoint | AUTHORITY HOLDPOINT
section | 4.24 MSE Wall Sample Panel
checkpoint | 4.24.01 MSE Wall Sample Panel
label | Acceptance / Conformance Criteria - Prior to the commencement of the permanent work, the Contractor shall produce one sample panel of similar dimensions and construction to the proposed final panels.
label | Standard / Specification - PS 22.16.5
label | Verifying Document - 3m Visal Inspection by Engineer
label | Frequency - Prior to the commencement of the permanent work
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT