## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2676-DOW-ITP-CV-0116-Roading Pavement - Subgrade to Basecourse | itp |  |  |  |  | DS2676-DOW-ITP-CV-0116-Roading Pavement - Subgrade to Basecourse Rev 1
section | 7.01 Subgrade and Undercut
checkpoint | 7.01.01 Bulk Fill Embankments
label | Acceptance / Conformance Criteria - The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Bulk Fill Embankments 12%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered.
label | Standard / Specification - PS 17.2.1, PS 17.2.2
label | Verifying Document - Scala Results
label | Frequency - 10m intervals along each lane or widening with a minimum of 5 tests
label | Activity - I
label | By - SE
checkpoint | 7.01.02 Insitu Cut
label | Acceptance / Conformance Criteria - The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Insitu Cut 12%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered.
label | Standard / Specification - PS 17.2.1, PS 17.2.2
label | Verifying Document - Scala Results
label | Frequency - 10m intervals along each lane or widening with a minimum of 5 tests
label | Activity - I
label | By - SE
checkpoint | 7.01.03 Insitu pavements
label | Acceptance / Conformance Criteria - The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Insitu pavements 5%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered.
label | Standard / Specification - PS 17.2.1, PS 17.2.2
label | Verifying Document - Scala Results
label | Frequency - 10m intervals along each lane or widening with a minimum of 5 tests
label | Activity - I
label | By - SE
checkpoint | 7.01.04 Unsealed Roads
label | Acceptance / Conformance Criteria - The Contractor shall confirm the CBR of the subgrade by Scala Penetrometer testing, or if subgrade is granular in nature, by laboratory soaked CBR testing. Unsealed Roads 5%. Tests shall be performed at 10m intervals along each lane or widening with a minimum of 5 tests for each type of subgrade or soil type encountered.
label | Standard / Specification - PS 17.2.1, PS 17.2.2
label | Verifying Document - Scala Results
label | Frequency - 10m intervals along each lane or widening with a minimum of 5 tests
label | Activity - I
label | By - SE
section | 7.02 Subbase
checkpoint | 7.02.01 Overlay Sites Plateau Density Tests
label | Acceptance / Conformance Criteria - The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
label | Standard / Specification - TNZ B/02: 2005 - 7.5
label | Verifying Document - MDD and Plateau Reports
label | Frequency - 1 test per 5,000m2
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.02.02 Sub-basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
label | Standard / Specification - TNZ B/02: 2005-7.6 PS 17.3.4
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.02.03 Sub-basecourse Layer thickness.
label | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitored for Layer thickness.
label | Standard / Specification - TNZ B/02:2005 -7.5 PS 17.3.4
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Activity - W
label | By - SV / PE
checkpoint | 7.02.04 Material Placement
label | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Activity - I
label | By - SV / PE
section | 7.03 Basecourse
checkpoint | 7.03.01 Overlay Sites Plateau Density Tests
label | Acceptance / Conformance Criteria - The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
label | Standard / Specification - TNZ B/02: 2005 - 7.5
label | Verifying Document - MDD and Plateau Reports
label | Frequency - 1 test per 5,000m2
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.02 Basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
label | Standard / Specification - TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.03 Basecourse Layer thickness.
label | Acceptance / Conformance Criteria - The Basecourse shall be monitored for Layer thickness.
label | Standard / Specification - TNZ B/02: 2005 - 7.5
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Activity - W
label | By - SV / PE
checkpoint | 7.03.04 Additional Rolling
label | Acceptance / Conformance Criteria - Further to Clause 7.5 of TNZ B/2 if it is not possible to ensure that at least 1,000 vehicles pass evenly over each unsealed lane the Contractor shall allow for carrying out 30 passes evenly spread per lane of a 2 axle truck with the twin tyred rear axle loaded to 10 tonnes.
label | Standard / Specification - PS 17.4.5
label | Verifying Document - Site Records
label | Frequency - Prior to sealing
label | Activity - W
label | By - PE
checkpoint | 7.03.05 Finished Surface Shape Approval
label | Acceptance / Conformance Criteria - The Contractor shall agree details with the Engineer including the road profile of the semi-temporary surface, cross falls and temporary details at the kerbs to control drainage until the final surfacing is placed.
label | Standard / Specification - 17.8.1
label | Verifying Document - Approval
label | Frequency - Prior to sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.06 Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | Standard / Specification - TNZ B/02: 2005 - 7.7 PS 17.4.5
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.07 Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - TNZ B/02: 2005 - 7.7 PS 17.4.5
label | Verifying Document - Survey
label | Frequency - Prior to sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.08 Running Course
label | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
label | Standard / Specification - TNZ B/02: 2005 - 10.1
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - S
label | By - SUP
checkpoint | 7.03.09 Benkelman beam tests
label | Acceptance / Conformance Criteria - The Contractor shall record the deflections of the finished basecourse after compaction, but before sealing by Benkelman Beam Deflection testing in terms of TNZ T/1. Tests shall be performed at 10m intervals in each wheel track in both lanes. Test results shall be reported to the Engineer prior to sealing. (95 percentile = 0.8mm / Max = 1mm)
label | Standard / Specification - PS 17.5.1, PS 17.5.2, Table 17.5
label | Verifying Document - Beam Report
label | Frequency - at 10m intervals in each wheel track in both lanes
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.10 Preselling Requirements
label | Acceptance / Conformance Criteria - Degree of Saturation (DOS) requirements for this site are DOS less than 60% prior to seal with the preparation of the surface for sealing shall be in accordance with TNZ B/2 and TNZ P/3.
label | Standard / Specification - PS 17.6.2, PS 17.6.1
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.11 Surface Finish post sweeping
label | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Standard / Specification - TNZ B/02: 2005 -7.8 PS 17.4.5
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.03.12 Pre Sealing Notice
label | Acceptance / Conformance Criteria - The Contractor shall give the Engineer 48 hours prior notice that the surface is ready for inspection and shall not undertake any surfacing until the surface preparation has been accepted by the Engineer.
label | Standard / Specification - 17.6.3
label | Verifying Document - Approval
label | Frequency - 48 hours prior notice to sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2676-DOW-ITP-CV-0117-Roading Surfacing - Chipseal | itp |  |  |  |  | DS2676-DOW-ITP-CV-0117-Roading Surfacing - Chipseal Rev 1
section | 8.01 Chipsealing General
checkpoint | 8.01.01 Sealing Procedure
label | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, P4, P17, and Q/1.
label | Standard / Specification - M/1, M/6, M/13, P/3, P4, P17, and Q/1.
label | Verifying Document - Methodology / Construction Pack
label | Frequency - Prior to Sealing
label | Activity - R
label | By - SE
checkpoint | 8.01.02 Seal Design / Binder application rate
label | Acceptance / Conformance Criteria - The sealing design including binder application rate to suit the surface conditions shall be approved by the Design Engineer prior to sealing.
label | Standard / Specification - TNZ P3, TNZ P4
label | Verifying Document - Approved Seal Design
label | Frequency - Prior to Sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.01.03 Adhesion Agents
label | Acceptance / Conformance Criteria - When used, Adhesion agents must be approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents.
label | Standard / Specification - TNZ M13
label | Verifying Document - Binder Aggregate Adhesion Test
label | Frequency - Each Adhesion Agent & Dosage Rate for a Particular Chip Source
label | Activity - R
label | By - SE
checkpoint | 8.01.04 Sprayer Certification
label | Acceptance / Conformance Criteria - The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
label | Standard / Specification - TNZ P3, TNZ P4
label | Verifying Document - E2 Cert
label | Frequency - Each Sprayer
label | Activity - R
label | By - SE
section | 8.02 First Coat Sealing
checkpoint | 8.02.01 Preselling Requirements
label | Acceptance / Conformance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%.
label | Standard / Specification - TNZ B02
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests Per Lot 1000m2 Max Lot Size
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.02.02 PreSeal inspection
label | Acceptance / Conformance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
label | Standard / Specification - TNZ P3 TNZ B02
label | Verifying Document - Hold Point Release
label | Frequency - Prior to Sealing
label | Activity - W
label | By - ENG
checkpoint | 8.02.03 Spray Temperature
label | Acceptance / Conformance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Prior to Seal
label | Activity - I
label | By - SE
checkpoint | 8.02.04 Binder Sampling
label | Acceptance / Conformance Criteria - A minimum of two samples per bitumen distributor load shall be taken. The first of these samples shall be taken at the end of the initial spray run and the other immediately before the final spray run. Bitumen to be tested on Engineers instruction.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Each Worksite
label | Activity - I
label | By - SE
checkpoint | 8.02.05 Quantity of Binder Sprayed
label | Acceptance / Conformance Criteria - The quantity of binder sprayed in any spray run, measured by dipstick reading, shall not vary from the amount directed by more than 50 litres plus 4% of the amount directed.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Every Spray Run
label | Activity - I
label | By - SE
checkpoint | 8.02.06 Chip Application
label | Acceptance / Conformance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Every Spray Run
label | Activity - I
label | By - SE
checkpoint | 8.02.07 Surplus Chip Removal
label | Acceptance / Conformance Criteria - Surplus chips shall be removed from the sealed surface prior to the removal of the temporary speed restriction signs.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - 24 hours of Completion of any Section of Seal.
label | Activity - R
label | By - SE
checkpoint | 8.02.08 Post Seal Inspections
label | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Standard / Specification - TNZ P3
label | Verifying Document - Engineers Acceptance
label | Frequency - Prior to TM Removal and After Final Sweeping
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.02.09 Chipseal Repairs
label | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Standard / Specification - TNZ P3
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.02.10 NAASRA - Chipseal Surfacing
label | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. No 20m reading in any lane shall exceed 70 NAASRA counts/km for chipseal surface.
label | Standard / Specification - PS 14.1.4.1, PS 17.7, NZTA M10:2020 - 10
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2676-DOW-ITP-CV-0118-Roading Surfacing - Asphalt | itp |  |  |  |  | DS2676-DOW-ITP-CV-0118-Roading Surfacing - Asphalt Rev 1
section | 9.01 Construction Activity - NZTA M10 - Specification for dense-graded asphaltic concrete
checkpoint | 9.01.01 Construction Trail
label | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. Asphalt manufactured in the production trial can also be used in the construction trial if it meets the requirements of the specification.
label | Standard / Specification - NZTA M10:2020 - 7
label | Verifying Document - Test Results
label | Frequency - As Required, two days before the site work is due to commence.
label | Activity - I
label | By - PE
checkpoint | 9.01.02 Paving Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Construction Work Pack
label | Frequency - 7 days prior to construction of the asphalt pavement.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.01.03 Preparation of Area to be Paved
label | Acceptance / Conformance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Activity - I
label | By - PE
checkpoint | 9.01.04 Protection of Services
label | Acceptance / Conformance Criteria - The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Environmental Inspections
label | Frequency - Daily
label | Activity - R
label | By - SE
checkpoint | 9.01.05 Ambient Conditions for Placing
label | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Activity - H
label | By - SE
checkpoint | 9.01.06 Tack Coating
label | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Prior to Paving
label | Activity - I
label | By - PE
checkpoint | 9.01.07 Asphalt Production Conformance
label | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
label | Standard / Specification - NZTA M10:2020 -Table 3.1 & 5.1
label | Verifying Document - Test Results
label | Frequency - 1 per 200T Min 3 tests per mix
label | Activity - I
label | By - PE
checkpoint | 9.01.08 Core Thickness
label | Acceptance / Conformance Criteria - The layer thickness determined from measurements on the cores shall be -0 mm to +10 mm of the specified thickness
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Lab Report
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Activity - R
label | By - SE
checkpoint | 9.01.09 Mat Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot
label | Standard / Specification - ASTM D5361 NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Activity - R
label | By - PE
checkpoint | 9.01.10 Joint Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Activity - R
label | By - PE
checkpoint | 9.01.11 Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - within 24 hours of them being cut from the pavement
label | Activity - I
label | By - PE
checkpoint | 9.01.12 NDM Density
label | Acceptance / Conformance Criteria - NDMs are to be completed at the time of pacing to ensure compile when cores are taken
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - IANZ Lab Report
label | Frequency - min 8 per lot (day)
label | Activity - I
label | By - PE
checkpoint | 9.01.13 Transverse truth of the surface
label | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Post Seal
label | Activity - I
label | By - SE
checkpoint | 9.01.14 Finished Pavement Level, Alignment, and Thickness
label | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
label | Standard / Specification - NZTA M10:2020 - 10
label | Verifying Document - Survey
label | Frequency - Continuous thought construction
label | Activity - I
label | By - SE
checkpoint | 9.01.15 NAASRA - Asphalt Surfacing
label | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements as per TM7003. No 20m reading in any lane shall exceed 60 NAASRA counts/km for an asphaltic concrete surface.
label | Standard / Specification - PS 14.1.4.2, PS 17.7, NZTA M10:2020 - 10, TM7003
label | Verifying Document - Test Report
label | Frequency - Prior to End of Defects
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.01.16 Skid Resistance
label | Acceptance / Conformance Criteria - The surfacing shall meet the requirements specified in the Waka Kotahi Specification T10 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments.
label | Standard / Specification - PS 14.2, PS 17.7
label | Verifying Document - Test Report
label | Frequency - Prior to End of Defects
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2676-DOW-ITP-CV-0119 - Roading Furniture and Marking | itp |  |  |  |  | DS2676-DOW-ITP-CV-0119-Roading Furniture and Marking Rev 1
section | 7.04 Road marking
checkpoint | 7.01.01 Setting out the new road markings
label | Acceptance / Conformance Criteria - Setting out the new road markings following resurfacing and Carrying out pavement marking within 48 hours of sealing.
label | Standard / Specification - PS 18.1
label | Verifying Document - Programme
label | Frequency - within 48 hours of sealing.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.01.02 Dry film thickness Inspection
label | Acceptance / Conformance Criteria - The dry film thickness of each layer shall be as specified in Clause 13.1 of NZTA P/22.
label | Standard / Specification - PS 18.1.3.4
label | Verifying Document - Thickness Checks
label | Frequency - During Painting
label | Activity - I
label | By - SE
section | 7.05 Traffic signs
checkpoint | 7.05.01 Sign Positions
label | Acceptance / Conformance Criteria - The sign locations shown on the drawings are indicative only (New and Relocated). Actual positions will be fixed on site jointly between the Engineer and the Contractor. The Contractor shall supply all pegs, paint etc necessary to achieve this. This operation shall be carried out before the manufacture of the signs and their supports.
label | Standard / Specification - 18.2.4.1
label | Verifying Document - Survey
label | Frequency - Prior to install
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.05.02 Relocated signs
label | Acceptance / Conformance Criteria - All relocated signs shall be in the same condition as prior to uplift and relocation.
label | Standard / Specification - 18.2.5.2
label | Verifying Document - Condition Records
label | Frequency - Prior to Relocation
label | Activity - I
label | By - SE
checkpoint | 7.05.03 Pre-Pour Inspection
label | Acceptance / Conformance Criteria - Complete a comprehensive pre-pour inspection and obtain approval (Inspection or Verbal) from the Engineer prior to pouring.
label | Standard / Specification - PS 27.6.1
label | Verifying Document - Signed Pre-Pour
label | Frequency - 24 hours prior to the casting of any unit
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.05.04 Delivery Dockets
label | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, admixtures and quality, mixing time, water added during batching and maximum aggregate size.
label | Standard / Specification - PS 27.7.11, PS 27.4.3.6
label | Verifying Document - Dockets / Bag Details
label | Frequency - Each Pour
label | Activity - R
label | By - PE
checklist | DS2676-DOW-ITP-CV-0120 - Road Opening | itp |  |  |  |  | DS2676-DOW-ITP-CV-0120-Road Opening Rev 1
section | 7.06 Road Opening
checkpoint | 7.06.01 Pre-Opening Safety Review
label | Acceptance / Conformance Criteria - Prior to opening the Works for use by the general travelling public, a pre-opening safety review will be undertaken by the Engineer and the Principal’s Road Safety Audit team, to approve the removal of any temporary works, speed limits and traffic management.
label | Standard / Specification - PS 7.5.1
label | Verifying Document - Safety Review
label | Frequency - Prior to opening the Works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.06.02 Post Construction Safety Audit
label | Acceptance / Conformance Criteria - Prior to the issue of Practical Completion, a post construction safety audit must be completed by the Engineer and the Principal’s Road Safety Audit team.
label | Standard / Specification - PS 7.5.2
label | Verifying Document - Safety Audit
label | Frequency - Prior to the issue of Practical Completion
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT