## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2676-DOW-ITP-CV-0121-Utilities And Street Lighting | itp |  |  |  |  | DS2676-DOW-ITP-CV-0121-Utilities And Street Lighting Rev 1
section | 10.01 Utilities and Spare Ducts
checkpoint | 10.01.01 ITS Equipment Protection
label | Acceptance / Conformance Criteria - The Contractor shall protect any such equipment from damage during the works until relocated by the MRA. The Contractor shall liaise with the MRA to arrange relocation of such equipment so that it does not impede on the construction programme.
label | Standard / Specification - PS 19.1.1.2
label | Verifying Document - Comms
label | Frequency - Prior to Works
label | Activity - R
label | By - PE
checkpoint | 10.01.02 Spare Ducts
label | Acceptance / Conformance Criteria - Spare ducts shall be fitted with draw wires and caps to allow future installation of services.
label | Standard / Specification - PS 19.1.1.3
label | Verifying Document - Site Notes
label | Frequency - During Install
label | Activity - I
label | By - SE
checklist | DS2676-DOW-ITP-CV-0122-Stormwater Overarching | itp |  |  |  |  | DS2676-DOW-ITP-CV-0122-Stormwater Overarching Rev 0A
section | 6.01 Stormwater General
checkpoint | 6.01.01 Setting Out Service Clashes
label | Acceptance / Conformance Criteria - The Contractor shall advise any clashes at least 5 working days before works are proposed to proceed to allow sufficient time for a reply.
label | Standard / Specification - PS 16.4.1, PS 16.3.1
label | Verifying Document - Notice
label | Frequency - At least 5 working days before works are proposed
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.02 Pipe Minimum Cover
label | Acceptance / Conformance Criteria - Culverts / pipes under pavement or trafficable areas (berms, access roads) shall have a minimum of 1,000 mm of cover unless specifically stated otherwise on the drawings. If minimum cover requirements cannot be achieved the Engineers input is required before work can proceed.
label | Standard / Specification - PS 16.3.1, PS 16.8.4.1
label | Verifying Document - Notice
label | Frequency - When Encountered
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.03 Pipe Alignment
label | Acceptance / Conformance Criteria - A proposed change in pipe alignment the Engineers input is required before work can proceed
label | Standard / Specification - PS 16.3.1
label | Verifying Document - Notice
label | Frequency - When Encountered
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.04 Unsuitable Founding Material
label | Acceptance / Conformance Criteria - If unsuitable founding material is encountered the Engineers input is required before work can proceed
label | Standard / Specification - PS 16.3.1
label | Verifying Document - Notice
label | Frequency - When Encountered
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.05 Dewatering
label | Acceptance / Conformance Criteria - The Contractor shall provide for keeping the works free from water at all times and shall provide, operate and maintain all pumping equipment, drains, sumps and other measures necessary for this purpose
label | Standard / Specification - PS 16.5.1
label | Verifying Document - Site Notes
label | Frequency - During Construction
label | Activity - S
label | By - SE
checkpoint | 6.01.06 Environmental Compliance
label | Acceptance / Conformance Criteria - All works shall be undertaken using an appropriate construction methodology to minimise the release of silt, sediment or other pollutants into any watercourse.
label | Standard / Specification - PS 16.6.1
label | Verifying Document - Methodology
label | Frequency - Prior to Works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03.04 Compaction trials
label | Acceptance / Conformance Criteria - At commencement of pipelaying, compaction trials shall be undertaken to demonstrate the adequacy of the proposed compaction methods to achieve the compaction parameters specified (refer to Table 16.7, and Section 16.7.3 of this Specification).
label | Standard / Specification - PS 16.12.3.1
label | Verifying Document - Compaction Trail Test Results
label | Frequency - At commencement of pipelaying
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03.10 As-Builts
label | Acceptance / Conformance Criteria - As-built details of all stormwater infrastructure shall be recorded by the Contractor and provided to the Engineer in AutoCAD and hard copy format. As-built details shall be provided not only for new infrastructure but also for modified, removed or abandoned existing infrastructure
label | Standard / Specification - PS 16.13.1, PS 16.13.2
label | Verifying Document - CAD Asbuilts
label | Frequency - Prior to PC
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2676-DOW-ITP-CV-0123-Stormwater Pipline and Manhole | itp |  |  |  |  | DS2676-DOW-ITP-CV-0123-Stormwater Pipline and Manhole Rev 0A
section | 6.02 Pipes Installation
checkpoint | 6.02.01 Geo-textiles and Filter Cloths Installation
label | Acceptance / Conformance Criteria - All Geo-textiles and filter cloths shall be handled and installed in accordance with the manufacturer’s requirements and have a minimum lap of 500mm when placed above the final water level an1m when placed below the final water level. Further to that shown on the drawings, all geotextile laps shall be orientated to the direction of flow.
label | Standard / Specification - PS 16.11.2
label | Verifying Document - Site Records
label | Frequency - When Installed
label | Activity - I
label | By - SE
checkpoint | 6.02.02 Pipe Support
label | Acceptance / Conformance Criteria - Concrete pipe support shall be a minimum of H2 unless stated otherwise
label | Standard / Specification - 16.8.2.1
label | Verifying Document - Site Records
label | Frequency - When Installed
label | Activity - I
label | By - SE
checkpoint | 6.02.03 Embedment Wrapping
label | Acceptance / Conformance Criteria - Where the pipe bedding / haunching / embedment material is not compatible with the surrounding fill or in-situ material (i.e. there are voids, or low-fines fill material is used in in-situ silt material) the trench shall be wrapped in filter cloth or an equivalent grade non-woven needle-punched geotextile filter cloth product complying with TNZ F/7.
label | Standard / Specification - 16.8.2.2
label | Verifying Document - Site Records
label | Frequency - When Embedment material is not compatible with the surrounding fill
label | Activity - I
label | By - SE
checkpoint | 6.02.04 Embedment Placement
label | Acceptance / Conformance Criteria - Pipe embedment material (haunch and overlay) shall be placed and compacted in maximum 150 mm lifts
label | Standard / Specification - 16.8.2.3
label | Verifying Document - Site Records
label | Frequency - Each Layer
label | Activity - I
label | By - SE
checkpoint | 6.02.05 Connections to Structures
label | Acceptance / Conformance Criteria - PVC-U or RCRRJ pipes shall include a pipe short adjacent to the connection to any structure / headwall and at all sumps / manholes. The exception to this is larger diameter RCRRJ pipes (>DN675) where pipe shorts are not available or may be omitted due to diameter.
label | Standard / Specification - 16.8.2.4
label | Verifying Document - Site Records
label | Frequency - Each Connection
label | Activity - I
label | By - SE
checkpoint | 6.02.07 Pipes on grades steeper than 10%
label | Acceptance / Conformance Criteria - Pipes on grades steeper than 10% (or 1:10 (V:H)) are to have cement-stabilised bedding and haunching wrapped in filter cloth.
label | Standard / Specification - PS 16.8.6.1
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Activity - R
label | By - PE
checkpoint | 6.02.08 DN375 and smaller pipes laid at grades of 20%
label | Acceptance / Conformance Criteria - DN375 and smaller pipes laid at grades of 20% (or 1:5 (V:H)) or steeper are to be SN16 PVC-U DWV pipe or Series 1 pressure pipe with an equivalent stiffness rating. A concrete bulkhead shall be installed at each pipe socket as shown on the Contract Drawings, excluding the manhole starter or finisher when cast into a concrete corbel.
label | Standard / Specification - PS 16.8.6.1
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Activity - R
label | By - PE
checkpoint | 6.02.09 Pipe Installation in or under an Embankment
label | Acceptance / Conformance Criteria - Where pipes are installed within or under fill embankments, the pipe shall be laid in an ‘induced excavated trench’.
label | Standard / Specification - PS 16.8.7.1
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Activity - R
label | By - PE
checkpoint | 6.02.10 Pipe installed deep under embankments
label | Acceptance / Conformance Criteria - Where pipes are installed under a significant depth of embankment fill material (>5 m), great care shall be taken to ensure the surrounding embankment material is well compacted and that the pipe bedding and surround material is well compacted. Use HS3 support in accordance with AS/NZS3725 where cover exceeds 5 m.
label | Standard / Specification - PS 16.8.7.2
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Activity - R
label | By - PE
section | 6.03 Inspection and Testing
checkpoint | 6.03.01 Sub-grade Visual inspection
label | Acceptance / Conformance Criteria - Visual inspection of sub-grade material prior to placement of bedding material where any unsuitable material, hard spots or weak founding material has been replaced.
label | Standard / Specification - PS 16.12.1.1
label | Verifying Document - Site Notes
label | Frequency - During Construction
label | Activity - S
label | By - SE
checkpoint | 6.03.02 Subgrade Testing - Scala
label | Acceptance / Conformance Criteria - A minimum CBR of 5% or 3 blows per 100 mm using a Scala Penetrometer is considered an acceptable sub-grade strength. The Engineer shall be notified where this is not achieved. Testing of founding material for appropriate strength at 10 m intervals or as otherwise directed by the Engineer.
label | Standard / Specification - PS 16.12.1.1, PS 16.12.1.2
label | Verifying Document - Scala Results
label | Frequency - At 10 m intervals
label | Activity - I
label | By - SE
checkpoint | 6.03.03 Low fines - Compaction Testing
label | Acceptance / Conformance Criteria - No compaction testing is required for ‘low fines’ material (defined as having 0% passing a 2.36 mm sieve) subject to having a compaction fraction of 10% or less (refer to Section 16.7.3.5).
label | Standard / Specification - PS 16.12.2.2
label | Verifying Document - Compaction Fraction Test
label | Frequency - Prior to Installation
label | Activity - R
label | By - SE
checkpoint | 6.03.05 Acceptable Compaction trials
label | Acceptance / Conformance Criteria - Provided the material and method of placement and compaction remain the same as determined by the trial, regular testing is not required where the construction is periodically inspected or supervised by the Engineer or his representative.
label | Standard / Specification - PS 16.12.3.5
label | Verifying Document - Notice
label | Frequency - At commencement of pipelaying
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03.06 Unacceptable Compaction trials - Bedding Compaction
label | Acceptance / Conformance Criteria - Where the Engineer has any concerns over the suitability of the bedding or haunching material, or the thickness of lifts being carried out, or an alternative means of installation is undertaken, testing of material compaction can be requested by the Engineer at any time. Testing shall consist of Clegg Hammers calibrated to the material at 20 m intervals for the bedding layer and every second lift of the haunch material. A minimum CIV of 12-15 shall be achieved for all embedment material.
label | Standard / Specification - PS 16.12.3.6
label | Verifying Document - Clegg and NDMs
label | Frequency - NDM at start of Run, Calibrated Cleggs every 20m
label | Activity - I
label | By - SE
checkpoint | 6.03.07 Flexible Pile Embedment Compaction
label | Acceptance / Conformance Criteria - Compacting approved material in 150mm lifts to a minimum compaction of 95% MDD
label | Standard / Specification - PS 16.12.3.2
label | Verifying Document - As per Trial
label | Frequency - As per Trial
label | Activity - I
label | By - SE
checkpoint | 6.03.08 Concrete Pile Embedment Compaction
label | Acceptance / Conformance Criteria - Compacting approved material in 150mm lifts to a minimum compaction of 95% MDD
label | Standard / Specification - PS 16.12.3.6
label | Verifying Document - As per Trial
label | Frequency - As per Trial
label | Activity - I
label | By - SE
checkpoint | 6.02.06 Wide Trenches
label | Acceptance / Conformance Criteria - Where insitu soil conditions are deemed unacceptable, the support zone needs to be increased in width. This would involve widening the trench to four times the pipe’s internal diameter and refilling with approved material in 150mm lifts to a minimum compaction of 95% MDD, or for cohesionless material a Density Index of 70%.
label | Standard / Specification - 16.8.2.5
label | Verifying Document - Site Records / NDMs
label | Frequency - NDMS every 20m every lift
label | Activity - I
label | By - SE
section | 6.04 Conformace Testing
checkpoint | 6.03.09 CCTV
label | Acceptance / Conformance Criteria - All pipes (excluding sub-soil drains) shall be filmed with CCTV once the surface above has been finished. The CCTV shall be reviewed for any visible defects in the pipes.
label | Standard / Specification - PS 16.12.4.1
label | Verifying Document - Footage and Logsheet
label | Frequency - Each Pipeline (Excluding Subsoil)
label | Activity - I
label | By - PE
section | 6.04 Manholes
checkpoint | 6.04.01 Manhole cover slabs
label | Acceptance / Conformance Criteria - Manhole cover slabs shall finish approximately 200 mm below the finished pavement to allow pavement construction or top-soiling above. A manhole access riser shall be included to make up the difference from the cover slab to the underside of the access cover frame. The total dimension from pavement level to the soffit of the cover slab must not exceed 500 mm.
label | Standard / Specification - PS 16.9.1.2
label | Verifying Document - Site Records
label | Frequency - Each Manhole
label | Activity - I
label | By - SE
checkpoint | 6.04.02 Manhole Connections
label | Acceptance / Conformance Criteria - When connecting the pipe to the manhole, neatly cut or core drill the concrete to match the outside diameter of the pipe to provide a gap of 10-50 mm. The gap shall then be sealed with epoxy mortar both inside and outside to seal the joint. Where the gap exceeds 50 mm or the concrete has spalled, a concrete corbel shall be constructed to seal the opening from soil ingress.
label | Standard / Specification - PS 16.9.1.4
label | Verifying Document - Site Records
label | Frequency - Each Manhole Connection
label | Activity - I
label | By - SE
checkpoint | 6.04.03 Manhole access cover
label | Acceptance / Conformance Criteria - The manhole access cover and frame shall be hinged, with the hinge position orientated towards the direction of on-coming traffic. The access cover, frame and access opening on the cover slab shall have a nominal internal dimension of 600 mm.
label | Standard / Specification - PS 16.9.1.6
label | Verifying Document - Site Records
label | Frequency - Each Manhole
label | Activity - I
label | By - SE
checkpoint | 6.04.04 Manhole Benching
label | Acceptance / Conformance Criteria - All manhole inverts shall be benched to form a smooth transition between the connected pipes unless stated otherwise. For pipes smaller than DN450 the manhole shall be fully benched.
label | Standard / Specification - PS 16.9.1.7
label | Verifying Document - Site Records
label | Frequency - Each Manhole
label | Activity - I
label | By - SE
section | 6.05 Sump
checkpoint | 6.05.01 Kerb Inlet
label | Acceptance / Conformance Criteria - All sumps located along a kerb shall include a pre-cast side entry lintel. The lintel shall be aligned to the face of the kerb. Where the lintel is proud of the adjacent kerb, the two shall be transitioned together smoothly over a minimum distance of 0.5 m.
label | Standard / Specification - PS 16.10.2
label | Verifying Document - Site Records
label | Frequency - Each Sump
label | Activity - I
label | By - SE
checklist | DS2676-DOW-ITP-CV-0124-Landscaping Installation | itp |  |  |  |  | DS2676-DOW-ITP-CV-0124-Landscaping Installation Rev 1
section | 18.01 Landscaping
checkpoint | 18.01.01 Work Plan
label | Acceptance / Conformance Criteria - A detailed work plan shall be prepared for all landscape works, at least two weeks prior to the landscape works commencing on site. This shall be submitted to the Landscape Architect.
label | Standard / Specification - NZTA P39:2013 - B5.1
label | Verifying Document - work plan
label | Frequency - At least two weeks prior to the landscape works commencing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18.01.02 Landscaping Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two working days prior to carrying out all activities detailed in Section B, Table1 of NZTA P39:2013 to enable the Engineer to inspect key works.
label | Standard / Specification - PS 25.1.3
label | Verifying Document - Notice
label | Frequency - At least two working days prior to carrying out Landscaping
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18.01.03 Planting
label | Acceptance / Conformance Criteria - Should the need for planting arise, the preparation of planting, supply of plants, planting, staking (of trees if required), fertilizing and mulching of all plant material shall fully comply with Section G of NZTA P39:2013.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Checksheet
label | Frequency - Each Planting Area
label | Activity - R
label | By - PE
checkpoint | 18.01.04 Reporting
label | Acceptance / Conformance Criteria - Throughout the implementation of the works the contractor shall monitor the progress and condition of the works and provide a 3 monthly report.
label | Standard / Specification - NZTA P39:2013 - B3
label | Verifying Document - Report
label | Frequency - 3 monthly report.
label | Activity - R
label | By - PE
checkpoint | 18.01.05 Plant Quality Samples
label | Acceptance / Conformance Criteria - Two samples of each area planted will be inspected. For planting areas less than 2,000 m2 , the sample area will be a minimum 5% of the entire area. For planting areas larger than 2,000 m2 , the sample area will be a minimum of 2% of the entire area.
label | Standard / Specification - NZTA P39:2013 - B6.1
label | Verifying Document - Inspection Result
label | Frequency - Two samples of each area
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18.01.06 Grassed Surfaces Quality
label | Acceptance / Conformance Criteria - Grassed surfaces shall be deemed in an acceptable condition when No ponding of surface water occurs (excluding stormwater assets) and Grass covers 95% of the grassed areas.
label | Standard / Specification - NZTA P39:2013 - B7
label | Verifying Document - Checksheet
label | Frequency - Each Planting Area
label | Activity - I
label | By - PE
checkpoint | 18.01.07 Hydro-seeding Quality
label | Acceptance / Conformance Criteria - Hydro-seeded grass surfaces shall be deemed in an acceptable condition when No ponding of surface water occurs (excluding stormwater assets) and Grass covers 95% of the grassed areas
label | Standard / Specification - NZTA P39:2013 - B8
label | Verifying Document - Checksheet
label | Frequency - Each Planting Area
label | Activity - I
label | By - PE
checkpoint | 18.01.08 Inspections
label | Acceptance / Conformance Criteria - The Contractor shall notify the Landscape Architect for inspection of the works as specified in P39 Table 1.
label | Standard / Specification - NZTA P39:2013 - B4
label | Verifying Document - Table 1 Checksheet
label | Frequency - Each Planting Area
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT