## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-041 - Rail Expansion Joint Installation Rev1 | itp |  |  |  |  | ITP-041 - Rail Expansion Joint Installation Rev1
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Design Drawings and Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | • Ensure that all employees and contractor involved in the welding process and are signed onto the relevent hot works permit
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.3 Check materials and expansion joint systems
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
label | • Check condition of rail sleepers / pandrols
label | • Ensure rail jewellery is of sound condition
label | • Ensure expansion joint box are of adequate condition
label | REFERENCE DOCUMENTS: AS 1085 IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Client, Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.4 Welders qualifications
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
label | • TLIW2012 Grind Rails
label | • TLIW3015 Weld Rails using Aluminothermic welding process
label | • TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.5 Ultrasonic testers qualifications
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
section | Expansion Joints Works
checkpoint | 2.1 Gap setting
label | FREQUENCY: Each box
label | ACCEPTANCE CRITERIA: Ensure the box is set to the manufacturer's gap setting and temperature criteria. As below;
label | REFERENCE DOCUMENTS: Prazska Drawing 1PA.031.000.00.00.1
label | • IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.2 Installation of expansion joint system
label | FREQUENCY: Each expansion joint box
label | ACCEPTANCE CRITERIA: Ensure the expansion joints are installed in the correct direction. I.e., moving and fixed end are in correct orientation.
label | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.3 Grouting
label | FREQUENCY: Each box
label | ACCEPTANCE CRITERIA: Contractor to ensure that non-shrinking grout fill is installed between bridge deck and rail expansion joint system.
label | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.4 Construction of expansion joint
label | FREQUENCY: Each expansion joint box
label | ACCEPTANCE CRITERIA: Ensure rubber boots are installed per manufacturers requirements prior to concreting.
label | • Use anchoring plates to hold the rail expansion joints in position.
label | • Ensure that all collapsed grooves are reformed.
label | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.5 Expansion joint bonding system
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure bonds are sealed as per agreed method with Yarra Trams
label | • Ensure the rail bond is correctly positioned from old 41kg rail
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
section | Construction Works
checkpoint | 3.1 Installation of pandrol plate
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pandrol plates to be installed as required/instructed by the client
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.2 Placement of rail
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All track work, including expansion joint systems shall confrom to alignment, offset, level and cant as per design drawings and track charts
label | • Bottom of rail and bearing surface shall be clean of foreign materials before laying
label | • Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
label | • Geometry tolerances as follows:
label | – Centreline location: +/- 3mm
label | – Level: +/- 3mm
label | – Line measured (>10m chord): +/- 3mm
label | – Twist (3.5m chord): +/- 2mm
label | – Cant: +/- 3mm
label | – Gauge (open track): +3mm, -0mm
label | Note: Cant shall be applied uniformly over transitions
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completion of track charts
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.3 Placement of jewellery
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Each pandrol shall be fastened to track with approved jewellery and rail clips
label | • Clips shall be installed with panpuller or equivalent
label | • All fasteners shall be sealed as per agreed method with Yarra Trams
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.4 Rail end preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
label | • Minimum closure length from proximity of welds shall be 2m
label | • Rail end conditions shall match (i.e flame cut - flame cut)
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.5 Welding of rail
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Joints shall be square across the track
label | • Maximum skew at square joints shall be 65mm
label | • Portions shall match rail type (i.e HHR, Ordinary)
label | • Welds shall not be within:
label | – 3m of another weld
label | – 3m of a rail end
label | – 1.5m of a glued insulation joint assembly
label | • Field welds shall be +/- 50mm from centre of bay between sleepers
label | • Weld Return forms shall be completed by qualified welder
label | • Welds shall be grinded after 1 hour
label | • Welds shall be free of water
label | • Post grinding, welds shall be cleaned for visual inspection
label | REFERENCE DOCUMENTS: CE-019-ST-0033 ccl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.6 Grinding & cleaning welds
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
label | • Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
label | • The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.7 Track adjustment
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths.
label | • In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
label | • Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.8 Reinforcement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
label | • All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
label | • Reinforcing mesh shall be handled carefully to prevent distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
label | • Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
label | • Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.9 Dowels
label | FREQUENCY: Where Required
label | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
label | • All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
label | • Dowels shall be clean and free from mill scale, loose rust or oil.
label | • Ensure that all dowels are securely held in their correct position until the concrete has set.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.10 Pre pour inspection
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
label | • Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, system drainage are satisfactory for the expansion joint systems
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: FH Track Inspection
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 Post pour inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
label | • Ensure no defects are present in slab
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Post pour checklist
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
section | Testing
checkpoint | 4.1 Track testing
label | FREQUENCY: Each weld
label | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator.
label | • Failed welds shall be cut out and replaced
label | • Testing documentation shall be recorded and supplied to the superintendent
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed Off
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer/NDT
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: