## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | ac504198-101b-44f9-ae4b-7aef708d377e |  | checklist | FHC-ITP-003 - Subgrade Preparation Rev1 | itp |  |  |  | Yes | FHC-ITP-003 - Subgrade Preparation Rev1 | 0c838bf7-1bbb-46d3-a472-4cde14144564
checkpoint-group | 38d83b7a-5627-4554-97c9-f917fdc42324 |  | section | 1 - Preliminary Works
checkpoint-status | b4ffbbdc-5e67-4fc4-b68a-ee060ef67b3f |  | checkpoint | 1.1 Check for correct documentation
label | 1824078b-d9d4-5522-b29a-d2cd46092662 |  | note | FREQUENCY: Prior to commencing any activity
label | 04d07202-1e69-5fd7-978a-8810ed26bf49 |  | note | – – – – – – – – –
label | fa0c6d31-4ace-5a98-b4b6-02a650405222 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | adcf9285-329a-5585-9af0-c59ab6607732 |  | note | – using the correct and complete set of drawings
label | 1175710d-dba0-567b-9380-8ab088bbd18c |  | note | – all drawings are the latest revision
label | fdd590e2-e92f-5717-b7f0-47d5077fe8b1 |  | note | – – – – – – – – –
label | 7d745fa6-6ef3-58a0-928c-3e68053f554a |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 8498a099-602a-5f46-b23e-693e4d6b984a |  | note | – – – – – – – – –
label | a0a75aff-c44d-581c-b079-f8ac75b1180a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | ec24fcc5-78a5-5cac-99b1-e0e4795df706 |  | note | – – – – – – – – –
label | 7060298d-27ae-50cc-92fa-01a8c60e670a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 84f010f7-ea71-51e8-8152-cb9c2ad483d7 |  | note | – – – – – – – – –
label | abaf86b0-606f-5fa8-867d-8625815bc46c |  | note | HP*
label | 033cdabb-5060-5ced-93a2-be61531b035e |  | note | – – – – – – – – –
label | 9adc2b29-1629-52df-b02a-021d11d20acf |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 644842e5-45a1-5fd6-a991-dfd32ebf3992 |  | note | – – – – – – – – –
text | f1115986-27f9-5e82-9d17-e24ec6ae0cc7 |  | textbox | DATE:
checkpoint-status | 48b2bce0-dcee-4f30-a32a-c0cee224d2e6 |  | checkpoint | 1.2 Implementation of all measures and controls
label | fdf7803f-1041-59bb-acb2-c15274360d92 |  | note | FREQUENCY: Prior to commencing any activity
label | dbc98cfd-7392-5f6a-8b53-577868aea875 |  | note | – – – – – – – – –
label | f622a023-e0cc-58d2-893e-806c39dfa868 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 3b06efba-963f-52f5-9b97-e304e9fcc591 |  | note | – – – – – – – – –
label | 60ffb8c5-3bd1-59ba-8d8c-9dd627612a9a |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 3a2daab8-3b86-541b-b73d-27d11acbccca |  | note | – – – – – – – – –
label | 703c32ef-44cf-5249-98fb-d9a88e4621fe |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | adbdc851-ac55-5bea-95a1-7c4e90a52d30 |  | note | – – – – – – – – –
label | 762d6637-c14d-5558-97c9-d40478f0a64d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 89e3ed32-f441-53d9-b119-b1af8944746c |  | note | – – – – – – – – –
label | fd76dae2-4884-5568-938d-645286bec4b2 |  | note | HP*
label | 1a4527f7-8a02-556e-9983-6ecd99a7b749 |  | note | – – – – – – – – –
label | 1d03b69f-ad85-59f6-97c2-417d6cec4fd6 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 1ab86946-8ce5-5500-afe9-ab00e96da746 |  | note | – – – – – – – – –
text | 2b8c3386-873d-5c77-adac-4a2777913d66 |  | textbox | DATE:
checkpoint-group | dbf93825-4572-416d-a348-6e54ecfe1018 |  | section | 2 - Construction Works
checkpoint-status | 57908879-16f5-4a67-8a02-273c59e15489 |  | checkpoint | 2.1 Survey Set-Out
label | cad83506-6c3c-5fae-82bd-fdfa7c1d2e6d |  | note | FREQUENCY: Prior to commencement of excavation
label | 39ba6dfa-cf2d-5051-8c93-7671af98604d |  | note | – – – – – – – – –
label | fd6b5567-365a-5ab8-923e-e79f4be2bc80 |  | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | 01799a38-7cc3-5abc-9705-5d63ebe115da |  | note | – – – – – – – – –
label | 5c4a6938-1655-5056-9da5-5c892dea6a46 |  | note | REFERENCE DOCUMENTS: Drawings, Work Procedure
label | 6b85ba2d-612f-5c6d-8c01-b9ae69ac8c87 |  | note | – – – – – – – – –
label | 4064b0b2-86fe-55d7-9ece-46aea8bd0349 |  | note | INSPECTION/TEST METHOD: Verify
label | 1cb307cf-df09-56fc-9cdc-859683690c6f |  | note | – – – – – – – – –
label | e57ba0b5-3f83-55fd-b720-b8dff8e4ebb2 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 70f040e6-9625-53eb-b7f2-00353ab666d4 |  | note | – – – – – – – – –
label | 8dca69ea-439a-5a9f-b4bc-41ab49f02cc0 |  | note | IP
label | fe144d3a-4533-5ce5-bcba-0d11bca9d5d4 |  | note | – – – – – – – – –
label | f5d5dbb6-16f0-59eb-9732-9509d3da05f8 |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | e9b2349b-0b9e-5d3f-8847-f3efdb51008d |  | note | – – – – – – – – –
text | 20dbe163-376f-5d80-a445-ffb163fe531b |  | textbox | DATE:
checkpoint-status | c7c77f2f-e8b6-4bf9-bbdb-15e22e2d60ad |  | checkpoint | 2.2 Excavation Permit
label | 9d89f5b1-540a-5c39-a5f3-a3ee94254ca6 |  | note | FREQUENCY: Each lot
label | c5e04f90-50d6-5d00-a67a-1dc72d1157ce |  | note | – – – – – – – – –
label | 1450753a-eed6-53b5-a782-15451be3a8a0 |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | 260a3988-166f-5403-b75e-73f24cbe4ee1 |  | note | • Plant and equipment shall be appropriate for the task.
label | a9f89916-bd69-52ca-896c-948662c9fec4 |  | note | • Excavation operations shall not disturb areas outside the limit of excavation
label | 544e7578-423a-556e-a669-d9601fbbd0c7 |  | note | – – – – – – – – –
label | bb27ad79-9d98-54aa-bfb5-6f46f00bae23 |  | note | REFERENCE DOCUMENTS: Excavation permit
label | 980401f5-1851-5f8a-87bf-68cb91d08eb2 |  | note | – – – – – – – – –
label | 32cdd57a-e9a2-533b-90aa-c732a12c558f |  | note | INSPECTION/TEST METHOD: Verify
label | 71b5f394-5ae4-540a-b590-492e9bfc3d9b |  | note | – – – – – – – – –
label | d90f40a6-574e-53e3-87de-b19d540d7fb4 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 3203d34a-9894-52fa-93cd-851c8ecb7785 |  | note | – – – – – – – – –
label | 773ea7a9-744f-562b-a13a-4f11b1474af2 |  | note | HP*
label | 9abe418d-87f4-5c12-b677-50d70290ed87 |  | note | – – – – – – – – –
label | 1b710d61-cea5-5304-af33-a61dbaa460b4 |  | note | RESPONSIBILITY: Site Engineer
label | 154a02f8-35e8-59cb-b314-66f7de553a42 |  | note | – – – – – – – – –
text | dccaf880-b51a-577e-aa23-eab89812d7ac |  | textbox | DATE:
checkpoint-status | b6e14ac0-9fec-4b0c-8b20-6cdf0bc829c5 |  | checkpoint | 2.3 Subgrade Material Properties
label | d4e371c3-c308-5b10-b537-0c192168dfe5 |  | note | FREQUENCY: Each Lot
label | ba89f1d5-047a-5bb2-990a-2d67e23417fc |  | note | – – – – – – – – –
label | fd95cda4-38f9-5252-ba07-faba0cd02dbb |  | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
label | 80ac9cf9-a800-522d-a759-506dd6a979ed |  | note | • If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
label | f1445599-8d32-5b81-8834-e8fe7b5db2a8 |  | note | – – – – – – – – –
label | a57d57dd-2bba-59eb-b252-8162ed2bf233 |  | note | REFERENCE DOCUMENTS: 204.06 (e)
label | dfb0227d-2cb3-5cc1-85da-0457b26f0e24 |  | note | – – – – – – – – –
label | 3990a869-8f1f-53f7-9381-3577c62f2530 |  | note | INSPECTION/TEST METHOD: Test Point
label | f4364361-08f1-5ec8-a93d-e9ba39388beb |  | note | – – – – – – – – –
label | e545a99f-9959-5e4b-a698-91f6f352ec2a |  | note | RECORD OF CONFORMITY: Test Reports
label | 3ba44e5d-b555-5f8f-90f0-a979d42360da |  | note | – – – – – – – – –
label | 658d720e-2cc6-5a91-9172-5c45e20ed9c4 |  | note | TP
label | 0263ff3e-5198-5ffb-99a6-e2f2a0847924 |  | note | – – – – – – – – –
label | 4c620043-6760-534c-97a1-263295a55531 |  | note | RESPONSIBILITY: Site Engineer
label | 9639cf83-9862-5a77-a036-e381091a368e |  | note | – – – – – – – – –
text | 0969ed68-ba7e-5def-a176-b19d910e4b22 |  | textbox | DATE:
checkpoint-status | 62fdfa35-6c85-4495-a764-16d823f4b10a |  | checkpoint | 2.4 Inspection of Subgrade Material
label | 2ee5b932-630f-5f2a-ada8-cf2304dd8815 |  | note | FREQUENCY: Each lot
label | 3effeb7b-f94a-5a00-a116-3e6a23035473 |  | note | – – – – – – – – –
label | 2efefdd3-eb95-5096-a778-69f1d59be508 |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | b703a95d-50bd-5bb9-84d1-ac706d97bb68 |  | note | – – – – – – – – –
label | 8ae47a8e-f517-519a-be0e-f7230efa9659 |  | note | REFERENCE DOCUMENTS: 204.06 (c)
label | b9db83b4-9957-5c4c-8e0c-c4784df48e2d |  | note | – – – – – – – – –
label | 0e3e5f03-4e57-5cdb-bcad-61b01a34f6dc |  | note | INSPECTION/TEST METHOD: Verify
label | d35d15de-1fe4-53e4-8962-3f40f76521dd |  | note | – – – – – – – – –
label | 0320b684-ea0a-5313-8aed-400a6e30f69c |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | bcf5ea5a-9a0e-59d6-b6a2-16f241013c92 |  | note | – – – – – – – – –
label | 4c9c65a7-3531-5b24-9e55-4ce0856723b6 |  | note | HP
label | e715827d-d873-5f70-9abf-bff92ceab6f1 |  | note | – – – – – – – – –
label | d2ac115e-c167-5ebc-bb54-093d14a2737a |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | ff5f7b8a-6cbd-55a4-8a7f-5d990f439b03 |  | note | – – – – – – – – –
text | 09e4ead3-09e6-5d9f-9064-3b9b13a41677 |  | textbox | DATE:
holdpoint | 9314a548-e424-448f-a1dc-40b6d16852f1 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 6829693d-88a2-43bb-ab52-1a3411b83eab |  | checkpoint | 2.6 Acceptance of Rock Subgrade (when applicable)
label | ffe0f3b0-da82-541d-9c7a-4666a62e9dbb |  | note | FREQUENCY: Prior construction of the regulating layer
label | ccc57c1b-302f-5cba-b58c-d447f5af2553 |  | note | – – – – – – – – –
label | f5fef11f-5eb6-502e-a7f4-f3c7b8bbc0c7 |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 6c1fd408-a320-55cc-8606-03adef1efbe9 |  | note | • Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | 2c5f5c8e-5fe3-5d44-a2e3-e0393f583a5c |  | note | – – – – – – – – –
label | f5dab8b5-9e8c-5b81-8d1b-83b5de261392 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | debea36d-c06c-51ce-b9e3-2ca2e3ee8496 |  | note | – – – – – – – – –
label | 90459e09-3b4b-54e8-829d-2c18f5c29038 |  | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | 315d4cbc-a848-56b1-aaf5-bcdfd38a43fe |  | note | – – – – – – – – –
label | 81fda7a1-654d-5933-8f44-92799b5d3b19 |  | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | 16886e72-5da2-58e6-96a0-47caf0a511bc |  | note | – – – – – – – – –
label | e2ece250-700c-5a70-9652-e1f317b40c62 |  | note | HP
label | 1064024e-8e30-5a5f-8ca3-3f0503b73a21 |  | note | – – – – – – – – –
label | 3f702e00-5e9d-50f0-81c4-cb1bc439b822 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | 5da559d2-ced2-5ae4-9c2f-8dbc3cb1414b |  | note | – – – – – – – – –
text | cb927843-4cfc-5e78-9cd1-e9cdd4fbb584 |  | textbox | DATE:
holdpoint | 20a6d157-766f-4530-81cc-7293fd24b39e |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 7445fb3a-791f-4a1f-9ed5-76ba89eba841 |  | checkpoint | 2.7 Unsuitable Material
label | a9eda42b-b221-5e62-99dd-e24198fcea1c |  | note | FREQUENCY: Each Lot
label | ae14c1bc-67cf-5c30-bd0e-8746f43ac1e8 |  | note | – – – – – – – – –
label | f38ea9c5-9a94-5722-8f19-5126c11ecea1 |  | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
label | 9d5063b7-04fd-57c8-b08f-8c358ba8cae3 |  | note | – – – – – – – – –
label | c0f3b01d-59b4-5065-bd37-150685745efc |  | note | REFERENCE DOCUMENTS: 204.07 (d)
label | dc4a0a6f-41da-528e-bfb3-b3b76bb80afe |  | note | – – – – – – – – –
label | 8999e0e6-38b1-59aa-a6de-4a4a3d1db52d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ebc96313-c8f8-5ac7-9536-37eb0e06c718 |  | note | – – – – – – – – –
label | a25ff275-81f5-5d86-98d8-318d31c10531 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | dd524304-9249-5e58-aba1-4ddb37ccde49 |  | note | – – – – – – – – –
label | b240bd7b-0d55-5152-a356-7a2efebe706b |  | note | HP
label | a6a44c34-8f54-5fb7-bc52-dba9c643d0d2 |  | note | – – – – – – – – –
label | a2b59c3a-850e-5eed-87b8-564a983438bc |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | 71d54fdf-ab9e-56ca-91f9-b37d25fbea83 |  | note | – – – – – – – – –
text | a1068af9-3b1b-56a7-9ffa-3a1805edcb50 |  | textbox | DATE:
holdpoint | 9a3a5044-1bab-4826-b2eb-37200df5be08 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 5cbf7750-3067-496b-8289-04a5073ef71c |  | checkpoint | 2.8 Groundwater
label | 1c8f3b7e-54c4-55cb-a30f-079a2f3937cb |  | note | FREQUENCY: Each Lot
label | 31a5cf6c-614e-53bf-ab38-ae9376c73cc6 |  | note | – – – – – – – – –
label | f4ca8451-d6cd-5ef5-aaa2-1a4fc8e66c3d |  | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 1e1e2a02-5325-5d6e-8c25-78b2edfdcd27 |  | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | febe3955-199c-5743-b283-fa1c31a176fb |  | note | – – – – – – – – –
label | e1b21896-ca1b-5bad-ab5f-a26d92e1349b |  | note | REFERENCE DOCUMENTS: 204.06 (h)
label | 2eb009d7-e279-5dbc-98fd-5bea1abba497 |  | note | – – – – – – – – –
label | 961a9a12-8d98-52b8-a581-bea26fc5b10b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 185640f7-9981-536f-87b0-2f9b08b7d019 |  | note | – – – – – – – – –
label | be9a7e3e-236a-51a5-a920-74fd431ac46b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0ac85dbd-040b-555a-af3f-444ff909f807 |  | note | – – – – – – – – –
label | e57ebf13-eae8-5576-b0f9-83ba31211948 |  | note | HP
label | 3e5cfd2d-4c3b-5d4e-964b-9f53459f5350 |  | note | – – – – – – – – –
label | 4bed11bb-1564-59c8-a58b-91640e3117d8 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | e5882e28-df21-55a1-adb1-747342dddc78 |  | note | – – – – – – – – –
text | 27d4a5ad-8114-564e-8371-fe551be95fd0 |  | textbox | DATE:
holdpoint | 33c6c385-f0a1-4d6d-a4aa-f4831dcf428c |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 714ef4cc-fff2-4741-96ed-8fa383c460b1 |  | checkpoint | 2.9 Trimming and Level conformity
label | 55da1024-afc6-540a-80ba-890378c2fd83 |  | note | FREQUENCY: Each Lot
label | 3feb4d3c-02c2-578c-8d6d-91d3a9e1bd5f |  | note | – – – – – – – – –
label | 0eb143c6-645b-58c9-9f02-b4c15ab4662f |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
label | f07b8baf-3787-5b97-936f-fc52747ea756 |  | note | ○ Level tolerances:
label | 881daeb5-2263-508f-874a-55515cc4e6e9 |  | note | • Range x = +15, -30mm
label | 5a607f5c-5d1e-55ee-8cc7-9086891ee594 |  | note | • Max S = 12 mm
label | 3f7dadb3-a190-5acd-80c2-42a9008b5716 |  | note | • 40 measurements per lot (Scale B)
label | 775d3a78-e05f-53fc-8611-739078ce2ce9 |  | note | – – – – – – – – –
label | b05c0e71-2e92-5be7-b86b-184ad8a955ac |  | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
label | 8c42af4f-1063-5615-a67b-b0ebb67cabc6 |  | note | – – – – – – – – –
label | b8ff3733-2a27-501b-bcc4-466780bc341d |  | note | INSPECTION/TEST METHOD: Survey Report
label | 78b87a71-1e49-55c0-8d24-2e7807ede393 |  | note | – – – – – – – – –
label | f8032fa7-ed26-5d24-93a2-457fbbe0c84e |  | note | RECORD OF CONFORMITY: Survey Record
label | 0cbc3e09-1183-5f65-bb2b-20e295bc93a3 |  | note | – – – – – – – – –
label | df8940c7-4ee6-5595-9da8-25570b8a311b |  | note | SCP
label | a903749f-0ee8-5bdc-91f9-74735d6bdaa5 |  | note | – – – – – – – – –
label | 0217ed07-5f98-5735-a7fa-ca5f120e1df2 |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | 78949d3d-0adf-5e2c-96bf-4a80dc4d6b67 |  | note | – – – – – – – – –
text | 22d3a343-fcfd-54ef-b839-5997f8a28031 |  | textbox | DATE:
checkpoint-group | bcf528c3-ec1e-45de-ba85-6532c400ecdb |  | section | 3 - Testing
checkpoint-status | 6eb745c5-0e3a-451c-957c-23cc92432db3 |  | checkpoint | 3.1 Proof Rolling
label | bad23527-7c24-5c44-8b4c-92e761063438 |  | note | FREQUENCY: Each Lot
label | 1a06064e-064a-59e0-96a6-5b99c09dcbf3 |  | note | – – – – – – – – –
label | a5bf020d-de55-5197-9d80-5d4ad1a1359f |  | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 20b9533e-7577-52e1-a4ce-0ee753f88459 |  | note | – – – – – – – – –
label | 45fd86d2-d367-5abd-ba79-cebd384bc024 |  | note | REFERENCE DOCUMENTS: Section 173
label | 463d7b5e-8f5b-589b-9839-88ee705e7fdb |  | note | – – – – – – – – –
label | 3da7c788-fee4-5f3f-8651-2dbddf7af2b3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 33fab8b9-1422-5d0a-afa7-c362601faf53 |  | note | – – – – – – – – –
label | 08677ac2-a43b-57d4-8a24-0a8e251ef5e6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 78c35c4f-36a3-5e7f-81eb-1af634cc8b4b |  | note | – – – – – – – – –
label | 43369f58-3bf5-5493-a220-4cab5038b23c |  | note | HP*, WP
label | c45082a5-c52d-5420-8233-5cbcc038aef3 |  | note | – – – – – – – – –
label | 94b27b24-13d5-5f98-abaa-8666c127f85f |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | b1dd475f-f1f5-5e08-9543-fbcc080b125a |  | note | – – – – – – – – –
text | 0996d461-1246-5829-8db4-1ea8b6c0ae5b |  | textbox | DATE:
checkpoint-status | ad1e7384-bc7f-4acb-9bd3-4cfe7583237e |  | checkpoint | 3.2 Minimum Testing
label | d2a47a3e-576f-5617-a1be-3b0235668fa5 |  | note | FREQUENCY: Each Lot
label | 93de0ce1-2c62-5d2a-9ce8-b9dee078b567 |  | note | – – – – – – – – –
label | 0b3c7083-1d6c-59c7-b32a-3028b13fddcd |  | note | ACCEPTANCE CRITERIA: Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
label | 6f14371c-44ab-5383-be35-db0177e1742c |  | note | – – – – – – – – –
label | fb805f6e-69c7-5a38-8e40-742f8fb42ab5 |  | note | REFERENCE DOCUMENTS: 204.14 c
label | 1de16275-a328-5e25-a546-6d5f22af08d1 |  | note | – – – – – – – – –
label | 992fde98-83fb-5f7c-80da-d6dd65910a3e |  | note | INSPECTION/TEST METHOD: Test Point
label | ff003c0b-0c95-5770-93f5-b185738f6609 |  | note | – – – – – – – – –
label | b55f345b-0e5c-53f0-b8b7-8cc97053dd62 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8eb499f5-a8e7-5e89-9855-cf99a9474445 |  | note | – – – – – – – – –
label | 9f12190c-8678-5109-a856-1a3f6444f1b3 |  | note | HP*, WP
label | 958649bf-dab1-56c0-aeb1-1065a6bf5925 |  | note | – – – – – – – – –
label | eef9e488-3a4b-5031-8372-5631a67af530 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | cf55e07f-b0bd-589a-acba-9d3157fd6be7 |  | note | – – – – – – – – –
text | 689e67fc-d4c3-58b4-97ad-d4f5cc8e05ca |  | textbox | DATE:
checkpoint-status | 055dd60b-e4e4-4eca-abaa-4a36763603f9 |  | checkpoint | 3.2 Compaction Testing
label | 373982b5-b562-5a9e-bec7-f046a59389a1 |  | note | FREQUENCY: Each Lot
label | f93c2d69-12d8-5cad-a5a7-077f2eb72ce4 |  | note | – – – – – – – – –
label | 25ec4d38-a99c-58a1-84db-e0c203a05b01 |  | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% SDD.
label | 5f06ec57-6586-535c-b0a5-000ce0f3a76f |  | note | • Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% SDD.
label | e0ca82be-5df5-5257-80e0-b3a48f7a587e |  | note | • Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% SDD.
label | 91f2c6cb-cf3e-57bf-b0d9-401dab3c927f |  | note | – – – – – – – – –
label | 160877c0-3e15-53a2-9b6e-7ae23260f7db |  | note | REFERENCE DOCUMENTS: Table 204.131
label | 0f137bca-e6b6-5ee3-8bba-8a945e013a95 |  | note | – – – – – – – – –
label | 604036c0-a2c4-5ec3-a78d-b879c2a52303 |  | note | INSPECTION/TEST METHOD: Test Point
label | ec8b9677-a24e-57e4-9ff9-5c999a1a427c |  | note | – – – – – – – – –
label | ede519d4-9f5e-526c-82b7-551eb76e832f |  | note | RECORD OF CONFORMITY: Test Records, Lot Register
label | b1bc2480-3424-5aad-8438-12d155bf8973 |  | note | – – – – – – – – –
label | 4ff8eef2-aad8-5571-bc92-cf80c805fa6b |  | note | TP
label | 60b6bdcd-7e93-570a-b0c4-1934d87d8c83 |  | note | – – – – – – – – –
label | 75518d21-98ac-5586-b0c6-c19c021ae035 |  | note | RESPONSIBILITY: Site Engineer
label | 15e3b602-7bbc-5047-86a9-66174056f377 |  | note | – – – – – – – – –
text | f4250265-4b57-507c-8b8f-186cecde1808 |  | textbox | DATE:
checkpoint-status | 35c5a817-9edd-4efc-affc-c9687977acd7 |  | checkpoint | 3.3 Compaction Testing (Small Lots)
label | 81357b09-7d11-57a8-8a29-a337e70c3086 |  | note | FREQUENCY: Each Lot
label | 454390ff-37c4-5652-ba10-e5e7d8f31f4a |  | note | – – – – – – – – –
label | 636933af-3fea-5de2-8412-e1e85917a152 |  | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
label | 2ee610e2-1f06-5875-9259-c64690845892 |  | note | – – – – – – – – –
label | c8315f4c-fe02-5839-bc2c-65141169b645 |  | note | REFERENCE DOCUMENTS: 173.04 d
label | 85599d07-70b7-5caa-b6c2-a8a7653e3db2 |  | note | – – – – – – – – –
label | 844a3a5d-2e21-5c25-885a-556c28911c64 |  | note | INSPECTION/TEST METHOD: Test Point
label | 50955e52-d602-5762-8400-687bc90464cb |  | note | – – – – – – – – –
label | 3c16cec1-bec5-5e55-a765-15e2f07a754d |  | note | RECORD OF CONFORMITY: Test Records, Lot Register
label | 37a4d476-7103-5857-a1f0-47b262df53a5 |  | note | – – – – – – – – –
label | 6b003ce6-5a2a-55de-a090-340af8db02df |  | note | TP
label | 772952d4-2ea8-54e8-be39-d9af1eaeecbe |  | note | – – – – – – – – –
label | 7cdb3f47-8a96-5dac-983b-3ba30cf6a067 |  | note | RESPONSIBILITY: Site Engineer
label | 8cca6124-f7e0-5de7-be5b-01756438e682 |  | note | – – – – – – – – –
text | 3119aa78-10b3-52c5-92d8-e397abfb07b6 |  | textbox | DATE:
checkpoint-status | 509bfc9f-ecbd-4ef8-b930-fe0a8382898c |  | checkpoint | Final Inspection
label | 5201f771-0a78-5a8e-8eb6-19e1b66f494b |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 219bb96d-99de-5819-b310-0cf57cd8e8e6 |  | textbox | Print Name:
text | 1e6789db-9023-59a6-9d81-2b49dd4a4f33 |  | textbox | Position:
text | 14e7936e-7494-5733-b229-7dbcddac418e |  | textbox | Date:
checklist-sectioned | b44c53f5-2775-437c-a27e-382ef6cef6b0 |  | checklist | FHC-ITP-027 - Pile Footing Construction |  |  |  |  | Yes | FHC-ITP-027 - Pile Footing Construction | 14631d90-23fb-47b9-ab76-c1c5268941cb
checkpoint-group | a9606d97-83a6-42bd-91f8-5f82cf6691c5 |  | section | Design and Submissions
checkpoint-status | 6aed04b1-273d-4082-aa0c-2d2c06c25eff |  | checkpoint | 1.1 - Check for correct documentation
label | 41b5fbfa-0c65-55f8-b8ec-2faa4920aa1f |  | note | Frequency - Prior to commencing any activity
label | d5cc93cd-55b2-547a-aada-21008d730254 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 5089950e-c80f-5435-b5f9-e658365c603a |  | note | Reference Documents - Drawings and drawing registers
label | 9111c2bf-499b-5d3f-965b-1b1d616658cf |  | note | Inspection / Test Method - Visual inspection
label | dea63f20-213b-5aaf-8ced-3bd1091dcea6 |  | note | Record of Conformity - This ITP signed
label | 84cb033c-daca-5e01-997f-3e89d32aefbc |  | note | HP*
label | 29fa5ad2-b165-52af-9639-39630c863223 |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | 63278886-be38-4500-8788-af26c2095326 |  | checkpoint | 1.2 - Implementation of all measures and controls
label | ea76ea31-532f-55c2-9b86-d7d890adf4fe |  | note | Frequency - Prior to commencing any activity
label | 68241834-6fda-587d-a3f2-753aae4a832c |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | a9ba51de-8f61-5a9b-8eb9-a856a13f19f3 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | d93df1f8-33e4-53fa-83ed-e78584fc8df4 |  | note | Inspection / Test Method - Visual Inspection
label | 27264cdb-f599-567a-a42e-1562aa52c91f |  | note | Record of Conformity - This ITP signed
label | a6b067f1-d2ed-5e57-bb6a-4db6f0ff7b4d |  | note | HP*
label | ff2d8007-1e3e-53fa-b409-5858451a86cd |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | ca5438c8-ec72-43c7-af9e-bb86a9bd2747 |  | checkpoint | 1.3 - Approval of mix design
label | 9e346216-a2f8-5c3a-a245-fb88a8604a97 |  | note | Frequency - Prior to the first concrete pour
label | c5c90217-dd4f-5eb0-aba8-33c1bcdfe4db |  | note | Acceptance Criteria - Structural Concrete Design & Submission ITP completed and signed.
label | cae5060d-a254-57c1-ad04-249a2157a854 |  | note | Reference Documents - 610.07
label | 50feb7a6-d997-5b8a-8592-ed8c5fcd7970 |  | note | Inspection / Test Method - Verify
label | fb8b9322-83b6-588e-af87-6727f6ec55cb |  | note | Record of Conformity - This ITP signed
label | 4d200d9a-c088-5d71-84a5-b35d440a0124 |  | note | IP
label | c3990c24-021a-5a85-a4a2-afc90ace4b68 |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | 77999047-2ff3-43c4-a3cc-d40bcc0e672e |  | checkpoint | 1.4 - Reinforcement schedule
label | 55110260-2523-5174-af97-effa788da9d3 |  | note | Frequency - Prior to concrete pour
label | 55b119ae-5ff3-58e3-a8e4-393b81ac0991 |  | note | Acceptance Criteria - Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | 6f6f2bf9-d07e-5383-a41a-506ce80874ae |  | note | Reference Documents - 611.04
label | c285b9a7-ee78-5aac-b8e9-857101a1cd5e |  | note | Inspection / Test Method - Verify
label | 8eb8ad1c-55ee-5ed5-8546-1faba1fb1bc7 |  | note | Record of Conformity - This ITP signed
label | 8e79e002-9f44-5765-9ef9-4aa7a1cd60d2 |  | note | IP
label | 35ae1da2-880f-5d46-915c-4fa82c4ec01d |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-group | 6a2de901-1239-4a24-bf1b-30ae5c9c5f15 |  | section | Construction/Erection of Formwork
checkpoint-status | 55c3e925-f079-45ae-bed5-f25d88341991 |  | checkpoint | 2.1 - Excavation (Pile)
label | 104e6d5d-d9db-542b-9c38-0df46a00178e |  | note | Frequency - Prior to concrete pour
label | 8f6f5052-15db-53b0-b708-0281df1914ab |  | note | Acceptance Criteria - The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
label | 732e1646-fbc2-5c4f-9bda-64971da9b889 |  | note | Reference Documents - 606.05
label | d2341ece-bd8a-5fbc-b916-beb8d7721e76 |  | note | Inspection / Test Method - Inspect
label | 801b9b68-5fea-5454-9378-d7c6c7e9606b |  | note | Record of Conformity - This ITP signed
label | 74ff7e1a-5463-56e6-8dba-6625c96e44cd |  | note | HP
label | a013ca08-b549-56f1-b157-f9e71392ddb8 |  | note | Responsibility - Fulton Hogan Engineer / Superintendent
holdpoint | ec1f205a-e28b-4f0e-a188-ee48b4ad0295 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 17205d50-a2e9-4b0a-8456-4b27f996a539 |  | checkpoint | 2.2 - Construction Methodology
label | 6948f667-bda9-5cac-b198-8327c2edcc85 |  | note | Frequency - Prior to erection
label | 65fd2c44-e188-50eb-a88f-0c3fcf42479d |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | f35a01a1-e2e9-5f47-91a3-30e7bea414cf |  | note | Reference Documents - 614.04 614.06
label | 21182d8c-272f-510e-81c8-6f68e02e0442 |  | note | Inspection / Test Method - Verify
label | d447e2ce-9cbe-5602-b203-250168abbbc7 |  | note | Record of Conformity - This ITP signed
label | e61fcd87-86bf-5412-b727-23ee52beb229 |  | note | IP
label | bf91616c-3cc2-5ea9-a3ad-220864fe4af9 |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | 9d26adc6-abcd-4f3c-96aa-ab8cbe38391a |  | checkpoint | 2.3 - Construction Methodology (Pile)
label | eccf29bc-83a4-5944-9713-1999ea6ccfdb |  | note | Frequency - Prior to construction
label | 11fe077a-b0a8-51e1-a0c7-87d5668b385e |  | note | Acceptance Criteria - Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained. Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
label | 1ff6f786-7e10-5fff-a123-45881c3e24d5 |  | note | Reference Documents - 611.10 606.06
label | 7ac7d958-a9fe-57ac-91e4-c7d89ff30e2f |  | note | Inspection / Test Method - Verify
label | 6be7516d-97d9-5875-9ceb-2ff616ae00ff |  | note | Record of Conformity - This ITP signed
label | 4ba494f4-a406-51a1-8d40-9d482adc26e6 |  | note | IP
label | 21875110-e14f-5b02-89e1-78347f66eb9e |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-group | dd1745e9-9a7a-4110-ab19-7bb6a9270019 |  | section | Pre-Pour Planning and Inspection
checkpoint-status | 19f0ab39-100d-4f55-bfb4-ed91ab89ad99 |  | checkpoint | 3.1 - Cleaning formwork
label | e266b62e-0aab-5cc0-9f3c-8c6a18532bbc |  | note | Frequency - Each concrete pour
label | fc2b384d-582f-573c-99ac-4e08baf63918 |  | note | Acceptance Criteria - Concrete shall not be placed until all foreign material has been completely removed from the forms
label | 38dc67d8-e1b3-594d-970c-1f033bbb495c |  | note | Reference Documents - 610.18 (a) (iii)
label | 0d851ab0-053e-5194-a2c9-54ab91cb0abd |  | note | Inspection / Test Method - Verify
label | 29e51262-4b6c-5fce-a36b-c5fa1dae30ec |  | note | Record of Conformity - This ITP signed
label | aa2a2062-c5f1-5eb7-b5e2-f755ccb59765 |  | note | IP
label | a99b692e-e797-55ea-8da9-4436256e0df6 |  | note | Responsibility - Fulton Hogan
checkpoint-status | ba276b2f-ca59-4f68-9e57-30d791ac92f7 |  | checkpoint | 3.2 - Correct forms, reinforcements, rag bolt assembly and embedments
label | 54e6d429-3681-5931-8731-015fc8d7c1f4 |  | note | Frequency - Prior to concrete pour
label | 0d8cc00f-536e-55ea-885e-6d77f679628f |  | note | Acceptance Criteria - Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
label | 9ffb4e76-cecb-5eda-b50f-810ad09fe976 |  | note | Reference Documents - 610.18 (a)
label | 9d1195ca-283e-50dc-94b7-16b69b16e8dc |  | note | Inspection / Test Method - Verify
label | f9635a85-c86b-5b08-8bb0-f7bec1da408c |  | note | Record of Conformity - This ITP signed & Pre-Pour checklist completed
label | 39ae11c6-5e5e-53fc-ab8d-35a1ebc1c93e |  | note | HP
label | 55762235-099b-5d8b-9833-bfbe662e6241 |  | note | Responsibility - Fulton Hogan / Superintendent
holdpoint | 1bcdc184-7551-4e98-9022-449d472b8025 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 59e1fa3f-5c96-4dc0-bbe8-6a9cf6b0fc07 |  | checkpoint | 3.3 - Reinforcement assembly of piles
label | 80d032e7-90e4-5566-8d31-31aa7096a40b |  | note | Frequency - Prior to concrete pour
label | 7fe3e4bd-af03-5ff7-b139-f3bf2a4b6293 |  | note | Acceptance Criteria - Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
label | 2b7e5ef5-a494-514b-ba6e-e709e5a6d939 |  | note | Reference Documents - 610.17 (b),( c), (d)
label | 11be937b-083e-516e-bb3d-3c569ba932d8 |  | note | Inspection / Test Method - Verify
label | 763cc17b-d87e-5830-b119-0de7e58f5675 |  | note | Record of Conformity - This ITP signed
label | 24ffe73d-2479-5b7d-9683-21972940042b |  | note | HP
label | 42629505-5ab9-5e9c-a867-45b62ceaa243 |  | note | Responsibility - Fulton Hogan
holdpoint | f9cfa77c-c435-4c1d-9ecb-41df250c24f4 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 79676b3d-6c02-4ca8-948d-008ec9baed98 |  | checkpoint | 3.4 - Monitoring weather
label | 6c4637e7-4ac8-5d64-a011-3a6754014dde |  | note | Frequency - Prior to concrete pour
label | 152e0784-f8b1-56b6-8684-6a57e79013bf |  | note | Acceptance Criteria - Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | c5995841-d4f7-58b8-a78b-784a4b2567fe |  | note | Reference Documents - 610.17 (b),( c), (d)
label | e86fd3a5-03e6-5b94-ae1a-71b0c2bc075f |  | note | Inspection / Test Method - Verify
label | 8baa2e9d-cefc-5d08-a3ed-38bb1ce35663 |  | note | Record of Conformity - This ITP signed
label | 04c43df5-0f35-59e3-8605-c2f780f0a29a |  | note | IP
label | b6023ca2-16cb-5781-84ec-19046c0bbe60 |  | note | Responsibility - Fulton Hogan
checkpoint-group | d160cb7d-efb0-407d-b9b4-bb5bb32d9110 |  | section | Placing and Finishing Concrete
checkpoint-status | 06f7f196-c73a-43fb-ab64-cefb6226feca |  | checkpoint | 4.1 - Carry out sampling of concrete
label | faee9827-b11d-598d-8cde-da7ee69d4187 |  | note | Frequency - Each concrete pour
label | dd88ce79-7eb7-526a-bcfe-8e84335fbda8 |  | note | Acceptance Criteria - Sampling in accordance with 610.16
label | ba56bd2d-8e7e-531b-8811-e9f150ab5bf0 |  | note | Reference Documents - 610.16
label | 44342323-a7cd-516c-860d-fb497500dcda |  | note | Inspection / Test Method - Checklist
label | 2b8f272a-e701-5daa-9692-fef959cf4fb0 |  | note | Record of Conformity - This ITP signed
label | dd1679b4-7e6c-52c1-a214-98acd2b4c7a9 |  | note | IP
label | b6c21dd2-17c1-5f28-bced-acb0435f8dc6 |  | note | Responsibility - Fulton Hogan
checkpoint-status | 38fd1056-9930-4a44-aa43-20482f6dd8dd |  | checkpoint | 4.2 - Discharge time
label | dad6b884-d4d4-5be8-9bde-e3d30b319f25 |  | note | Frequency - Each concrete pour
label | de46c082-818a-52d4-9667-c1b729bb9b13 |  | note | Acceptance Criteria - Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
label | 33282b20-955b-5962-99e3-a39de2d849c1 |  | note | Reference Documents - 610.13
label | 25f0b82f-ffdc-5861-9a49-45459af90b34 |  | note | Inspection / Test Method - Verify
label | acd2881d-cb67-5284-a970-7ee840a796bc |  | note | Record of Conformity - This ITP signed. Accurate Site Notes & Load Mapping
label | d6c7f8e0-03fd-5a70-bdb1-5f88fa26db3f |  | note | IP
label | 71a193bc-0cf1-5cb7-ba40-5ef170ebee8b |  | note | Responsibility - Fulton Hogan
checkpoint-status | 2c760b5c-1d46-4bbf-871f-c77200b573ef |  | checkpoint | 4.3 - Methodology of placement (structural)
label | 5191d644-6362-5021-a4dc-9ee9255c9342 |  | note | Frequency - Each concrete pour
label | e72d49ff-6adf-568b-99f9-1a8a0d6bfb6f |  | note | Acceptance Criteria - Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials In continuous pours the max. time lag between truckloads on site is 25 minutes
label | 60620b75-3adf-5718-9a40-9b26ecfb9a37 |  | note | Reference Documents - 610.18
label | 3384093f-d743-53db-96b5-52ca61313fba |  | note | Inspection / Test Method - Verify
label | 35ccd945-f007-5aa4-a080-a90a73ed21b7 |  | note | Record of Conformity - This ITP signed
label | 435ccc89-1b94-5123-a666-c838d7e91ec4 |  | note | IP
label | a235b76b-499a-509f-8354-063ee8a3b024 |  | note | Responsibility - Fulton Hogan
checkpoint-status | d41a7348-257d-4c22-9354-9be74bc96e0b |  | checkpoint | 4.4 - Methodology of placement (piles)
label | d62e3a04-2ad7-553f-a867-23db2c60ba86 |  | note | Frequency - Each concrete pour
label | d40e2577-0309-5433-b92f-6055db88b3c5 |  | note | Acceptance Criteria - Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation. Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
label | 9f98a56c-3d0e-5e6a-a936-cb7252789ef0 |  | note | Reference Documents - 606.03(b) 606.05
label | 472dbe60-9d17-5669-8f60-a5c91dc116e2 |  | note | Inspection / Test Method - Verify
label | d872d330-c818-597d-aff1-96695a23698a |  | note | Record of Conformity - This ITP signed
label | e59cfb15-2488-571c-9005-517251794ba4 |  | note | IP
label | 7bbdcd88-b0b1-5b93-88e2-cef4c90b0db8 |  | note | Responsibility - Fulton Hogan
checkpoint-group | 340c9a40-014e-4119-b2d7-4cb5bf6139eb |  | section | Post-Pour Details and Inspection
checkpoint-status | 97201dd0-7470-4848-911e-97b8348ca8dc |  | checkpoint | 5.1 - Curing
label | 6b2ec9f9-26e7-5c4f-a7f6-f0c54df1498a |  | note | Frequency - Each concrete pour
label | b77ffcd8-01df-59e0-aefc-a9bcc69ebb73 |  | note | Acceptance Criteria - Sufficient time shall be given for the concrete to cure prior to loading.
label | 924bc59d-e5bf-569f-830c-8955c19313b9 |  | note | Reference Documents - 610.23
label | f48c59d3-0c42-5c5b-90c5-5ffbebad1853 |  | note | Inspection / Test Method - Verify
label | eec77213-632c-5d99-98e4-37f8d5faf11e |  | note | Record of Conformity - This ITP signed
label | f76c478a-f448-5857-a287-b40547b4a573 |  | note | IP
label | 814fdc63-3d0f-5338-8aa9-c4c772db32e8 |  | note | Responsibility - Fulton Hogan
checkpoint-status | d416af72-8ef1-4f05-837b-ab35a4c3e107 |  | checkpoint | 5.2 - Formwork removal
label | 62c75727-4e20-5d69-b8bd-6ae76fb0093d |  | note | Frequency - Each concrete pour
label | 30956ed4-2d67-54a2-85da-514daac270ea |  | note | Acceptance Criteria - Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | 11460b4f-fffd-5851-98a4-1ef2ddbb3856 |  | note | Reference Documents - 610.25
label | cf54a589-066b-55e8-8bf9-802c0cab5bf5 |  | note | Inspection / Test Method - Verify
label | cef41683-1980-5506-be0c-685c3bb96fb0 |  | note | Record of Conformity - This ITP signed
label | c5fc8f30-71f4-53df-ba79-bac53dc2f563 |  | note | IP
label | ca7d804c-dd0f-5cba-9d41-cce29e50774d |  | note | Responsibility - Fulton Hogan
checkpoint-status | fe0a317d-c234-4f51-99b6-9c771b3654f1 |  | checkpoint | 5.3 - Positional tolerance and dimensions of concrete members and piles
label | be793b8f-8805-5c94-9006-a5911b7761ea |  | note | Frequency - Each concrete pour
label | ead02442-53fd-5ff2-9656-27cf9da3086f |  | note | Acceptance Criteria - The centre of the pile head shall be in the specified plan position ±75 mm;
label | c80f312e-1a92-5043-9c85-e1ff51916959 |  | note | Reference Documents - 607.06
label | b3cebe4d-1cc7-5fc3-ac47-f0377a83e72b |  | note | Inspection / Test Method - Verify
label | 8d0ec1e8-28a7-58f7-a540-3c98c1caeb99 |  | note | Record of Conformity - This ITP signed Post Pour Checklist completed
label | 1f8f02b9-cea6-5ec5-915b-8356b80b89fe |  | note | IP
label | 59b4166c-f7bc-5a3e-a681-cee2829555fd |  | note | Responsibility - Fulton Hogan
checkpoint-status | 4d00edab-6aac-49d6-a3a7-81ee24c361ad |  | checkpoint | 5.4 - Concrete Sampling and Testing
label | a09c58dd-dd0b-576e-b7e6-dafe3f6ced57 |  | note | Frequency - Prior to lot closure
label | 1691a350-b210-59b7-845e-2f9324914400 |  | note | Acceptance Criteria - Concrete sampled and tested for Compressive Strength: - 2 cylinders @ 28 days Compressive Strength=32MPa - 1 cylinders @ 7 days for Compressive Strength=20MPa
label | bb036c42-6f29-5742-8a7e-da9915f28b1d |  | note | Reference Documents - 610.05 610.06 610.13 610.16
label | 1d7416e5-d528-546d-bf77-21274c7ccf38 |  | note | Inspection / Test Method - Verify
label | 95fb1b75-5ee6-5c2a-83f4-f2fbf92e91ac |  | note | Record of Conformity - This ITP signed
label | 5726aa87-1c3a-51da-988f-05da1bbb3298 |  | note | TP
label | 9cf89bae-1b5e-551c-9486-1ed071d0a994 |  | note | Responsibility - Fulton Hogan
checkpoint-status | 98102819-03e1-481a-ab26-68af6f449bd4 |  | checkpoint | 5.5 - Protection of Adjacent Piles
label | 2d2fc5a0-0c39-508c-9be6-a6688672a2e2 |  | note | Frequency - Prior to commencing any piling
label | b2e8ac37-bff0-518a-842c-e7fc1b76d8a3 |  | note | Acceptance Criteria - No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa. Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
label | 86eb7f8c-3ab7-5e46-a3bf-81e630b8527e |  | note | Reference Documents - 606.04(a) 606.04(c)
label | e6e14890-595c-507c-94e8-eaf3b7fbd743 |  | note | Inspection / Test Method - Verify
label | 2351f335-8221-5b4c-a897-5b118a1b2427 |  | note | Record of Conformity - This ITP signed
label | 3c4cc24b-eaea-54c0-9b0e-20878168a82c |  | note | HP*
label | 8a3240af-7eca-5d38-b292-cf63ca5d21c5 |  | note | Responsibility - Fulton Hogan
checkpoint-status | 4fd8e4ce-331c-4d7c-863e-142326f7e3c3 |  | checkpoint | 5.6 - Testing Post-Pour
label | e1797f58-9370-5757-b5f3-11569e77fab2 |  | note | Frequency - Prior to lot closure
label | 413b5e4f-993e-5d82-ace1-7ac592732849 |  | note | Acceptance Criteria - Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
label | 13801b1b-5146-5cc6-b435-99e55b00741a |  | note | Reference Documents - 606.07
label | 0e7f76c6-0588-51af-ad12-cb20a22bcdaa |  | note | Inspection / Test Method - Verify
label | 33bde039-ac34-53c4-9804-2acb9bfba7e9 |  | note | Record of Conformity - This ITP signed
label | 4e97a354-3c72-5172-96a4-a4126c64da03 |  | note | TP
label | fe3ed722-af6a-58a3-9679-98b9acaad95b |  | note | Responsibility - Fulton Hogan
checkpoint-status | 66c81391-2390-4652-9da1-2114912acd1e |  | checkpoint | 5.7 - As Built Drawings
label | fc5624dc-f5b1-5e19-8f57-612a07e96b01 |  | note | Frequency - Prior to lot closure
label | c826f6f4-31ea-5541-b538-241403f8ba89 |  | note | Acceptance Criteria - Recorded of as-built drawings
label | ca3d3e80-e4de-5149-be29-91406315d872 |  | note | Reference Documents - Fulton Hogan Procedure
label | 1fd47524-96d1-57dc-b4b1-1746c7931d24 |  | note | Inspection / Test Method - Verify
label | 19995901-d6d7-5e4d-8332-decd8eaa709a |  | note | Record of Conformity - This ITP signed
label | a1030f85-90d4-56da-af70-ffa7df4b4ecb |  | note | IP
label | 010bdfda-ddee-52b7-91e4-2d557d9c0f33 |  | note | Responsibility - Fulton Hogan
checkpoint-status | d3d581e3-d49d-4d8e-a579-369bb77cb50e |  | checkpoint | Final Inspection
label | 7addda81-6635-50fe-ad77-0aacdf678c00 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 5b88f1cc-2273-504c-a2c0-5e1442b31792 |  | textbox | Print Name:
text | 613a9401-f597-5261-a635-af34abe6abca |  | textbox | Position:
text | 33c004a5-b7fa-57ff-b9cc-5653b0f99fc4 |  | textbox | Date:
checklist-flat | f2fde9e7-9c31-4b6a-b1b5-5c987f27409a |  | checklist | Contract HoldPoint Checklist |  |  |  |  | Yes | Contract HoldPoint Checklist | 47e3f28e-96d9-4351-92d9-383af79cfeb3
checkpoint-status | 96a78813-95b0-48fa-9a93-357ec9a1b8cb |  | checkpoint | Holdpoint Release
text | e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 |  | textbox | Enter Name
text | 1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b |  | textbox | Enter Description
holdpoint | 60a1eb35-e850-40c9-a4b9-af7b0196da59 |  | signoff | Contract Holdpoint Release
checklist-sectioned | 05c95a1d-ece9-4142-afe5-30a27c45afea |  | checklist | FHC-ITP-011 - Class 4 Crushed Rock Rev3 | itp |  |  |  | Yes | FHC-ITP-011 - Class 4 Crushed Rock Rev3 | 55812fd2-b08c-4832-bc3c-7b2b93cae074
checkpoint-group | 13a05ccc-9fca-4c49-954f-3a407ec334cd |  | section | 1 - Preliminary Works
checkpoint-status | cf7839e9-6062-461f-835d-e293c5c34c79 |  | checkpoint | 1.1 Check for correct documentation
label | 52f777d9-a4f2-5a64-ad91-ad085231b8e5 |  | note | FREQUENCY: Prior to commencing any activity
label | 56fc93fd-a433-5082-8a88-c5c8a66bc914 |  | note | – – – – – – – – –
label | 3a87c55c-66bf-582b-bdf6-b6a43b6430d3 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | b9f45824-bfd1-5e02-901c-6a6287af5bd3 |  | note | – Using the correct and complete set of drawings
label | e7f142b9-0d77-51c4-916f-913db59f91e3 |  | note | – All drawings are the latest revision
label | bfff3284-483a-52f1-b92e-5d7a0284e95e |  | note | – – – – – – – – –
label | 3565c3b0-aa6f-5022-b1da-8ec7db50ea05 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 567cfc46-ab82-53f5-8442-c76d2605cded |  | note | – – – – – – – – –
label | b2f67a6b-ef60-506e-894e-c4e6a450a40b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 9455841e-4592-5987-9d45-3ecd1400448c |  | note | – – – – – – – – –
label | f4f4ef16-22b0-5ce0-848f-49640953bf61 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 482093ff-2216-5c7a-99bb-d79b4428c57b |  | note | – – – – – – – – –
label | 11e85779-4adf-57ee-8fbd-2218409964bf |  | note | HP*
label | 1a23518d-0207-5e1a-923a-dfec6ad20782 |  | note | – – – – – – – – –
label | f5fe2c26-f9fb-5678-a93b-2d53c404d2c7 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 42680a55-459b-500f-a715-8b3a2f9864a3 |  | note | – – – – – – – – –
text | 5fc7b41d-3cbf-510f-9710-87123eeebacc |  | textbox | DATE:
checkpoint-status | 21fd0523-c71f-4374-91e2-02809f8dbe86 |  | checkpoint | 1.2 Material Mix Design
label | 74a8b6d6-96a3-5912-ae61-d17972c70cd7 |  | note | FREQUENCY: Prior to commencing any activity
label | 0a55c5c5-e948-5f51-b9ab-3bdd7ee99722 |  | note | – – – – – – – – –
label | 09e84020-2757-54b9-b056-6e3a5603758f |  | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
label | ee7dd801-f461-57e6-948b-6c16248632bf |  | note | – – – – – – – – –
label | ad4eefec-e754-53cb-a842-c9bbfc3fe87c |  | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
label | 3e41b062-7289-541d-992d-140e62a38429 |  | note | – – – – – – – – –
label | 1e806484-ba0c-5387-bdda-d9e59272562d |  | note | INSPECTION/TEST METHOD: Document Review
label | 31248f62-7013-574e-bbf0-3f0a29410d66 |  | note | – – – – – – – – –
label | 8ebae2b8-650c-5262-ae15-13ccadceeb76 |  | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | 4cb84bdf-0bf2-51a8-b9f4-266c3808dc91 |  | note | – – – – – – – – –
label | 53cce32f-4336-5aba-aa38-c95fc3a9126c |  | note | HP*
label | 578e8547-028a-5d36-b157-5069ccf2ae25 |  | note | – – – – – – – – –
label | b35ffc57-ea3d-56d7-86c5-6cb175678a2d |  | note | RESPONSIBILITY: Site Engineer
label | 0b734c2c-188d-560b-bc38-d09cb0af1831 |  | note | – – – – – – – – –
text | 41626ab0-e696-5028-ae14-4fba98f8ec10 |  | textbox | DATE:
checkpoint-status | 5e06ad8a-42f9-400d-87a1-983091549610 |  | checkpoint | 1.3 Implementation of all measures and controls
label | ac6c4cba-8f86-5e47-9dc7-8daa5dc8efd9 |  | note | FREQUENCY: Prior to commencing any activity
label | 30485c4a-ce61-525b-be84-b9727c674e51 |  | note | – – – – – – – – –
label | 422a4ef2-b81d-5c80-9cce-1b72a8b7aa7d |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 1e82f27b-ca49-5283-9e51-c328a98cb055 |  | note | – – – – – – – – –
label | 7e9d5278-8f43-51e7-bbec-dc731b73e4f9 |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | c05545d2-536c-5dbe-8982-1f73adac5c4f |  | note | – – – – – – – – –
label | 5134a8a1-edc3-5a70-ad6f-dd353bfd3d2f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 146bc9b2-f4ce-5d8c-89b6-32faa7f6a1d6 |  | note | – – – – – – – – –
label | 73f2d9da-3d90-5d55-adcc-29b1ea7665e3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 7bb121f2-391f-5146-a37b-8fa5cd7cd688 |  | note | – – – – – – – – –
label | c995619e-d9f1-508d-9563-32d6bcc5d7bf |  | note | HP*
label | ef5832c3-0002-517a-a184-b184896ce908 |  | note | – – – – – – – – –
label | 63825648-bda5-59bb-b9cb-9bf4b36f54ac |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | d1b46b7d-8481-5c80-8799-28d4fa1bfe48 |  | note | – – – – – – – – –
text | 90ce5684-2ee5-5f91-b40e-955296973076 |  | textbox | DATE:
checkpoint-group | 334d1828-c8ee-4678-8b9f-11a3890a694b |  | section | 2 - Construction Works
checkpoint-status | 3907ab4b-2ad2-40cd-86f0-666191169c19 |  | checkpoint | 2.1 Transverse Joints
label | 64acfbec-34e9-5984-a5b4-0a2a8fdd503a |  | note | FREQUENCY: Check prior to placing material
label | c86dc8a9-63d6-5e7d-9f72-39266735db2b |  | note | – – – – – – – – –
label | c873e689-28b5-56b0-86e1-54ab08aa6e85 |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
label | a2e31b44-5410-57a4-82eb-49241f40808a |  | note | – – – – – – – – –
label | 5402bea3-ae35-5014-b4c9-80d0339695fe |  | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
label | eb8d1160-0ee9-5713-8e2d-6d514150c3c6 |  | note | – – – – – – – – –
label | 0aa4d5f0-7036-597d-ba2d-31c95720ffd7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 5d3236f4-9e00-574b-bf62-b8c09fddbf1f |  | note | – – – – – – – – –
label | 5f167bcd-9aae-5030-9c0a-d6742b6d1d37 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 2cc8d678-2846-579f-a428-da0a1be3d909 |  | note | – – – – – – – – –
label | 4f7396eb-39c4-5eea-9b3d-a32fbd0bd02d |  | note | IP
label | d52bcbb6-8fb9-5439-8b88-1564ef3d1084 |  | note | – – – – – – – – –
label | e48305b5-c5c9-58c9-9b6b-512bf0b0ad1f |  | note | RESPONSIBILITY: Site Engineer
label | 63306a61-624b-5290-90d3-5f22f6c78756 |  | note | – – – – – – – – –
text | 6162bc43-2357-5bc1-849c-a25bfb60466a |  | textbox | DATE:
checkpoint-status | 5870bd0e-cbd0-4d7d-b0b9-3a53faaa3868 |  | checkpoint | 2.2 Longitudinal Joints
label | 2334312e-6020-5cd1-832e-5e9bf0413b99 |  | note | FREQUENCY: Check prior to placing material
label | 59353fc6-6710-517d-94cc-8ff91d1725a6 |  | note | – – – – – – – – –
label | ba13287d-e6d2-5182-8db5-0b238592bbe0 |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | c95a266b-3c4e-5927-83d3-f9434df8b6c9 |  | note | – – – – – – – – –
label | 8ab37c23-3c07-5e65-9b12-8d0b44380bb1 |  | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
label | 4565df8c-f46e-5de7-a830-8217b57142aa |  | note | – – – – – – – – –
label | a2910e7d-6255-5230-a698-2df498ed582d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 53e84bd2-56a9-577b-ae5c-5949ff2078a8 |  | note | – – – – – – – – –
label | 2bf3c335-b0df-5272-91c4-29af300fb5bb |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8b2472af-5474-5d5f-bf92-b1a6468127be |  | note | – – – – – – – – –
label | 58fd8593-37c7-5667-a874-9fb85119e37b |  | note | IP
label | 77d81ff9-2a1c-5061-8530-94c180c81863 |  | note | – – – – – – – – –
label | ba7475b8-4a56-5342-aed8-1aeb02684072 |  | note | RESPONSIBILITY: Site Engineer
label | 6a6f5f07-cc21-5e89-b70e-ca3936ea7d34 |  | note | – – – – – – – – –
text | 69618b48-1b6b-5e6a-915f-cb0dcb315f52 |  | textbox | DATE:
checkpoint-status | 448523ad-68d1-4d10-bc72-53ff2f964fef |  | checkpoint | 2.3 Lot Size
label | a80581ee-4882-5fdc-94e6-a8d77087beae |  | note | FREQUENCY: Check prior to placing material
label | 3e97694f-d348-56b7-bde6-2ac7a2c94ff7 |  | note | – – – – – – – – –
label | fe931fa6-0815-5879-94f1-3f234c04b8ed |  | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | 41feef02-95ba-5246-a96f-999145a03bb2 |  | note | – – – – – – – – –
label | 7c5eccd6-3537-5039-9873-dbb78d04526b |  | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
label | 97cc8e5d-d74b-564f-97be-3b0ecdf7ef3a |  | note | – – – – – – – – –
label | fdd6752e-61bf-5cd1-87af-1a63fed4fef9 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | e88a90f4-4713-53e9-9452-30ba5bfe08fe |  | note | – – – – – – – – –
label | 3c70bee5-7931-55e0-bfe8-ccbecb38e6d6 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 063b6f19-11d1-5216-89ab-dbe0ccb5c9f0 |  | note | – – – – – – – – –
label | 10482acc-0ad0-5feb-85b1-5d0c6c7f94ee |  | note | IP
label | adbe3f20-631d-5c45-bb17-0c9831c0a476 |  | note | – – – – – – – – –
label | d3b83c78-2b2e-59cc-975b-b5b32230e635 |  | note | RESPONSIBILITY: Site Engineer
label | d06137e6-560f-52d5-8fcc-f52f4a9972b2 |  | note | – – – – – – – – –
text | c4e23d15-867c-513c-814a-2754371f8fef |  | textbox | DATE:
checkpoint-status | b8f3829a-0a7b-4dc8-a5b7-a10192c80f01 |  | checkpoint | 2.4 Layer Thickness
label | 1292d33b-9c74-5513-9dd1-a40541eba1d2 |  | note | FREQUENCY: Each Lot
label | e4a0c118-9d1c-5966-a1e9-7ac3989bc066 |  | note | – – – – – – – – –
label | 68119b59-5a7a-5930-ba5e-aaa8aad080cb |  | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | 71d3caa2-2f12-5b9e-971d-c05c6c18967c |  | note | – – – – – – – – –
label | 3fac4f73-4409-5cae-bd4a-ebd32a8dc8cf |  | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
label | 244ebb56-f9da-5a51-82bb-86547f4192fb |  | note | – – – – – – – – –
label | 3daea68b-cd05-513d-96b8-d1188f921ab5 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 59c04903-98ab-5b08-b700-babf4dce73eb |  | note | – – – – – – – – –
label | 72e5beac-04c0-5dc4-ad4c-1e4a4b1674a5 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 91534d2c-933f-541e-8a04-975e44d26128 |  | note | – – – – – – – – –
label | 5b4ea9da-0937-5f1f-bb5a-eefaece9068f |  | note | IP
label | e407e8f8-829a-5c17-80af-53d3a0b6fbbe |  | note | – – – – – – – – –
label | c9f5d1dc-cc7c-5507-9394-971b43fd8d72 |  | note | RESPONSIBILITY: Site Engineer
label | b05f385f-7c7e-5dfc-b1fb-f47e6b981e61 |  | note | – – – – – – – – –
text | 3b23de9c-3c41-59cd-9179-0503f317ede3 |  | textbox | DATE:
checkpoint-status | 21d2e5e8-9544-4212-9b43-99ac8bbe1b58 |  | checkpoint | 2.5 Proof Rolling
label | 8a362a6a-1f19-5507-92c5-3c4c3eef425b |  | note | FREQUENCY: Proof Roll each layer
label | cb05dd67-437c-523c-a42d-214e4cd7702a |  | note | – – – – – – – – –
label | 38eb918a-e71b-5ee7-9676-c40ebf642072 |  | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | 7717e6a7-659b-5aa4-9722-a49c13ac55c6 |  | note | – – – – – – – – –
label | cde28855-0c1d-5ff5-9365-dab266397bc1 |  | note | REFERENCE DOCUMENTS: 173.03
label | 7d183582-868c-5f77-888c-8e244c35642f |  | note | – – – – – – – – –
label | f1decbc7-cb02-50ca-b892-1c4a44eae770 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 622f9ff9-3e80-5a4d-843c-6d40f80025fb |  | note | – – – – – – – – –
label | 78843111-c0a2-5c7f-8866-d8354a403171 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6001ecf1-f4fb-541f-9a0f-22f8cc58768b |  | note | – – – – – – – – –
label | 08494f61-d637-5fce-8818-9dd82f2e7a9b |  | note | HP/ WP
label | 4c2f70aa-d8e3-5421-b0df-cb2396780047 |  | note | – – – – – – – – –
label | 26665c7d-5596-5a73-bd96-4809c0fdffd7 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
label | 44d567ca-a6bf-57ba-a7b7-1ce25215ff74 |  | note | – – – – – – – – –
text | b910d5af-4895-5038-8842-54dc98ef6439 |  | textbox | DATE:
holdpoint | 7772db6f-e701-4fe6-bbce-dd56dd73cb31 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group | 90ce4cf8-99ab-42e0-b140-1a98a28f0ece |  | section | 3 - Testing Requirements
checkpoint-status | 1bb68dc4-0221-4f6f-adb2-e5ce5f1f7c8a |  | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
label | ebb31d1c-6d39-5333-bdc9-283b2367dc14 |  | note | FREQUENCY: Prior to Testing
label | 8877183e-be87-57be-8a33-560cba21cef1 |  | note | – – – – – – – – –
label | 6035885c-fcd2-545a-a04c-ee81c7cbfa6e |  | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
label | 466e39a6-604e-5795-9665-226a8bdc81d3 |  | note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
label | 1af90ad2-2b2e-57ac-9d57-49ede4ee506f |  | note | – – – – – – – – –
label | 4ad8ea79-2ab7-5828-9981-8300ae167374 |  | note | REFERENCE DOCUMENTS: Table 204.161
label | 73a2f69a-9d42-52da-8166-4008a35baba1 |  | note | • Cl.304.08 (a)
label | 8b7df758-68ac-5f73-b169-1bd99fe3e99c |  | note | • Cl.304.11 (b)
label | 2b8971a8-6ecd-5de3-aa18-8c887ac6ca87 |  | note | • Cl.304.11 (c)(i)
label | 791d8e6e-68a9-511a-9536-88a5d509ef1e |  | note | • Table 304.111
label | 96624e12-b44b-56b0-897f-2f0cc4dc38be |  | note | – – – – – – – – –
label | 00c51bbf-193c-54fc-a575-a70a819371c8 |  | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | b566aeac-93ce-5a2b-839c-55f6e870dadf |  | note | – – – – – – – – –
label | a87b2522-9326-54fb-8846-a706866bf80f |  | note | RECORD OF CONFORMITY: Signed ITP
label | 8587960b-f1b9-5864-88f9-b8025b8f920f |  | note | – – – – – – – – –
label | 07eb4f98-fc64-5203-8e37-1e3d0c0e25db |  | note | AP
label | 71a49fdd-ebca-512c-955e-ac4ce7dced40 |  | note | – – – – – – – – –
label | d7454d48-f2ad-52de-a192-c44dc284421f |  | note | RESPONSIBILITY: Project Engineer
label | 8b1061a5-df97-5526-9973-4e9ba78f7118 |  | note | – – – – – – – – –
text | 039aaa5d-bfb3-5229-9639-436eea318437 |  | textbox | DATE:
checkpoint-status | 69ca73d3-7d03-4b88-844b-f3765659e749 |  | checkpoint | 3.2 Compaction Testing
label | 7164db2c-997a-5607-9000-4a87a9162c23 |  | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
label | 58444bca-759e-542c-bb9c-022a381c35c8 |  | note | – – – – – – – – –
label | 5a722c9a-bbc2-5d65-a7c7-27ccb44870fa |  | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
label | e0463edf-146e-56c6-b332-fe47956bf8ab |  | note | – – – – – – – – –
label | ff11fbe1-9c06-59fd-994b-320680a419f8 |  | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061
label | de96fc47-e68e-5229-9a99-0801cdf2c3a4 |  | note | • Cl 304.11 (b) Table 304.111
label | c04e4ee9-bde6-5e53-bb7c-a7a638efc09d |  | note | – – – – – – – – –
label | 569c57ab-2198-568a-a812-b94f3f6f1bcc |  | note | INSPECTION/TEST METHOD: Test point
label | a73baea3-69ef-515c-af5e-181e19db0347 |  | note | – – – – – – – – –
label | 5a509b12-4bf6-5df7-b490-53a4454d4238 |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | 2b61fd1b-dac0-5500-b774-b94f986e4d9c |  | note | – – – – – – – – –
label | d89e021d-ae47-54ea-b9bd-1edb0f795c8a |  | note | TP
label | a93d856a-1e68-5c9f-8e74-041fe122d15f |  | note | – – – – – – – – –
label | 8b63fd75-5602-5cd5-b809-65f9e24d25b0 |  | note | RESPONSIBILITY: Site Engineer
label | 3d3e3144-db39-5838-b7a0-9a7df25eafc8 |  | note | – – – – – – – – –
text | 589f60e5-2e11-5279-999c-5d474542cd1e |  | textbox | DATE:
checkpoint-status | 2553d43d-1f08-4ed3-98f4-bdad315739c0 |  | checkpoint | 3.3 Compaction Testing (Small Lots)
label | 0ad5e02d-a7a4-5a9a-b028-5c49b342d69a |  | note | FREQUENCY: Each Lot
label | 4130f84c-90a2-5c0f-841f-3e9aded3505f |  | note | – – – – – – – – –
label | 8ddd7044-d852-52e1-b02d-ed7a1a174119 |  | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
label | 3903b014-9649-51d4-918b-e7115d942a22 |  | note | – – – – – – – – –
label | 7f7ec1f9-2412-57aa-b336-f474ed72d2cc |  | note | REFERENCE DOCUMENTS: 173.04 d
label | b62b8cc0-221f-533f-bc56-caf0ced6318f |  | note | – – – – – – – – –
label | d6898013-9ac4-5515-ba7c-d72ee3df9a52 |  | note | INSPECTION/TEST METHOD: Test Point
label | e0efdbfe-7478-5690-93ce-5d9aecda0331 |  | note | – – – – – – – – –
label | 8d899e9b-f65d-539e-adec-9f5a8a962901 |  | note | RECORD OF CONFORMITY: Test Records, Lot Register
label | a0fe97b1-e9a0-5672-9d7a-9a34392c1ab0 |  | note | – – – – – – – – –
label | 24316d61-bdd7-58c5-a3e7-ce04950eb96b |  | note | TP
label | 228287f9-460c-5a26-9de3-2ef3a68f3009 |  | note | – – – – – – – – –
label | 6a811017-b4b6-5191-9a33-17a4582172cd |  | note | RESPONSIBILITY: Site Engineer
label | e0ef418f-a1be-5eb2-abc2-34b52c04b2de |  | note | – – – – – – – – –
text | 7f6dcadc-5e09-5f0b-8d5d-c3324d6d4678 |  | textbox | DATE:
checkpoint-status | 152b38d4-58d4-4c2c-8952-f10be3b88c6b |  | checkpoint | 3.4 Material Grading - Post Compaction
label | fbe3abdd-785d-5f3d-868e-afd732ce3c9f |  | note | FREQUENCY: First Lot Only
label | 65d41393-5a4c-5511-8959-0b4ac05d5cfe |  | note | – – – – – – – – –
label | c5973af6-f4bf-5c10-ae7b-4fd271283ebd |  | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
label | ebd1e8e8-8791-5d6c-90a4-f461e2e6f0d1 |  | note | • Class 4 - As per Table 304.101 - VR Spec. 304.10
label | 50e211ce-069c-5dc8-a030-6ceeb71a6d38 |  | note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
label | 0c501e60-e7f6-5aa4-bdbc-c540b560e96e |  | note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
label | d9f8dbf4-f555-53c1-91d7-a7a7270cfa66 |  | note | – – – – – – – – –
label | 98bbc528-4051-5065-be5f-92499cf2f152 |  | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
label | 094882a3-468a-5e66-8f33-113b299410d0 |  | note | – – – – – – – – –
label | 449fdf3e-3e0e-5030-8612-b6e050d688ee |  | note | INSPECTION/TEST METHOD: Test point
label | c2afe059-c7ae-530d-9603-fe3351da3caa |  | note | – – – – – – – – –
label | ede31420-6c33-57a9-8553-091690dc71a5 |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | a3901c26-5cc6-57fe-8b2e-7741792db477 |  | note | – – – – – – – – –
label | 167e4a08-bd56-5367-b5a0-8c4532f4a677 |  | note | TP
label | 6fdb3c7e-9dfb-5e6e-b529-92808ee1ab94 |  | note | – – – – – – – – –
label | 2daf8f41-f349-564d-91c4-eba5b4731d61 |  | note | RESPONSIBILITY: Site Engineer
label | 3ff4413d-b3e3-58dc-ae06-255af634840e |  | note | – – – – – – – – –
text | 55da9979-b7c2-5f1a-83a8-37055802d07b |  | textbox | DATE:
checkpoint-status | 534fc721-779d-48c9-a0c6-d6e8bf05327e |  | checkpoint | 3.5 Plasticity Index - Post Compaction
label | 679ab7c2-f0d0-5284-bedd-3010072b0983 |  | note | FREQUENCY: First Lot Only
label | aacb44d9-3f7d-572d-9455-0988ee31dc7c |  | note | – – – – – – – – –
label | b9fd7a20-b383-5e37-9e73-4b4e48b911e3 |  | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
label | 1055a9c7-fb22-5896-bb17-8e14d7e88849 |  | note | • Class 4 - 0 to 10
label | 80435de4-5363-542a-8c76-ae6fa5dbf8b4 |  | note | • Class 3 - 0 to 10
label | 9d649f10-2cc3-5368-b2af-f8267c184a0d |  | note | • Class 2 - 0 to 6
label | 446b144b-a89b-58ff-bc62-ee03bbd5c8b5 |  | note | – – – – – – – – –
label | 9bf798b9-4054-5753-9d28-f8474eb88efe |  | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11 Table 304.103
label | bd430a81-d8f9-5f30-bf20-49dfe3fb3fdf |  | note | – – – – – – – – –
label | 19614a82-f491-5eec-ac35-e2008e2d1d5b |  | note | INSPECTION/TEST METHOD: Test point
label | 912a244f-4ebb-5cae-be01-d3c5950a9d42 |  | note | – – – – – – – – –
label | 9e67804b-7d3b-516f-975d-c1ece828f33f |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | 50e56967-a752-53b2-a4b2-961c5cb1bdda |  | note | – – – – – – – – –
label | e4d4d178-f63c-5261-a0d9-4eddbb76d080 |  | note | TP
label | 96c63afb-c456-5f51-8479-e85956fa020c |  | note | – – – – – – – – –
label | a9e74989-1f32-518d-b5c4-b4fceba0aab4 |  | note | RESPONSIBILITY: Site Engineer
label | fd3a889c-addb-56ac-bbe9-3220abd626c9 |  | note | – – – – – – – – –
text | c220174d-b9b0-56d9-bede-1c6805afbfb2 |  | textbox | DATE:
checkpoint-status | 51700fa9-549c-4815-9580-412bc622e807 |  | checkpoint | 3.6 Survey Conformance
label | 9e5ba55e-7964-50d1-9809-b06b94f39a30 |  | note | FREQUENCY: Each lot
label | 582c413c-6dae-555b-8761-1374925b2260 |  | note | – – – – – – – – –
label | bafc7d1a-af31-56f4-aeae-ad4631405d3b |  | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | 430159a4-34bc-57b9-aa4c-c34dcd554a65 |  | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
label | 7ab11389-9404-5232-a226-87cd44df2f1e |  | note | • Surface level tolerances:
label | 941bb0ee-0ce8-5325-8f17-a3b5c16c1489 |  | note | • Range x = +6, -16mm
label | be7687f8-fd68-5348-a8c7-7bb0355d1f30 |  | note | • Max S = 15 mm
label | 22b51c84-cb43-57d7-8914-b41e2a4b6158 |  | note | • 40 measurements per lot (Minimum)
label | afd6da62-9b2d-541d-b752-6cebbe641d65 |  | note | – – – – – – – – –
label | 026ed3c6-e2f6-5531-99d1-f128bd5c6574 |  | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
label | ed42da8f-1b4d-5402-9a42-42eae9993e97 |  | note | – – – – – – – – –
label | 7ae3a6dc-0436-514a-9bcf-c04dff93a47a |  | note | INSPECTION/TEST METHOD: Survey
label | d8afadc4-dbcc-5897-8b8f-18a3809cab0c |  | note | – – – – – – – – –
label | 4c8ceef7-855a-5294-8730-3d35816a4001 |  | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
label | f709a8a6-8c3e-5dd0-ab98-b820e2004967 |  | note | – – – – – – – – –
label | 7836049d-0155-52e7-98e8-b961683e68d5 |  | note | SCP
label | 9228a04b-01be-5450-900d-772b3f251233 |  | note | – – – – – – – – –
label | f29a7fbc-c673-52f1-b46e-fc06ebaa10a0 |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | bd87e28d-f013-5590-a4bd-d2de0e29797e |  | note | – – – – – – – – –
text | 84946892-bdda-519a-a4f9-fe5a03112fc5 |  | textbox | DATE:
checkpoint-status | 062e52da-69c5-4114-ba54-cf73b096106c |  | checkpoint | Final Inspection
label | c43c7e0d-ea0e-5f9d-b3fd-22f370ddfd61 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | cacc2b44-3c6e-533d-b657-0184707c6222 |  | textbox | Print Name:
text | 33985be5-3b50-518a-a307-d0b02a05dd8f |  | textbox | Position:
text | b25a4e60-6e2a-554f-84db-def378be5f0f |  | textbox | Date:
checklist-sectioned | d8f6abd4-20c6-435a-ac3b-1fcc82c85756 |  | checklist | FHC-ITP-006 - Class 3 Crushed Rock Rev3 | itp |  |  |  | Yes | FHC-ITP-006 - Class 3 Crushed Rock Rev3 | 60e08ef2-890e-47b4-a803-e1b82e56ebf0
checkpoint-group | a30e4c7e-9a5e-4b1c-9102-233c8de77683 |  | section | 1 - Preliminary Works
checkpoint-status | ea1bd294-bb7b-461b-8025-3b80249702d7 |  | checkpoint | 1.1 Check for correct documentation
label | e151b9e9-bd36-5db5-8d7a-fe9a0db004b7 |  | note | FREQUENCY: Prior to commencing any activity
label | 11b93b0b-c312-5e9e-8116-1d7b9b6d682a |  | note | – – – – – – – – –
label | 7fff74da-b562-5e3e-bb1f-394c4f6d2b83 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 8111b207-dce0-511e-9158-be666ca44505 |  | note | – Using the correct and complete set of drawings
label | 0dd3588c-a2ef-55e2-b716-987a264d273e |  | note | – All drawings are the latest revision
label | cb88a438-3b37-546a-a257-e79144d9d0c9 |  | note | – – – – – – – – –
label | e2f29c5d-994e-58f9-85d0-1850fb2b83cb |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 66cb3191-bbac-5d17-af17-cd557994486e |  | note | – – – – – – – – –
label | 11cc1e07-1830-5c46-99d1-86dd342c4549 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 9a030bde-b5ac-5077-8da8-1ae61a37e432 |  | note | – – – – – – – – –
label | da0e6719-f2dd-5e0a-9c1a-e7d56cd8014a |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9dde0721-2bf1-5b5f-a414-da229c3b8820 |  | note | – – – – – – – – –
label | c2c2e81f-901e-5a92-be9c-f66ed0a3f861 |  | note | HP*
label | 60f3a13c-c04d-5b8b-93fb-c7598acb7bea |  | note | – – – – – – – – –
label | cd156557-2154-5c3a-9cae-947a6a7ad4b7 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | d4d08293-e48c-5c7f-a5b3-5e13486bce3d |  | note | – – – – – – – – –
text | 1f6abf40-be81-51ec-9cfe-520322c05d5a |  | textbox | DATE:
checkpoint-status | ef2d7601-9469-4167-8f89-d566d314c6b6 |  | checkpoint | 1.2 Material Mix Design
label | 2b50e18f-7dcd-5db0-995b-1e594188c355 |  | note | FREQUENCY: Prior to commencing any activity
label | 83fd1e27-6fe9-5469-9b57-f78b1b9a9b84 |  | note | – – – – – – – – –
label | d383a059-ceec-5f98-b60c-39983c318d9e |  | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
label | d8db8125-9a99-5c99-8670-11bc3c35a963 |  | note | – – – – – – – – –
label | 65843d6d-c28d-5654-84af-9797b7b8f8fe |  | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
label | 1b1bf21e-412e-543e-8dbf-41b9b903166f |  | note | – – – – – – – – –
label | 98b7c2cd-f951-59e4-b604-d0064e78d9fa |  | note | INSPECTION/TEST METHOD: Document Review
label | affacc0a-f72b-566a-acfd-e4c45a2aa09c |  | note | – – – – – – – – –
label | ca5104cf-ce72-51f8-8dfa-e50b214f24dc |  | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | 600b2b07-ede6-5d59-854f-be601d2fa9b5 |  | note | – – – – – – – – –
label | cf6be215-34be-59c6-9891-5792e17d4c14 |  | note | HP*
label | 9d27045c-2451-596f-b8b3-af6667dcb7f3 |  | note | – – – – – – – – –
label | 60cd0eff-fc17-5147-a313-96d1cfa286df |  | note | RESPONSIBILITY: Site Engineer
label | 673b60d5-d269-59b0-86d8-17f2cc275715 |  | note | – – – – – – – – –
text | c1d5fc14-f866-53f3-9464-0d25127f5570 |  | textbox | DATE:
checkpoint-status | 211eb33f-25bf-4a0e-83f2-168019cfbca8 |  | checkpoint | 1.3 Implementation of all measures and controls
label | 1fbc8bf0-fc69-5cde-a6d2-6b7ebca58eab |  | note | FREQUENCY: Prior to commencing any activity
label | 666c6ee7-00a8-5596-9e06-0ff141b0c8a2 |  | note | – – – – – – – – –
label | 2d013906-4363-5e30-8690-eb4899c9ed16 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 33132e12-8b59-576b-b4ae-896cc65f719f |  | note | – – – – – – – – –
label | b7e13e40-8523-51b7-bf92-af14a0316dfb |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 2005c1ce-13e0-509b-8484-5ed1a1755a86 |  | note | – – – – – – – – –
label | 506b0104-4589-5f07-9f2e-6da39aed2573 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 68f11b69-12d9-50f9-b54a-f86e1479883f |  | note | – – – – – – – – –
label | 8e0432b3-685c-5704-ae1e-664458eb2a13 |  | note | RECORD OF CONFORMITY: This ITP signed
label | dfb16a33-8b1e-54dd-9ea2-18d24a5af2b5 |  | note | – – – – – – – – –
label | c355ace3-f08b-53f7-a15b-9fb4fb1a1dc4 |  | note | HP*
label | f1592848-8106-59ac-b9bf-82ef9ad89cbb |  | note | – – – – – – – – –
label | 69cc6efc-bfb1-564e-9e11-4ebb2d0e34ee |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | cb34e07d-1fe9-5f42-85cf-dff173fa2724 |  | note | – – – – – – – – –
text | 8f54dc11-0821-5bf3-9a07-c4a68525f9b8 |  | textbox | DATE:
checkpoint-group | 3fbbe2a0-4b56-4a45-a7a1-238e82c53326 |  | section | 2 - Construction Works
checkpoint-status | f83048a3-aa1c-4bdc-99aa-a30ea1992ef5 |  | checkpoint | 2.1 Transverse Joints
label | 17f35af6-e587-5a8b-9591-fa64c4075132 |  | note | FREQUENCY: Check prior to placing material
label | e0a74f98-1aea-5214-9a80-a5e8f7406e19 |  | note | – – – – – – – – –
label | 787c94b2-50ce-5be5-9fe6-d1d0fbe9e56b |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
label | 2aee5cf6-8f0f-556f-9a56-316d33168a7b |  | note | – – – – – – – – –
label | 46db11f2-2bfa-5e34-880f-1a1a2406c2f3 |  | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
label | 170066d1-5de0-5501-becf-0c6d72181966 |  | note | – – – – – – – – –
label | c0632b07-e8b4-557e-b5b8-be83fbfe937a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4029a8d5-32cb-5ca3-9b8e-1a0a00625571 |  | note | – – – – – – – – –
label | 207b0046-e86a-58e1-a756-8014f65e47cc |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d3d6dd73-9dca-5358-8f8b-88370fc9f62f |  | note | – – – – – – – – –
label | 2f0188bc-e76d-5c00-a10d-a6edf6742215 |  | note | IP
label | 8fa69a21-3a8a-58c9-af5a-eb6edcb78b7d |  | note | – – – – – – – – –
label | a0314594-b3f2-5c2f-ab67-405888afb197 |  | note | RESPONSIBILITY: Site Engineer
label | 5231d98e-dc5c-50f1-aba5-7ce01c41a922 |  | note | – – – – – – – – –
text | dee827a9-f3d9-5669-96ad-13aceba525e0 |  | textbox | DATE:
checkpoint-status | 1e23a84a-6681-491a-a9a2-29739e0467b9 |  | checkpoint | 2.2 Longitudinal Joints
label | daf01f4b-5b90-5be5-a895-e3358791bb6d |  | note | FREQUENCY: Check prior to placing material
label | 983376c5-1038-532a-8f91-d48f759a7b27 |  | note | – – – – – – – – –
label | 21d15db8-1da0-56dc-8121-f3bdc7d6179e |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | f5ccca38-55a4-5364-b726-530921fbfa9e |  | note | – – – – – – – – –
label | 33d23ac9-55c3-57a2-8d54-4f025fa1790f |  | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
label | 5766097a-3d01-521b-9af1-63aeffb88fc1 |  | note | – – – – – – – – –
label | 94c2f87f-5002-56f4-9bc1-ecd71df020be |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9a5c1d97-b1a9-572f-8522-c3fdc8d50ee8 |  | note | – – – – – – – – –
label | db2f34a3-edf5-5678-aa59-0b2e6b67b49b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1eb5c4c3-783b-59ee-a609-8fd3da8cc234 |  | note | – – – – – – – – –
label | 6e6ab02d-fb70-55e4-9f74-82c9d6efcd37 |  | note | IP
label | dfabebcf-5354-5de8-8012-ed42ca5b7164 |  | note | – – – – – – – – –
label | df61708b-3eb0-52f4-8c8a-05c91f9aeddc |  | note | RESPONSIBILITY: Site Engineer
label | 75458774-f0dc-5a5b-8dab-86b22321f66a |  | note | – – – – – – – – –
text | c63e4c6e-08b9-53a1-b579-598da4acfaf7 |  | textbox | DATE:
checkpoint-status | 05c5a61e-a7c3-465a-952c-68f07c2dd3d5 |  | checkpoint | 2.3 Lot Size
label | 1f8852ad-29fe-533f-ba32-793d814098a7 |  | note | FREQUENCY: Check prior to placing material
label | e36c8554-e421-5b5b-a2d2-822feb5de47c |  | note | – – – – – – – – –
label | 73b78eab-6293-5db1-bebf-f7a56f2d3bf0 |  | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | 5296bf04-92f2-5768-88bc-2cacad1fd934 |  | note | – – – – – – – – –
label | 5b2e99fd-85a6-5957-bcf0-6ea2fb761c2f |  | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
label | 2aa8ac8e-0096-5409-b427-1920ff86ccc4 |  | note | – – – – – – – – –
label | 598c9d68-dc18-5796-9262-f2f9d9afed28 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | a02a805b-133b-5c29-a0b4-6c3983332c23 |  | note | – – – – – – – – –
label | b554507d-2a3d-56e6-be60-3daf174e8387 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 1d9053bc-c8cc-5e24-a413-03f782d5736a |  | note | – – – – – – – – –
label | e1e3ec90-f8dc-5df6-800b-19c5e2438598 |  | note | IP
label | 698dce88-573c-5352-9a19-04bd2345aeea |  | note | – – – – – – – – –
label | ceff557a-4ca8-5c0d-880d-24d404024856 |  | note | RESPONSIBILITY: Site Engineer
label | 9628b130-4ba1-50de-b271-930932d0c1f6 |  | note | – – – – – – – – –
text | 5125f59b-63df-53b9-ac20-938679d11314 |  | textbox | DATE:
checkpoint-status | 4e517ead-0eeb-48c3-8449-609a7744cfa1 |  | checkpoint | 2.4 Layer Thickness
label | ec4dff1c-b0a9-5722-b10e-d0f29ae5a5a4 |  | note | FREQUENCY: Each Lot
label | 2ad2e794-d704-5d71-bbaa-33071cff2248 |  | note | – – – – – – – – –
label | 96146336-5dc1-5817-9729-fbb4ad0d7c9d |  | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | a87d48ae-34a1-580b-b279-cb5dae2496fb |  | note | – – – – – – – – –
label | cf25db32-329b-57d1-b6f7-d33d8546975c |  | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
label | 628d6d65-a49b-5087-b7b9-7e46c06c8c08 |  | note | – – – – – – – – –
label | a9c69790-32e8-5f28-ba9c-6a31fa930d7b |  | note | INSPECTION/TEST METHOD: Site Inspection
label | e1d01bdb-875e-5a98-8697-b0d3d7198134 |  | note | – – – – – – – – –
label | 143a095b-0237-5bb1-8c1c-4894291dea63 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 4c14536f-58d7-5b6e-a8d9-a5d85e059be1 |  | note | – – – – – – – – –
label | 680ccded-009d-55ef-8014-da7893ea21ef |  | note | IP
label | e36a67ad-7b2e-5cec-a262-2ce38a076c3d |  | note | – – – – – – – – –
label | b5201ec7-8c10-550e-8ca1-bd50b24fb44a |  | note | RESPONSIBILITY: Site Engineer
label | 2b4927fb-1c33-5541-8841-9062eab0cad9 |  | note | – – – – – – – – –
text | 3a3e08e2-11ad-54f5-8f7a-8230b3ef463f |  | textbox | DATE:
checkpoint-status | 81b797cc-fb9c-44d0-be8b-feeac677ec49 |  | checkpoint | 2.5 Proof Rolling
label | 52d2c6a2-f3a1-5dc6-86e9-5e3ff20df4d9 |  | note | FREQUENCY: Proof Roll each layer
label | 3df5926a-9060-519f-a412-da4b438e9b8b |  | note | – – – – – – – – –
label | b232b218-d122-534a-960c-3b71778f95fa |  | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | 5b8d3160-72f6-5c59-ad88-b66ec7294bad |  | note | – – – – – – – – –
label | 24d2a678-d7ce-50bd-95c1-6338b2183a52 |  | note | REFERENCE DOCUMENTS: 173.03
label | e06f7188-acd9-574a-8125-a952be54d864 |  | note | – – – – – – – – –
label | 3e0dced7-f711-503e-81b1-9903bfa1f59b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 7bd32565-516e-53d9-9ffe-18a07ed52711 |  | note | – – – – – – – – –
label | a269afc7-384c-575c-8551-cb2be6c723c0 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 819d2fd6-772e-56c9-8e3c-e4538e15aa47 |  | note | – – – – – – – – –
label | 236e4c95-f34b-5b24-84ed-35e485ef50cb |  | note | HP/ WP
label | 16bcfad2-8efd-5767-86ef-fe26db4704d7 |  | note | – – – – – – – – –
label | 99a1053e-a594-5b04-bcef-e4f5aa6c53b0 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
label | 212045ba-772a-5abc-9f48-7897d22c91ef |  | note | – – – – – – – – –
text | 5256c0e4-8190-5fdc-8608-9a65f1be2eb0 |  | textbox | DATE:
holdpoint | 693d91aa-00e1-4968-978d-05ab96356590 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group | 4cd5ffa2-e422-4c1a-becd-55b62bf656a9 |  | section | 3 - Testing Requirements
checkpoint-status | a332993a-8dcf-4008-9590-18d870fa218d |  | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
label | 90cde675-589a-5d33-ac62-d95d6435257c |  | note | FREQUENCY: Prior to Testing
label | fea2a450-d847-5925-9e0a-9b52d3744c71 |  | note | – – – – – – – – –
label | 9b37128e-defa-5805-9966-94ef020f6757 |  | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
label | f19a698f-fe27-5f82-8676-7e1f20c0da04 |  | note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
label | b72cb5a7-9290-5516-9baa-046db6a56bd4 |  | note | – – – – – – – – –
label | bfbf863a-8be7-59f1-a444-bca11dee8050 |  | note | REFERENCE DOCUMENTS: Table 204.161
label | 0aa915e8-32bb-5cac-824a-38229da08fe0 |  | note | • Cl.304.08 (a)
label | bc84ca9d-9d2b-5c6c-b056-81382c91b508 |  | note | • Cl.304.11 (b)
label | d9b6c677-189b-58a5-8f62-6df4c4d31788 |  | note | • Cl.304.11 (c)(i)
label | a99ff2a3-a4cd-5bcb-aee6-008d18564efd |  | note | • Table 304.111
label | a25b84fd-1f46-5804-b072-42f422740e1f |  | note | – – – – – – – – –
label | bdc64e77-0549-5383-8fd6-b84d13ae69db |  | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | d362771d-d3cc-511c-b769-606057e43bcc |  | note | – – – – – – – – –
label | efa50231-b30c-57b2-8fac-00bd64bb429d |  | note | RECORD OF CONFORMITY: Signed ITP
label | 7f1ceeba-93a1-554a-8de8-637fd42a9225 |  | note | – – – – – – – – –
label | b78da926-4233-5b3d-8299-7b60eebb7699 |  | note | AP
label | e6f10b78-dafd-5de3-9358-92e3ffc6ab3c |  | note | – – – – – – – – –
label | 792044a2-2c2c-53e7-8dd1-d808a40a3b2b |  | note | RESPONSIBILITY: Project Engineer
label | be5635f7-c197-5ab3-9fd4-3bb72d5d7479 |  | note | – – – – – – – – –
text | a42c7ccf-1c9f-5df5-89fa-73f87cf1408d |  | textbox | DATE:
checkpoint-status | 00355920-f961-47c7-80a0-5c0a7f37ddd4 |  | checkpoint | 3.2 Compaction Testing
label | 22b3a4b3-f2f3-5574-81ab-8332213c3a29 |  | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
label | c891e039-2ecc-5e5b-8f59-2867e2908e05 |  | note | – – – – – – – – –
label | a3502877-5b9e-5622-beb3-18071228161d |  | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
label | 5e792dc8-e959-5a1d-9170-1b023dae43e5 |  | note | – – – – – – – – –
label | 135f9704-7ab6-5f71-903a-b072515aac3b |  | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061
label | b89c49f6-d675-5748-a446-e387a3a1a022 |  | note | • Cl 304.11 (b) Table 304.111
label | a4550e92-db77-5616-ae5c-f8ff8431c438 |  | note | – – – – – – – – –
label | 94c727ae-68ae-5a34-b01a-b67bd677f4c0 |  | note | INSPECTION/TEST METHOD: Test point
label | 142275f9-8424-55d5-a3ee-fa072dbfdce6 |  | note | – – – – – – – – –
label | b3e38774-22e8-5c46-ad58-e75c6ef73c81 |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | 59cb9d17-d5e5-507e-9163-09abc0797945 |  | note | – – – – – – – – –
label | f08a77e3-d4c6-5535-ab0e-fb38dd79c362 |  | note | TP
label | 26a55c17-db79-535b-a082-d09a27d0d833 |  | note | – – – – – – – – –
label | afb063a3-5ee3-5485-9a56-9eff598cc330 |  | note | RESPONSIBILITY: Site Engineer
label | aa7fcebd-88f4-577f-94a0-0e6dac35c31c |  | note | – – – – – – – – –
text | 7c0451a7-bd6a-5a60-a127-dc34181aec98 |  | textbox | DATE:
checkpoint-status | d12843b3-9f02-4c68-9c89-374dc79c0d53 |  | checkpoint | 3.3 Compaction Testing (Small Lots)
label | 135848c1-d5f4-585e-bc94-c8dfad0edd80 |  | note | FREQUENCY: Each Lot
label | e5b02bd7-e56f-5536-8070-657456fae21b |  | note | – – – – – – – – –
label | e19d8d97-a66e-5326-9a35-024570d6ae1b |  | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
label | 4f8df1fb-192d-564c-86a9-0b10c649f25f |  | note | – – – – – – – – –
label | 0a85665f-ccc9-5818-a771-29b07de86a1c |  | note | REFERENCE DOCUMENTS: 173.04 d
label | 125b7ee4-c5f7-549b-b719-8415b6e7faf0 |  | note | – – – – – – – – –
label | 237fc9fc-cec8-5a9e-b400-61ca13949219 |  | note | INSPECTION/TEST METHOD: Test Point
label | 07707553-6591-54f5-8c77-8d56da97f349 |  | note | – – – – – – – – –
label | 5dcc7846-5bdb-5568-b8a3-718fb3aabd9b |  | note | RECORD OF CONFORMITY: Test Records, Lot Register
label | 525f6ac4-7adc-5661-a67c-1ec556f4bdd3 |  | note | – – – – – – – – –
label | 4e43ad90-170f-5bec-8640-84821cdc501f |  | note | TP
label | b9a12272-f51a-51f0-849c-83621640b952 |  | note | – – – – – – – – –
label | d22ba784-98d1-5e6c-853f-5c7fa114746c |  | note | RESPONSIBILITY: Site Engineer
label | 92f24bda-ca88-5e4d-843a-d845f61d9751 |  | note | – – – – – – – – –
text | 7fda187a-2aa6-5c93-8f6b-45314e31fa58 |  | textbox | DATE:
checkpoint-status | b1097e39-ad16-4dec-98e9-25a00ff41656 |  | checkpoint | 3.4 Material Grading - Post Compaction
label | 177a29ab-0738-5c3a-89ab-b87af58d368f |  | note | FREQUENCY: First Lot Only
label | 9316fc65-600c-5339-8b92-abdb58983153 |  | note | – – – – – – – – –
label | b1c23368-af72-5ff5-b3b7-b6c3f32676c1 |  | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
label | e1ddd6d4-2f56-5cf7-9e14-d3aaf0753aa5 |  | note | • Class 4 - As per Table 304.101 - VR Spec. 304.10
label | 179a4ed7-cd99-5554-b977-b2ce6c5a45f3 |  | note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
label | 3300762d-a3c0-5f19-8baa-905c9ffb7219 |  | note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
label | 552a6e99-4dc8-5bc4-b11d-c60a52560bd4 |  | note | – – – – – – – – –
label | dc66a390-a4e5-52d4-bd11-2a7e7f2ab6bc |  | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
label | 1d412e35-133c-58bf-9081-458d520de803 |  | note | – – – – – – – – –
label | af3373f4-4db4-5c71-a123-aa94b4d808e4 |  | note | INSPECTION/TEST METHOD: Test point
label | 3de18131-4689-5500-96b7-9ff58e9b51ef |  | note | – – – – – – – – –
label | 45ebf700-3e14-5704-b708-9a039d5149ad |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | 8c14f0c5-72bf-53fe-989b-67721a10da8a |  | note | – – – – – – – – –
label | c551db7f-ee9d-5598-9d4c-3dbf5b40138a |  | note | TP
label | 0c98dbc8-1cad-5b02-9ce6-795f3e82d24a |  | note | – – – – – – – – –
label | 4a75e285-9865-5560-a642-818f73f092ea |  | note | RESPONSIBILITY: Site Engineer
label | 938b01fe-5574-50e3-bdaf-21f5f15b8f16 |  | note | – – – – – – – – –
text | 1f1eff70-bea5-5689-914f-5269bbb39be6 |  | textbox | DATE:
checkpoint-status | 8d05e8a5-ccf9-4f75-b1d1-22d5fc50ce4f |  | checkpoint | 3.5 Plasticity Index - Post Compaction
label | b3efafda-632b-5dd2-b9a7-81bada3e6eac |  | note | FREQUENCY: First Lot Only
label | 0c40b72c-b88f-559b-9771-5d850dab090c |  | note | – – – – – – – – –
label | e17fc843-757d-5935-92a6-712a99aa541b |  | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
label | 425bcc13-1073-5ab2-9fd4-91f1b1e29f5e |  | note | • Class 4 - 0 to 10
label | e8c6445b-eb62-5d38-a7ee-b0fbf229bac9 |  | note | • Class 3 - 0 to 10
label | 322bdbf6-8223-5ec5-a9ba-5d79fbc1b118 |  | note | • Class 2 - 0 to 6
label | 155885c5-e8cb-599e-b40a-3ef4b2e6679b |  | note | – – – – – – – – –
label | c10c338d-c201-53c4-8c87-05d2bfe0dcad |  | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11 Table 304.103
label | 83d87a3c-1314-5c54-bf5a-06f61cdbe01d |  | note | – – – – – – – – –
label | f996819f-ec51-52cc-9036-f8557b39a14e |  | note | INSPECTION/TEST METHOD: Test point
label | f21133e4-8c0c-5ce9-b7f8-3655fce0163e |  | note | – – – – – – – – –
label | 07aefd5d-abc5-5f17-a40f-c7ed40d4a52c |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | a357b240-0b28-5132-9845-ae6c5bbe09c7 |  | note | – – – – – – – – –
label | 198af113-f1d1-594a-8708-60a65dec3f3f |  | note | TP
label | d976e4ce-b7bd-53fe-bdc4-48e8549d3062 |  | note | – – – – – – – – –
label | 3bef3db4-8e68-5d45-87c5-0c08d90bcdff |  | note | RESPONSIBILITY: Site Engineer
label | 2687e302-9d11-5cd6-aa72-1b1888adab96 |  | note | – – – – – – – – –
text | 4f4a5edf-56c1-54d5-9890-e23d92ec450a |  | textbox | DATE:
checkpoint-status | 85dddfc6-64bf-42d4-bc55-0499d5e74f30 |  | checkpoint | 3.6 Survey Conformance
label | 9d460925-9ea9-533d-9249-0076dffba24c |  | note | FREQUENCY: Each lot
label | 5013764f-062f-529a-b3cb-f960e19abf10 |  | note | – – – – – – – – –
label | ad14a049-5775-5de1-87b7-c44f6df5e994 |  | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | 25094ce2-bb2a-5f38-9e4d-53765d6630ee |  | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
label | e4d14b6f-5d5c-557c-8761-cc2c5907dd77 |  | note | • Surface level tolerances:
label | a0340739-fb66-589f-bec3-5e250b486584 |  | note | • Range x = +6, -16mm
label | d6024a36-4fd1-5a94-83c5-3f5adb4b4cb8 |  | note | • Max S = 15 mm
label | df6ac1cf-6523-51ed-9949-04dc45da3b22 |  | note | • 40 measurements per lot (Minimum)
label | ecab63ee-14ea-5986-8792-783ffc059d40 |  | note | – – – – – – – – –
label | b9f0ddbf-85bc-519d-ab39-68651a1d8e2b |  | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
label | 8c883d5d-1c96-5788-9ed5-ec2fb686986b |  | note | – – – – – – – – –
label | 94ed5097-40a4-5aa9-bb16-c867af4e7a46 |  | note | INSPECTION/TEST METHOD: Survey
label | c7049e8e-df5b-55cd-8894-f5cb4ad83c0a |  | note | – – – – – – – – –
label | e47fb5c0-5d39-54c8-87bc-600226d25e2d |  | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
label | 466b6f91-c90f-5f86-a1d0-5f545b52b496 |  | note | – – – – – – – – –
label | aa44a9a8-a747-538e-82ae-41335b9706b2 |  | note | SCP
label | 76e19809-d0da-566d-8aa2-518c3bf11f48 |  | note | – – – – – – – – –
label | e68fecb0-f1a0-569b-a231-34ef65e0478d |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | 9cdf03f3-77e5-57f1-bffa-5d99d991463a |  | note | – – – – – – – – –
text | 869b632e-0b5b-54b4-9bc6-636964e883f4 |  | textbox | DATE:
checkpoint-status | 2269a98a-4fbe-4c5c-8a7e-79fc28468fe2 |  | checkpoint | Final Inspection
label | 478136e9-6bd5-51a9-b7f4-b31a2a865e77 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 75c24828-54be-5571-b557-932ea6a1040a |  | textbox | Print Name:
text | 5a33e069-5b20-5ca4-951a-f3944d7e1334 |  | textbox | Position:
text | db5f45c4-2b8d-50c9-99c6-9a221304e55b |  | textbox | Date:
checklist-sectioned | 7e65a7e5-d482-41a6-99d8-29409d589aca |  | checklist | FHC-ITP-007 - General Demolition Rev1 | itp |  |  |  | Yes | FHC-ITP-007 - General Demolition Rev1 | 87a42c89-e8d2-4972-bbf6-2c60c4ab4d23
checkpoint-group | debcca96-6870-4024-8e76-4f712e75f78e |  | section | 1 - Preliminary Works
checkpoint-status | 8d3a6e5d-2184-4646-8936-cde6f2473701 |  | checkpoint | 1.1 Check for correct documentation
label | df6012eb-90d8-578a-a14e-e4ff0b7fc480 |  | note | FREQUENCY: Prior to commencing any activity
label | 597e5149-918d-5ffa-8294-01257c2e61b9 |  | note | – – – – – – – – –
label | a08c2ad1-8e96-5ea3-b856-b25c5ba5c733 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 52c16e84-73f5-5171-aa4c-b116a74852ca |  | note | – using the correct and complete set of drawings
label | 03acd100-5975-5275-8cb4-6a2bfa2aac22 |  | note | – all drawings are the latest revision
label | 0fbff04b-1d0d-589b-96f5-21ca69f0eb61 |  | note | – – – – – – – – –
label | 5514b563-ff63-5656-ae25-8fa8a2b465eb |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 9121c074-aae7-5df2-b252-d09964df6ec0 |  | note | – – – – – – – – –
label | e6f53646-eef1-52a3-90c1-9715f4d14dc4 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | bd7877ac-023e-5a8e-8f34-07bd8586ce84 |  | note | – – – – – – – – –
label | 50852312-2e56-501c-97d0-99c88668a14b |  | note | RECORD OF CONFORMITY: This ITP signed
label | bb07ad05-2b78-5609-95b1-bb07d1ebb3ae |  | note | – – – – – – – – –
label | 552aaf4b-31ab-5ea0-b962-a13dfe20db14 |  | note | HP*
label | c42d969b-c983-5f23-8ab3-99f29176ab09 |  | note | – – – – – – – – –
label | bc147509-bc74-5c27-856d-4f5a88943091 |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | b760f9ee-9c08-579f-94a3-5576983b6c34 |  | note | – – – – – – – – –
text | 750f67fe-048c-59b5-9901-40f9492837dd |  | textbox | DATE:
checkpoint-status | b9021a4f-23f5-4371-a586-f066c07d15af |  | checkpoint | 1.2 Implementation of all measures and controls
label | 3f157a80-4b3c-5e09-956d-90174093ffd2 |  | note | FREQUENCY: Prior to commencing any activity
label | f40c649a-aa79-5603-8623-ec5c4867b53c |  | note | – – – – – – – – –
label | cdb1f75c-b8bd-5369-9769-6cd46525f410 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 4b15cce4-21b1-517d-86e9-9ed8ed48fc14 |  | note | – – – – – – – – –
label | 8e3a6076-441a-51ab-a2a2-1bb1ac334733 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 8494aa4f-676f-59aa-b090-48a3e3c68aac |  | note | – – – – – – – – –
label | def16d3a-697c-50fe-b77a-3161f06f5f54 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 121d3109-dc0d-5239-a058-221cd0ea5bb2 |  | note | – – – – – – – – –
label | 6d4c2168-7e94-52a3-b966-fcf3ccd9f2a9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | c6e4b942-d1d0-5514-9868-2b52ad76332c |  | note | – – – – – – – – –
label | 39a7d4e9-6d9b-5d6e-a472-206e2e390623 |  | note | HP*
label | d428a88c-bbab-54c6-8edd-8166b961346a |  | note | – – – – – – – – –
label | be7be447-b29f-51d4-8154-be64adc65d0d |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | ae17996c-7529-56a0-b3b1-9483c93ff714 |  | note | – – – – – – – – –
text | 89f5945a-1176-5080-9e3a-de60b3af7077 |  | textbox | DATE:
checkpoint-status | 877c5abf-0715-4661-9780-b28f1ba6a43e |  | checkpoint | 1.3 Service Identification
label | a669f715-54c5-55bd-af60-823806b96bf3 |  | note | FREQUENCY: Prior to start
label | bf45c9ef-c6ad-59e2-874b-44620dbd9171 |  | note | – – – – – – – – –
label | 8fa82c07-1c42-5db4-9f5c-a82a43c517fd |  | note | ACCEPTANCE CRITERIA: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
label | d31140b0-f219-5761-a670-225281b5af1b |  | note | – – – – – – – – –
label | e7779ca6-c1ec-5026-97ea-a134f58dd100 |  | note | REFERENCE DOCUMENTS: ITP sign off
label | c15fc12c-d20f-5c12-858f-a57ece666502 |  | note | – – – – – – – – –
label | b58e406a-d431-5252-8954-eb1178e594fb |  | note | INSPECTION/TEST METHOD: Verify
label | 5484943b-9935-5885-a082-b086affe6d36 |  | note | – – – – – – – – –
label | 793e7e3e-47e6-5be3-b9e7-f4c9b28b3d4f |  | note | RECORD OF CONFORMITY: This ITP signed
label | 987641a3-566a-577a-bbc2-a407afa54202 |  | note | – – – – – – – – –
label | 9cd54f6e-aa05-5f60-ad65-6f8ab9f41033 |  | note | HP*
label | 453c1f05-9ddc-57ba-aa55-754374bc1138 |  | note | – – – – – – – – –
label | 8525759e-4f70-5675-becb-a840bcde690d |  | note | RESPONSIBILITY: Site Engineer
label | df6001f8-e7ff-55ef-9228-5954dd79c4d7 |  | note | – – – – – – – – –
text | bc340cc3-2e3a-5523-ab5c-bf3248e505ba |  | textbox | DATE:
checkpoint-group | e3292e98-9bb7-4b31-85fa-ac1135bd6c05 |  | section | 2 - Construction Works
checkpoint-status | 14b66475-10e4-458b-8013-0a388d21837a |  | checkpoint | 2.1 Saw cutting
label | 727daec6-5eed-5736-8cc3-3b2798186985 |  | note | FREQUENCY: Where required
label | 9693ac95-5907-56ab-baa6-f42b227d1b06 |  | note | – – – – – – – – –
label | ead4b070-dae9-5501-bbb2-42b960bdb031 |  | note | ACCEPTANCE CRITERIA: Extent and location of cuts to be clearly set out and checked prior to saw cutting
label | e7c7243e-f9cc-5b7b-9cc6-0555b6fb8284 |  | note | – – – – – – – – –
label | 92cb0043-0c5c-5480-bb9e-5a6af32b86fd |  | note | REFERENCE DOCUMENTS: ITP sign off
label | c7b0a1e8-7d97-58cd-a39c-1f9063da4b8a |  | note | – – – – – – – – –
label | 8dc05b7d-20b8-5080-b4bc-49ba69d2b317 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 125ec3ff-0cc4-550f-bf01-890178f3ac34 |  | note | – – – – – – – – –
label | 3310c1ac-86da-558e-aa6d-ae9077098848 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8aacc636-807d-5d9d-a6a4-8ee36e4ad7f1 |  | note | – – – – – – – – –
label | e55c8fd1-ddc6-5844-8774-eca692eb4d9b |  | note | WP
label | 89081531-3e9f-57a1-9f3d-a3158c5ed296 |  | note | – – – – – – – – –
label | dcbc86f5-d080-5a3f-8251-7618893f8c09 |  | note | RESPONSIBILITY: Site Engineer
label | 779f61c3-b20a-5451-bbbb-f30c6c16ccf3 |  | note | – – – – – – – – –
text | 227d9c3d-0ad9-5feb-8a18-e1b2bf4f142b |  | textbox | DATE:
checkpoint-status | 1a68c326-710d-4fc7-a3d7-9133a1ea96ee |  | checkpoint | 2.2 Excavation Permit
label | 0685f7c7-c41d-5b57-b2a0-613ffb04d61e |  | note | FREQUENCY: During excavation
label | d46bef5a-f8fb-589f-9417-b5ec8fbf7283 |  | note | – – – – – – – – –
label | 9c4b8328-df8e-5534-afe8-24217a367567 |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | fa2efc0a-d754-5b8c-899a-55593cd2eab2 |  | note | • Plant and equipment shall be appropriate for the task
label | bb6bc2b3-72ff-5259-9567-7ffc3bf98af9 |  | note | • Excavation operations shall not disturb areas outside the limit of excavation
label | 3113516d-f65b-5097-b2c6-313ef624bddc |  | note | – – – – – – – – –
label | a1518f87-ef3d-55b8-905a-684331b3c66d |  | note | REFERENCE DOCUMENTS: VicRoads 204.06
label | 1bfd7064-6869-5a66-866b-39b396096dbc |  | note | – – – – – – – – –
label | 90007c2d-53c9-5d41-8856-283771962c3b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 606311c9-448f-55db-9493-dc0dff861d79 |  | note | – – – – – – – – –
label | c8be3115-8385-51bf-a376-6519d8956191 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 92acbd21-96b1-5eb4-b078-0c592eee8382 |  | note | – – – – – – – – –
label | 76507a6c-970e-5ab3-9bd7-02f3901c557d |  | note | HP*
label | 1460fe9d-a81b-5a98-84ea-1690c0fc50b2 |  | note | – – – – – – – – –
label | ef1c3eb9-408a-5f6b-b062-b293ff8259b4 |  | note | RESPONSIBILITY: Site Engineer
label | 385f222b-84d4-58a9-a1a6-b42ed23aa6fd |  | note | – – – – – – – – –
text | 1d6d3a3f-a570-582c-bf53-80699b506b8a |  | textbox | DATE:
checkpoint-status | 800a5694-e03b-4120-b9d0-bfa0fe2af0ba |  | checkpoint | 2.3 Redundant Pits
label | e4778281-ee8b-50d4-96ad-403645e4658a |  | note | FREQUENCY: After clearing
label | e3c830d6-f4f5-588e-a3ff-e547cc09b138 |  | note | – – – – – – – – –
label | b53114d2-2a14-5c91-8fbf-3704b360719a |  | note | ACCEPTANCE CRITERIA: Any redundant pits, are to be removed to a depth no less than 0.3m below the stripped surface or no less than 0.6m below finished subgrade (wichever is lesser)
label | 2153616e-fc39-5d3e-a43b-0ee2318d0dcb |  | note | • Seal any pipe openings with concrete and backfill pit area with material and compact to a density ratio of 95% (standard compactive effort)
label | 06385c25-a0d4-56bb-b702-387f603e7a48 |  | note | – – – – – – – – –
label | 7c48c1d4-9ed0-553c-b7e5-f5d88ddc3adc |  | note | REFERENCE DOCUMENTS: 201.05
label | 0a303729-db6e-5d31-b7e2-8ac48f1326d6 |  | note | – – – – – – – – –
label | e111603c-9dbb-57d9-90a2-946a538003bc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7a75ef14-ac91-5eb3-9680-412e7918bb64 |  | note | – – – – – – – – –
label | 312571b1-0e79-50bb-bd74-edf045772242 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 57f334da-edaa-5cbe-9202-089be0994c02 |  | note | – – – – – – – – –
label | e668d7dd-7cc6-597a-8724-0ffc700213a9 |  | note | IP
label | ff45c08b-f710-5976-8743-ffca18365cca |  | note | – – – – – – – – –
label | ace237ca-d4e9-510f-8c09-6d88bf7ec78e |  | note | RESPONSIBILITY: Site Engineer
label | 301b3fbb-7a4c-587c-bacb-fee71a0e564a |  | note | – – – – – – – – –
text | 00293c63-2d0d-5bdc-8666-9379f942845b |  | textbox | DATE:
checkpoint-status | 48054a26-24ea-4bda-92d2-14aab1066642 |  | checkpoint | 2.4 Disposal of Material
label | ad0aa656-2e53-516b-9e08-2173f6d60fd2 |  | note | FREQUENCY: All times
label | 74a44bd5-3655-5614-b249-1e374ab22750 |  | note | – – – – – – – – –
label | d2f2ca37-322b-5586-8ce5-5746c600c896 |  | note | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
label | f70db071-1240-5e62-a8dc-afca0cf91a7b |  | note | – – – – – – – – –
label | f0978719-2755-54b0-ab5c-6c1f4548f0b4 |  | note | REFERENCE DOCUMENTS: ITP sign off
label | b4bdc89c-1c46-58e1-bee8-d5785f1da137 |  | note | – – – – – – – – –
label | 45da89af-2f48-5ea9-b6b2-6bd468b29072 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | abd4e96d-c0df-52b0-9c54-9af5de0eef22 |  | note | – – – – – – – – –
label | 0a3b6125-0485-59d2-8189-291ceebdd7f5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 610df51f-bd81-5fb4-b384-b4e2bf41eadd |  | note | – – – – – – – – –
label | 4c3d4887-aab9-561c-aa8b-92ed648da9c6 |  | note | WP
label | 9fc922f3-890f-5128-854e-68524c24bc89 |  | note | – – – – – – – – –
label | 1cb9b201-8a42-51a4-9898-61d4a8e3b73e |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | 9063200a-3a87-5e32-a29c-fc1fee865a1a |  | note | – – – – – – – – –
text | 0d5b66dd-3496-5691-a067-13bff9281e25 |  | textbox | DATE:
checkpoint-status | 8f82c5e2-07b1-4fa0-bc57-f97d0a519488 |  | checkpoint | 2.5 Maintaining cleanliness of site
label | 0b525960-4620-527d-ac8c-ecc5fe7df4b1 |  | note | FREQUENCY: All times
label | d54bb11a-8022-5ae8-a1ad-89bb00bfbd19 |  | note | – – – – – – – – –
label | 2c8959b3-afe8-54cf-9c06-714e8c47c060 |  | note | ACCEPTANCE CRITERIA: Site and surrounding environment are to be maintained at a good standard of cleanliness
label | 689ecdef-b563-565f-add9-078fbfb81894 |  | note | – – – – – – – – –
label | 1cbc5927-6e3f-5da8-a3e2-763fa8418433 |  | note | REFERENCE DOCUMENTS: ITP sign off
label | 9b623fe5-39c5-5f78-b88b-4e123883fb3a |  | note | – – – – – – – – –
label | 2f809241-68b4-54b7-930d-b88b8105f5fc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d7576e9a-0cf1-50c3-8d3a-e841cc38eb9e |  | note | – – – – – – – – –
label | e9236435-c2f5-5f6e-8c55-76b4224123c0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 086a39ec-b509-5c1d-8512-c1aae7aa5876 |  | note | – – – – – – – – –
label | 9dde9364-66ef-57a3-8ea9-df735ead8986 |  | note | WP
label | 1c22771b-f83a-584b-9c31-042be18ee7b4 |  | note | – – – – – – – – –
label | 0e320487-f627-5be1-b34a-da952ff4eacd |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | f05d5fbc-e001-562e-be00-4e5a44b8b431 |  | note | – – – – – – – – –
text | 1dc3ee7e-2160-5af9-8d1b-bd06195d22a9 |  | textbox | DATE:
checkpoint-status | 887194a3-4d74-44b0-a08e-fd90c2077e65 |  | checkpoint | Final Inspection
label | 2139fa7c-c198-5879-81c4-07cd5b142c7e |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 668c4a4e-961b-5c48-8503-f99336c42a9f |  | textbox | Print Name:
text | 2efe18cd-257c-554e-92c2-f19f63ed6d06 |  | textbox | Position:
text | 7f6e2996-d6db-51bb-97f8-a644809f941e |  | textbox | Date:
checklist-sectioned | 8aaf6575-e4a1-4469-a4c5-f472a855846f |  | checklist | FHC-ITP-023 - Conduit, Pit & OCS Installation Rev1 | itp |  |  |  | Yes | FHC-ITP-023 - Conduit, Pit & OCS Installation Rev1 | 9f84535b-869b-4327-b731-6e0d85366071
checkpoint-group | d938e43b-4565-4f0c-beb2-d0036883fe15 |  | section | 1 - Preliminary Works
checkpoint-status | a2692f12-21e6-4587-9362-87237c6b6834 |  | checkpoint | 1.1 Check for correct documentation
label | 3d3d5c80-9a50-5624-a046-92c857679aff |  | note | FREQUENCY: Prior to commencing any activity
label | 56aa97f4-b39d-5fbc-8b54-7c6dd6a43190 |  | note | – – – – – – – – –
label | c8cd1a62-8972-53f8-919a-5b07b0a66b04 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 708c5928-0fc9-5804-b78b-a4660c5a7930 |  | note | – using the correct and complete set of drawings
label | 5c2956b8-26d0-5263-af9e-846055e4a8c9 |  | note | – all drawings are the latest revision
label | a7caf196-4037-5315-9384-286af124eef6 |  | note | – – – – – – – – –
label | 05fad10f-2820-5127-b4f2-471e82fc178d |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 53caedb7-cf8d-50b5-8e45-a18a64a069ee |  | note | – – – – – – – – –
label | c15886e2-2168-5396-bca6-3423fc7b399e |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 638f108e-31a3-5964-9b3d-82fef219a433 |  | note | – – – – – – – – –
label | 5cd7da32-e5d0-5442-9a2e-fb25d9c20104 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 2281d742-bea5-553c-81f7-a852b20c7925 |  | note | – – – – – – – – –
label | 71679241-4d4c-56b5-96df-2cdb41e6256f |  | note | HP*
label | 8e850072-6440-5c69-8a36-c25086da590e |  | note | – – – – – – – – –
label | e7f27845-d771-51ae-9cd1-648d279ea5ee |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 43a39eb5-58c9-5d9c-8ef1-610b4e839f3e |  | note | – – – – – – – – –
text | cf9d8f5d-2286-5b61-a63a-bcc7ff6cc660 |  | textbox | DATE:
checkpoint-status | 5b6bc7ad-f75b-457a-8351-03788dcac769 |  | checkpoint | 1.2 Implementation of all measures and controls
label | e6817546-5cff-54aa-887c-0e8926de6f04 |  | note | FREQUENCY: Prior to commencing any activity
label | 43624bcd-9c7c-5fac-bf38-9251c2a37f65 |  | note | – – – – – – – – –
label | 04ae78fb-2029-5adc-b95f-78adfb045c6a |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 5918f115-ed9b-5930-a57e-af0d3fabc797 |  | note | – – – – – – – – –
label | 1f441c05-089c-589e-81ee-367c389fd964 |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | c1122cc5-13a7-5886-8240-7137c7bada94 |  | note | – – – – – – – – –
label | bb935c61-48ab-52cb-be65-ec7b02af255f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6a723798-c8ff-5342-9445-9a3cbe71bae2 |  | note | – – – – – – – – –
label | 2ef4a2db-4aaf-5ea8-bd47-ceff7fdadc32 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0f38de2e-22d5-5ab9-b182-f14e4de04e5c |  | note | – – – – – – – – –
label | f2ebb82d-04f6-586a-b7a3-d7613eaf332a |  | note | HP*
label | dfcdb1b4-6437-514f-ae90-6b81db8d19ac |  | note | – – – – – – – – –
label | 220ba8d7-818e-59bb-ae08-bfea1b2e221b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | d16add69-a3a5-5900-8d74-669bcb264bcd |  | note | – – – – – – – – –
text | eb3d1aa8-35e0-57a5-aa72-130162e7beb1 |  | textbox | DATE:
checkpoint-status | b3f50c6e-2d6f-4854-904e-2c3510e6fdf9 |  | checkpoint | 1.3 Materials
label | 9ed0b570-d252-526d-ad5e-9b35b0ba7c68 |  | note | FREQUENCY: Per Batch
label | df586ea5-79ad-50f2-9c53-56b86ddfdecd |  | note | – – – – – – – – –
label | f3124e3d-51f1-5484-873e-534bd9054d23 |  | note | ACCEPTANCE CRITERIA:
label | d2eca6cf-f61d-59d9-9874-0515f8e4cd90 |  | note | • Carpark Lighting A pit is to be installed adjacent to each lighting pole with 1 x 100mm HD conduit and 1 x 63mm conduit installed between pit and the point of supply. 2 x 32mm HD conduits are to be installed between the pit and the pole mounting base.
label | da61e833-697c-52e4-bcfe-96fe6999bfb2 |  | note | • Electrical supply conduit all conduits for underground mains shall be heavy duty 'Orange' underground category PVC pipe complying with the most recent issue of AS/NZS 3000 Australia/New Zealand Wiring Rules.
label | adca53d8-134b-524f-ac0c-d793e204dbc0 |  | note | • Communications conduit to be white 1C50 HD PVC conduits and 1C100 HD PVC conduits
label | 0094fabf-068f-57f9-9b07-731a74a200e3 |  | note | • Camera mounting poles and structures shall meet AS47806.2 (2006) Section 5.4.1 (k)
label | 5e4bbd49-c3c6-5741-86a5-d94a11282fe3 |  | note | • Cable pit lids shall be VicRoads type approved, impressed with 'VicRoads' and 'Electrical', 'Communication', 'Traffic signals" as appropriate as per VicRoads Standard Drawing TC-1220
label | bbef8651-04a6-51ef-80d4-dcd5341da572 |  | note | • All equipment labelling to comply with requirements of NIST-013.4
label | 620d1e8e-b3d5-5cf3-9b58-7c9257ecd422 |  | note | • Cable pits shall be 435mm dia x 550mm deep, Type 43 plastic HDPE – Aco Cablemate cable pit with concrete lid or equivalent
label | 71c4ebf7-31a8-5e9f-ac63-6fe3fac2f244 |  | note | – – – – – – – – –
label | e22a464c-4abd-5827-8414-887efee6a22f |  | note | REFERENCE DOCUMENTS: NIST-5031 3.2.2.5 (f), Drawings
label | 8a044274-f763-59ed-b304-21e8d628f170 |  | note | – – – – – – – – –
label | 1052ad00-d302-5884-aff1-4e9516f13946 |  | note | INSPECTION/TEST METHOD: Verify
label | 60c98819-5686-527a-90ed-eb6f080d3bcb |  | note | – – – – – – – – –
label | 9e5efed4-83dc-5242-bc9e-4b747370ac6f |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5ac00e02-34b7-5265-8c55-9743e7749421 |  | note | – – – – – – – – –
label | 79e14b33-2d19-5cfe-bf0f-7a97dfeb26b2 |  | note | HP*
label | 71c63833-35a2-5c69-87c5-a19a7cff3863 |  | note | – – – – – – – – –
label | 9c02bd02-1eb6-5319-858a-4ebc6ba478a0 |  | note | RESPONSIBILITY: Fulton Hogan Engineer, Electrical Subcontractor, Vline representative
label | 0f5e00a5-8b78-5fc1-97b3-5c004a3ed332 |  | note | – – – – – – – – –
text | 6bd82fca-025a-5b75-878f-d6fcb1012197 |  | textbox | DATE:
checkpoint-group | 6f68fc16-2f33-4f2c-ace3-8d9a5c1ec8a1 |  | section | 2 - Construction Works
checkpoint-status | 4df94196-34a4-48de-84c0-1cd574891fda |  | checkpoint | 2.1 Survey set-out
label | 11d73252-8f52-5345-9cfc-5fe55fe3bf9f |  | note | FREQUENCY: As required
label | fbb41fb5-5aca-5997-844a-c37854173eb0 |  | note | – – – – – – – – –
label | 819f5bb9-d16b-501a-ade2-29b6fb792331 |  | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
label | ded4b3dc-fa81-523b-948e-74b5621d3a9d |  | note | – – – – – – – – –
label | 619700d4-8f6c-5621-a0fa-f5862dab6d9e |  | note | REFERENCE DOCUMENTS: Work procedure, Drawings
label | 7058bf53-f9ce-5286-96a7-9164dfc0d78b |  | note | – – – – – – – – –
label | 80bccae2-4c12-5e3d-8a05-7ac42ee0d02c |  | note | INSPECTION/TEST METHOD: Verify
label | d1c61ffe-7b6b-5106-820a-667d304c43a5 |  | note | – – – – – – – – –
label | d3c22dd2-2e07-57f4-a8e4-d71bf3674583 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9c540ae7-ce50-53ea-a5dd-9251549783a4 |  | note | – – – – – – – – –
label | 2b60e7ad-ba83-59fe-9a91-609c97747eb2 |  | note | HP*
label | ce6d30fe-f423-5bb5-b22c-07647ae5938e |  | note | – – – – – – – – –
label | dd2e1e8a-64b3-5fbd-a910-faf60ce42b14 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 6f862b00-6374-5adc-a5ec-b0ed69d3e3a9 |  | note | – – – – – – – – –
text | 972cd9c5-d90a-5862-bdc7-fd9a82119cb1 |  | textbox | DATE:
checkpoint-status | a859cbe7-03d2-47c3-befd-b102726c7fda |  | checkpoint | 2.2 Excavation/Boring & Trenching
label | 65d49897-6183-55d1-b36a-4a6af2773b4c |  | note | FREQUENCY: Prior to Backfill
label | f4a7ba14-e204-52c2-9aa8-7df41a76d6b4 |  | note | – – – – – – – – –
label | a849fc92-54cd-56ca-a3b4-723d53344129 |  | note | ACCEPTANCE CRITERIA: Trenches shall be excavated to a depth required to achieve the specified depth of cover and drainage slope, plus an over-excavation of approximately 50 mm to allow for bedding sand. The width of trenches shall be as required to fit all the conduits and pipes for services sharing the trench with specified separations, plus a further 50 mm minimum clearance from the outermost pipes or conduits.
label | 2f567053-8086-51ee-85ba-cc261bc483b7 |  | note | • Where trenches are excavated across roadways, car parks or paved areas, the Electrical Contractor shall backfill the trench with 20mm of Class 3 crushed rock. The crushed rock shall be placed in layers not exceeding 150mm finished depth and compacted to a minimum of 95% of standard density. The backfilling shall extend for a minimum of 1.0m outside all paved areas and shall be subject to the supervision of the V/Line delegated representative.
label | 268b92be-387e-50b4-aa1f-1a640ce8f839 |  | note | – – – – – – – – –
label | 911c0106-79ea-50cd-8a34-e7ea203298bf |  | note | REFERENCE DOCUMENTS: L1-CHE-STD-077 Sect 6.10.6
label | 51c365c3-e578-5d9e-a26c-78b7ae56272d |  | note | – – – – – – – – –
label | 307e34a5-15a5-56c9-ac2c-4efcc99d7ffa |  | note | INSPECTION/TEST METHOD: Verify
label | d9f1de37-6f91-5875-95a7-144dc8426664 |  | note | – – – – – – – – –
label | 7499e5e0-807a-508b-ad65-d95d16ccdcda |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8b006422-c0cb-5d34-9646-b7e54ee1fe7a |  | note | – – – – – – – – –
label | e0063011-ef53-52fc-b327-c533c13ee8a4 |  | note | HP
label | fac46bc9-554e-59da-b8cc-5e5d88d672b9 |  | note | – – – – – – – – –
label | b9afb1e1-967d-5069-b0b1-8bdfc5001e3c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 15a26431-5b6c-5216-b078-882ee69db480 |  | note | – – – – – – – – –
text | 2cf5bd59-d4b5-5c01-8510-3ffb0956d16e |  | textbox | DATE:
holdpoint | 9ed860dc-164d-4c0b-9b48-c84edee170de |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 452f80eb-84a6-4a4c-b062-f81c7e2e3e34 |  | checkpoint | 2.3 Installation of Pit and Conduits
label | ec1d176b-4046-50cc-a3de-dff379c407d4 |  | note | FREQUENCY: Each Lot
label | 62cbfbcb-9a42-53f9-a8fc-92accb845cc2 |  | note | – – – – – – – – –
label | 10cdfd46-497f-53aa-b2bf-a93d2ba82519 |  | note | ACCEPTANCE CRITERIA: Underground conduits shall have a minimum 450mm cover if around the site but away from the track corridor, should only be in the non-trafficable areas. If exposed to traffic, the depth should be 650mm.
label | f5ec7e40-04f2-55d8-9d33-b00adcff17ba |  | note | • Upon installation conduits shall be cleaned and tested using a mandrel of at least 90% of the conduit inner diameter and length three times the inner diameter.
label | 81e653e2-a287-521f-9cfa-97d801d00b07 |  | note | • Multiple conduit entry penetration holes on a pit wall shall be spaced at least 50 mm apart in horizontal and vertical planes
label | a7264fbf-dfa8-5d76-9152-92bea2dd009f |  | note | – – – – – – – – –
label | 469d464b-a99a-5e24-8145-dda416f446ec |  | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 4.2, L1-CHE-STD-077 Sect 6.9
label | f8ad8b7c-a0ea-599f-8daf-c31768176fa7 |  | note | – – – – – – – – –
label | 01646e53-9038-59e7-b06c-9fb3f893ffdd |  | note | INSPECTION/TEST METHOD: Verify
label | 81a435eb-1680-577f-9a93-454a1568d1a0 |  | note | – – – – – – – – –
label | fbf604d8-94d7-5b5e-9db0-3030cb98ec7d |  | note | RECORD OF CONFORMITY: This ITP signed WP
label | 4a23442d-4656-55af-8a9c-4d3253afe793 |  | note | – – – – – – – – –
label | f06eb101-0868-5a7c-9ee3-43ad484b2f08 |  | note | IP
label | 68a455b5-38a3-5e60-81e6-3ad6efe3a76b |  | note | – – – – – – – – –
label | f2f63d24-2f51-53b7-b0bb-54bdc71b6b3a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 0a338fea-0938-5d13-b305-4f66c0dc7823 |  | note | – – – – – – – – –
text | 3863ef32-ecf8-5c4d-9ddb-2df36b3c19f7 |  | textbox | DATE:
checkpoint-status | f2b02ff6-e967-415f-ac63-8e04c47c6011 |  | checkpoint | 2.4 Back Fill of Trenches (Trafficable)
label | 0f7bf268-4587-503e-8a70-a7aa96deed5a |  | note | FREQUENCY: Each Lot
label | 7b1f0558-4006-5111-865e-b13164ee695c |  | note | – – – – – – – – –
label | 372f6a7d-fb82-5b5c-977c-a6c4b6e5736a |  | note | ACCEPTANCE CRITERIA:
label | 1b1198fc-650e-5db8-9849-45273189a048 |  | note | • Bedding: Graded recyclable glass in accordance with MTM standard L1-CHE-SPE-313
label | 694e1b67-a754-5e65-907b-ed8ee0dcdb9c |  | note | • Backfill: VicRoads 20mm class two crushed concrete base compacted to 95% of standard density in 150mm thick layers
label | e07a473d-1637-557e-a941-b548a314daee |  | note | – – – – – – – – –
label | abf549a9-d109-58c3-9a14-615eb7bfafe4 |  | note | REFERENCE DOCUMENTS: NIST-5031, L1-CHE-SPE-313, MRP-708-C-AUR-DRG-20-TNT-CLT-0810
label | de3a9930-96d6-58a5-a3c0-5aca9f4d8e62 |  | note | – – – – – – – – –
label | cb038940-5f94-5efa-9e59-b1b4b1d88149 |  | note | INSPECTION/TEST METHOD: Verify
label | 8a625af0-8f14-5ee0-ac6d-6754c6ccbeae |  | note | – – – – – – – – –
label | f80c71a0-96aa-57d6-bdef-3d397fe1b7f9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | c75d9647-99c8-5dc8-a130-912faebbdf42 |  | note | – – – – – – – – –
label | f9e156b1-741c-545d-93b4-18681a317091 |  | note | WP/IP
label | edf7cbd5-4f9b-509c-a97f-946fbb633b72 |  | note | – – – – – – – – –
label | dd7436b1-7e5d-5f8d-a5b7-1014c9840f0d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 09b84ce5-7521-5e86-b885-8b4ef1dae001 |  | note | – – – – – – – – –
text | 39b55c4b-644b-5965-aeca-ad790caee25d |  | textbox | DATE:
checkpoint-status | 29882b57-af82-4e92-a19d-f5381bde94ea |  | checkpoint | 2.5 Installation of Draw Cords
label | 22640a98-2290-5fce-93bb-3967aea59be6 |  | note | FREQUENCY: Each Lot
label | 8047f197-6c27-5c8a-858f-9970bbfebc32 |  | note | – – – – – – – – –
label | 469f7e85-1e4a-53c1-ad5b-5db7ab37d5bb |  | note | ACCEPTANCE CRITERIA: A draw wire of 6mm polypropylene blue/yellow rope shall be placed in each pipe and suitably anchored at each end. Pipe ends shall be sealed using pipe end caps or an approved equivalent to prevent the ingress of dirt or sludge into the pipes.
label | 23463575-fc82-5b4a-9493-8dba313657dd |  | note | – – – – – – – – –
label | 445c598f-4828-55ca-8d60-a39efe05a558 |  | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.12(d)
label | 5a75c83a-5243-5bdd-b3aa-7ce9588d092e |  | note | – – – – – – – – –
label | 64837f27-a6fc-52b8-9195-8c1e0fe8c662 |  | note | INSPECTION/TEST METHOD: Verify
label | 2daba89a-f35b-59b0-8393-30768b9b527c |  | note | – – – – – – – – –
label | 0438095c-3f60-5713-a034-319c8bb76ef0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 27ba2918-82d0-54c0-8605-f5ffdc163d77 |  | note | – – – – – – – – –
label | 2dd4f515-2304-5dee-bbdc-6d910d8d4c2a |  | note | IP
label | eb41fb0e-ed79-5b95-b00d-aea561b25772 |  | note | – – – – – – – – –
label | 4802adea-7ac7-5eca-b54b-98a874c3ff16 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | aa35a51c-0d80-5131-99f7-8a4823c02810 |  | note | – – – – – – – – –
text | 00b7ea6d-b830-51c4-a829-5a9f8fa9efda |  | textbox | DATE:
checkpoint-status | 98e1f791-d9b3-4219-b703-2cd134419425 |  | checkpoint | 2.6 Installation of Marker Tape
label | 7a8b4184-35e1-506b-aa86-7a93bcc686ef |  | note | FREQUENCY: Each Lot
label | e7992ecd-203b-5268-9cf6-b03a9b732925 |  | note | – – – – – – – – –
label | df7d9e01-1580-50cd-8ecd-ad30ad079a35 |  | note | ACCEPTANCE CRITERIA: A 150 mm wide orange coloured PVC marker tape with the words “DANGER BURIED CABLES” shall be installed in all trenches at 300 mm below ground level except where cables are permitted in shallow trenches due to rock. In this case the depth of the marker tape shall be at the discretion of the Infrastructure Manager.
label | e1978151-e518-5333-be93-87fdbb50da04 |  | note | – – – – – – – – –
label | 9116f2a6-40b4-542b-b3af-35a5e73ff710 |  | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.11.1
label | 7999e916-9e77-5c6f-a8df-83b95808b156 |  | note | – – – – – – – – –
label | 41056d76-f46a-5cf2-bf63-819a9d77695d |  | note | INSPECTION/TEST METHOD: Verify
label | 0ebcb908-436e-5a62-89c7-aa02d3eccad2 |  | note | – – – – – – – – –
label | c8898386-5574-580a-85e6-a3b9296cfc69 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4ab96c9b-553e-5ce2-8b82-bf7b0978348f |  | note | – – – – – – – – –
label | 111ad1ca-81c8-5917-8053-06efd45e3b02 |  | note | IP
label | 5b2f85a9-8df5-57d8-ac17-91e8478388ed |  | note | – – – – – – – – –
label | e4e9720e-a961-5323-9a55-62a10b3ab01f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | a38f585d-4620-5fac-9614-a40172f29b02 |  | note | – – – – – – – – –
text | 801685e0-baeb-52b4-a340-35e78ce00350 |  | textbox | DATE:
checkpoint-status | 140e7dd1-022b-41ca-ac64-3370f79ce064 |  | checkpoint | 2.7 Cable Pits & Pit Lids
label | dea11f25-dffc-56f7-bcf5-5e07df23ce6b |  | note | FREQUENCY: Each Lot
label | c35fdb6c-b718-5027-a161-0d5c6c5df8bd |  | note | – – – – – – – – –
label | cd55995e-a42b-51e5-bc79-66fc1c9ef92a |  | note | ACCEPTANCE CRITERIA:
label | c989e47f-3807-5de6-b67a-d02af13f6489 |  | note | • Cable pits constructed and installed as per drawings
label | 63e5f1df-8d79-53d0-9e8f-1b5411f2042c |  | note | • Pits shall be placed at each horizontal change in direction or at spacing no greater than 100m
label | f470ca4a-32f3-5970-a675-fa43ab6e7fdb |  | note | • Seperate pits shall be used for power conduits (orange) and communications (white).
label | c0a2038f-833b-5fa7-8bd4-191237362c42 |  | note | – – – – – – – – –
label | 040998a0-11b4-577f-b1e9-f46d335fa107 |  | note | REFERENCE DOCUMENTS: OCS Drawing Package
label | b093efb8-9e42-5dc1-b973-e72bbed6e0ba |  | note | – – – – – – – – –
label | 8d6193d4-1a1d-574f-9ed5-1d06ade9a2e7 |  | note | INSPECTION/TEST METHOD: Verify
label | b0c879ea-5aeb-5a15-82d1-580dfede7ab4 |  | note | – – – – – – – – –
label | 00dcaebd-6de1-5c78-bd9b-3b98d0ddcefc |  | note | RECORD OF CONFORMITY: This ITP signed
label | 53be3e55-7300-5c6d-8496-35254c20198d |  | note | – – – – – – – – –
label | 0c59bcd1-45ad-52cb-bbd0-64ff9ec6813c |  | note | IP
label | 9cb7c6cc-d60c-5573-881d-9faf8d97b990 |  | note | – – – – – – – – –
label | 57f9d7c4-c72c-5e49-a4c5-05ba2b98f5c4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | adb6d222-eb28-5048-aa37-0ab329e14f50 |  | note | – – – – – – – – –
text | 0d7200f3-b62c-5b3e-8d66-29c0316ffde2 |  | textbox | DATE:
checkpoint-group | 6ae7168b-69a5-47f6-8fc2-9b246bf42f9b |  | section | 3 - Completion
checkpoint-status | 55ec55ab-3ae5-42b2-97c4-f7474055f813 |  | checkpoint | 3.1 Cleaning of Site
label | b97fc449-5090-530d-a2a3-7753755ca209 |  | note | FREQUENCY: Each Lot
label | 82901f64-c998-52be-821a-3141ec59ddd1 |  | note | – – – – – – – – –
label | f8f1f49f-0dcb-5f5e-af53-96b1e0f3c8e5 |  | note | ACCEPTANCE CRITERIA: All obselete cabling to be removed during installation and disposed of appropriately. Upon removal of all redundant signalling equipment; the site shall be cleared of all project scrap and associated rubbish.
label | be3ec934-20fd-5eea-aa33-5494e6536ac4 |  | note | – – – – – – – – –
label | 51576848-902f-54b5-9b9e-42139214657f |  | note | REFERENCE DOCUMENTS: NIST-012.2 Sect 23
label | c82ee209-56c4-5177-9cf0-c76522fde233 |  | note | – – – – – – – – –
label | ad8bf034-05e4-58bb-90d5-0567b21203b0 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | d438e2de-cdc8-506f-a926-6f69ed79da6f |  | note | – – – – – – – – –
label | 3b8ca024-cbe6-5701-a13f-491b286d0bc0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 12bf0715-18b0-52d8-b8f3-4a6c6b48cd49 |  | note | – – – – – – – – –
label | e707a024-bbef-5335-8a3a-aa02f967b2cf |  | note | IP
label | 038a38b6-7931-5da1-8c55-7cb3d45ab071 |  | note | – – – – – – – – –
label | 11dd937d-1160-57c6-ba69-10516bd82ee0 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 32733bb4-2265-5d45-9030-693826b9b34e |  | note | – – – – – – – – –
text | f07e1c3f-e0b5-57ba-8d9d-a12a12584ce5 |  | textbox | DATE:
checkpoint-status | 4623e14e-e8e9-42e4-b6ec-08489227de4d |  | checkpoint | 3.2 Recording/As Built
label | 9b9b8039-76d4-5862-9a76-c3aa4323df72 |  | note | FREQUENCY: Each Lot
label | 1631db43-edac-5b2d-9a87-78d65778261d |  | note | – – – – – – – – –
label | 602a93d6-85d8-59bc-a1d0-73cb6adea9d7 |  | note | ACCEPTANCE CRITERIA: As-built drawings will be completed by the Contractor based upon the installed system by a process of editing the approved ‘for construction’ drawings.
label | a12b4031-f765-5654-853c-04e3a578cd15 |  | note | – – – – – – – – –
label | 967ed97d-45de-5513-bcce-53a195b5f83c |  | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 5.1.3
label | 1b85ee8c-fc97-521b-a614-d4e7922fdfd6 |  | note | – – – – – – – – –
label | 647a8625-8304-5631-9279-ecca49b623d0 |  | note | INSPECTION/TEST METHOD: Verify
label | 67ed3186-3bbd-56be-ad88-8416ab29228c |  | note | – – – – – – – – –
label | 4a173c41-7804-5cc3-b0b3-fb77b5eede50 |  | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
label | 6934bfe0-c35f-50f6-baaf-add36605eb35 |  | note | – – – – – – – – –
label | 139272a0-d3e1-559d-9be9-166c82019759 |  | note | IP
label | 0976288b-6a30-546d-bf6e-71f3031fe1e0 |  | note | – – – – – – – – –
label | 02843c3c-dc66-5fdb-99fd-9486ff1dd002 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 48992625-df0a-5e92-be83-5a2fc15bdf38 |  | note | – – – – – – – – –
text | b9558d94-e18f-526d-9e02-b250f8dca459 |  | textbox | DATE:
checkpoint-status | 097982d7-67d4-433e-8b08-ac17e8cc7bff |  | checkpoint | 3.3 Commisioning
label | 535240e8-4377-5556-8c7d-330e5c24ce46 |  | note | FREQUENCY: Each Lot
label | 20d613d9-ad8d-5d37-b109-a8243c6130a0 |  | note | – – – – – – – – –
label | f346deab-da6f-5e61-bef7-942e21e12c91 |  | note | ACCEPTANCE CRITERIA: Commisioning to be checked against V/Line checklist. For OCS Only
label | 8d0fcbbc-12e0-5178-9ac2-3730a97018fa |  | note | – – – – – – – – –
label | 816ea823-8f04-50e8-9b37-6673396a3a09 |  | note | REFERENCE DOCUMENTS: V/Line Commisioning Checklist
label | e781056e-4913-5deb-8962-e41dca16dc28 |  | note | – – – – – – – – –
label | ba68a5f2-595d-521e-b9b3-f43b4cfa0fa4 |  | note | INSPECTION/TEST METHOD: Verify
label | 5888d2a8-cbb0-5743-8d96-51e4c1d76bdf |  | note | – – – – – – – – –
label | 46f9c1e6-1ada-5bef-9c49-18110647f712 |  | note | RECORD OF CONFORMITY: This ITP signed, V/Line Checklist signed
label | 380d6794-76a2-51be-84f6-ee24726bae96 |  | note | – – – – – – – – –
label | fe59133a-ec14-529d-b033-0bf4e45cdf7e |  | note | WP/TP
label | 7c3f95d8-b5e7-593f-bf56-add53e8e5e1c |  | note | – – – – – – – – –
label | 51aad85a-b28b-5ce0-8f44-514f8f6950b2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | e7266f20-09fe-550f-9b08-fb10a1d6ace4 |  | note | – – – – – – – – –
text | 14c28eb2-4eff-5870-8d88-e289b2df945b |  | textbox | DATE:
checkpoint-status | e4e24f4e-bc6f-41b9-a86c-d0e603cae69a |  | checkpoint | Final Inspection
label | 8f702ff7-6f3f-55b0-a5b1-253a2bb6ae94 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 14a7186d-10ca-56e1-82b9-2ab3dd66b0d1 |  | textbox | Print Name:
text | 8bf21596-8e53-5d29-8cd0-98eb861a66d5 |  | textbox | Position:
text | fcaf7c67-9f25-5b8a-9f5e-86068ab630c5 |  | textbox | Date:
checklist-sectioned | 01bd7efc-71f8-4c42-8962-874a95b65d1b |  | checklist | FHC-ITP-014 - Subsurface Drainage Rev2 | itp |  |  |  | Yes | FHC-ITP-014 - Subsurface Drainage Rev2 | a4102fca-fdb5-480c-8866-1299f41c6729
checkpoint-group | 2e0a480b-193d-4ebe-98c7-300099df0616 |  | section | 1 - Preliminary Works
checkpoint-status | 1d19c950-725c-4cc0-9084-b02fc92d73aa |  | checkpoint | 1.1 Check for correct documentation
label | e3a874f8-3461-59ba-af29-e416b1ac3e30 |  | note | FREQUENCY: Prior to commencing any activity
label | 063c4623-48c2-5bf4-865d-52d04398fef3 |  | note | – – – – – – – – –
label | d491a1ac-2cdc-55fc-a191-215c7649d976 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 03e1169e-da6a-5e2c-b020-041561d5997f |  | note | – using the correct and complete set of drawings
label | c7b6d11b-9f7a-5478-9d93-621aca039bdd |  | note | – all drawings are the latest revision
label | c0a9bffd-4f94-55a6-8a87-c58e4b9026dd |  | note | – – – – – – – – –
label | 4d8546a5-083f-5665-af14-90b17765cff9 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | de01ed69-02f5-5d3c-9981-fc4d28f3eac7 |  | note | – – – – – – – – –
label | e204fa49-4e89-5d04-8c2d-4f17ccf416d4 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | b5c5a22b-06b9-5f06-a4b5-fb5f3289a91b |  | note | – – – – – – – – –
label | b1c0b997-fd33-564a-b3d6-cde943a8e6ec |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d282fc23-977f-5b69-b37a-dc35fdd92f57 |  | note | – – – – – – – – –
label | 2f466e0c-366e-5852-80d6-b8dfe5ec2471 |  | note | HP*
label | 16b9159d-094a-501e-a4b2-36caf1440db2 |  | note | – – – – – – – – –
label | d8b4e7b5-f2e5-5c13-b383-31eb6ef67337 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 4556fefe-dfe0-526d-9885-1530c498fb09 |  | note | – – – – – – – – –
text | a24cf8db-eb35-58c9-a777-e9c1adf6341e |  | textbox | DATE:
checkpoint-status | 2bd9a33d-4201-484a-8ebb-cfc00972c1aa |  | checkpoint | 1.2 Implementation of all measures and controls
label | 1c98acbd-63be-5344-a47b-971d0100ed1f |  | note | FREQUENCY: Prior to commencing any activity
label | da854f34-df41-5551-ac3f-b0ce1f4bff75 |  | note | – – – – – – – – –
label | ba3cbf8f-f781-5465-a719-3b3f2e3868a8 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | ab3822a3-b8dc-5275-9e5e-e81ad6bbed7b |  | note | – – – – – – – – –
label | c3909108-8ad9-5584-addd-237594e1ecbe |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 6558563c-e1eb-5506-b391-61a7ffcb9e5a |  | note | – – – – – – – – –
label | 3faf18e4-fa0b-5fb8-aaf3-17b373a29291 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2cdc1771-5b5d-5afc-9856-2ba477c27a2c |  | note | – – – – – – – – –
label | b3d7cb0a-f284-5e51-a79d-550f4b19e399 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | fcac3787-0cd8-5174-a8d7-5f887900033b |  | note | – – – – – – – – –
label | 935dfd0c-2dbc-5107-bf5c-abc0ee239881 |  | note | HP*
label | 67432755-3201-5dc5-a02c-ceb7e0bfaa7d |  | note | – – – – – – – – –
label | 3d2f758a-e23c-5231-918d-bcd1d06f41ec |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | bb42acd3-d221-5624-9904-d8f7277d51c2 |  | note | – – – – – – – – –
text | 8cf26ff5-3584-59f2-8714-3b6cc5eca970 |  | textbox | DATE:
checkpoint-status | a72ca572-333e-41b5-abf1-ba3fad548951 |  | checkpoint | 1.3 Placement of no fines concrete
label | 4c930151-8fdd-555b-9d96-6163c6f496ee |  | note | FREQUENCY: Prior to works commencing
label | 713ba0ac-4687-55bf-aa26-385c998d454e |  | note | – – – – – – – – –
label | 0aafb9c6-5978-5651-bc1a-7dc3fc7717a2 |  | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete.
label | c71218ee-9581-5c29-b991-07fd091db827 |  | note | • The method of compaction shall be in accordance with the Contractor's quality procedures
label | 360c2cd0-d143-50ed-951a-f0f8f484719b |  | note | – – – – – – – – –
label | fa0b976f-22a5-5a70-aebd-eea2ffb80df1 |  | note | REFERENCE DOCUMENTS: 702.09(g)
label | bb42840c-1e1f-5e01-b59e-87dc8defae28 |  | note | – – – – – – – – –
label | 07fc6f4b-2064-5bb9-bc2e-056df5bfd770 |  | note | INSPECTION/TEST METHOD: Verify
label | a1bae5f7-8d1b-520f-bad8-34567d04e00b |  | note | – – – – – – – – –
label | 7d14100c-59be-5d63-b7d9-f83bd78b12da |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 07809632-8fb8-5179-a215-6663a9e81671 |  | note | – – – – – – – – –
label | 67843b68-9ef5-5768-a5ab-8d2da4e6e4ec |  | note | HP
label | 90e9b5d4-51ae-56c3-9485-4683ec636172 |  | note | – – – – – – – – –
label | 795b5297-97a4-5a8a-a006-a6193971dc3a |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | 42a1c325-6795-5313-8f09-49e624b4d37c |  | note | – – – – – – – – –
text | a525c2ee-f234-5be9-9ef6-d61e29d5b64e |  | textbox | DATE:
holdpoint | 73f046a5-1844-407e-8c0f-030b9a01e5a0 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 30831df1-8289-4f84-b4c6-f0a4909677b0 |  | checkpoint | 1.4 Material Classification
label | 9199f492-9acc-5a8c-86a8-d78232650514 |  | note | FREQUENCY: Each Lot
label | d10269a1-336b-51e8-b4be-5ffa6b390b78 |  | note | – – – – – – – – –
label | 1aeb132a-e072-5ba1-8ce6-f4095b78653b |  | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes:
label | 8ce75c99-bdb6-5751-bf39-3299f9df5eaa |  | note | • 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | a2ca498d-bc71-5617-942d-04658b7aa737 |  | note | ○ Granular filter material for bedding and backfill:
label | c388ffde-4b43-59c2-8452-9fd71575aec1 |  | note | • Trench backfilled and bedded with specified material on drawings
label | 84b3de14-5c5a-5502-bdbb-dd22b017ac32 |  | note | ○ Geotextiles:
label | bca7363a-55a5-55d1-9790-c79be37989eb |  | note | • Shall comply with Cl 702.06.
label | ea1076c2-dd4b-5852-a81b-8b3f1543e257 |  | note | ○ Subsurface drain pits:
label | 19a6a9df-d091-5005-9bec-6878b5daf2ba |  | note | • All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ce9fca0d-043c-5c83-8f76-75bb5188fe4e |  | note | ○ Pit Lids:
label | a1759dc7-e555-5c8d-9ee9-e5c30333ff09 |  | note | • Type M3 circular lid (as per SD 1051) for Type S1 pit
label | dc4fba0e-52ae-593e-a9d0-8ec880f00c1f |  | note | ○ Flushout risers:
label | 28a64bcc-fa2d-5b92-996a-2f48149b35da |  | note | • constructed to the detail of SD 1631
label | 6335e7d5-33ca-5b51-b91f-7ae74d6edd44 |  | note | – – – – – – – – –
label | 7c0a4c40-d6e0-5b9a-b476-7271deb892a4 |  | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
label | 3309d69f-5602-5d9f-97c5-a70fb0f00448 |  | note | – – – – – – – – –
label | b464b532-a501-541e-8eb8-15887e5a7562 |  | note | INSPECTION/TEST METHOD: Verify
label | 29008222-172f-5d17-bad8-69b5a8eaf3fc |  | note | – – – – – – – – –
label | 6c1a00ce-42d7-5c9e-b964-4119cebd3561 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 4744d743-c017-505d-ab3c-ad9e2dea339d |  | note | – – – – – – – – –
label | 49d8626b-68ad-5d04-b84d-4000fbf9be01 |  | note | WP
label | 0a418518-6272-5cfd-ad68-4085f755c757 |  | note | – – – – – – – – –
label | 1c321bd3-ef09-5b06-953e-be628c84942c |  | note | RESPONSIBILITY: Site Engineer
label | 98ee20be-a405-51fd-9205-e09f89d04e17 |  | note | – – – – – – – – –
text | dc50a563-18d2-5f81-b7be-799fd7f39af1 |  | textbox | DATE:
checkpoint-group | ee42d9ce-33c2-4b07-887f-47da1cbd11ce |  | section | 2 - Construction Works
checkpoint-status | df20fb12-242e-42a8-8ff6-a67310df2eea |  | checkpoint | 2.1 Excavation Permit
label | d20dab5b-f5e2-54e4-a7d9-50cc3ce6e07c |  | note | FREQUENCY: Each lot
label | 2f1a4b81-3b7e-5d9c-96a3-5c787393bbf4 |  | note | – – – – – – – – –
label | dd0b0e06-4125-519e-a0a6-204338e92f24 |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | d25ebb9e-f2e2-5f31-8fd6-b1cca6584cd9 |  | note | • Plant and equipment shall be appropriate for the task.
label | bb990f25-a8a0-5713-b9f9-a5cdd299d4ba |  | note | • Excavation operations shall not disturb areas outside the limit of excavation
label | 0db491e0-3eb0-5836-86ab-5cb8507f10c9 |  | note | – – – – – – – – –
label | f1b0385c-7b9f-5d5e-8b6c-137b5975bab7 |  | note | REFERENCE DOCUMENTS: Excavation permit
label | dd521745-7eeb-5719-9be4-681488ff8f6a |  | note | – – – – – – – – –
label | 9beaa457-c42f-5e58-9a46-98a88295db0a |  | note | INSPECTION/TEST METHOD: Verify
label | 501d23b0-1289-5f56-b01b-a01e5d6764a7 |  | note | – – – – – – – – –
label | 87b051df-3ea0-5785-89ca-6ec78289f0c4 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 283ef53f-f6b9-5f44-9b6f-d68fed99d4e0 |  | note | – – – – – – – – –
label | 74ec60fd-fb90-5441-8cc1-467b4ce82666 |  | note | HP*
label | 8ae2d622-8d36-50f5-a1ea-6714633becf6 |  | note | – – – – – – – – –
label | e6634db0-475e-53b2-9b5c-a9ec4f8bd6da |  | note | RESPONSIBILITY: Site Engineer
label | 25db9026-617f-5066-8761-fc8a41ec4ab1 |  | note | – – – – – – – – –
text | e9cb386e-7cbd-5010-bf2e-bc50e47f851e |  | textbox | DATE:
checkpoint-status | f885c4db-e78e-4564-80cc-f82938ce6f11 |  | checkpoint | 2.2 Excavation of Trench
label | b3e558a0-0104-545a-a4fa-5b5fe2dfd90b |  | note | FREQUENCY: Each Lot
label | 857d4bae-bd80-5c0a-866e-f94f6e34a31f |  | note | – – – – – – – – –
label | b3d22ec7-f3e3-5c2c-a98d-86672b41173f |  | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert.
label | e58a9768-6f18-5b59-8fdf-d11b7cdf9f19 |  | note | • Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed.
label | 604439df-c907-53a2-a6b4-eabcdb39e6a8 |  | note | • To be inspected by Superintendent
label | 340c42ea-932d-50a1-9e05-c767e1440326 |  | note | – – – – – – – – –
label | e8152846-ca31-52d1-a152-c28ab396b0ce |  | note | REFERENCE DOCUMENTS: 702.08
label | 2288e16c-6069-5c63-9707-305102ebd532 |  | note | – – – – – – – – –
label | 8af79426-884c-58f3-a707-82c1268c721e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 179caef7-16dc-54b3-bcdc-fb6bec9cc104 |  | note | – – – – – – – – –
label | 18aa4477-16a4-5d86-b71b-60b24a6ec58b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 155610da-a14e-502e-8b0a-0b26af43c769 |  | note | – – – – – – – – –
label | 1993736f-f145-552c-a7dd-600c4f2a11bc |  | note | HP
label | f1d8ba55-e5ef-5b5e-8337-d12ff7318a25 |  | note | – – – – – – – – –
label | 74e366e6-660e-5b31-8a37-497946deb0e5 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | cb943bf2-12f5-551c-a629-408677b110e6 |  | note | – – – – – – – – –
text | 2b691a8d-c933-5be9-a809-ca9257d177a7 |  | textbox | DATE:
holdpoint | 16131469-875a-4200-af59-02eea1ee242e |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 32a5429e-5b07-4f8a-b7c5-f356304a5843 |  | checkpoint | 2.3 Placement of bedding
label | 3c1461f9-32ea-51e8-b5a8-b89c07b49662 |  | note | FREQUENCY: Each Lot
label | 9c58eaa9-55a6-5b9a-b6b5-43be6dc8c8d1 |  | note | – – – – – – – – –
label | 117d19dd-79a6-52f1-aa68-eaf27801db8c |  | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | 304745b0-5e8e-5b0c-9dd1-58df0a1e1042 |  | note | – – – – – – – – –
label | d9bb14ba-0fab-56ed-81ee-a5979ea68f2c |  | note | REFERENCE DOCUMENTS: 702.09 (c)
label | 98c707a9-948e-5f3b-a5d9-ea8db0238629 |  | note | – – – – – – – – –
label | 2546e7df-6da3-5c35-80b1-e9063991f069 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 22043134-0794-5527-af6e-b97b3203f335 |  | note | – – – – – – – – –
label | 50de7a7e-2a62-5db7-828d-98b3c32feb8c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | efd18ebc-5fb8-555c-a00c-9083b768fd6b |  | note | – – – – – – – – –
label | 99e648d6-6e15-5aaa-956f-59b76cdb5378 |  | note | IP
label | 2d10c35f-3a34-5b7c-9647-d50ed43353a9 |  | note | – – – – – – – – –
label | ac77c018-ff78-5903-a1df-99b6958ac0f8 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 40e16499-9c27-5fd8-81e3-43c516326c47 |  | note | – – – – – – – – –
text | 8b389ddd-f4ff-55df-81c6-f28b5c31cff4 |  | textbox | DATE:
checkpoint-status | 072c5b16-0a97-4c3d-8b8d-865837256783 |  | checkpoint | 2.4 Placing pipes and geofabric (if required)
label | 5bbeb04c-7ffe-5b4b-a648-4d188de33ef5 |  | note | FREQUENCY: Each Lot
label | 5da94d8c-cbdc-5f36-9759-ca327180e9de |  | note | – – – – – – – – –
label | 8d83ada1-2087-5bc9-a999-d453febbd9a6 |  | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | 42dd2f33-f2b3-5824-b867-f92196838a1a |  | note | • If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | 812c0e19-0480-5997-a3b8-8ca91ce2efae |  | note | – – – – – – – – –
label | 2ca5f623-674d-57d6-bfd7-c7459a1a5eb3 |  | note | REFERENCE DOCUMENTS: 702.09
label | 2c81e6c8-47ea-5c26-a1d3-2e6452eefae3 |  | note | – – – – – – – – –
label | 4191252a-82a7-55ba-9402-2033f247d367 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 096c3f57-93f8-50b2-afdd-909afc3a4723 |  | note | – – – – – – – – –
label | 1ec70074-203b-54ae-a3d2-b2ccda17382b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1bffcecd-6483-5cdd-aaad-ecbe3fefbe08 |  | note | – – – – – – – – –
label | 065a2ab0-7178-5fdb-bd6e-890aa166bd26 |  | note | WP
label | aef9d969-e66f-5d3a-bfd9-1fa3d3f50628 |  | note | – – – – – – – – –
label | a852fccf-c789-5ae1-b435-23992c378aeb |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 2eb9ce34-2bbf-55d4-96d4-809693ca0a8b |  | note | – – – – – – – – –
text | 582a81da-c002-5d1d-ba98-e0dd71b6dcbb |  | textbox | DATE:
checkpoint-status | 0bd1a307-6ab6-42f4-93c4-c66714de598e |  | checkpoint | 2.5 Placement of backfill
label | c1e50043-b12c-579e-bf83-a5723c687a96 |  | note | FREQUENCY: Each Lot
label | a8b8096d-6779-512c-8138-40d24bae0656 |  | note | – – – – – – – – –
label | 78ddb4e7-7c65-57da-ba33-3842f9c4266c |  | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes.
label | da923ce2-f5d2-5d9f-9862-b16351836807 |  | note | • Concrete is to be placed and compacted within one hour of mixing
label | cc3ad047-dc37-5329-8bea-c0fd4a7a6591 |  | note | – – – – – – – – –
label | 5c7a463a-5e70-5e21-a1f8-add3f18ff77d |  | note | REFERENCE DOCUMENTS: 702.09 (g)
label | ba22ce98-dd3a-571a-a7b1-a649de746b3d |  | note | – – – – – – – – –
label | 11accd78-a869-5c99-990d-5c4b2aae41a2 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 14d5c769-326a-5a2f-adac-9c6f3d8f19a2 |  | note | – – – – – – – – –
label | 624cb29f-5d9d-57e8-a64f-27813865e7b0 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 506eed55-1dc7-56e5-8d53-1e735fd5bfab |  | note | – – – – – – – – –
label | 21a52fb5-f34a-5f27-9ccf-be1527def868 |  | note | IP
label | 7dd2c495-a909-548b-9a49-957b0dc0f18b |  | note | – – – – – – – – –
label | cfac3392-6c5c-5570-b77f-0be98d41a895 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | aea8f946-d866-5b81-a6f7-f89eef64b58e |  | note | – – – – – – – – –
text | 25970e3b-6f8f-550e-9c46-7555e2dbb047 |  | textbox | DATE:
checkpoint-status | 57f20122-8937-4ac0-93fc-9b9040cad5e5 |  | checkpoint | 2.6 Install Pits and Flushouts
label | 352edeea-72d1-5ddd-b1a1-a8205b98ae66 |  | note | FREQUENCY: Each Lot
label | 03e2e9a6-0b98-52fb-9b4e-347c702665a3 |  | note | – – – – – – – – –
label | 92b4d5fe-f720-57e2-9199-6027fcae0e8a |  | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | 80c7fa07-cdda-5859-8481-e71b1490ee76 |  | note | – – – – – – – – –
label | cc41841c-b543-5f30-9ec7-1ec35527bdb0 |  | note | REFERENCE DOCUMENTS: 702.1
label | 5387772c-3677-588f-abd7-fc9956f3c86d |  | note | – – – – – – – – –
label | f136f998-c61e-5e51-9710-b3567f5b024f |  | note | INSPECTION/TEST METHOD: Verify
label | b7f606c0-a2dc-5016-b137-74ea43e3d9e4 |  | note | – – – – – – – – –
label | cd593395-ff5d-588a-bf76-97d2a27bd654 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | ab42215f-6b06-586d-83d5-edd723eafc25 |  | note | – – – – – – – – –
label | cd73e14d-7558-55bf-a9fe-fef38d69e9d8 |  | note | WP
label | 48d5d505-6b85-5399-a409-6648fc0c8776 |  | note | – – – – – – – – –
label | cddb36a3-3544-53e6-983f-d95fe6f20785 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 714d6cea-fd24-55ed-98b9-a5f6c2d02314 |  | note | – – – – – – – – –
text | 387782fa-a4d5-5b29-b2cc-9fb337465913 |  | textbox | DATE:
checkpoint-status | 0c1608f3-505a-41e0-aae3-7012b198be9e |  | checkpoint | 2.7 Flushing Test
label | 04769a3c-68ec-5f45-9f34-2f52331fd427 |  | note | FREQUENCY: At completion of stage
label | 10792bca-d11d-5a7c-8b88-a9c1089083a6 |  | note | – – – – – – – – –
label | 28ebc8b5-1279-5b47-ad9c-293ac6ed8096 |  | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | b9741883-20e1-5f9c-ae12-cde4091cf703 |  | note | – – – – – – – – –
label | cefe31f8-c900-5d09-8289-deb53ba2a9b3 |  | note | REFERENCE DOCUMENTS: 702.09(i), 702.09(h)
label | c610f2f5-279c-5f0b-b24a-9bd4c3b81caa |  | note | – – – – – – – – –
label | 9562b066-9d20-515c-be52-3da1b292b6ea |  | note | INSPECTION/TEST METHOD: Site inspection
label | 33729ca8-2416-5c39-903a-90af68d9c357 |  | note | – – – – – – – – –
label | 6b783d32-0a86-54d9-987c-e4880738ae7f |  | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | 640db40a-2944-5870-a8ea-df88e5c18ab4 |  | note | – – – – – – – – –
label | acff837c-579f-5f8d-8767-9e81fe91b5bc |  | note | WP
label | 22b57d3c-a0e5-5cf0-aa5b-a19354cb4f7e |  | note | – – – – – – – – –
label | 7f96e6a6-6565-5b38-9d57-7e1a15ccf404 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
label | ad910ba9-4fa6-5bd7-be9a-429ff6dac53b |  | note | – – – – – – – – –
text | 54c68165-251f-5b5e-8238-abdadb04aec1 |  | textbox | DATE:
checkpoint-status | d9769b10-169c-4d37-a235-805ed02a46e6 |  | checkpoint | 2.8 CCTV
label | 9e69de3a-43db-5bce-aa19-84ba133361f3 |  | note | FREQUENCY: At completion of stage
label | 7077780d-8e07-50c9-98af-c3b5af461c40 |  | note | – – – – – – – – –
label | 6fca9033-2890-5454-b736-6bd3fcbe3c80 |  | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
label | 997d8d3e-468c-55a5-bbea-babea31f14c9 |  | note | – – – – – – – – –
label | cf49a67d-bf02-5b26-aff0-45f0f9a250ab |  | note | REFERENCE DOCUMENTS: 702.09(i)
label | 656c4a9e-b60f-5b77-a005-feb85c93638c |  | note | – – – – – – – – –
label | 7a288178-8dcb-59f7-a111-b92f61046bb0 |  | note | INSPECTION/TEST METHOD: Site inspection
label | 8166e803-f4c1-5346-8e7f-5854606caee3 |  | note | – – – – – – – – –
label | efbb5b0b-7a1b-5756-8f06-28c125e5abef |  | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | 3971a81f-045b-5ce2-bab1-fe49400ea05c |  | note | – – – – – – – – –
label | 2f6805a5-a4e4-5ee0-8d74-21bb28c243c0 |  | note | HP
label | 74db2ce3-6b39-5400-8007-5533fe801d7a |  | note | – – – – – – – – –
label | f1288389-44f5-5d1c-b8c6-640d333982e9 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
label | 288b9b39-36de-53df-b27f-08e9c236ec99 |  | note | – – – – – – – – –
text | f7fad7e6-9ee7-5e98-9835-d303c6222f54 |  | textbox | DATE:
holdpoint | 0dfc3d1a-be9d-476e-8506-e3be7cdfaad7 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 12120c89-2cba-4bde-97b4-04cbb1f5d554 |  | checkpoint | Final Inspection
label | 20a922e1-3165-5590-8c69-9279ba74e8d7 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 7bdc869b-dab4-5399-8d87-209aacf1777e |  | textbox | Print Name:
text | 533c9815-486f-5a64-8f4a-c4873841e47e |  | textbox | Position:
text | a886b4b2-1158-5a81-ba34-aaeeaa7a0e84 |  | textbox | Date:
checklist-sectioned | 5602779b-0511-465c-93a1-d01ac8cae3a0 |  | checklist | FHC-ITP-001 - Clearing & Grubbing Rev1 | itp |  |  |  | Yes | FHC-ITP-001 - Clearing & Grubbing Rev1 | b4c10e08-0957-48ab-b550-649e50b6f452
checkpoint-group | 5056e0ef-7061-42ad-8bf0-973f310f7146 |  | section | 1 - Preliminary Works
checkpoint-status | e0d7666c-e451-4d5b-8f6b-7ee897a228d6 |  | checkpoint | 1.1 Check for correct documentation
label | 85790e24-e5f5-591f-b3a3-3f5e86f337bf |  | note | FREQUENCY: Prior to commencing any activity
label | 6237e5a7-ad59-5eaa-ab85-c3260b2dc761 |  | note | – – – – – – – – –
label | abebb59d-b410-5d90-94ef-37586b937b96 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 86444a8f-8739-512a-8dad-ab52b734b9fa |  | note | – using the correct and complete set of drawings
label | a63d38e8-baeb-5ce0-9973-3d5635cb06bd |  | note | – all drawings are the latest revision
label | 52249fc6-5811-58da-87a7-8c02d92be099 |  | note | – – – – – – – – –
label | ccfdb724-6465-5242-a029-a4c507df34db |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | f150e617-4d82-57e2-835f-be5b013a3320 |  | note | – – – – – – – – –
label | 26e34435-0075-5ce2-b013-c7726e283c42 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | fa249159-2648-5af9-bf05-aed619d60b61 |  | note | – – – – – – – – –
label | 61f7bc0b-8ebb-5ad4-a5db-8d68182659f3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5490a368-000a-51b8-8279-843701f0c71e |  | note | – – – – – – – – –
label | a5c1ad82-aad7-5479-b301-df256929c818 |  | note | HP*
label | a7acbb5f-493c-5717-ac16-7523579e095d |  | note | – – – – – – – – –
label | 577e7277-ed6a-5672-8c69-68b23b8fa016 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 9917db73-a554-5b63-aa11-382746f99e04 |  | note | – – – – – – – – –
text | b7e761f5-a1fd-51c0-8471-0ffff56e7f90 |  | textbox | DATE:
checkpoint-status | 927f1bc9-a3f6-41d4-b623-d4e814c8785e |  | checkpoint | 1.2 Implementation of all measures and controls
label | 44d15383-15a6-57ae-ad5d-374e5fdb7bae |  | note | FREQUENCY: Prior to commencing any activity
label | 435e5912-d4b4-52a8-b314-4b1ef1b19a2e |  | note | – – – – – – – – –
label | b92bc0a6-9993-5135-8d1c-b71e661dc224 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 8f1bf357-c2b1-5e08-8b59-9cefb5bc2469 |  | note | – – – – – – – – –
label | 08eb87f1-b3fd-500d-8d7a-b651ae30dff0 |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | e259b134-da3a-5105-95d5-4880d19957ab |  | note | – – – – – – – – –
label | fc8810e8-537f-56a4-b3e6-db1ac69d85db |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 764730c3-c3b6-55ea-8bf6-86a2a5fa672d |  | note | – – – – – – – – –
label | dbd0cbe9-2625-57c5-9189-ab272076e778 |  | note | RECORD OF CONFORMITY: This ITP signed
label | d8f13ad2-7e54-592e-8661-3df9c2b519f1 |  | note | – – – – – – – – –
label | 001a64b6-a1d8-5779-b03f-23c4a6aa5e51 |  | note | HP*
label | 1c9ce619-25e3-5bda-9fa9-4aad509f6281 |  | note | – – – – – – – – –
label | 2cb675ce-dcd1-58e3-977b-8778e7a1eed8 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 31b69d4a-6ecf-5fab-b75b-8c789af30a36 |  | note | – – – – – – – – –
text | f30115ea-0347-563d-b240-b9d14c351b1b |  | textbox | DATE:
checkpoint-status | 12000731-0940-4642-a714-09a90a46c876 |  | checkpoint | 1.3 Flora & Fauna
label | 751a4507-09a8-5d6f-b469-668ab7ecf5cc |  | note | FREQUENCY: Prior to commencing clearing
label | 01d1e9ac-3a4b-5c92-80dd-22088218a16d |  | note | – – – – – – – – –
label | bf11dd2c-30ad-533e-8294-6bb0eaea5f0f |  | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
label | 0a95ae53-8388-56f3-a690-9debc7401015 |  | note | – – – – – – – – –
label | 338b8cc5-7971-551c-b806-36d0b1ed7d71 |  | note | REFERENCE DOCUMENTS: EMP, ECP
label | 7de4000d-3c8e-58ab-8ce4-b724b9ebf686 |  | note | – – – – – – – – –
label | 3e9de13a-258a-55b5-88e6-312895651758 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b3fb69a3-a124-5e56-8cfe-b7ba72862920 |  | note | – – – – – – – – –
label | 0bbac84f-8def-50d8-980e-daddb542569f |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 63d4cc05-58fb-5bcc-abc5-360756fb166e |  | note | – – – – – – – – –
label | 4e0d30dd-641e-5e5f-b1fa-20163ac09663 |  | note | IP
label | fc1cdf62-09f5-5057-8485-68c69be0c545 |  | note | – – – – – – – – –
label | 6d7d6c1a-7cce-5a60-bbbf-d912b09d2f70 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 1e4a3e19-728a-5fed-8366-aea7a007f8ea |  | note | – – – – – – – – –
text | a7486b63-c5fa-578e-8c60-f366b3460bc0 |  | textbox | DATE:
checkpoint-status | 93fb3c2f-ce4a-477f-b513-f3e5bef63ed1 |  | checkpoint | 1.4 Permit to distrurb flora & fauna
label | 25e72b6e-b3a2-5879-ba45-27f0f635841a |  | note | FREQUENCY: Prior to commencing clearing
label | d8b26a07-13d6-5f5d-82a9-b2bfdff50a41 |  | note | – – – – – – – – –
label | 8eefd7b8-e81a-528f-8a4d-4467f8b0a6c4 |  | note | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | e612aaa3-b64d-5ece-8b8b-a6bbbb62e47d |  | note | – – – – – – – – –
label | f1d6ecbf-4f99-517e-836d-e69d721b286d |  | note | REFERENCE DOCUMENTS: EMP, ECP
label | 7550b470-c3d0-5f0f-a87f-7ed91b2e96a0 |  | note | – – – – – – – – –
label | 281ea013-b6b0-5458-bff7-27b691b1fa83 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 271a2bd9-c3c2-5642-8244-7cd1b65b1a5a |  | note | – – – – – – – – –
label | cc7789a3-e786-5635-bcca-225cb9caa916 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9e525d43-8aa1-572d-bed5-de8b8cc29fc8 |  | note | – – – – – – – – –
label | 3341d8c9-dc01-56f2-9e06-5328d9d1b705 |  | note | IP
label | 2cd9525d-4ca1-5aeb-b5d9-96cebdee56cf |  | note | – – – – – – – – –
label | b1baabaa-5a6e-52a6-bb1e-f81d2df948f0 |  | note | RESPONSIBILITY: Project Engineer
label | b850d379-72d3-5720-99c6-05963751f118 |  | note | – – – – – – – – –
text | 6c656bb8-3e10-511d-8364-1f225979167f |  | textbox | DATE:
checkpoint-group | 9b4e55e8-9db6-4a30-acb2-acec7ee03724 |  | section | 2 - Clear & Grub
checkpoint-status | 11f21b79-5d9d-4434-962c-46b01c3226f8 |  | checkpoint | 2.1 Define work area
label | 9ed3ed3b-8a65-5bbb-ae5f-aa70529b956a |  | note | FREQUENCY: Prior to commencing clearing
label | e1a00a1a-3171-5904-b674-5c131f9c3793 |  | note | – – – – – – – – –
label | c881ea3c-6edf-52ec-8345-95f029a9d897 |  | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | 1601715c-b3d2-544e-ae13-21894dee7771 |  | note | – – – – – – – – –
label | e1cfe4c3-c44e-5e80-a9a1-49cdba9aebf8 |  | note | REFERENCE DOCUMENTS: 201.03
label | 5a4795cf-856f-5f46-b86b-5e30e59052c5 |  | note | – – – – – – – – –
label | 80cad0b8-8db8-52f2-9a49-2e32530ef343 |  | note | INSPECTION/TEST METHOD: Inspect
label | d756d229-797c-54b2-b17c-09a1564d334c |  | note | – – – – – – – – –
label | 0bdbc982-d1fd-5669-b32f-cd4569f2bc3c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 185efeb4-ba5b-54c9-8650-b8b65baa94bd |  | note | – – – – – – – – –
label | 460e19a1-4c4b-5fb7-9f1c-92058cd06a6b |  | note | WP
label | 054ceee9-967f-57cd-a00e-20700bed7fc1 |  | note | – – – – – – – – –
label | be7fa55c-d394-5157-9684-f12028878cb9 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
label | f6ce5360-185f-5614-8126-823f1dd8ff60 |  | note | – – – – – – – – –
text | 35e7d0ce-ec1b-55f9-b959-5d7be48da89f |  | textbox | DATE:
checkpoint-status | b255148f-c197-40f0-ac0d-f958d9fc8e66 |  | checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
label | 0d943b94-53b0-5cd5-a968-57ad8528adc7 |  | note | FREQUENCY: Prior to commencing clearing
label | 6152291b-d316-526b-a351-b1eaeca877df |  | note | – – – – – – – – –
label | c3955192-f2df-5a1c-b5bc-31243fd9aec8 |  | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
label | a6f26ba7-ae10-544a-9039-82339ed39fc2 |  | note | – – – – – – – – –
label | 65b602fc-70bc-5e1c-ba6d-0fa35431b07e |  | note | REFERENCE DOCUMENTS: Drawings 201.10
label | ca4f7b91-f662-5551-81a0-dcb92efa8aa2 |  | note | – – – – – – – – –
label | a7f5eeab-debb-5a0b-8cad-843b20915375 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7bc754ef-fa51-5b03-a343-6d7da2552baa |  | note | – – – – – – – – –
label | 9fbc7c4c-b6ac-5676-aade-464608621e20 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 86435fbc-6849-5550-93d7-b4bd5e7d3cd3 |  | note | – – – – – – – – –
label | 4516dc5d-936e-5116-acd2-c54f5add8543 |  | note | HP
label | 2d94bb62-6865-5184-8343-af99bf05b89e |  | note | – – – – – – – – –
label | 347c7647-c27f-563d-a9f2-aadf2a0707d7 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
label | 3ad58c1c-0b7d-5c93-85a2-01f95575d999 |  | note | – – – – – – – – –
text | 19d36c41-4d69-5d77-b8eb-f75dda87d9a5 |  | textbox | DATE:
holdpoint | 26010539-0e24-45fb-b50e-afd2086ccf98 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | bad90f2d-cfdb-468b-a5c7-e0f34b7c28d9 |  | checkpoint | 2.3 Identify No-go Zones
label | 143ea1b6-7ee6-509c-a798-6d4475e1df91 |  | note | FREQUENCY: Prior to commencing clearing
label | 89000ed6-b0c4-598a-beac-5d4aa203ffc8 |  | note | – – – – – – – – –
label | 22d3b077-9da1-5a57-95a6-8ff8d1b1f9f2 |  | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
label | 1853b644-9cf8-5dec-a1f7-86d6f1e1c821 |  | note | • Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
label | 7e2da812-d0a7-5f52-a9a5-e1b512a6d882 |  | note | • Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP.
label | aa19df41-efd1-5abf-9a48-3324359e0a73 |  | note | • Any works required inside TPZ shall be completed under the supervision of an Arborist
label | 1e47b39e-65aa-5a0b-b287-1c393cd9c578 |  | note | – – – – – – – – –
label | 43d1f34a-5e07-524a-b895-df0558da9c04 |  | note | REFERENCE DOCUMENTS: Drawings 201.10
label | aeeb6fa4-a44c-5d9f-9ecd-62e844947a63 |  | note | – – – – – – – – –
label | af82a7b8-f34e-58ee-b236-2097261b0f33 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3031c5e8-137a-5ba5-8eb6-88ad658c3f92 |  | note | – – – – – – – – –
label | 38ace839-c42c-5ef0-9ec7-9a3221f64a02 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | d6af50ae-0c83-5e1c-9d5c-430fbd1b8f90 |  | note | – – – – – – – – –
label | 0bef3e61-ab7b-55d5-8655-732d3f439910 |  | note | HP
label | 6091a22f-3380-5ba2-9132-f72a506d832c |  | note | – – – – – – – – –
label | 90d97e82-6575-52e0-ad8f-6fdfdd704a64 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
label | 42d23c91-3002-5711-9f07-311b20b13ef8 |  | note | – – – – – – – – –
text | 58a55d3c-2122-5a84-9486-df7596abcbf9 |  | textbox | DATE:
holdpoint | 876fcf1b-b5a4-48aa-811d-d0ee41246053 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 2e95ab62-f165-46ff-9cc4-6aee6ced7d80 |  | checkpoint | 2.4 Clear felling distances of trees are adequate.
label | 2cca8de8-2709-5bcd-addf-0208f8e86dd7 |  | note | FREQUENCY: Prior to commencing clearing
label | 75a0424c-c3b5-5a1b-a23f-ac22bfc67938 |  | note | – – – – – – – – –
label | 0139f76a-6950-531c-b093-7c6885b60ae6 |  | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
label | 4f6c28a5-45ad-52f5-99fa-325fef38a6d6 |  | note | – – – – – – – – –
label | 1fd1282c-47e7-50f3-b57f-9ac451ee8f95 |  | note | REFERENCE DOCUMENTS: 201.04
label | 61aef769-0bd5-5cad-ab1f-39e0ff0457f6 |  | note | – – – – – – – – –
label | 6b60750a-90f4-5f09-baae-53d78ae02995 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 25cd2178-11d9-5250-8598-a8cc9ea15a32 |  | note | – – – – – – – – –
label | 89f9438a-2518-543a-9c74-e9187d8216d8 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 45b43b96-8b44-55f2-a33e-cadb0cf092d0 |  | note | – – – – – – – – –
label | 6a942206-e8ec-5c0a-90e4-0257599229d0 |  | note | IP
label | 529de333-2b96-5340-9c7d-eebc4e3179dd |  | note | – – – – – – – – –
label | b9341aab-1618-5eb2-b9e4-ef8a524ff653 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | c5774739-e2ca-57f4-87d1-88948a88f1e6 |  | note | – – – – – – – – –
text | 5a702f82-1d4b-5bd5-94dd-a64ab31784db |  | textbox | DATE:
checkpoint-status | 77502b3e-ffe9-4362-b68e-5d0a91c77b44 |  | checkpoint | 2.5 Clear and grub trees and vegetation
label | 336ab5ff-475a-5629-9a25-ef0e19adfdf2 |  | note | FREQUENCY: After clearing
label | 83cc3712-e8d2-56fd-9c04-440ba12d2507 |  | note | – – – – – – – – –
label | c4fdea82-cff4-5c94-b934-87fbe65a2b46 |  | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
label | 8a681883-37c0-5068-bfc8-e468f837585e |  | note | • Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
label | c2ad1d6d-9b31-5c74-9765-3ff35697ac5b |  | note | – – – – – – – – –
label | 3f281082-2131-50b3-8302-22d174ea807c |  | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
label | 8af60a35-c258-57d7-b5bb-b1362d9199c9 |  | note | – – – – – – – – –
label | eb68580e-2a94-5746-a8d4-a17b7fbe7f9e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9c9481cc-3c5e-5651-a2d4-bbdf4287ab2f |  | note | – – – – – – – – –
label | f602f990-08d3-53d1-aca7-8f8289e17c0d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9aab7197-ee1b-5a37-a97b-8262077191c7 |  | note | – – – – – – – – –
label | b3db9ffa-1ac5-5cf9-a3be-67c07ba9e75e |  | note | IP
label | db14b33f-4608-5538-932a-500b1761883f |  | note | – – – – – – – – –
label | 4adc3f6f-8765-5ee0-93bc-f383b88277d0 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | cb900f33-60d7-57b1-a4cd-84711fd04a60 |  | note | – – – – – – – – –
text | 0556e71e-c703-5814-8991-ae9435b80e8a |  | textbox | DATE:
checkpoint-status | 7518fa77-d771-4fb4-a887-26df387bb2a7 |  | checkpoint | 2.6 Backfill holes
label | de2e72ba-f0cf-52bc-a382-cb0f68144041 |  | note | FREQUENCY: After clearing
label | a18dd509-3df2-5f74-bf34-54b9b2cdba8f |  | note | – – – – – – – – –
label | c7293d85-593f-5eee-accb-2a039cac0422 |  | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
label | 19e5e9f5-a936-5150-9d04-8d611ecbd106 |  | note | – – – – – – – – –
label | 97bf45b1-a2dd-51aa-985e-83050ef6f55e |  | note | REFERENCE DOCUMENTS: 201.05
label | 39b45a35-f8a0-5108-83e3-3b7589414de5 |  | note | – – – – – – – – –
label | 9a6f1b90-06cb-57ad-b67f-d5b38d540459 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2f703398-80a9-5c43-9291-86e0fde779db |  | note | – – – – – – – – –
label | 0eca8b64-d84f-5619-a564-59caa62cc17c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 86998011-a3a6-5679-852b-ca4f30550cbf |  | note | – – – – – – – – –
label | cb82b229-8236-51e9-b2aa-2dba61623116 |  | note | IP
label | ba6592ab-816d-57dc-bf04-8a17c84081be |  | note | – – – – – – – – –
label | c58f7cf4-93b5-580e-b752-4e78789bffc6 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | e4845189-2256-5587-9029-c6ebb6d9330b |  | note | – – – – – – – – –
text | 7da7683b-e0ec-5cb4-aa79-edad0a100fa6 |  | textbox | DATE:
checkpoint-status | c9a31d02-29a4-4ff1-b997-be292c2c13f8 |  | checkpoint | 2.7 Dispose of Trees and vegetation
label | 6cfbade4-4f60-5d34-84e9-9faff42244e4 |  | note | FREQUENCY: After clearing
label | 618a3da8-65ea-5048-a79d-43d7b65c7bc6 |  | note | – – – – – – – – –
label | 21fc9df9-fd3f-5c60-8b39-3368e5947003 |  | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
label | bc629063-4cdd-568e-a102-d7f6d1cf7fe4 |  | note | • Noxious weeds shall not be mulched.
label | ec790847-bb29-508c-ac85-ce8491ebc79f |  | note | – – – – – – – – –
label | 6506ff5c-6d13-5d94-8bcb-a637506c1262 |  | note | REFERENCE DOCUMENTS: 201.07
label | 171180cd-92a1-5807-85d3-ee1e05525951 |  | note | – – – – – – – – –
label | 1e57c38d-f6e6-5826-b990-fc6431f27fc1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | eed09962-0bab-50b9-b240-9214aecc755a |  | note | – – – – – – – – –
label | e5a56c3f-7cd9-5159-a994-7b2692a831af |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | da79d145-ddbe-59ac-a314-1d1fdc9ec87b |  | note | – – – – – – – – –
label | 4924d4d0-4411-58ee-89ec-2cbae9254a03 |  | note | IP
label | 8aa8be68-8ce1-52d0-a549-5b0c39fd286f |  | note | – – – – – – – – –
label | eae6f1bb-907a-539a-b08f-f1645b895650 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 27045c5b-5ec5-5415-86c8-120bc413ceaa |  | note | – – – – – – – – –
text | 41a58957-2fb5-5aab-b6d3-0818821dec4f |  | textbox | DATE:
checkpoint-status | c593b093-df4c-4bae-8d70-a440dedcf9dd |  | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
label | f2e1bc67-dd0f-5006-9edc-716e3bb862ba |  | note | FREQUENCY: After clearing
label | abe6ecc4-401f-5397-b41f-fdbd387f6763 |  | note | – – – – – – – – –
label | 065f4676-5fba-5b90-bc34-83da07ead8ca |  | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
label | 212f83b7-8fdd-57d2-be8f-56a723a1f47b |  | note | – – – – – – – – –
label | fad89740-36bd-596c-969f-2414a83a3741 |  | note | REFERENCE DOCUMENTS: 201.07
label | 895393ff-4dd7-5437-89a7-96b83dd81114 |  | note | – – – – – – – – –
label | 9e8f2b02-f9d6-58ea-ace9-af459c339595 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9b9440e3-d4bc-57e2-8e6d-74b1b6d9ab14 |  | note | – – – – – – – – –
label | 43446636-86a3-543e-9a91-c7c702ea41c6 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 048b9b23-debf-5a68-bddd-ca71fd02e2eb |  | note | – – – – – – – – –
label | 0e54203a-65b1-51c1-b029-d6caf85d6174 |  | note | IP
label | cdc3665a-f8cf-5ddf-a8c1-3d5068a4605a |  | note | – – – – – – – – –
label | d086f342-659c-56a6-95d6-bcc219e13c86 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | c2011e36-927e-5e63-a7e4-19be5f141815 |  | note | – – – – – – – – –
text | 613e1b20-d5c2-5851-a1fa-348ce5538c18 |  | textbox | DATE:
checkpoint-status | 7225dbae-6537-4eb3-95ca-e0723a277510 |  | checkpoint | Final Inspection
label | a60cb05c-cae3-5325-a94c-c4cbf755ddd4 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | fa47f71b-eb28-5f2d-8193-f13984ae029d |  | textbox | Print Name:
text | b1a1fce5-a4b3-50e5-9742-01cf394174e5 |  | textbox | Position:
text | b3f8d783-9a63-5356-8747-94d6fd38b7e0 |  | textbox | Date:
checklist-sectioned | 12bb117c-72fe-4212-beda-85992950b217 |  | checklist | FHC-ITP-016 - Sign Installation Rev1 | itp |  |  |  | Yes | FHC-ITP-016 - Sign Installation Rev1 | bdac733d-291f-4c4a-8865-e0725baf7a0f
checkpoint-group | 58c2bac5-35f8-48d4-8b7c-7c3b826a1b38 |  | section | 1 - Preliminary Works
checkpoint-status | 9b056ddb-5f3b-42bb-b393-c74f9069bf94 |  | checkpoint | 1.1 Check for correct documentation
label | 9c27dd7e-4ded-5f17-bf87-ae90e60f4880 |  | note | FREQUENCY: Prior to commencing any activity
label | 9fbd2f2f-3650-560f-a1c4-06be54c06a31 |  | note | – – – – – – – – –
label | e72ffc19-f882-5952-abc5-8b7a410f116e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 150d2898-8a83-53d9-bbf5-bf6eb3bfe36b |  | note | – using the correct and complete set of drawings
label | 13b6bda2-98f1-5e3d-95ed-acfd212d9ecc |  | note | – all drawings are the latest revision
label | c24d5855-e8c7-569a-a70f-12679e13e802 |  | note | – – – – – – – – –
label | d14510a6-8577-5e5f-979d-a0128f4adcf5 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 534d907c-43be-5d4d-8da0-979c486a9292 |  | note | – – – – – – – – –
label | 25cf48fc-9cfd-5af7-994f-66d1e791136a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 70b3d830-9c8a-5bfe-825e-a77987580d01 |  | note | – – – – – – – – –
label | 2b33a405-4a41-52a1-abf6-5689b8d71f0f |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8605f5c4-3f9a-5654-b146-c258a154594f |  | note | – – – – – – – – –
label | b1e82581-a413-5436-8029-320347da5b43 |  | note | WP
label | f2206e0d-494f-5a91-8524-22c339755cdb |  | note | – – – – – – – – –
label | a3628e7e-d2aa-5080-9f24-dd2c260186bc |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 2c4b30b3-9169-58d4-a9ae-6243f5a47caf |  | note | – – – – – – – – –
text | 7a14ef17-de65-5fa8-b546-8281fdb5ea82 |  | textbox | DATE:
checkpoint-status | 8590cef8-3016-43c4-9d26-1192f769e2f2 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 7c0dd943-ee99-5bfb-8197-f0f5afbf273a |  | note | FREQUENCY: Prior to commencing any activity
label | 183ef929-e143-54c3-b36f-40f7fcaca001 |  | note | – – – – – – – – –
label | de652e4b-c1ef-58e5-9462-7ccab9b94845 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 86f2706d-7060-528e-a013-36613bf7ddc3 |  | note | – – – – – – – – –
label | 2f2a0a7d-5a43-5530-8d0d-7b799cccfd73 |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 2c7b3892-939a-5522-baf1-b29ae64e9711 |  | note | – – – – – – – – –
label | 08ccc976-35c0-53c3-ac29-2bf8456d7301 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | eba9efd0-db31-53c5-8657-0f92603f190f |  | note | – – – – – – – – –
label | da14850f-6124-5a8a-9f49-05e4802082e2 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1f075c7a-753e-5fb1-b0e4-9118058bd1eb |  | note | – – – – – – – – –
label | a4358156-ace3-5ebf-b338-42034b34c000 |  | note | WP
label | be2035fe-2241-5b3c-963b-55f9f5bbb0ea |  | note | – – – – – – – – –
label | 2b605143-3bd7-5274-bbd8-7f9f291d29cc |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | b240ba06-99e7-5d40-bf3c-45d5e8ddc073 |  | note | – – – – – – – – –
text | ddc7aa42-d224-5a2c-a6ef-9a136bc7b90d |  | textbox | DATE:
checkpoint-status | 0e6b9a99-cf8a-480c-a85c-623796e63f97 |  | checkpoint | 1.3 Signage Conformance
label | 35798345-0be4-507f-b0db-488204a2c243 |  | note | FREQUENCY: Before commencement of activity
label | 754b5c5a-bcab-5c6f-8dad-1626e5f6d2bb |  | note | – – – – – – – – –
label | 59275387-35e8-5cfe-bbae-1bbf927a94d2 |  | note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
label | a21688e9-a60f-5bac-861c-27f6d834c138 |  | note | – – – – – – – – –
label | 6a36ac2e-4511-5197-a875-3e39628d4504 |  | note | REFERENCE DOCUMENTS: Drawings AS 1742
label | 5890a6fd-3a78-5e36-a85a-702eab6da777 |  | note | – – – – – – – – –
label | b49d1f03-220b-5188-a1d5-f8f749c11748 |  | note | INSPECTION/TEST METHOD: Verify
label | 49522911-32c9-55f7-8cdc-d822b815367e |  | note | – – – – – – – – –
label | c1e04f61-a01e-5beb-b6bf-b8df3ec7b6c3 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e99a3ca6-8055-597c-a19d-1f9da112c666 |  | note | – – – – – – – – –
label | d50c28f3-73fa-53ea-984c-3e7b47b5507c |  | note | WP
label | ae16bfa5-7d6c-585b-8a31-2577444ebdce |  | note | – – – – – – – – –
label | db770921-7ef7-5047-99bd-638ae2e0e649 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 4e638eed-a712-59a1-b123-26608527568c |  | note | – – – – – – – – –
text | f4e102bd-acee-57c3-b9d8-2411c7563732 |  | textbox | DATE:
checkpoint-status | 874dc28a-60ef-4856-887a-aff91cbe4720 |  | checkpoint | 1.4 Service Identification
label | 43bd179d-c0b2-596f-b3db-fe79334c6c87 |  | note | FREQUENCY: Prior to start
label | bf7fe35c-dca9-5dd5-a195-bfb654f40e00 |  | note | – – – – – – – – –
label | e1cf3b4f-ce8f-5c67-9f91-f5727dbcfda7 |  | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | 051ab3d8-5926-5469-9201-3c3a1b79bb2d |  | note | – – – – – – – – –
label | 65df6554-bbd2-51ce-8c38-e5ef6574d28a |  | note | REFERENCE DOCUMENTS: DBYD, Service chart
label | f2f4c1f7-bce9-5df4-8e1d-9f2767cc3bf5 |  | note | – – – – – – – – –
label | b3f23486-3bfc-5b5e-a0f5-206110b8b45a |  | note | INSPECTION/TEST METHOD: Verify
label | 5df765ef-a3a7-5c48-aa0a-5ea761252bc8 |  | note | – – – – – – – – –
label | 50430cce-9781-5142-aaec-00131282f795 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1678b2ad-2416-5da0-b1a0-1f3825991da6 |  | note | – – – – – – – – –
label | 3eb7b383-23b1-5ff4-a98a-8e147cc45956 |  | note | WP
label | 6d74268c-6979-5448-9516-48cddf82ce9c |  | note | – – – – – – – – –
label | 61eb8828-e2e4-5f4f-9013-72297b281aa2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 8513533f-180a-5557-80ad-0a9e46cb1595 |  | note | – – – – – – – – –
text | 638c42da-cc91-547b-912f-d02d98f393cd |  | textbox | DATE:
checkpoint-group | 58cb6de6-05d4-4304-8141-9bd010acae72 |  | section | 2 - Construction Works
checkpoint-status | f0264b9b-f71a-4377-82f0-a1d65b46ced6 |  | checkpoint | 2.1 Setting Out
label | 27a70679-a823-5a19-aca5-a4164c93f885 |  | note | FREQUENCY: Prior to start
label | a9a6c93e-b10a-58dd-8c44-701fdf78d436 |  | note | – – – – – – – – –
label | ff6941ab-ced5-5541-bf83-c92ddbe50312 |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | dc2f5368-7940-5946-b732-bfef99208d60 |  | note | – – – – – – – – –
label | c2392769-da03-5e2c-a8f2-dfb97ea95d5e |  | note | REFERENCE DOCUMENTS: Drawings
label | 6863d742-2f23-568e-b19a-2c24a9490b08 |  | note | – – – – – – – – –
label | 2eae5966-91a6-55b9-9443-9548b58c4b03 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b1b7c114-fe56-532f-aed3-810e0e098407 |  | note | – – – – – – – – –
label | 98191a27-ff62-5198-a5ba-7b0f14baf09b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d06504f8-e24a-51f6-8713-10aa49eb482e |  | note | – – – – – – – – –
label | d78d6168-31e8-5dd9-958a-e0f37ce070fa |  | note | IP
label | 5b335cc3-cac9-57d8-aba2-46cdd3114dcc |  | note | – – – – – – – – –
label | f2415921-46a3-55cd-bd3d-2038f956f649 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 9ac927b6-8dbf-59a6-88b1-4dec91881806 |  | note | – – – – – – – – –
text | 99ea328e-2e9c-53a8-9747-f98fd8a6dbe1 |  | textbox | DATE:
checkpoint-status | 2299c011-7089-4547-b70f-c9c0df64dbe4 |  | checkpoint | 2.2 Post & Foundations
label | 9ebeca40-16b4-56bc-97e3-1aded9aaa985 |  | note | FREQUENCY: Prior to Start
label | 232bb0ba-d54b-56dd-99cd-6fee0587adac |  | note | – – – – – – – – –
label | 29129a5b-446d-5742-b911-c8f009805f6e |  | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | 032f2df3-38de-58d3-806a-b9968bbef758 |  | note | – – – – – – – – –
label | 2ecf07cf-123b-5d42-bb18-e32f3d3d1a07 |  | note | REFERENCE DOCUMENTS: 714.06
label | 71852fa9-c27c-5b2b-a68f-d434647a2d19 |  | note | – – – – – – – – –
label | ed81bc92-84ec-5fd9-a1d7-d4bea7f528b8 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 58b4ba42-8887-57e9-a32a-8493f4af8525 |  | note | – – – – – – – – –
label | 1d117c96-7774-5e9b-956d-0fc10c2cb2e1 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a2d9df63-8506-53bb-920f-560e833b3b29 |  | note | – – – – – – – – –
label | 953c32e7-44bf-5d37-82f6-e455f009f674 |  | note | HP
label | 7c06a83f-a867-5808-b558-d9c060272569 |  | note | – – – – – – – – –
label | 651e367a-ef4b-569d-8e56-142b01e9ff83 |  | note | RESPONSIBILITY: Superintendent
label | 71e78f97-b4f6-5f0e-a080-e4b8668f45ae |  | note | – – – – – – – – –
text | 438e443f-37d7-52d9-b2d2-2f8a9c9ae880 |  | textbox | DATE:
holdpoint | 1076672d-d849-4db0-9c46-2a6dfd824cd5 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 38c0ca2b-7dc1-48a7-b7d1-7d02fcf61c46 |  | checkpoint | 2.3 Signage Install
label | e456a3c8-1c94-51f1-ad04-42236ef7214b |  | note | FREQUENCY: Each Sign
label | 1b2bd97a-1d0d-57e9-b473-e4ceec7f3be8 |  | note | – – – – – – – – –
label | bfddd562-096d-54a1-86d0-b62c29ede6c7 |  | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
label | b9d7903c-e341-59b0-bdb0-42a9e4a2bafc |  | note | • Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
label | a17b4314-7982-55a9-bc18-1bb3e3293b4b |  | note | • Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | a60915b7-faa0-5a80-b1c0-6f1477a9163d |  | note | – – – – – – – – –
label | fe47f7f4-aba4-5523-b6c7-d44681abea34 |  | note | REFERENCE DOCUMENTS: AS 1742, TS 1313, Drawings
label | 3009958d-2dc9-5b38-9cb5-e34e52aacb13 |  | note | – – – – – – – – –
label | a841963c-763b-5320-8b0b-c7606f5746f7 |  | note | INSPECTION/TEST METHOD: Verify
label | 0f68af0a-b473-58cd-8c81-43c0fcbead0a |  | note | – – – – – – – – –
label | f7cc7dcd-ee0b-565f-a911-e164e96c7b7e |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 7920b2f6-d04a-5ab5-a571-afa8f240c222 |  | note | – – – – – – – – –
label | dd4bf362-a22b-5736-b14f-7a9b9fce96d6 |  | note | WP
label | a935395b-d980-5ce5-922f-9fbb969fecd4 |  | note | – – – – – – – – –
label | 686c1aa1-15d9-59e6-af1f-53501b100d29 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 26bf37c7-6ba3-506e-b521-6f0a03f2fbeb |  | note | – – – – – – – – –
text | b85cb1de-264a-53ca-811e-f877c3dba698 |  | textbox | DATE:
checkpoint-status | 6ea0bb5e-5a66-4c46-9e37-884e3da9be8a |  | checkpoint | Final Inspection
label | e67bf3b0-e137-573a-87aa-64d8106cef87 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 18a8517b-e24d-5b52-9697-19d3f83ab7e7 |  | textbox | Print Name:
text | 6a2d090e-f94e-5845-bc9e-92d960b2ee67 |  | textbox | Position:
text | f4fbdaf1-d319-58c3-8c7b-67322c13127b |  | textbox | Date:
checklist-sectioned | 8e099100-e0eb-4258-8bc7-f6d625bd8534 |  | checklist | FHC-ITP-008 - Stormwater Drainage Rev3 | itp |  |  |  | Yes | FHC-ITP-008 - Stormwater Drainage Rev3 | cec230a7-8453-4d98-bb64-6ef1767c0922
checkpoint-group | fa158688-5d9e-443c-84fc-f355e18c94a7 |  | section | 1 - Preliminary Works
checkpoint-status | 649f09f6-1f07-4a6d-981e-1c4511e74fc0 |  | checkpoint | 1.1 Check for correct documentation
label | d546597f-d884-5247-91f7-7fadd0991924 |  | note | FREQUENCY: Prior to commencing any activity
label | c1e7eacb-7f25-580e-a761-9f347ddee59d |  | note | – – – – – – – – –
label | 12286196-8f21-5353-aa4e-d8ead4dfae5d |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | a45291f7-c7cf-55f5-b5bd-15c0e8bcac59 |  | note | – using the correct and complete set of drawings
label | 2b7690da-1b58-52dc-bb35-b6bf25065a9c |  | note | – all drawings are the latest revision
label | 4abbfbfe-4261-5661-83cc-b22c6bb50938 |  | note | – – – – – – – – –
label | 87b8b8e1-0c21-5b79-aeab-d01ba0bb130d |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 226f4a7f-70ec-5895-864f-f35d8a2f7705 |  | note | – – – – – – – – –
label | 37e1c3ac-ac38-5c06-ade5-dfdc80c596aa |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 696d026d-2b2b-5e92-817a-ab5dc160ed65 |  | note | – – – – – – – – –
label | 5cad6e0f-71ae-5f56-8fe5-cf9ee6bb73fc |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1f7be475-922f-52fb-a0d5-66cb35b2674f |  | note | – – – – – – – – –
label | 470556db-cbe2-50bf-89b3-28ba318bc3e7 |  | note | HP*
label | 1729a02b-16b6-5cad-b180-7ddfc3244b1a |  | note | – – – – – – – – –
label | ffadf36f-0ac7-5355-9888-4bd870c4a257 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | c68eea3b-d1da-50fa-9488-6cfc0174d2e8 |  | note | – – – – – – – – –
text | 25defbc1-3612-5880-8a26-7ee35ac02412 |  | textbox | DATE:
checkpoint-status | 3e93a7ca-78a0-4db7-935c-513fc0c98024 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 7217330e-9596-5f49-84b2-ca8016a20635 |  | note | FREQUENCY: Prior to commencing any activity
label | 204b6863-cbae-5a83-b66a-e14890462f03 |  | note | – – – – – – – – –
label | 54d1ba27-6e6c-54c0-9499-3dce6f7e08f2 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 2f1831ee-28f2-5211-85e9-19c1291dad22 |  | note | – – – – – – – – –
label | d208f134-1bf0-50f6-bdc3-bdc81e70f482 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | bccde30f-bd44-5ca7-abdf-ec4a2b395629 |  | note | – – – – – – – – –
label | 0dbbbbaa-a743-5cf2-9c08-ccc229f8a87e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 94aa573e-4af5-5cc8-8eae-016b25360b98 |  | note | – – – – – – – – –
label | f8fdadce-b07a-5c91-824f-205a73bb2a47 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 90192782-6410-5fad-b8fb-5f0b3ccb1574 |  | note | – – – – – – – – –
label | f94cda4b-4cd2-5705-abe1-f905b204bb64 |  | note | HP*
label | ad52ab76-9f84-5a5f-a7da-dd034f671817 |  | note | – – – – – – – – –
label | 00d7677e-3551-5106-9638-0c6c4612f71e |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 38cb39e5-b574-5b66-972b-c1cbab346ba9 |  | note | – – – – – – – – –
text | 122bb4d5-81d3-55d1-9cc1-89b1cab2c293 |  | textbox | DATE:
checkpoint-status | 894baee8-255c-42e0-95ef-747201e47920 |  | checkpoint | 1.3 Precast Materials acceptance
label | b6aef6e7-97e4-5010-b30f-e2ee02e718c5 |  | note | FREQUENCY: Each Delivery
label | faea7071-52d4-5a08-914f-acc7ca4dc5ff |  | note | – – – – – – – – –
label | 6e536bde-fb88-5c10-82be-550d1dcd9d4d |  | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
label | 6112cccf-7b47-5039-b990-73ec08b92cab |  | note | – – – – – – – – –
label | 8234ae2c-a6d5-5d9c-888d-92d7077cab1e |  | note | REFERENCE DOCUMENTS: Cl. 701.05e
label | 18ee3a6a-4253-5d63-b483-d78db4b5c877 |  | note | – – – – – – – – –
label | 53793db0-7e96-56ca-ba2e-ed734daa93a3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ea54a42b-fbbe-5e50-b61a-2debcb6c8e18 |  | note | – – – – – – – – –
label | dcb886c3-bee9-54b4-b846-060554b18c96 |  | note | RECORD OF CONFORMITY: This ITP signed, Receival and Inspection Checklist
label | c83fcec9-472c-51fa-ac8b-7a42a0dd2eb5 |  | note | – – – – – – – – –
label | 9787c41b-f145-5e57-a59d-151ac5f3e3e4 |  | note | IP
label | 938318b0-710b-587d-b956-6c13fed048e2 |  | note | – – – – – – – – –
label | fdbf9824-90a1-5a6c-9452-c0cd32dc81e8 |  | note | RESPONSIBILITY: Site Engineer
label | 8e4d21cf-00f9-5fa1-b2a8-87bb2be927c7 |  | note | – – – – – – – – –
text | 71a79dfb-43e9-56ee-9b91-828b591d7d71 |  | textbox | DATE:
checkpoint-status | 040891eb-178a-4cdf-9c3e-5dd6028cdc83 |  | checkpoint | 1.4 Precast Pipe & Culvert Compliance
label | 40d59723-c135-5d29-a212-03b724b52fa3 |  | note | FREQUENCY: Prior to Commencing
label | 96d8d7b6-a93a-51a6-bc1d-75d6c6c85388 |  | note | – – – – – – – – –
label | c0f0f516-5ea3-5d22-8b66-33b709a2086b |  | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
label | 1d9ccf08-c938-5646-94b7-13a2ab3351d0 |  | note | Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
label | f068b1ff-0ae9-5574-bb3d-db6727c85f1a |  | note | – – – – – – – – –
label | 362ef407-d678-5bf3-aa29-ac0e4d278b90 |  | note | REFERENCE DOCUMENTS: VicRoads Spec.
label | 6c504ed3-f466-5ded-88d7-78b8d1063522 |  | note | • Cl.619
label | 25a8e3b7-5a00-55da-b94d-094acc3dd5ee |  | note | • Cl. 701.04
label | 6d461287-a6b7-56e6-be84-bbb4872cbd30 |  | note | • Cl. 701.05(a)
label | 35b175a6-613d-5f91-aed4-5bb3ae5b1e03 |  | note | • AS4058
label | a65bcbda-31b7-5ceb-ad8b-096cd66b9558 |  | note | • AS4680
label | d3e0f8c9-659f-5346-8368-714f3b0ef13c |  | note | – – – – – – – – –
label | 9021b46a-bad4-5998-be3b-0f53f67a7b58 |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 3d0e8d16-f9cb-5ab3-a23a-eb7ea5c40210 |  | note | – – – – – – – – –
label | 0baf92b1-7f9e-5e9d-ab92-d26254e17074 |  | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | 8a7587ba-c52d-5328-972d-9056c599db13 |  | note | – – – – – – – – –
label | 25049117-1521-577f-b920-3e96695a3a81 |  | note | IP
label | ee102d44-9db8-538e-a09d-4bdddc1c22a7 |  | note | – – – – – – – – –
label | 52683c5a-00b9-5be9-8ff6-4eaead697596 |  | note | RESPONSIBILITY: Site Engineer
label | ea1279b8-4762-5536-b07a-5a6ebce78795 |  | note | – – – – – – – – –
text | f3697572-0673-5dcc-aee4-2f97e58c0413 |  | textbox | DATE:
checkpoint-status | abd2a123-da44-43ab-b8e6-e67043b6a45c |  | checkpoint | 1.5 Precast Drainage Pit Compliance
label | a0c0643c-3c41-5708-98b9-64b75ad56dc4 |  | note | FREQUENCY: Prior to Commencing
label | 32863b6d-f9b4-5349-8273-1d3028b901bb |  | note | – – – – – – – – –
label | 9308fceb-d902-5a5b-a938-576dfe37e163 |  | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
label | 2f82eb1f-5f51-5e05-8baf-4211dbf0b64c |  | note | – – – – – – – – –
label | e343c594-7089-57cd-bfbe-13c575bfa4ab |  | note | REFERENCE DOCUMENTS: VicRoads Spec.
label | 05c1dc6c-a6bb-5c1b-968c-9ba3427c5560 |  | note | • Cl.610
label | 014bf931-f9ba-5e38-aa4d-c52b93fc0c8d |  | note | • Cl. 705.04
label | 63e2643c-d2d0-5fe7-bb55-a7d416708798 |  | note | • AS5100
label | 0afd2463-d611-556c-84bb-ff57cd441ef2 |  | note | – – – – – – – – –
label | e6dbf4bc-fc7d-578e-86f0-dfe9b041adb4 |  | note | INSPECTION/TEST METHOD: Document Review
label | 1de05e5e-25cf-51de-8793-8382a37f7f8c |  | note | – – – – – – – – –
label | a0823d3b-c53c-576a-837c-5d1daf440dce |  | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | 7a3da105-da77-5e6d-8679-dba33b8119ce |  | note | – – – – – – – – –
label | a3e42306-bf90-5dc0-aec3-24f61bafd9f9 |  | note | IP
label | 4f3a28c6-cf45-5413-9032-24d324269ab5 |  | note | – – – – – – – – –
label | 1090eb68-f0eb-5961-a51d-3dd2523c9ba2 |  | note | RESPONSIBILITY: Site Engineer
label | 0682814f-441c-5967-9e85-5835f7b4aed7 |  | note | – – – – – – – – –
text | f4333e1a-3404-57ca-8e92-e94a7ccce907 |  | textbox | DATE:
checkpoint-status | 8a2b864d-a222-4c2e-80da-c6671cc41e59 |  | checkpoint | 1.6 Bedding material classification
label | 8f6850df-a71f-576c-8dcb-6241ac0fffa5 |  | note | FREQUENCY: Prior to start
label | 4629e0e6-29b6-58ce-bd05-86fc5af15e4b |  | note | – – – – – – – – –
label | c1b6f326-c1e8-53af-a50f-0773142225a3 |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
label | 39a09ea2-f0c6-5310-b16f-613205452af7 |  | note | – – – – – – – – –
label | 552b3862-f97e-5c17-a88c-65b95dbacfcb |  | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
label | 68fe69a9-3fe2-5082-8a16-80f060af67a9 |  | note | – – – – – – – – –
label | 37b4f281-4457-5a89-b588-6d34a874a132 |  | note | INSPECTION/TEST METHOD: Verify
label | 958e7949-80a8-52e8-bc86-9008a3868f75 |  | note | – – – – – – – – –
label | 909fffd7-cd3c-5528-868c-287572e2d7b2 |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | 52464093-a8fa-5c5f-9795-8f5e58b619d4 |  | note | – – – – – – – – –
label | 594eff92-50b2-5d4b-9b81-66a83a65c421 |  | note | TP
label | a03c5b2b-4acc-5399-b36b-91cd72c500b3 |  | note | – – – – – – – – –
label | 623d6c8f-d6bc-5204-9178-7287daacb1a2 |  | note | RESPONSIBILITY: Site Engineer
label | 197752a0-f19e-5078-96ed-0fa05a7404c4 |  | note | – – – – – – – – –
text | fbae2111-03df-5359-bfe3-c6402d4bdf2b |  | textbox | DATE:
checkpoint-status | 5faae101-b345-476e-ba0d-18b5f08fd22c |  | checkpoint | 1.7 Backfill material Classification
label | 3c57001e-c29c-59e4-a3f7-09f785c5c0b6 |  | note | FREQUENCY: Prior to start
label | e442b6a5-f7c7-5bbc-81ca-ecea6a8a25aa |  | note | – – – – – – – – –
label | e4b7aa66-a380-51f8-9e1d-672ad06790b8 |  | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
label | ea579e98-4d44-5fed-b717-6f568e7bee11 |  | note | – – – – – – – – –
label | 44613d6d-f73f-5027-aa84-d7e1bd762141 |  | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
label | a1038be0-3eac-5d0a-974d-8fede996d89f |  | note | – – – – – – – – –
label | d0016803-1509-5953-8999-914535ab2ba2 |  | note | INSPECTION/TEST METHOD: Verify
label | 1e084a2b-72de-5cec-a72e-d129f11eb847 |  | note | – – – – – – – – –
label | b88450f4-94af-5043-aeff-f2877a25aa60 |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | 5ce666cf-4ae9-585a-90d8-1f56fe1e90aa |  | note | – – – – – – – – –
label | 73762daa-dd4a-5960-9702-857aaf6345db |  | note | TP
label | 5645d3f4-c424-5a9a-bf47-09893a6513dc |  | note | – – – – – – – – –
label | 4c380bd2-93c3-5f27-8f9a-73a49c5d4804 |  | note | RESPONSIBILITY: Site Engineer
label | 6d900140-3db5-54e4-8bc2-fc9ef2787899 |  | note | – – – – – – – – –
text | 402d8de8-5849-5175-a38d-9967f8181459 |  | textbox | DATE:
checkpoint-status | db4e6b80-fbc6-4d6f-9d86-b3b9b702a439 |  | checkpoint | 1.8 Mortar material classification
label | ede7d76f-6633-5246-a40a-d0984a2949ad |  | note | FREQUENCY: Prior to start
label | 5a78d693-ff80-56c7-a605-4afb3614d436 |  | note | – – – – – – – – –
label | a8ced59a-30ff-5631-b50f-2a776259f594 |  | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | df835a20-b1c4-5dbd-8d10-97399487cec5 |  | note | – – – – – – – – –
label | 7e1e7bd5-c734-51d4-a100-e463e593204a |  | note | REFERENCE DOCUMENTS: 610.33
label | ca6a0429-59d7-5aa2-a6d2-e55e13872953 |  | note | – – – – – – – – –
label | 86229764-41c1-584e-83da-261be639c5f3 |  | note | INSPECTION/TEST METHOD: Verify
label | f7eb6fe1-bf55-5caa-a0a5-8544c2319933 |  | note | – – – – – – – – –
label | eeafa4b1-10a1-5e46-8bc3-f57401be6ba3 |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | a11d4d65-83fa-54b9-8335-09eefb313d18 |  | note | – – – – – – – – –
label | a1028bbd-f524-58bd-a4c3-14aa6e846953 |  | note | TP
label | 4f9f5ba9-5846-5dcd-9b39-d59b9479bdad |  | note | – – – – – – – – –
label | 115e263c-f0d1-597b-8cdc-ca6be7ac763c |  | note | RESPONSIBILITY: Site Engineer
label | 67f5904a-d06f-5f5b-a16a-6f064071ad55 |  | note | – – – – – – – – –
text | ab9ae617-52d5-586c-8a55-bd2feec832c4 |  | textbox | DATE:
checkpoint-group | da6d4634-e9eb-48bc-ba82-397f3defad04 |  | section | 2 - Construction Works
checkpoint-status | 2ad644f1-0446-41a9-914d-523b4154d803 |  | checkpoint | 2.1 Excavation Permit
label | 0edc254f-1f5f-5ce7-a4f8-1a34d0530c4d |  | note | FREQUENCY: Each lot
label | ff33128d-750f-5d67-9e3a-308dc5535792 |  | note | – – – – – – – – –
label | b0ef937d-365e-5562-a5c7-f671c5ab8b95 |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | 5799d026-870b-5133-b16e-c94f4c83f66b |  | note | • Plant and equipment shall be appropriate for the task.
label | 8ee4e531-9428-5b97-b5fb-079969c53020 |  | note | • Excavation operations shall not disturb areas outside the limit of excavation
label | 2a3dca4c-417e-53b3-9a32-40e6c3906776 |  | note | – – – – – – – – –
label | 04d9cfdc-269a-59af-bfb7-1786da73e98d |  | note | REFERENCE DOCUMENTS: Excavation permit
label | 0143d891-c499-5f9b-b994-55719426f6d6 |  | note | – – – – – – – – –
label | 23beb5e0-1f18-5824-b3e0-520effc5b184 |  | note | INSPECTION/TEST METHOD: Verify
label | e41d3c5a-c71f-5cc3-a82e-42d289159770 |  | note | – – – – – – – – –
label | 950bca74-3ee8-5b41-af17-7e44f74c559b |  | note | RECORD OF CONFORMITY: ITP Signed
label | 38d63006-515b-5426-b097-bbd4b285d114 |  | note | – – – – – – – – –
label | afd06ad7-8029-5edb-a518-bb9e64350c14 |  | note | HP*
label | ec0de322-999f-5b54-af1f-399eb9252e14 |  | note | – – – – – – – – –
label | 45c5a4b4-aec1-5846-bd23-49d971020fa5 |  | note | RESPONSIBILITY: Site Engineer
label | a927522d-d3bc-5915-afc8-ff720ce62ec7 |  | note | – – – – – – – – –
text | 29c65067-2345-55c3-ab5f-f1d7031703fe |  | textbox | DATE:
checkpoint-status | 079407a4-15cf-4cd4-b273-24ac1dfd0ca7 |  | checkpoint | 2.2 Set out drainage
label | e6791434-e979-5e04-b031-9ba0c2310c0f |  | note | FREQUENCY: Prior to backfilling
label | 7af16554-8466-58fd-9a9f-bbeecd9b594b |  | note | – – – – – – – – –
label | 1242812b-a705-500b-8c41-c119ca20eceb |  | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | 0c6fb1b2-ac8b-5740-9334-394ea2292e98 |  | note | – – – – – – – – –
label | ae960e21-e9b2-5e15-b4c8-87d63bc2298e |  | note | REFERENCE DOCUMENTS: Drawings 701.10
label | 53328690-e238-5a66-8436-2c8a4754b12e |  | note | – – – – – – – – –
label | aaeb549c-662b-5729-a024-f253bf9dbbac |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6b5502bd-2378-5661-baf3-17e15458566c |  | note | – – – – – – – – –
label | 53409ab9-82cc-58b4-8c7f-1487712d91fb |  | note | RECORD OF CONFORMITY: ITP Signed
label | 20e666f5-3c2e-5236-8da4-abbffc8e42f3 |  | note | – – – – – – – – –
label | 5e8ef6d9-8850-5731-bb6b-8c90a8964e42 |  | note | HP
label | 1f0ac85d-0a7a-59cf-987f-2038e74c8349 |  | note | – – – – – – – – –
label | 07bf438e-6536-59e7-90cd-e599d1aa470e |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | 754ae0f9-9cc1-52db-99e5-4e763982c070 |  | note | – – – – – – – – –
text | 4b4a7073-a465-54cc-ad70-df7fea90db84 |  | textbox | DATE:
holdpoint | 31664eff-ed91-4bb5-b1a1-a67e693f1a84 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 03cee5e2-a011-4c0a-b2c7-b37e0603074c |  | checkpoint | 2.3 Excacation (pipes)
label | 34c9f4ff-1f26-51e2-af87-a8e7b4365ce6 |  | note | FREQUENCY: Each Trench
label | ac04f539-8e10-5bb7-96bd-c20c7bceac7c |  | note | – – – – – – – – –
label | 31705813-1e3b-5651-a04e-12940112b537 |  | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
label | 96012c68-0a7e-5056-b067-93bdc3b99b39 |  | note | ○ Depth of trench:
label | 5587b7b0-1b40-5426-85e3-05a6b3135e7d |  | note | • > 100mm below underside of pipe (for pipe width < 1500 mm)
label | 9c66326b-fcff-5f98-9472-c58120d32850 |  | note | • > 200mm below underside of pipe (for pipe width > 1500 mm)
label | 3425168a-5160-5cbd-8c50-7e41032369e0 |  | note | – – – – – – – – –
label | be451ad1-a323-57b7-bd5b-4531cee78676 |  | note | REFERENCE DOCUMENTS: 701.151, 701.15
label | 3917362d-7301-54d6-9072-a3c939864570 |  | note | – – – – – – – – –
label | 13b8d065-054b-5a6c-86a5-8a5651de314e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1f0ab38e-f20e-5f18-9e1b-e3284271f452 |  | note | – – – – – – – – –
label | 2deabc08-d926-5a72-9951-94d6732abdc6 |  | note | RECORD OF CONFORMITY: ITP Signed
label | c0cf54ff-8812-52bd-ab29-7a563e0b89df |  | note | – – – – – – – – –
label | d7459d88-9be8-5dd7-8496-392a98f4adbe |  | note | IP
label | 55c49eb6-6bc5-501a-971d-1a12ee0ac003 |  | note | – – – – – – – – –
label | a58688f8-ffc8-5521-92f4-0143ac9198ed |  | note | RESPONSIBILITY: Site Foreman
label | 19fd8ab4-1481-5786-b4e5-958b6fd7e616 |  | note | – – – – – – – – –
text | 3a333cb6-7524-5455-aa2d-8780dee3b47e |  | textbox | DATE:
checkpoint-status | f7b782fe-4082-461e-bc71-368786e1ff4a |  | checkpoint | 2.4 Excacation (pits)
label | 3baf19d2-1759-51cc-bcae-bc32a67b0877 |  | note | FREQUENCY: Each Pit
label | 35720b53-885c-5bbc-9205-1b24b4a84bc5 |  | note | – – – – – – – – –
label | af24836b-0d1a-5775-b4ca-d60bb6ada44a |  | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
label | 7824d2bd-6ed3-51f6-a4a7-4294ff258442 |  | note | – – – – – – – – –
label | 4df700ba-9e94-57e4-8b8c-3bee44e3b3b7 |  | note | REFERENCE DOCUMENTS: 705.05b
label | e9ff0d66-dd10-5a7a-95ae-7a38dffc4661 |  | note | – – – – – – – – –
label | a49915bc-25ad-5f4b-bef0-19a3a0c09df0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 89eeafbe-96ae-5783-90f6-02159aa9e2ef |  | note | – – – – – – – – –
label | 9ec2a29b-dcbe-5bd5-b91b-5340748d9f54 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 36a9c7f3-8db0-5340-a83f-9ecab671b6fe |  | note | – – – – – – – – –
label | 8adc3f9a-0c40-5f98-b2af-6019f7ca93fe |  | note | IP
label | 8da70816-8026-5846-b569-f565ad6eeae4 |  | note | – – – – – – – – –
label | 1492ea17-e66c-5484-b5e4-4f960617af35 |  | note | RESPONSIBILITY: Site Foreman
label | 89f664b8-7c50-5f01-9e6b-73dde858da3d |  | note | – – – – – – – – –
text | 28b521cd-1542-5e80-b2d2-4eaa7fdd9709 |  | textbox | DATE:
checkpoint-status | 47724198-d4a8-4541-a120-b127a6e0bbcd |  | checkpoint | 2.5 Compact base of trench
label | 942c9167-00f5-5015-812b-c7dd829f3c39 |  | note | FREQUENCY: Each Trench
label | 64b61b48-ad8e-5e46-a5c0-c67ff08260f8 |  | note | – – – – – – – – –
label | 46c2f24e-89bf-5dd0-921a-a7f2f4710acd |  | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | fe3888cf-a458-5fab-b2c5-a23ff9e71b02 |  | note | – – – – – – – – –
label | 450cd916-a0a2-5652-bf09-2c78429f2a0c |  | note | REFERENCE DOCUMENTS: 701.15
label | 02e44af6-c402-5936-a742-896a8cdd4f74 |  | note | – – – – – – – – –
label | ffe8d32c-c124-5916-bf56-e7f669c58a5a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6f61d143-7f30-5d3b-be73-85c13b80294d |  | note | – – – – – – – – –
label | 68ab99f1-ab5c-5024-97a6-3f51e88e996d |  | note | RECORD OF CONFORMITY: ITP Signed
label | 4bd9beb5-b693-505e-b449-b85a16120bf1 |  | note | – – – – – – – – –
label | e1787b4c-9636-5dcc-af31-90be6bc08ee5 |  | note | IP
label | dcaf23cd-48f1-56d1-b38f-80d21e783cd8 |  | note | – – – – – – – – –
label | 13f739a4-514e-5651-8b91-1e5f4fd09052 |  | note | RESPONSIBILITY: Site Engineer
label | b852cce7-fe73-50b6-b215-1bbfc032873a |  | note | – – – – – – – – –
text | f5c52895-7c93-551f-a361-5bedb3ced59a |  | textbox | DATE:
checkpoint-status | 8562b8bb-dfe4-434c-95bf-edf1f46bad9c |  | checkpoint | 2.6 Place bedding material & compact
label | 8482f3df-eef8-5d42-acbd-969ba2143adb |  | note | FREQUENCY: Each Trench
label | 2f318434-acf7-5391-a059-6da2f92a7082 |  | note | – – – – – – – – –
label | 802b0a3f-017b-5481-bdc5-38640fb856fa |  | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | a1536230-2abb-5c3b-960c-d5b4d3a0b068 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment.
label | f0112910-79b1-5c1d-84f8-37c7c36abce5 |  | note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 7fd68a8b-6e17-562b-ae41-3f47c7ba6a79 |  | note | – – – – – – – – –
label | 7dbc0e1d-d153-5a05-a72c-2aef3f66f6e6 |  | note | REFERENCE DOCUMENTS: 701.20, 701.20a
label | 3665665f-8e7b-5ce6-82f8-cb48c0b45383 |  | note | – – – – – – – – –
label | 2a4f18ba-0264-55b6-a30c-5c6e871b5f7d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4efee428-026e-5aa8-b68d-269048979e18 |  | note | – – – – – – – – –
label | f1506f31-89e3-5c2d-81e4-1ab8e092fed4 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 9fa9e05f-338c-5dcc-abb2-f15e66d75afb |  | note | – – – – – – – – –
label | 02540b14-6a0e-574b-85b9-21a6e041f6c5 |  | note | IP
label | a4bbddc4-54cc-5828-9920-e421518eb444 |  | note | – – – – – – – – –
label | d34aa26b-68a9-5ae1-a167-d0ea070fde39 |  | note | RESPONSIBILITY: Site Engineer
label | 3a17e343-69c8-5f99-8139-5798558be716 |  | note | – – – – – – – – –
text | 4c723051-ca5a-5bc2-a40c-09478158de87 |  | textbox | DATE:
checkpoint-status | 47785958-2122-41cf-9af2-a8578c43a2a7 |  | checkpoint | 2.7 Place pipes & precast pits
label | 3c80f99c-1375-5666-8853-9edee872ddf6 |  | note | FREQUENCY: Each Line/Pit
label | 86786b16-3502-5ca7-9f2d-6b6540f7c9d9 |  | note | – – – – – – – – –
label | d59c4db4-d947-5e47-b400-1dc4727ad61f |  | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | fa256aba-78ae-5b5b-a186-8b2c2aeef2df |  | note | – – – – – – – – –
label | ceba75e4-fa0a-578b-9bc9-4ba0729645e5 |  | note | REFERENCE DOCUMENTS: Drawings
label | d30af5fb-920b-55a6-88c9-d08a2913b40e |  | note | – – – – – – – – –
label | a3d45cd9-c489-55f0-a750-978819492a2d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b9f7ef81-d0ef-59a8-91a7-cd361b4c1cf3 |  | note | – – – – – – – – –
label | 9a1ec911-4aad-5e15-bc49-2bf3067f8417 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 6a0923c1-bb73-5be7-acf2-6fc87475b407 |  | note | – – – – – – – – –
label | 64715310-8814-5c71-b3d0-c40b8859a422 |  | note | IP
label | ce1e7632-9b59-5c71-8b99-7d17218bf878 |  | note | – – – – – – – – –
label | c4c4da92-a43c-5f91-80a9-653b920ba1f2 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 2ee5ceda-420e-5702-bcf8-91ddc1a77553 |  | note | – – – – – – – – –
text | 39702f4f-656b-587a-863e-8f5ae5fcb355 |  | textbox | DATE:
checkpoint-status | 87f0ab3b-d5f9-4ab8-b5c8-0a264de28893 |  | checkpoint | 2.8 Jointing pipe sections
label | d8e53ce8-b4a2-5cf1-9aa8-536fb429c87a |  | note | FREQUENCY: Each Line
label | ff624d2f-ec69-59e7-ad27-f1bba74fd320 |  | note | – – – – – – – – –
label | fc6259de-0a48-500c-9bbb-93e028a0ff5f |  | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | c94dc9be-e02c-5cf0-98ec-a149a20e9216 |  | note | – – – – – – – – –
label | 1f061cd1-d728-50c1-bd40-c18bef05c2af |  | note | REFERENCE DOCUMENTS: 701.18
label | 5d6e64c7-fa50-5b90-8cda-d420a1963746 |  | note | – – – – – – – – –
label | 44fb7718-3a97-56b9-8c11-bc5e965c5f36 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 268785b9-1528-5654-b088-311403098210 |  | note | – – – – – – – – –
label | b39029d5-b439-50da-86e8-eedb7c920388 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 0a9845d0-8043-5daf-bb5c-c51e7dcdecb3 |  | note | – – – – – – – – –
label | 3c5a8919-ef61-5c58-a5cf-6ef6dbf70503 |  | note | IP
label | f7c47c4b-c967-5d81-b36e-a4ea1f1212e1 |  | note | – – – – – – – – –
label | 34c3c6d8-d11c-5fc7-a055-17d866351ccb |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 77fcf8db-e934-5485-9fa2-1065ab00d162 |  | note | – – – – – – – – –
text | 379862ab-5e42-5f56-89c9-93c36a97f971 |  | textbox | DATE:
checkpoint-status | c9042e98-57fd-4131-86d9-dc91687fbe2f |  | checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
label | cbaa70d7-7eca-58f1-b9c0-21a2fe759d00 |  | note | FREQUENCY: Each Pit
label | e84a2572-6831-57b6-b0d5-c6670ae9f28a |  | note | – – – – – – – – –
label | f17708df-8a10-54ad-bd07-339810c54364 |  | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared.
label | 71871a37-9b10-5eba-b858-0305eaf6de24 |  | note | • The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
label | 06060fde-c454-5f0b-a5dd-88cd15772a92 |  | note | – – – – – – – – –
label | a06eb006-28ac-5ea4-b0c2-6179c165d642 |  | note | REFERENCE DOCUMENTS: 610.32, 701.17c
label | de07e449-6bcb-533c-9e2c-42d0523487fc |  | note | – – – – – – – – –
label | 0e48bd40-26a3-5be5-a28f-96eff3b61bd4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d9589e5e-1fb8-511e-857a-c0df652d90a7 |  | note | – – – – – – – – –
label | 021b60ce-73fc-5c9b-a8aa-4a2220a46ea0 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 691c3414-d940-570c-9d93-db1286272c30 |  | note | – – – – – – – – –
label | ea3db6af-ddb9-59e2-9be9-b86768ad1886 |  | note | WP
label | e5518555-d4ad-5bd9-abe4-2d7e96e5564b |  | note | – – – – – – – – –
label | 1bd4e360-4601-5cdc-a2cf-b1f69bf91295 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | c81068e5-8f0b-52f8-ae59-1a7e4fb95dc5 |  | note | – – – – – – – – –
text | 38011518-7df6-5973-9cf2-8e1534633577 |  | textbox | DATE:
checkpoint-status | cd6100b1-e65f-4e71-9cb0-692cdcc856b6 |  | checkpoint | 2.10 Survey of laid pipe or pit
label | b66bc46e-4eea-5cc8-b161-495f174c29e3 |  | note | FREQUENCY: Prior to backfilling
label | a43e1fbd-e50d-5c3b-b8cf-2f00d1881df4 |  | note | – – – – – – – – –
label | cabbc2bb-0aaa-5b45-81b0-f30423a54d3a |  | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 1dea3074-b0bd-5537-b10b-eb2465038722 |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | 4692957e-861d-5341-801c-4ea324591999 |  | note | (c) invert level of pipes at pits ±50 mm
label | d0edbf24-0c51-53fc-8aeb-d43c8997c17c |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | bca61451-65a9-5de7-8d7a-6d884954f44e |  | note | – – – – – – – – –
label | 11c2ba71-6bc0-5ae4-a54d-965d2be79247 |  | note | REFERENCE DOCUMENTS: 701.1
label | 8a103ea6-5b6e-5e9d-a2ec-0e45dad80d85 |  | note | – – – – – – – – –
label | 655f27b4-080c-5961-9c27-286a1a585f20 |  | note | INSPECTION/TEST METHOD: Survey Conformance Point
label | 23f26ca3-e232-52e6-99b6-516d2f81a653 |  | note | – – – – – – – – –
label | d8ef8e9d-a763-54d4-86da-ae9880cd0ffc |  | note | RECORD OF CONFORMITY: ITP Signed
label | 3d811c19-676f-54cf-92be-56615d2241d0 |  | note | – – – – – – – – –
label | 25ddbeb4-916d-5d84-892b-d8f9aea0f93d |  | note | SCP
label | 460fc67c-4563-5749-841a-8ebf50b3c886 |  | note | – – – – – – – – –
label | 11c6daa7-3b4d-52cc-be47-6e1143723b73 |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | c15d99f1-fad7-505e-9c6f-2333615b0f04 |  | note | – – – – – – – – –
text | 1d455a37-67a3-5d52-ab6b-2e510087a9ec |  | textbox | DATE:
checkpoint-status | 560b48e1-685d-41c7-8721-b807596d9512 |  | checkpoint | 2.11 Haunching & compaction of bedding material
label | fb7aea96-422b-52f3-8698-7e7b65dab487 |  | note | FREQUENCY: each lot
label | 6d64e2d6-0735-5603-b40e-0c3d4938c961 |  | note | – – – – – – – – –
label | e36f5435-1525-5226-88e3-05da25172752 |  | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
label | 78c6c8e3-8815-5a5a-ae73-a1a9beac4c0c |  | note | • Loose layer thickness <=150mm
label | 2603a2f4-9d69-58f9-a5d4-5110f8a77873 |  | note | • Compacted to refusal using hand held mechanical equipment.
label | 861c3c00-2071-5142-a54c-e346c524a28c |  | note | • 1 lot = 150mm layer
label | 90493dd2-c8ec-5de9-a5d4-b063057be8ff |  | note | – – – – – – – – –
label | 5a2275b3-21c5-5cd3-b11a-c2972828a091 |  | note | REFERENCE DOCUMENTS: 701.16, 701.20
label | 8102aa76-6a34-5beb-a355-d8dce97b6c11 |  | note | – – – – – – – – –
label | d49e0c19-b6ac-52c8-afa6-f7da866d1708 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 816cc3d1-c4d7-5b05-83b1-548180542874 |  | note | – – – – – – – – –
label | 6874e54a-1cf4-5373-ba5e-c544d85e0b90 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 5c9370fd-ba7a-5e9e-b585-5378aff84a98 |  | note | – – – – – – – – –
label | a2f17376-90d4-5214-bac3-7bed72af6e25 |  | note | WP
label | 0feb74bf-7b89-5d14-b7b5-3356278984c4 |  | note | – – – – – – – – –
label | 834416b8-af91-5d03-a543-f6d6c6bf86b6 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | db76c001-dc63-5c8c-b420-324ce2202b79 |  | note | – – – – – – – – –
text | 3fc1752b-6859-508c-82c8-fb0465fe23f0 |  | textbox | DATE:
checkpoint-status | 1fc6c611-e7f0-43c9-95d7-67f469de8a85 |  | checkpoint | 2.12 Place & compact backfill material over pipes
label | 4a287c4c-ad02-5e44-9d5c-76305bdd7193 |  | note | FREQUENCY: each lot
label | f53e85e7-301d-5864-87cd-35fac9d34672 |  | note | – – – – – – – – –
label | a9dc921d-1781-50a6-8d9e-3e5d77d45f7c |  | note | ACCEPTANCE CRITERIA: Backfill under paved area:
label | 0381dca2-2c28-5d20-bd40-32b9e73a5328 |  | note | • fill trench with selected back fill material to subgrade level
label | 918900ab-cf8d-514e-9aec-56300249d693 |  | note | ○ Backfill under area not paved:
label | 42336cfb-ece2-5a0f-bc7b-c6d8352a7558 |  | note | • Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | 30243682-77d4-5758-93a5-2f54e4364d46 |  | note | • Loose layer thickness <= 150mm.
label | 0f6f98f3-612e-5df2-9360-e7b87e6bbe75 |  | note | • 1 lot = 150mm layer
label | 0233f343-4671-5364-ae4b-dfbfa0e7986b |  | note | – – – – – – – – –
label | ca26d191-f0e9-55b4-a5a0-0814407dda84 |  | note | REFERENCE DOCUMENTS: 701.19, 701.20
label | 96cb5906-45f4-53ba-bb4e-8026d0dc1331 |  | note | – – – – – – – – –
label | bea37f8c-3c69-5d61-8147-68e151bfe652 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c4e431ab-285f-5149-95d8-7a686766f21d |  | note | – – – – – – – – –
label | 5698910d-650d-56cf-8983-e1ae310789d2 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 4a63bb39-7993-5a39-8abd-34c414902406 |  | note | – – – – – – – – –
label | 7bd6b911-9a62-5038-a39e-0c68db6882a9 |  | note | IP
label | a68aa43b-e59b-5011-bc96-a8da42eb75be |  | note | – – – – – – – – –
label | cc0658b0-d8e7-5cb8-80b5-0fe1cd281eba |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | b113f7cb-18e4-5629-a302-6cb4d45bbcbc |  | note | – – – – – – – – –
text | 235d98eb-f9b5-5963-987f-abfc198ec7b7 |  | textbox | DATE:
checkpoint-status | 40a80e4b-c0ed-4b8e-b37d-e8724f2ca18c |  | checkpoint | 2.13 Place & compact backfill material around pits
label | 34d72838-5094-57e6-ad7b-a59adb827d47 |  | note | FREQUENCY: Each Pit
label | 313379eb-b007-5e81-ba57-47cedb0a7e9d |  | note | – – – – – – – – –
label | e2c067a5-3b5f-5932-8a2c-9b852e0125cd |  | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm. Compacted to refusal using hand held mechanical equipment.
label | 518da4f8-833f-5ee0-9330-aa65ab30e6c1 |  | note | – – – – – – – – –
label | 23ce6b97-79ad-590e-9d3f-7472de83fd54 |  | note | REFERENCE DOCUMENTS: 705.18
label | a680df95-48c3-533c-9ad6-2260edb658f0 |  | note | – – – – – – – – –
label | 2fb008e1-1188-5af2-ad09-e27a1b4ca50b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8691c870-d04f-5629-9fbe-2651a7bdaeeb |  | note | – – – – – – – – –
label | 43090b22-80ea-520b-a6e8-4ddace5bde57 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 9022fe9d-a989-58e3-87a5-a7f3c6a850ee |  | note | – – – – – – – – –
label | c24afc9c-7ec2-56f2-90a6-a901482f792d |  | note | IP
label | 6dbeb05c-a76e-5f06-92fc-bb6e126dd643 |  | note | – – – – – – – – –
label | 0345a5d4-9a18-56c4-aae3-cf899ecfd7de |  | note | RESPONSIBILITY: Site Engineer
label | 56f6e7fe-e718-59c8-a565-33eaaaf85804 |  | note | – – – – – – – – –
text | 97e79488-2edb-5f9e-9021-d3e86704358b |  | textbox | DATE:
checkpoint-status | eb398469-5a5a-4166-b99c-24d5d41eb9ab |  | checkpoint | 2.14 Backfilling with cement stabilised sand
label | 0f8aa4dc-cddf-5d84-a9f0-48d5d2425648 |  | note | FREQUENCY: Each culvert
label | f4f99ae7-dcdb-502a-a41b-a20ad02019c0 |  | note | – – – – – – – – –
label | ccd3e686-4cd6-52ee-813e-0cca198c5043 |  | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
label | 4d735177-4e30-5d88-8869-4efecca7bbfe |  | note | – – – – – – – – –
label | 778f47b6-c692-5104-96fa-04a42b2009fa |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
label | a7298f5c-34a5-5b70-9947-460b043fe390 |  | note | – – – – – – – – –
label | fd98f313-733c-5112-9d18-f4ebbc9ff2c4 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 9a5ba956-85a7-5c8f-8386-fa92dd5aca98 |  | note | – – – – – – – – –
label | 1f8d40f3-c86c-58c4-b0de-b34e4a24be4e |  | note | RECORD OF CONFORMITY: Superintendent approval, ITP signed
label | c701bf8d-758f-5021-87c3-236d95cfc734 |  | note | – – – – – – – – –
label | 309d0505-f78e-596c-9681-5946281c7cce |  | note | AP
label | f71fffcb-5ddf-5c5b-9445-e3036fd65a19 |  | note | – – – – – – – – –
label | 9bcfdb40-176c-5198-9fb5-a1e40d6979fd |  | note | RESPONSIBILITY: Project Engineer / Superintendent
label | 0898b746-0cbb-586b-93ed-bdbeb62c9b28 |  | note | – – – – – – – – –
text | c9f0990c-8e32-5ea9-9fa4-05d321d9e7c6 |  | textbox | DATE:
checkpoint-status | da135a98-018b-4cdc-9c90-3f7bf985f3a7 |  | checkpoint | 2.15 Install step irons
label | 7ba00082-1a43-549c-a7f8-4585f4ce61c6 |  | note | FREQUENCY: Each Pit
label | 0c93133d-65f5-5fe7-ac14-ce0aebad1f4f |  | note | – – – – – – – – –
label | 675a40ab-1529-5589-a8e2-813908ec77bc |  | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
label | 0e696a95-c4e0-5a83-bd66-db71cb0bfc9f |  | note | – – – – – – – – –
label | 989d60ab-bf31-5ee5-896b-549ca6e473d0 |  | note | REFERENCE DOCUMENTS: 705.12
label | 22dc9c10-78e0-57c9-8a7f-429878b54900 |  | note | – – – – – – – – –
label | 158b51e3-dfe0-5701-b0b3-f2917f29e791 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 058d8875-d532-575b-a81f-450df4febe27 |  | note | – – – – – – – – –
label | 7add5017-3b7e-5a4b-a93d-f73069511c93 |  | note | RECORD OF CONFORMITY: ITP Signed
label | cdbfc87b-d247-5ed2-a9f3-20c9e141b7c8 |  | note | – – – – – – – – –
label | 0bf579b2-7ffb-5e28-a689-198b077b2512 |  | note | IP
label | 5d6d18f1-e2aa-5907-b56c-3cd2d12a205a |  | note | – – – – – – – – –
label | 26531c9e-5371-5620-a6be-b507d6acdcbe |  | note | RESPONSIBILITY: Site Engineer
label | f2896125-d89b-5d6c-8230-120d7d1e601b |  | note | – – – – – – – – –
text | 08123e30-4f7a-5060-8bc7-6412eafe0435 |  | textbox | DATE:
checkpoint-status | 1dd079f0-d076-46df-9857-07257d33ad13 |  | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
label | 5fa942e1-c1dc-5a3f-bb3f-498dda50918c |  | note | FREQUENCY: Each Pit
label | 464af7aa-1478-5f0a-b9f7-0cf662bf6694 |  | note | – – – – – – – – –
label | b427e78a-dcc6-5d89-9787-041cea2ff61a |  | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
label | c57123da-9f71-50ac-8ee4-9ebe2fccbd5a |  | note | – – – – – – – – –
label | 8edd762c-1158-5a78-af05-af473feadf48 |  | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
label | a81cf99a-3ba3-5cd3-bc4b-b4ddc893ab36 |  | note | – – – – – – – – –
label | 7114182c-0cd1-50d6-823d-b80553c25750 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 73498565-38a3-5d71-b697-782197164356 |  | note | – – – – – – – – –
label | 31af69d2-5e9f-5f9c-926b-a9e5861c072e |  | note | RECORD OF CONFORMITY: ITP Signed
label | 71592e7b-b06a-5614-966e-c84e1084c6ee |  | note | – – – – – – – – –
label | 896b92a4-5fea-5ef7-ab41-f9de47118f37 |  | note | IP
label | 66cbbb85-3089-58d9-ac8a-3acbb15d9664 |  | note | – – – – – – – – –
label | 633f7a44-b2a7-5e14-a9db-95c25192b5df |  | note | RESPONSIBILITY: Site Enginer
label | 8994078c-e0b0-574a-8b8c-6377d14fb382 |  | note | – – – – – – – – –
text | 9e0d9cc3-3778-5788-be18-07ba3f2f70fa |  | textbox | DATE:
checkpoint-status | 374bc933-8029-4978-98a5-c17bffbdf354 |  | checkpoint | 2.17 Place pit covers
label | 81380180-eb90-51dc-9326-3a83ca527c83 |  | note | FREQUENCY: Each Pit
label | 8830047d-95fa-5a0d-af9b-57ce0551a302 |  | note | – – – – – – – – –
label | 4232a470-5322-52d2-8f19-bda05c7f4902 |  | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
label | c85919f0-4f56-5f29-aa7d-9d8d4d91ac8f |  | note | – – – – – – – – –
label | 311749ea-9a8b-557d-a02c-5c9bfc8a614b |  | note | REFERENCE DOCUMENTS: 705.17
label | f564d929-3678-5c68-a7db-66da595c2a63 |  | note | – – – – – – – – –
label | cb66ca2e-25cb-55f5-b6ea-4f75aa88b496 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 28a15754-1ad3-55a1-aeab-b24ebff4c1d4 |  | note | – – – – – – – – –
label | 0d8c6198-d88d-5df3-baaf-4ee961453080 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 39add330-4654-5df2-a4f7-5814180a2e9c |  | note | – – – – – – – – –
label | af48d8f4-8460-57d1-bb70-b6f5722643c8 |  | note | IP
label | 766212e8-12e3-5265-b878-782022a4d195 |  | note | – – – – – – – – –
label | 17502056-1fde-5942-8d62-adfb08427870 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 4058a235-67bd-5ed8-94e4-1f8654d9f5ff |  | note | – – – – – – – – –
text | 488a18a9-d7ea-5ad5-bb50-b644a9e366c3 |  | textbox | DATE:
checkpoint-status | 1bba2a62-88cf-4e17-b3f3-fc2b3cecd14d |  | checkpoint | 2.18 Repairs to damaged pipes and box culverts
label | e01355af-e7c9-5f95-95b8-1c8fee870537 |  | note | FREQUENCY: Each damaged pipe or culvert
label | a4040404-5f49-5053-a018-b3aadc6b7899 |  | note | – – – – – – – – –
label | 9a9d1310-5a1a-5632-a575-f33e03d0e6df |  | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
label | fa830726-3cb8-5022-ac59-9986067f42a8 |  | note | • All repair procedures undertaken in accordance with Cl 701.25
label | 9510b794-694f-57f8-bef8-5c81e8929a4b |  | note | – – – – – – – – –
label | 97b0a5df-812b-5492-a73b-71c67e1f4e01 |  | note | REFERENCE DOCUMENTS: 701.31a
label | 3bf34708-1453-5e4d-a11c-c356d46a8912 |  | note | – – – – – – – – –
label | d4232710-b1cf-59c3-ab22-8ba3f0a10314 |  | note | INSPECTION/TEST METHOD: Verify
label | 5dae14d9-71dd-5c62-9cfe-2a0d01abd6ff |  | note | – – – – – – – – –
label | dfecd365-3c16-5dbd-a9b8-385a23e193fe |  | note | RECORD OF CONFORMITY: ITP Signed
label | 0a9df478-43aa-5694-bd11-25c0c8624d0f |  | note | – – – – – – – – –
label | 530ecbdd-cc76-5b8f-b10e-cb1d84eeb9c2 |  | note | HP
label | 5b143385-7ad3-55c1-aa40-bc3572d9d463 |  | note | – – – – – – – – –
label | e9e9e928-2a8c-5403-92d1-f84a2111ed94 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | 9f0b6e59-ed86-534d-920d-35cde312e37b |  | note | – – – – – – – – –
text | f6dfbf86-8ade-55f3-9259-892fda11c376 |  | textbox | DATE:
holdpoint | d2a7241d-f383-43b8-b946-47d20e9462f3 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group | de2ba678-23ec-4e72-8bad-a3ce4d54917d |  | section | 3 - Testing & Completion
checkpoint-status | c468889d-1c25-4d34-99cc-1e5b4ad96c88 |  | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
label | f2123c55-1b3e-570c-a85d-4501da979df9 |  | note | FREQUENCY: at least 20% of all lots
label | 40da2fcd-e1f3-5a5c-805f-9c06bdb2501e |  | note | – – – – – – – – –
label | abd8dd31-e95b-5519-9418-8daae6133ef1 |  | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
label | b5318fe2-7f70-5ac8-9ff3-1e1d664637bf |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment.
label | 28caed54-12a6-584c-a184-b336faeeece0 |  | note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 0e636ae9-051a-58a6-8431-f22d25ae01d4 |  | note | – – – – – – – – –
label | 104835f3-1d93-57eb-a988-c35c9d0a5a52 |  | note | REFERENCE DOCUMENTS: 701.20a, 701.20b
label | 91b84a42-8e79-55db-9c35-9047a1f6f6f0 |  | note | – – – – – – – – –
label | 229b89a2-3564-57ae-943b-c69e289249f3 |  | note | INSPECTION/TEST METHOD: Verify
label | b678cddd-43b7-5f67-9a9e-9fbf7faa680b |  | note | – – – – – – – – –
label | 5cdfd0e9-9375-5351-bbed-3bdf44d72c92 |  | note | RECORD OF CONFORMITY: Test Reports
label | 1e99e197-6520-5e47-ab56-aa95bd888905 |  | note | – – – – – – – – –
label | af9ed0be-0dce-5b0d-9c5d-dd7acb554efb |  | note | TP
label | a0ac3a92-6940-598d-bc4e-eba4c35fc91b |  | note | – – – – – – – – –
label | 79d7aa47-4b8d-5a3c-9263-ae7ccf73172d |  | note | RESPONSIBILITY: Site Engineer
label | 0bff546b-ab65-5717-806e-eccd91aa29f4 |  | note | – – – – – – – – –
text | 4d3f376a-ef49-5092-af84-395eed93f2a6 |  | textbox | DATE:
checkpoint-status | 0778e13f-ba47-41e6-83cf-28dec2999c23 |  | checkpoint | 3.2 CCTV inspection
label | a00321ba-d57b-5afc-8ede-c687d189c2a1 |  | note | FREQUENCY: each lot
label | e1e8e5e0-d034-5579-931a-84e9e314b811 |  | note | – – – – – – – – –
label | f011972f-64fe-51be-8976-a32587c880ef |  | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | ea361b97-2ff0-5e83-9016-a2c960f51ca6 |  | note | – – – – – – – – –
label | 20f8c983-ebc3-550b-b3ab-efcbad70d9e1 |  | note | REFERENCE DOCUMENTS: 701.3
label | 49ee0d6f-1bfe-586b-8652-961d7d1dc5bc |  | note | – – – – – – – – –
label | b37c1c0d-2452-5aff-9a62-9cd315d57305 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | e72413af-0de8-5a67-8b2b-08e14a33b648 |  | note | – – – – – – – – –
label | b909aa93-7d91-5807-a604-c9d77b806956 |  | note | RECORD OF CONFORMITY: CCTV Report
label | 1bce1e6d-3173-569b-bdbc-571e0d57e03b |  | note | – – – – – – – – –
label | fbd59b1e-965d-5cd4-bf0c-ddda27b3d9d2 |  | note | HP
label | 117d6dba-256e-5f0b-92d0-d4858a581fd8 |  | note | – – – – – – – – –
label | bed1c1fc-8f70-585d-b28c-6527ef7384b0 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
label | fc73545f-232a-5f4d-a5d1-a71c48aaf65a |  | note | – – – – – – – – –
text | 311196c8-2fe9-5d41-bfc6-343c4d7e2e58 |  | textbox | DATE:
holdpoint | 6d749eab-6f01-475b-865b-6913e2741719 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 75604c67-a2af-4f6f-af70-67aeb7f82398 |  | checkpoint | 3.3 Flushing of pipes
label | 8d43e5bf-d603-5d64-ae4e-06d6773abc56 |  | note | FREQUENCY: Each line
label | 36856903-c862-5656-86a1-d55b5d115de6 |  | note | – – – – – – – – –
label | 25cbabb1-9fbc-5088-b891-7765112457b1 |  | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
label | 49ebf325-1122-502c-9504-4b4a776a0550 |  | note | – – – – – – – – –
label | a9df5cbc-0fb0-5518-bd3b-c3098269deb0 |  | note | REFERENCE DOCUMENTS: 701.28
label | c17e72fc-88e8-59c6-bb53-b28114f96a5a |  | note | – – – – – – – – –
label | 2a24bad1-a243-5109-8b21-64e8ca0ee04f |  | note | INSPECTION/TEST METHOD: Verify
label | a6165111-d2f2-53b2-a264-3379797d2a2e |  | note | – – – – – – – – –
label | e902a610-54a6-504f-9b09-7cddfb1da97f |  | note | RECORD OF CONFORMITY: ITP Signed
label | bbab3530-beab-53d6-ba29-0cf01f37e994 |  | note | – – – – – – – – –
label | 3369d242-36f7-51ed-a662-48b684915200 |  | note | IP
label | b589b919-3d5e-5d28-ab16-7c7cd75ed9b5 |  | note | – – – – – – – – –
label | d8024b48-300d-5e80-8036-0ca45c338f1d |  | note | RESPONSIBILITY: Site Engineer
label | f6311747-abb8-5269-9222-bb2f5e0c66a0 |  | note | – – – – – – – – –
text | d98b9ea1-ccc8-5c18-82db-75e9e5c5687f |  | textbox | DATE:
checkpoint-status | 04a74e19-53d7-4a42-9900-c48fbe3de4a7 |  | checkpoint | Final Inspection
label | 7c57d421-888b-541a-b2cd-1c6ccd4c830b |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | e96ddf66-b438-5c9e-8ede-c837dcdf1553 |  | textbox | Print Name:
text | 9c32011c-a98a-5607-b20c-8ad8c420c258 |  | textbox | Position:
text | c5d07929-9b71-5f23-ace3-38bb24b574e9 |  | textbox | Date:
checklist-sectioned | 7d3137c5-652a-459c-94cc-e4da8999437e |  | checklist | FHC-ITP-034 - Cement Treated Crushed Rock Sub-base Rev0 | itp |  |  |  | Yes | FHC-ITP-034 - Cement Treated Crushed Rock Sub-base Rev0 | d67790e1-a389-4714-8ee9-d59f394842f3
checkpoint-group | bb020c89-a712-4714-ac21-242c836a60d3 |  | section | 1 - Preliminary Works
checkpoint-status | dbd99c95-46c0-4d5c-ae13-3931ab3a5588 |  | checkpoint | 1.1 Check for correct documentation
label | 3640f9bd-9444-5278-98a5-c606e4328d8b |  | note | FREQUENCY: Prior to commencing any activity
label | 6e776c15-2a4d-565f-bb8c-944854d7f4c0 |  | note | – – – – – – – – –
label | 7fd1099a-1475-5de8-9aae-e88c91b126aa |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | ec3abcb9-987e-5cde-bab2-d8c24c03b686 |  | note | – using the correct and complete set of drawings
label | b273f3ae-1231-580e-a829-a3c13d06ad82 |  | note | – all drawings are the latest revision
label | 7751e1c7-f25b-5d8a-8d6e-8de7bc86e8f0 |  | note | – – – – – – – – –
label | 017de6d9-6fe5-52a7-a644-2f7cb8aff4c7 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 9a6b0bb4-436b-5fd3-9135-7d38b32e6ecc |  | note | – – – – – – – – –
label | 78e001dd-aba5-53a6-99c9-2d29d66528ff |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 66d41447-bd3d-5a44-821b-fa48be309bb1 |  | note | – – – – – – – – –
label | 55e8d1ff-a067-50b2-846e-23d0973b77d8 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 44e18f58-b53f-5bd6-b5d8-8c1f3ab985d1 |  | note | – – – – – – – – –
label | f043846d-54aa-58b3-b380-2fc94fe75e42 |  | note | HP*
label | c3b306df-1761-57d5-9825-82b98bbe54d8 |  | note | – – – – – – – – –
label | f218a855-49ad-5683-95d1-20c6c887db64 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 7f067ed7-85a1-5998-acfc-b67ad2e29c53 |  | note | – – – – – – – – –
text | 2ceb29a2-e7e8-5d3a-b192-c231f186927d |  | textbox | DATE:
checkpoint-status | 8f2d8ca9-f721-4683-b1a2-1f7db218e12f |  | checkpoint | 1.2 Implementation of all measures and controls
label | a992ba7a-9afa-5a45-8afd-48f62ce51a78 |  | note | FREQUENCY: Prior to commencing any activity
label | 7578ed5b-af11-5790-8256-0e3544c9ded6 |  | note | – – – – – – – – –
label | 0bcca2d0-d7f2-5db3-83ba-e0392ba787a9 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | eb0d1223-13a4-549c-9841-12ac4b32be9e |  | note | – – – – – – – – –
label | d264170e-b762-5d1e-b20c-54ca76074d81 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | fb3845ee-c439-5a5c-84d6-75c21d697f5e |  | note | – – – – – – – – –
label | 4439050d-894b-5a29-839a-b0635d7e75e0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f98558bb-f0d3-59ee-afa0-55f6152c542f |  | note | – – – – – – – – –
label | a3238d91-0670-5f83-8018-9cd193fe32e1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e51e7017-c775-56d9-93fd-d5fa0bdf826a |  | note | – – – – – – – – –
label | 78bd1038-6c70-551f-9775-7b96049253aa |  | note | HP*
label | 5cca0ea1-7b42-57d1-873a-8187b989a4c5 |  | note | – – – – – – – – –
label | 85cc35c0-9794-5473-8227-06c247c3670b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 67801205-d8fd-5faa-8ac9-b2fec58a0255 |  | note | – – – – – – – – –
text | a75ad751-fac5-59d2-9180-18af3081c944 |  | textbox | DATE:
checkpoint-status | 7645f93d-3ed9-4c57-91f6-991c69d812c1 |  | checkpoint | 1.3 Verify Material
label | 66307776-6f28-53c0-a135-2ad1c7c19ade |  | note | FREQUENCY: Each day
label | 2164a31d-1417-5822-8dac-8c5f2a9208de |  | note | – – – – – – – – –
label | ca6a7755-887d-5677-a383-d14fa93840cf |  | note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase.
label | 6651e4f1-2ba9-5954-934e-e76adef7e8dd |  | note | • The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
label | 5d26f32a-25d3-5e68-894c-a308a5d96d88 |  | note | – – – – – – – – –
label | 213b5bab-e0c5-565e-ad08-2f7a19d9db4f |  | note | REFERENCE DOCUMENTS: Section 815 Cl 306.04
label | 27a3dc6d-2024-5e6b-af6d-67f355115b9e |  | note | – – – – – – – – –
label | fcc1c7d0-d773-54a2-8011-e623b9425967 |  | note | INSPECTION/TEST METHOD: Verify
label | fce1b77b-2f24-57e9-9cee-1b3cc74b59fd |  | note | – – – – – – – – –
label | 4b8dd5c1-ada2-51ec-80f8-bba708d29d6f |  | note | RECORD OF CONFORMITY: Material certificate from supplier
label | bf9d2bb3-172b-5f87-9d8f-446dcf1e08d3 |  | note | – – – – – – – – –
label | bb700aa8-1768-525e-b2c0-feebf8e2d3b0 |  | note | HP*
label | 983ace69-eb7a-59bb-af75-8a40d4e2204d |  | note | – – – – – – – – –
label | 32d4e250-06f8-52d0-8519-b7d7e85c05b4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | b3845197-2608-50ab-a042-35badeef43f6 |  | note | – – – – – – – – –
text | 9eb33dd0-fad5-514c-9d64-3e10ecfbdecf |  | textbox | DATE:
checkpoint-status | 0c8f095b-8ea4-488b-a2f4-8f47e6ebe0c7 |  | checkpoint | 1.3 UCS Testing
label | d7c779fc-2048-580c-90b6-e85a52a04043 |  | note | FREQUENCY: Each day
label | c9ab78c8-53b6-5960-9c57-fa1e2506e0cc |  | note | – – – – – – – – –
label | dcec5a7c-36a8-5f22-8a6a-c936eadea112 |  | note | ACCEPTANCE CRITERIA: The Contractor shall carry out UCS testing in accordance with the test frequency specified in Table 815.141.
label | db19cf02-0efb-5fe3-bda3-5f87a86ba72b |  | note | • The UCS during production shall be assessed on a ‘rolling average’ basis where the average of the most recent three UCS test results shall not be less than the minimum value specified in Table 815.101. For the purposes of UCS testing, one representative sample of fully mixed cement treated material shall be taken either from the plant or at the point of delivery in accordance with AS 5101.2.2
label | cbf66f58-e623-54d0-a20c-e55cd4ca061c |  | note | – – – – – – – – –
label | 7083273e-1719-5153-bde4-fc6e9e0ccc22 |  | note | REFERENCE DOCUMENTS: Section 815
label | 23ed8e3f-8567-5dfd-9d45-581092a8f987 |  | note | – – – – – – – – –
label | 7f29f35f-dad8-59b2-b5c6-4e6169233bfd |  | note | INSPECTION/TEST METHOD: Verify
label | f7b0dc31-7563-501a-b45c-323253850da5 |  | note | – – – – – – – – –
label | 043eab86-c48a-50d2-b0ba-cc9e756b9eee |  | note | RECORD OF CONFORMITY: Test Results
label | 8d91155e-a598-51cd-a698-62d00ed5a1c8 |  | note | – – – – – – – – –
label | 06c22fc5-3e8e-5c8b-8267-ffd3fa56e4e0 |  | note | HP*
label | ec4175aa-2588-5676-ac77-f644eaa90cfc |  | note | – – – – – – – – –
label | 07ebe683-521e-5570-ab0d-98171a013db8 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | b8e1d8ab-971e-59b4-b011-0f85a6d695c5 |  | note | – – – – – – – – –
text | 5a478d2b-4443-5a0d-b4f1-a7322e37f6ef |  | textbox | DATE:
checkpoint-group | 4632941d-8ccf-4639-8a25-72242bccd1a8 |  | section | 2 - Construction Works
checkpoint-status | 59329201-9759-4f3d-8721-0914a5add1a8 |  | checkpoint | 2.1 The area has been inspected and Proof rolled by MRPA and consent has been given to proceed with placement of sub-base).
label | 9431004d-9250-5aec-92d9-d2c9b8edcaa7 |  | note | FREQUENCY: Each lot
label | a127f0b1-4f0a-5077-864b-972d84d496f2 |  | note | – – – – – – – – –
label | de87628a-0b5a-527d-b6bd-966b4d9309cb |  | note | ACCEPTANCE CRITERIA: Sub-grade has been inspected, No visible deformation or springing in presence of Superintendent's Rep. Test rolling Plant to comply with requirements of Cl 173.03.
label | 2fda9767-6875-5fd2-88a8-4acefc3576b8 |  | note | • Where any groundwater is encountered the Superintendents representative must be notified.
label | 787295ab-9a26-5f46-b74a-e69220db3af8 |  | note | • Ensure that test results for underlying lot are available prior to placing sub-base material
label | 801bb901-dd37-5a03-b134-ed2721eeaeb6 |  | note | – – – – – – – – –
label | 39d36e10-d54a-50ee-bffe-6aa9bf078681 |  | note | REFERENCE DOCUMENTS: Cl 173.03
label | a8b74352-e49f-5e84-b0f9-70be5ddfe710 |  | note | – – – – – – – – –
label | ca5aca17-78cc-5bfa-8525-c14c0ad4f1a3 |  | note | INSPECTION/TEST METHOD: Verify
label | f0e8c991-9013-5935-96ac-421a030466e6 |  | note | – – – – – – – – –
label | 1daa248f-25d0-518b-8c1e-afae85099859 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 627940e2-3324-5920-b8c1-7b550ea75b91 |  | note | – – – – – – – – –
label | d172c240-988b-52ce-98e5-6b544aa22198 |  | note | HP
label | 3bb92ec2-f7d8-5045-8b66-2dfeeddb5026 |  | note | – – – – – – – – –
label | 1c963ac9-2110-5cf5-83e7-1ae806fdb156 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / MRPA
label | 4504ba98-5670-5ff1-9568-b65e710fbde0 |  | note | – – – – – – – – –
text | 8efd8cce-559d-5195-be63-692d1afc4223 |  | textbox | DATE:
holdpoint | a651d70a-a13e-4d30-b63b-641305e136ca |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 34f94655-4cc4-4ff6-b1c5-b3c2ba05828e |  | checkpoint | Maximum allowable working time and moisture content
label | 6e8aed59-52c9-5c28-b54e-74c2d12b492b |  | note | FREQUENCY: Each lot
label | 818ece81-309c-5259-91ef-eddc95dbbb39 |  | note | – – – – – – – – –
label | e64faf32-e801-590e-9334-08e33de48445 |  | note | ACCEPTANCE CRITERIA: The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time specified in Table 306.091.
label | bbde2f11-7534-50a1-b128-649a8fa0d67a |  | note | • The moisture content of the material at the time of spreading and compaction shall not differ from the Modified optimum moisture content, by less than 0.5% and not more than 1.0% by mass.
label | 427cf6ee-e3d4-53c3-a9e2-c424395772ae |  | note | – – – – – – – – –
label | 4d57de6a-a311-5f06-a62e-2abf6ba9bfd2 |  | note | REFERENCE DOCUMENTS: Cl 306.05, Cl 306.09
label | 65d3972d-1edb-5dbf-90e6-9a57df9d2fc3 |  | note | – – – – – – – – –
label | 6d5eec6e-91e6-55e1-bb53-aff6ad7be640 |  | note | INSPECTION/TEST METHOD: Verify
label | 403969e4-bf59-5a71-884c-a110328f74f7 |  | note | – – – – – – – – –
label | 74c64c60-d263-531c-9a64-0ee92d02e46b |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5521a907-1298-550c-b6b3-bf05f1329deb |  | note | – – – – – – – – –
label | 0f61afcc-af0e-5e31-a912-7483fa7d5d22 |  | note | HP*
label | 50b49565-b53e-5120-9577-e5d8b90545b0 |  | note | – – – – – – – – –
label | d2b27190-05ab-5c10-ab41-8ef38b4bff23 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 78edd749-ee43-524e-bfb3-34f9e3567446 |  | note | – – – – – – – – –
text | b98abade-7ce8-56cb-8ce7-1ff8c437bab5 |  | textbox | DATE:
checkpoint-status | c055e6c8-e707-41ea-83b4-6caffbaeb6a7 |  | checkpoint | 2.3 Jointing
label | 689769fc-678f-5d0b-ace1-7d311b8de3bb |  | note | FREQUENCY: Each lot
label | 7c79379e-0799-5897-9441-2b046364fc4f |  | note | – – – – – – – – –
label | 83a38aa2-45a3-5cae-b3e6-76b928cd6b37 |  | note | ACCEPTANCE CRITERIA: a) material shall be spread in such a manner as to minimise the number of joints;
label | 6c700481-c0ec-57cb-8163-f82276a918e1 |  | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | 94353fc2-49d7-5536-bd20-a2618c50d9c4 |  | note | – – – – – – – – –
label | dbff17c1-2786-5c5e-8647-70a66f9b4351 |  | note | REFERENCE DOCUMENTS: Cl 306.08
label | d90eb57f-e5bf-50bf-9ee6-44f46f4a0fb0 |  | note | – – – – – – – – –
label | 73b0f141-4dfd-5fc0-be66-a8538c8210dc |  | note | INSPECTION/TEST METHOD: Verify
label | ec9e88e4-e505-59a6-b2f7-b8f78dae6401 |  | note | – – – – – – – – –
label | 1d4ed091-8c43-579a-b9a6-21320cb19194 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4438288d-655c-5d66-8525-5d406ded34b1 |  | note | – – – – – – – – –
label | 7cce449f-b6ce-5ebd-92f4-e3f38e3c2fde |  | note | HP*
label | 13ec14d7-324b-51d0-a4b4-16ebb84c85da |  | note | – – – – – – – – –
label | b8d30504-6d50-559b-9a4e-8035ba2ad895 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 0ab53aa4-534e-5f47-a73e-250e118c46f8 |  | note | – – – – – – – – –
text | 366fa687-d085-58c7-8197-58de0adf0265 |  | textbox | DATE:
checkpoint-status | 932af0a1-ee89-4907-aa95-89676bd5340f |  | checkpoint | Compaction Testing
label | 9f22db29-595a-5b5c-844a-0fccb4ac7a33 |  | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
label | 3961acdd-accc-5e14-8bb6-dec460a31087 |  | note | – – – – – – – – –
label | d499e176-2b48-5ccf-b199-656cecc0dbdc |  | note | ACCEPTANCE CRITERIA: Minimum MDR of 96% using Modified compaction effort. 3 lot test (Scale B).
label | 2ab0f14e-3fae-5b95-b71d-ad02a5e3472e |  | note | • LOT SIZE = Lesser of 4000sqm or a days production is defined as a Lot.
label | 069c704d-f461-589b-ad64-665319ff63a2 |  | note | • Every Lot to be tested for surface levels and density ratio using modified compactive effort
label | b0feb624-c743-5806-b972-ee735f6decf3 |  | note | • Compaction Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the requirement and then resort to one test per 2 lots .
label | cfbe8559-ac43-5bdd-b12c-acbe071599df |  | note | – – – – – – – – –
label | a8367f45-1916-5a34-ba55-d790bd9ba5f9 |  | note | REFERENCE DOCUMENTS: Cl 306.09
label | a6b0434e-22b7-5e42-9136-556b3205f68f |  | note | – – – – – – – – –
label | 98190026-369f-5f0b-b18b-27214207b6ca |  | note | INSPECTION/TEST METHOD: Test Results
label | 5838542f-7132-5f0c-b709-a24bf457e787 |  | note | – – – – – – – – –
label | 9837b72f-6282-5422-a0bd-f7140c77f194 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1888a255-a705-5b1f-a2c2-d385e5dae167 |  | note | – – – – – – – – –
label | 7e5c896f-ec5b-5aeb-91ac-2f7a71aec1fa |  | note | TP/WP
label | b7304bc0-76fe-54b5-abc2-e526dcd4084b |  | note | – – – – – – – – –
label | 78b7252c-3e99-5cf2-b28c-2362e357656e |  | note | RESPONSIBILITY: Fulton Hogan Engineer / MRPA
label | 9360cc91-2b63-56a6-bbf4-d7fd51f1d076 |  | note | – – – – – – – – –
text | e7b37391-2f33-56f5-9d31-7deec5fdd2ac |  | textbox | DATE:
checkpoint-status | af9983f2-42af-4157-b2d7-d53394c73759 |  | checkpoint | 2.4 Level Checking and Conformity with Drawings
label | 26ab56ff-51dd-5a80-b5c7-896ba48fc6d1 |  | note | FREQUENCY: Each lot
label | aecc9992-7a46-5b43-8821-326b8bb0736d |  | note | – – – – – – – – –
label | 9fbe3a27-ce03-5548-b511-5cf0d0022093 |  | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
label | 695b29b0-5f20-5cfe-a2c6-8124a597d9c4 |  | note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | 67a7e3d4-2a96-5c0a-83d0-1116c62c7295 |  | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
label | 26ae1636-9131-5874-aea5-40cb55f28c02 |  | note | • Surface level tolerances:
label | 7c167646-6d97-5160-a2ca-52771d0414f3 |  | note | • Range x = +6, -12mm
label | 6614811b-3285-53ef-a1c3-a1a18886593c |  | note | • Max S = 13 mm
label | 912c11a4-b962-57f4-96c9-ded4c3acca75 |  | note | • 40 measurements per lot (Scale B)
label | dd6edb72-021f-566a-afce-27c47f9ef93b |  | note | – – – – – – – – –
label | 780d4816-be3a-5c29-bedf-b321777975f8 |  | note | REFERENCE DOCUMENTS: Cl 306.03
label | a8ac5025-ffcd-5e7b-8a7d-402af1be4eaf |  | note | – – – – – – – – –
label | 1e7e163a-d316-5cfb-93ea-8940d915634b |  | note | INSPECTION/TEST METHOD: Verify
label | 49cc08bf-18af-5972-84b8-d52b4d8c2d39 |  | note | – – – – – – – – –
label | c32f08d9-b986-54ae-8dc1-6db9a6a0b9f6 |  | note | RECORD OF CONFORMITY: Survey Report
label | def56804-732a-52db-bf7e-4bf0eea0f853 |  | note | – – – – – – – – –
label | 8d60288c-31f6-542d-9c81-17dd51e49d04 |  | note | SCP, WP
label | cd7fcfbf-8364-5d6f-a769-553377ba8296 |  | note | – – – – – – – – –
label | acc7c92b-4a90-5257-84aa-275938ff31a3 |  | note | RESPONSIBILITY: Surveyor/Fulton Hogan Engineer/Foreman MRPA
label | a4b3f33f-b416-5d7f-9552-d159656e5402 |  | note | – – – – – – – – –
text | acf3a92c-edcd-5742-af85-43a0cb2cb69d |  | textbox | DATE:
checkpoint-status | 80e5885a-5b04-4109-ade1-6b4130689b15 |  | checkpoint | 2.6 Final Proof Rolling
label | 34d6c852-cc35-557b-906d-ee0837bbab5a |  | note | FREQUENCY: Proof Roll each layer
label | 5b156d8b-c363-5306-b052-f3f4b178e81f |  | note | – – – – – – – – –
label | 84682a76-8170-5a6b-9164-c5aa2272a60b |  | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | 9396b2af-bfa7-538d-bd33-360f836b8cc2 |  | note | – – – – – – – – –
label | 23347b17-8360-5e06-9e84-b7be4d76e9c5 |  | note | REFERENCE DOCUMENTS: Cl 173.03
label | fc036694-5669-5dd6-accd-3d2ec1dcd046 |  | note | – – – – – – – – –
label | bed484c5-93f3-5dc4-a74b-03575c25e458 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 3338e39e-0a17-51e1-a9b0-99ae43230d1a |  | note | – – – – – – – – –
label | a3405821-fb3c-5443-9cb6-f9391655e2fa |  | note | RECORD OF CONFORMITY: This ITP signed
label | a753ccde-0d00-5290-8576-584efd7bd44c |  | note | – – – – – – – – –
label | 6cfe7f72-8ae3-5db1-80ac-4a28bd4a509d |  | note | HP
label | 2cb6d9ff-e4a6-519e-ae5f-9c1f7c88f90b |  | note | – – – – – – – – –
label | 9502f7cb-01da-5096-be56-797e8a7076bc |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
label | 9536c61c-818d-512c-80d1-20c4c8b1b60e |  | note | – – – – – – – – –
text | f555efc5-fcf6-5f29-8a58-d8c6f9705637 |  | textbox | DATE:
holdpoint | 58de8ce6-375d-4cce-88ca-5d92eeb911d8 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 4f37429e-b84d-4ed0-a999-3a9044c28ba2 |  | checkpoint | 2.4 Curing and Protection of Compacted Layers
label | 43f517c4-e828-5ad6-ae67-56405bd248d7 |  | note | FREQUENCY: Each lot
label | 9e3853c8-e964-5bba-a586-5c0ccaee39c9 |  | note | – – – – – – – – –
label | dabe2a87-9192-5840-9188-2144ba4ea815 |  | note | ACCEPTANCE CRITERIA: The minimum compacted thickness shall be not less than 100 mm and the maximum compacted thickness shall be no more than 180 mm and constructed within the tolerances specified in Clause 306.03.
label | 6b8b9bac-6e5f-58a7-be1c-66de7e11bb82 |  | note | (a) Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified:
label | 175ee5f6-26e2-5d4c-ab74-5b117c9d9fff |  | note | • The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | 969da388-addb-5324-87fa-7d96ac4aa89b |  | note | • Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
label | 6381c4ed-46d5-5153-ab20-aa71b196249d |  | note | • The subbase shall be kept in good order and condition and free from contamination.
label | 071e5fac-2ced-5548-9aea-6d24072fe48e |  | note | – – – – – – – – –
label | ed15bc14-ef83-53fb-8449-5732c33b432d |  | note | REFERENCE DOCUMENTS: Cl 306.11
label | a8c7a009-dc1c-56d5-bdc2-8a0e046cd092 |  | note | – – – – – – – – –
label | e8a3e0ff-6ee0-5335-96e5-f6a21400e255 |  | note | INSPECTION/TEST METHOD: Verify
label | 521080dc-1685-50e3-a4fe-a8f6a92a6893 |  | note | – – – – – – – – –
label | 03d6ac65-4260-5d45-8be9-fb35c61b8af1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | a2f3fb1e-ecfe-519f-8022-6116528afa9a |  | note | – – – – – – – – –
label | 42188607-80c7-5c4f-ba99-ce86b08a4422 |  | note | HP*
label | 2dfe25b5-1a8b-5462-b260-c087d14a2528 |  | note | – – – – – – – – –
label | 59407a61-4027-5921-b396-1a52e941825e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 25b111cb-4a3c-540d-8e67-256eb27e8763 |  | note | – – – – – – – – –
text | 6b655267-2543-5fd3-9781-190347958541 |  | textbox | DATE:
checkpoint-status | af4cc265-6a11-4967-a855-259d0128f994 |  | checkpoint | 2.7 Delivery Dockets
label | 13c02834-2637-5b80-aeb6-1109a0eb3f4d |  | note | FREQUENCY: Each Day
label | 23a3195a-fab2-5ea5-91dc-b9969590f678 |  | note | – – – – – – – – –
label | 91de1c8b-57e2-5c36-a811-350ff09956b0 |  | note | ACCEPTANCE CRITERIA: FH shall make delivery dockets available for inspection on request
label | 4a22894d-f25b-5799-ad9a-4df8fad09d59 |  | note | – – – – – – – – –
label | c0fc9ccd-df94-5af6-816a-1ef6ddbf8eeb |  | note | REFERENCE DOCUMENTS: Cl 306.07
label | f8798c04-54bc-5351-b1a6-fd0a0c3709e3 |  | note | – – – – – – – – –
label | bae78c57-34be-50e6-8dcd-edc2ed9acb88 |  | note | INSPECTION/TEST METHOD: Delivery Docket Submission
label | 233df27b-a660-5da8-8076-5bd02c8bc19d |  | note | – – – – – – – – –
label | 48152f9f-6805-5603-914a-7c1ed4affd00 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 76ff9429-b415-505e-a8fe-165853f861ef |  | note | – – – – – – – – –
label | 96283044-fdbb-57c3-b573-ffe9a008bb7e |  | note | HP*
label | 7bdbc0e2-e29e-54c6-8486-c7bf2d7af6ea |  | note | – – – – – – – – –
label | 47587523-929d-5bc0-a39c-2e77fb0fdb9b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | ae28fd9f-f474-52aa-b7ae-d3524aba34e1 |  | note | – – – – – – – – –
text | aeb0a879-a17a-525d-ae4f-991b8e4405c2 |  | textbox | DATE:
checkpoint-status | b9ba2284-8753-4666-9b02-d2f9b339c65a |  | checkpoint | Final Inspection
label | b13ff992-c563-53f0-9c97-890ac5dfb93e |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | bd8fdd8f-581e-59a4-b0fb-d635b8960d59 |  | textbox | Print Name:
text | bfb6ede0-b01d-522e-8752-0a0725966470 |  | textbox | Position:
text | 1b865c10-f3c2-509d-af93-fa1b2c97dd2e |  | textbox | Date:
checklist-sectioned | 7908328e-0e2f-4736-80a4-b671ab3b92eb |  | checklist | FHC-ITP-004 - Type A Fill Placement Rev3 | itp |  |  |  | Yes | FHC-ITP-004 - Type A Fill Placement Rev3 | d9377644-fc02-409e-962f-d8cb24bff5f6
checkpoint-group | 431bf8ae-8b5e-4761-9953-7eddaae8a31a |  | section | 1 - Preliminary Works
checkpoint-status | 11ba19c9-d5b2-4ed6-9660-b3d0396adfb2 |  | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
label | a5d984a3-055c-5c59-ad7e-dcc98ce305dd |  | note | FREQUENCY: Prior to commencing
label | b72a8410-09cc-5339-a486-f1d7212940b9 |  | note | – – – – – – – – –
label | d8b0a033-044a-5b5e-9dc9-7562538e2617 |  | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
label | 65331b8a-63b1-5838-956c-636dc6a3903a |  | note | – – – – – – – – –
label | d8590672-aa25-588c-aa25-c1ee1067ba63 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 390a8059-8e40-553e-987d-0055551feba8 |  | note | – – – – – – – – –
label | 545b32f7-887f-5405-86db-e1d2bda9568a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ea397fb5-40d6-5b7a-9f92-82bbb1db4a58 |  | note | – – – – – – – – –
label | 68efd504-d2f1-5d90-8731-a2dab91e52e3 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 07c5d6d5-175e-5d2e-bd69-3a9da222d095 |  | note | – – – – – – – – –
label | 6c5ea600-01d1-5531-9708-e0e0b6bce51f |  | note | HP*
label | aa24835f-a2e2-5729-8be1-01323de8d5c0 |  | note | – – – – – – – – –
label | 66ed8394-6682-5d44-9777-f6b1a028c321 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 73c0e2a9-62d0-564b-be47-c6675c4c2675 |  | note | – – – – – – – – –
text | 7abaafa3-a653-551d-9fa3-00bdf9c3a2db |  | textbox | DATE:
checkpoint-status | de7a129c-f72d-40fc-9392-e573f65b1249 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 188e31b4-d164-5fca-9384-9b3e1e810508 |  | note | FREQUENCY: Prior to Placement/ Each Lot
label | 4c66d80c-6227-5939-b93a-3248adc06228 |  | note | – – – – – – – – –
label | e775797e-4faf-552e-8277-385281f1c81f |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 26b0238e-6ac7-5b9f-9629-44d50ebdaf4c |  | note | – – – – – – – – –
label | 2dfd52b7-7caf-58e4-b441-21bad67e3f8e |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | a588543d-3278-5b40-8523-7dee2871b3b9 |  | note | – – – – – – – – –
label | 2dc65420-9104-5e87-a9cd-230e42c759c4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2ff98e0e-16cd-5527-9bc7-23c78cc3f7b8 |  | note | – – – – – – – – –
label | 1de2a81a-2d0d-5fdb-9a1c-e077c6d166a5 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 19172f25-869d-5c3e-b5ae-7a3cd034904c |  | note | – – – – – – – – –
label | bd1d62e3-d257-59f6-95ab-af796fe4a9f7 |  | note | HP*
label | ff1bb1a3-7fa6-512a-af32-000d2e4dccd2 |  | note | – – – – – – – – –
label | 59bfd478-5da3-5380-8555-798dfd90f5ef |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 550bcc31-5a75-5743-86bf-23352e88c06f |  | note | – – – – – – – – –
text | 316c9fa2-2544-58d7-8701-8eb9a2e20407 |  | textbox | DATE:
checkpoint-status | 59d67d60-94c8-4050-af82-f586bc258489 |  | checkpoint | 1.3 Verify Material
label | 360dbaf4-a2ea-5e62-8af3-12284b462ea6 |  | note | FREQUENCY: Prior to Placement
label | aa2294b3-c2d7-56e0-b64a-47305cbd22c9 |  | note | – – – – – – – – –
label | 131f6684-6e84-526f-9a13-304664a65995 |  | note | ACCEPTANCE CRITERIA: Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive.
label | acf0e6db-dc53-5f53-8ff7-04fa8cf7caa3 |  | note | • Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075.
label | 1590e629-0a2e-5f4c-aa2b-716b359b5505 |  | note | • PI between 6 and 25.
label | e137146c-c9f3-53ee-82c9-62adf4853e27 |  | note | • Permeability of less than 5X10^-9 for capping and verge material
label | ffe02c39-dc10-52e0-b833-a3f9d4ed4d92 |  | note | – – – – – – – – –
label | 0ac76d29-082b-537f-8a4c-f3676943d81c |  | note | REFERENCE DOCUMENTS: VicRoads Spec.
label | 668e793d-1716-547f-b1e4-dc94c72828ec |  | note | • Cl. 204.04(b)
label | c9f8a244-46c1-5ef3-86ed-dd770e582140 |  | note | • Cl. 204.06(c)
label | 118e1398-637d-5c52-9100-ed83abe0a655 |  | note | • Table 204.041
label | 252ab28b-83d3-5aed-874e-441d7c43890c |  | note | • Table 3020.052
label | abdfb2e5-6f2e-5ffb-abc8-ea00107fae39 |  | note | – – – – – – – – –
label | 9faf5524-5626-5467-8e0c-0666c8cd5db9 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 5f636c6c-3f17-5d21-8b2f-5b6558558036 |  | note | – – – – – – – – –
label | 3cf5f29f-f7b7-5f53-bce8-b2f2851464a1 |  | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
label | 01a53044-5059-585d-8415-26fd4914540a |  | note | – – – – – – – – –
label | de1c00e7-d72f-56fb-912b-4bc00adec6af |  | note | HP
label | 00109d07-27ff-5c8f-a644-e45c51cfc3fb |  | note | – – – – – – – – –
label | 5ffb24d6-ccf5-55a0-9af3-b472deef79c6 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
label | 9d7d1a68-ef30-5825-aa5a-d08ad0547148 |  | note | – – – – – – – – –
text | 98f0ed82-dca3-5b59-a5b9-b84b57260364 |  | textbox | DATE:
holdpoint | 39a0fcc7-d22e-42df-86df-d6c1b48e04e3 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 34c59c6f-7878-43e8-aeae-13664de23dc3 |  | checkpoint | 1.4 Excavation Permit
label | a036bb37-8543-54ad-b929-2a3861a28c53 |  | note | FREQUENCY: Each lot
label | e3212340-6e3b-509d-a490-779b9490fb51 |  | note | – – – – – – – – –
label | 42d78d78-616f-5ca2-9e41-3b7bf5d6e04b |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
label | cfb02939-cd01-50cb-be88-432032b47d3d |  | note | • Plant and equipment shall be appropriate for the task.
label | ef355372-6e58-53ad-a009-dff1ac54d3ef |  | note | • Excavation operations shall not disturb areas outside the limit of excavation
label | 789bbef9-420e-52f9-b794-3bf558d6dc01 |  | note | – – – – – – – – –
label | 6116af6b-e20c-5f77-909b-fc17baefe07c |  | note | REFERENCE DOCUMENTS: Excavation permit
label | d1261487-2e73-51bf-a0c1-d1a240ea2512 |  | note | – – – – – – – – –
label | 5d5e24c1-7cdf-54ef-b783-fa601fa506f6 |  | note | INSPECTION/TEST METHOD: Verify
label | 4d64d6ce-7bd0-5424-bbd4-9ac7d127e924 |  | note | – – – – – – – – –
label | 4775e948-1e29-554f-8636-aa03ced7a824 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | feb822f0-c3a4-5ef3-9420-3da9f61b5af5 |  | note | – – – – – – – – –
label | 32dfca65-1ce2-5ec4-aedb-34351a88c54f |  | note | HP*
label | df33f347-40f3-5689-98cd-60dc8867b32d |  | note | – – – – – – – – –
label | d074842a-c910-5d3d-9460-6e3405d55b9f |  | note | RESPONSIBILITY: Site Engineer
label | 184ef280-beae-5b4b-9fb8-de9be8b48530 |  | note | – – – – – – – – –
text | c23ed124-aa07-5d1f-983c-fbf7960cb1f1 |  | textbox | DATE:
checkpoint-group | 073cdcb3-b5d7-4098-9267-05dea677487e |  | section | 2 - Construction Works
checkpoint-status | 0f1335cd-916c-44b9-9bf4-07ac9f19206b |  | checkpoint | 2.1 Survey set-out
label | 405d64e4-8cc9-58eb-9b48-63bf6fb7a10f |  | note | FREQUENCY: Prior to Commencing Excavation
label | 9b112375-e3b3-5331-9f13-33d098553124 |  | note | – – – – – – – – –
label | c7d33b89-78fb-5268-adff-0aecc9e17a2b |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.
label | 1952a017-3595-5fcd-85ac-db5390bb831c |  | note | • The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
label | 05958f6d-886d-5d81-8948-4c7528b636d0 |  | note | • IFC and latest available revision used
label | 2e4bf5ef-816b-58a6-9143-8a1ffd8c3425 |  | note | – – – – – – – – –
label | 32681ae3-cbaa-5c90-bd20-314dba64f86b |  | note | REFERENCE DOCUMENTS: Latest IFC Drawings
label | 7e3d0118-bc49-5f67-95ca-a81593cca3e0 |  | note | – – – – – – – – –
label | cab212ba-bd7c-5200-b8d9-9e4e02ac5cb2 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | d9ba2db4-3ab1-5630-b998-b8b7393aebac |  | note | – – – – – – – – –
label | 61c36bc8-b90e-526f-af65-94f45b596bc9 |  | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | 82f42d1c-a695-5b77-9b7c-30dd1ceab81f |  | note | – – – – – – – – –
label | 400701fd-a31c-5da1-aa4d-fd3f23e080ee |  | note | SCP
label | 7e59273f-7356-54ef-b1db-b0693f16ac1f |  | note | – – – – – – – – –
label | 9c3ae920-7207-530c-b12b-9b85d31b58b9 |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | dcd156e4-e97c-5a41-8a50-a9f781023035 |  | note | – – – – – – – – –
text | 00e2257b-8581-5ef7-a826-d91a03dd8eb2 |  | textbox | DATE:
checkpoint-status | eedd5ac2-c9dc-4881-8fdc-dc356939133c |  | checkpoint | 2.2 Inspection of fill area
label | 70f2d44d-c7d9-5681-88f1-696d8ac0ee9c |  | note | FREQUENCY: Each lot
label | 27db335b-1fe5-5870-85dc-7d1970bb1689 |  | note | – – – – – – – – –
label | 5e8956e8-c246-56b1-8b75-a95e94595978 |  | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | f927b01c-0694-5ed9-95f3-66c9525a0e40 |  | note | – – – – – – – – –
label | 3070b12b-580f-5c4b-a29b-adc5edd98e4d |  | note | REFERENCE DOCUMENTS: 204.10 (b)
label | 5a4bcebc-edfe-54d1-8042-57abc7435f1b |  | note | – – – – – – – – –
label | 785d42c4-d6a2-5b70-9e7c-0749ae8d8d32 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 91a7649c-18f8-5341-a3f9-fa73ba471b5e |  | note | – – – – – – – – –
label | 48bf541c-f1d9-5823-82b3-2338f8d8a4c9 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 3ab8da62-83a1-50a7-a8e5-37e883571fed |  | note | – – – – – – – – –
label | 13c51497-7803-5e2e-9b1d-a03055cb4300 |  | note | HP
label | d5296611-f9c9-5ffa-91f4-4c89216f72ff |  | note | – – – – – – – – –
label | 943da16a-dce2-53d6-9afb-ff0d84039559 |  | note | RESPONSIBILITY: Site Engineer / Superintendent
label | eaa8a684-5b31-52eb-b863-0b4d27778c16 |  | note | – – – – – – – – –
text | 08d4b911-ceba-5cf8-925e-5ea752df1463 |  | textbox | DATE:
holdpoint | d3fed012-d43c-415b-a0c1-df08a28b6b61 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 39bd98a4-9376-404b-8637-a9695100a222 |  | checkpoint | 2.3 Layer Thickness
label | c94dc0a6-9891-5e62-8827-9768d7990ad0 |  | note | FREQUENCY: During Excavation
label | 9e6b9eb1-1a53-5a9f-8ae2-7e900a198e2d |  | note | – – – – – – – – –
label | a7f48170-c7f6-5a57-ac8d-83d28f5c2a8a |  | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
label | 9cf52854-af0a-5ba4-935d-9428fe6c7d16 |  | note | – – – – – – – – –
label | 01b6ecd4-d0fe-56ec-8136-8ddeb5575ba1 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
label | b1d78a89-2aa4-5cbd-a657-3a7f1d7bbf3e |  | note | – – – – – – – – –
label | 7260fdba-8bf5-5e83-875b-d9ae812e3548 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3225f008-d761-50aa-898f-609c7991c6c0 |  | note | – – – – – – – – –
label | 3a00f733-c860-539e-a988-cf51abe83d28 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | e60d1462-00a0-5382-bcb6-a7429375b53e |  | note | – – – – – – – – –
label | 6e11f1a1-df90-57a8-b25a-461b4f5f3e4e |  | note | IP
label | 423012e0-f566-501f-9da2-f4bc5380cdc1 |  | note | – – – – – – – – –
label | fc52bb37-5bc1-5ffe-b2b0-bbe3f631fcb6 |  | note | RESPONSIBILITY: Site Engineer
label | 9a61d89a-5f76-52f5-86ab-18a19a8f9a25 |  | note | – – – – – – – – –
text | a29eb0a0-bde9-54ec-ac8b-212b1a865853 |  | textbox | DATE:
checkpoint-status | 3293d6dd-33df-4a8a-9f47-8905014e66ec |  | checkpoint | 2.4 Maximum Lot Size
label | 7627cf40-8985-5a0d-b20e-e86ba6939a21 |  | note | FREQUENCY: During Excavation
label | d6ad636a-b340-5507-af30-dad53ea32d5c |  | note | – – – – – – – – –
label | f7c701aa-eea9-5196-9e8b-c8911b50449c |  | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
label | dd72db3b-6293-50d9-a2cc-7a0371d852fd |  | note | – – – – – – – – –
label | 32e44b07-aaaa-5f48-90b2-6f295504a831 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
label | 1052fb51-94cb-52f5-a0ff-4a2322f9acd6 |  | note | – – – – – – – – –
label | a6d9fea1-ac8f-5f94-b0f1-36fa1cd72366 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 12ccb617-01f6-5b24-8f00-4afc01e4a01e |  | note | – – – – – – – – –
label | ce715f33-02ec-5a84-80c4-03368c46dd5c |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 69506b92-0556-52b3-850d-926b5db81106 |  | note | – – – – – – – – –
label | 3d551a10-ba41-5b79-a0bd-0aaa2eb6854f |  | note | IP
label | e36e65f7-55df-5e21-b4c8-ba8b8b5c6cb9 |  | note | – – – – – – – – –
label | 92fbb73b-4395-5e32-af13-94caffa7d275 |  | note | RESPONSIBILITY: Site Engineer
label | 6ca987c7-b5fa-5424-865e-ece8912deaad |  | note | – – – – – – – – –
text | d5094d01-cc90-5fa5-a4ba-e277fc9a3e82 |  | textbox | DATE:
checkpoint-status | 0cbb0431-2e97-48b5-aeb7-54ee04994a07 |  | checkpoint | 2.6 Proof Roll
label | f5f5173d-2889-5408-aeb7-1f99345f0bb6 |  | note | FREQUENCY: Prior to placement
label | 273c1189-7a30-5f11-b039-33dfc46cd62c |  | note | – – – – – – – – –
label | e041c4f2-6b04-59fc-9e01-8c070b38940c |  | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | e259f7be-a462-591c-b8a4-e1e2e09bc7ef |  | note | – – – – – – – – –
label | 81707c3e-4258-52a2-8004-8411a62d7564 |  | note | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
label | 0c286b70-8d5d-58e4-977d-b2967b977108 |  | note | – – – – – – – – –
label | dc9ee3f8-4a81-59e6-a8a9-3b6453441fd3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cc449278-2f30-52d2-8bce-e709c68138f0 |  | note | – – – – – – – – –
label | 406db1ce-9409-581f-9006-68bb0ad1b79d |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 1b874194-e55f-5dd8-9ed2-ffff77092fe6 |  | note | – – – – – – – – –
label | a9875015-f6ea-5c8c-99cb-aa28a286402d |  | note | WP
label | 6d5fef45-5a8e-5e2e-b75a-a41166429389 |  | note | – – – – – – – – –
label | 7caad16e-c76e-56ff-a4f1-71d642717241 |  | note | RESPONSIBILITY: Site Foreman/ Superintendent
label | 41d2031a-34d7-53eb-bf3f-a01c4d0d99da |  | note | – – – – – – – – –
text | 3503e15c-b42f-554c-9793-f2129e1b83d4 |  | textbox | DATE:
checkpoint-status | b5dbf244-3210-44a5-83e8-5bf4b45c3b53 |  | checkpoint | 2.5 Type A Placement
label | baccd38a-09f2-5a58-955c-23ef8418c385 |  | note | FREQUENCY: Prior to Placement/ Each Lot
label | 9822642c-fe6c-5df8-8dd0-cc6887318796 |  | note | – – – – – – – – –
label | 626fef1e-b1bd-575a-8fb7-9be15ed852a6 |  | note | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas
label | 98cf967f-8b4d-5ed2-8ecb-fd07b681bdcb |  | note | • Any rocky material present must be uniform throughout the layer
label | 16b89026-64f6-5f38-8c31-96e5a0091987 |  | note | • Each layer shall be kept generally parallel to the surface of subgrade
label | bc6fd3c6-c4fd-54c2-bb03-7bdd85c92c14 |  | note | – – – – – – – – –
label | c944d022-5dfd-5b79-8412-a3f5ae9577c1 |  | note | REFERENCE DOCUMENTS: 204.10 (d) (i).
label | 2102a029-46d1-5fd0-a116-48dfa19b5711 |  | note | • 204.10 (d) (ii).
label | e3f861ab-52f2-57c4-a189-d3a4521c35af |  | note | • Table 3020.052
label | 0ca8b622-5826-5202-ac86-c964e2162d8f |  | note | – – – – – – – – –
label | 96c62f73-3698-5f7e-ae20-fb7fcba88ac3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 49b3628d-c16c-53fc-8cb6-d3c19dcb5e83 |  | note | – – – – – – – – –
label | 51174f80-005e-5d9e-a753-a96ce6d2950a |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | c41303d0-344a-5056-a35e-dd669399b279 |  | note | – – – – – – – – –
label | 926df8e7-a734-5883-8b6e-46ebd9b855c7 |  | note | IP
label | 31a71012-9edf-51f1-8dfe-3dde42d9e5ad |  | note | – – – – – – – – –
label | bb593c37-dd58-5ce3-8149-87d0217f72db |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 16814aec-523d-5a9c-a715-233f52dee38b |  | note | – – – – – – – – –
text | 2eca47d6-f822-57f0-9159-3961f213e584 |  | textbox | DATE:
checkpoint-group | 7c10b8c7-a7cd-4e81-8129-041aea4f3bbb |  | section | 3 - Testing
checkpoint-status | 47f970f7-b655-4b1f-8b8b-d386d7b1fd10 |  | checkpoint | 3.1 Reduced Test Frequency
label | b76b8684-8389-56d6-a23f-0f15e0892e7d |  | note | FREQUENCY: Each lot
label | a1adf6aa-d9c9-5365-aae0-6f1c4c7f0445 |  | note | – – – – – – – – –
label | f5b0c69c-5dca-5c9d-ab13-e6618548d296 |  | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification.
label | 5e3df8e3-c8f0-574d-aee1-d730efa7b0af |  | note | • Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
label | 7b3d6e1f-152c-5ca6-8016-ecee34221d71 |  | note | – – – – – – – – –
label | a381c329-4533-5b72-9464-d23ca6fb266b |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
label | d788af8c-1677-5eb9-a28e-1a6033472ed7 |  | note | – – – – – – – – –
label | 2f4ded4c-aee6-51f6-933f-6673724d9c50 |  | note | INSPECTION/TEST METHOD: Test Record
label | d755f229-0521-586d-8d4b-2c51ca355264 |  | note | – – – – – – – – –
label | 5d516ad2-775c-5572-8d08-d8103baf8b19 |  | note | RECORD OF CONFORMITY: Test Records
label | 6fc46445-f0a4-58df-8e20-87887a77d3d6 |  | note | – – – – – – – – –
label | 898dba1d-9c9c-5b36-b733-0daf83de3e99 |  | note | AP
label | a909e1e4-a2db-528b-a815-40142eaf19a1 |  | note | – – – – – – – – –
label | b074ec8e-1719-5135-b595-a31ceb6e89d3 |  | note | RESPONSIBILITY: Project Engineer
label | 58b35b13-3d53-5baf-a7b2-299b41cf2e95 |  | note | – – – – – – – – –
text | 59f5f27d-c2d3-5e04-822c-2df3c93101d3 |  | textbox | DATE:
checkpoint-status | d2e77e5b-915d-491d-a803-d89bfca1e6fc |  | checkpoint | 3.2 Compaction Testing
label | 34b8dca0-3d82-5d25-827e-aac466b28b6c |  | note | FREQUENCY: Each Lot
label | cc0c388f-97bb-5812-9085-9122a3f4ddf1 |  | note | – – – – – – – – –
label | 016167bd-e535-5996-8a81-76711ca02120 |  | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
label | 8cf8541a-0d5a-5023-aa97-5321fb2ea2fe |  | note | – – – – – – – – –
label | cabacc4b-c376-5762-97b6-f7249f163f0b |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
label | bd5bc083-f331-5b43-843e-6ca71c5d694c |  | note | – – – – – – – – –
label | b1249d16-33c4-52ce-9021-1e2764eb9e4a |  | note | INSPECTION/TEST METHOD: Verify
label | 147874e1-c97e-5e6a-82fc-b8d7fd80adb6 |  | note | – – – – – – – – –
label | 2efe2800-4029-557e-bf04-30957ac5eab8 |  | note | RECORD OF CONFORMITY: Compaction Test Records
label | a54752ca-1c4b-5d34-96f9-c688303ee119 |  | note | – – – – – – – – –
label | 8e601248-cc82-5aaa-99a0-3ebb8fbe4e5e |  | note | TP
label | 3f069e00-8a0f-53fa-9b40-37dcaffb9890 |  | note | – – – – – – – – –
label | 69c2bd25-c0ca-568c-8235-628e93f0dbc3 |  | note | RESPONSIBILITY: Site Engineer
label | 5ce7837b-77cb-573c-bda4-047967186d70 |  | note | – – – – – – – – –
text | 33f2703c-a8ad-5d90-bad7-90ae6385832d |  | textbox | DATE:
checkpoint-status | eda59a64-b0dc-420d-a622-4148e1002206 |  | checkpoint | 3.3 Compaction Testing (Small Lots)
label | d40b3b82-e546-53de-bb2a-a7865beca63e |  | note | FREQUENCY: Each Lot
label | fc61565c-18f9-51cb-9ee0-2772147f6391 |  | note | – – – – – – – – –
label | 1da5a5a4-f556-5a4e-8c96-2adddb050e0c |  | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area.
label | 70dd7402-7a24-5b5b-a31e-96a1405cdb11 |  | note | • Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
label | 1b8513dd-c541-5db3-832f-5c435b792a09 |  | note | – – – – – – – – –
label | 3bcf6f7d-522b-5d2c-b888-d88ebf6e17f3 |  | note | REFERENCE DOCUMENTS: 173.04 d
label | 5bd8e39e-2a7a-52d8-a0c0-7e2760809aa9 |  | note | – – – – – – – – –
label | a2669df0-746f-5280-8c79-05feb5f08c1c |  | note | INSPECTION/TEST METHOD: Test Point
label | b53222d9-066e-5712-a23d-9ae0571c047d |  | note | – – – – – – – – –
label | 1f35a184-c926-5f53-bf39-0be54c89e6f9 |  | note | RECORD OF CONFORMITY: Test Records, Lot Register
label | 60cf7281-3877-5504-ba62-8ef2daaf0c8f |  | note | – – – – – – – – –
label | 695b498f-caa4-5353-9987-c564204545d3 |  | note | TP
label | 69f5281c-e197-5ac3-b53e-452b85d24f36 |  | note | – – – – – – – – –
label | 4df51fe2-cbf0-536e-a8f8-95deafe59b33 |  | note | RESPONSIBILITY: N/A
label | 3544dd08-3c89-5e94-89e2-5a431a6e043c |  | note | – – – – – – – – –
text | 703e2e79-d29a-5d87-8070-c470eba82fe9 |  | textbox | DATE:
checkpoint-status | 2bda3e0f-2cec-49dd-b54f-88d3f8952429 |  | checkpoint | 3.4 Maximum Particle Size
label | 63e12a72-e649-5a20-9e72-7a2dd7ffa80f |  | note | FREQUENCY: Each lot, unless reduced frequency has been approved
label | 59a39622-9dfc-57c7-aa0d-3152efb3811b |  | note | – – – – – – – – –
label | 42c88ed2-69ab-50b6-b525-d87fe7aa5621 |  | note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
label | bb9a22d8-8504-50e3-81cc-a9c6d32a8d3f |  | note | – – – – – – – – –
label | 5e8e6655-38ef-5ede-9f4f-436b23bea74e |  | note | REFERENCE DOCUMENTS: VicRoads Spec.
label | 3877c5c5-8bb3-5c9d-a4a9-4c466cf1610b |  | note | • Cl. 204.14(a)(ii)
label | 24591524-427b-5e04-a3b7-cda869363014 |  | note | • Table 204.141
label | 937e84c1-6102-55a5-838f-1d34271b49c3 |  | note | • Table 204.041
label | 9199d250-499c-5639-b2e8-5b69c692a63c |  | note | – – – – – – – – –
label | ba105dcc-a105-5c9f-a95a-cf9f2f7eb250 |  | note | INSPECTION/TEST METHOD: Verify
label | f193146a-4b89-542c-a479-c288ce947625 |  | note | – – – – – – – – –
label | 27e141e8-ed65-546c-b016-85d5a71aba52 |  | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
label | 392a8de1-61b5-5d37-ad6b-60b7b4b6f28a |  | note | – – – – – – – – –
label | 95608c26-11b7-5dc2-a881-9c5b7b8ced78 |  | note | TP
label | a10cd1eb-4405-5df9-b2c0-cbfbc1d633ee |  | note | – – – – – – – – –
label | ad75e59d-a215-533f-bec0-8b6c9d42f0fe |  | note | RESPONSIBILITY: Site Engineer
label | 84c862db-e64a-5435-ac51-5944491aef95 |  | note | – – – – – – – – –
text | 5ac2414c-bab4-5544-bcf3-f873d6a73453 |  | textbox | DATE:
checkpoint-status | a626e672-bed0-48d8-b1ea-dfc1437a973f |  | checkpoint | 3.5 CBR/Swell
label | 7aa28b18-d0f1-585f-a300-eba2ec582170 |  | note | FREQUENCY: First lot only
label | 9ce889d5-9c73-5f0f-858e-171e65650a02 |  | note | – – – – – – – – –
label | ef1092c5-fa08-5d20-b32f-e5cd587f1dc5 |  | note | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
label | cfb8dd18-bb78-5168-a844-8b5d3ffbc3c6 |  | note | – – – – – – – – –
label | c4ed3d97-91c1-5c32-9412-0d7ed4c40169 |  | note | REFERENCE DOCUMENTS: VicRoads Spec.
label | f06c8b40-3cc0-5d0b-8e8f-cfffcb1c48da |  | note | • Cl. 204.14(a)(i)
label | 55e11b60-645f-5ec5-a823-17d216a471a9 |  | note | • Table 204.141
label | 2ae743f7-354d-56ce-ab26-37a4f616df44 |  | note | • Table 204.041
label | 2a69ac20-ed4b-542a-8cb7-66731a50afde |  | note | – – – – – – – – –
label | 40e53466-06fb-53cd-ac70-f519eec58fda |  | note | INSPECTION/TEST METHOD: Verify
label | 0cc63b15-9ca5-52bf-9b4a-e94d6dd075ec |  | note | – – – – – – – – –
label | f4c44e8d-05b9-5a54-b55c-727b9228f8b4 |  | note | RECORD OF CONFORMITY: CBR/Swell Test Records
label | c78fbe88-37ba-57a5-8b48-0c857dd74d96 |  | note | – – – – – – – – –
label | ea11a43e-34db-5e6f-bae4-5d7d948301dd |  | note | TP
label | 92ec4b20-d201-5153-b9bc-18de432ca718 |  | note | – – – – – – – – –
label | 11a34e10-d87e-5002-bf4d-59cd506edbf4 |  | note | RESPONSIBILITY: Site Engineer
label | 3db4acb0-c4f3-5104-84a0-22384077e532 |  | note | – – – – – – – – –
text | 35a528b2-a812-5862-8e0d-b2caddfbec2b |  | textbox | DATE:
checkpoint-status | adb4be59-5a4d-4ec2-91f9-5fcdeeb5487c |  | checkpoint | 3.6 Atterberg Limit Tests
label | c71d3c19-07c3-514a-a737-4d39204a9e88 |  | note | FREQUENCY: Each lot, unless reduced frequency has been approved
label | 8b216a2c-6817-5c37-af92-953025766e40 |  | note | – – – – – – – – –
label | d4e31369-1c81-5dd9-b679-2ca0fc32dd58 |  | note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
label | 7c1f5cfb-d0a4-5b8a-909c-e47adeaecf5c |  | note | – – – – – – – – –
label | 3dda9ae7-ebb8-5c6a-b29d-5f94f310677c |  | note | REFERENCE DOCUMENTS: VicRoads Spec.
label | 0c7b9faf-9357-5f2f-bcc2-da98431b60af |  | note | • Cl. 204.14(a)(ii) Table 204.141
label | 6e6cc2a6-8704-5ae8-ad88-d0193c9ee955 |  | note | • Table 204.041
label | 10be0a9a-11c9-55ae-b7c2-e77fd498e17f |  | note | – – – – – – – – –
label | 83c9c539-31ea-5def-89f4-f5ac5808de94 |  | note | INSPECTION/TEST METHOD: Verify
label | 89cafd74-9376-5652-9e6a-82e9f7ed475d |  | note | – – – – – – – – –
label | 3221b150-deb6-52d7-928a-e54b0027bb7b |  | note | RECORD OF CONFORMITY: PI Test Records
label | 4627dc18-2950-5ff3-b5ca-5ad3cf6acd55 |  | note | – – – – – – – – –
label | 4ebe6c9c-e150-5348-8521-6b94d75c4ea3 |  | note | TP
label | d7f23613-21da-560c-9902-1f1ffc4508ed |  | note | – – – – – – – – –
label | 58b74fb7-4125-5f15-82cc-6cff265c2552 |  | note | RESPONSIBILITY: Site Engineer
label | 161eb127-b67e-563f-8716-7a4dc966a457 |  | note | – – – – – – – – –
text | d09465f4-d74a-50be-bc83-f73dda66e6af |  | textbox | DATE:
checkpoint-status | a2d8fae4-d61c-4658-bd32-6ba48a8fb543 |  | checkpoint | 3.7 Permeability
label | 967a1872-2905-51e4-b547-bb7f0c3233da |  | note | FREQUENCY: Each lot, unless reduced frequency has been approved
label | b50811ec-db71-578d-8302-f003d821b878 |  | note | – – – – – – – – –
label | 30ec0572-0d00-5908-a18c-a36de44b515d |  | note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
label | ceb33ab4-3910-5c36-8a50-060b1e24b839 |  | note | – – – – – – – – –
label | bf9288c2-a84d-5bf1-994b-42ef67190570 |  | note | REFERENCE DOCUMENTS: VicRoads Spec.
label | 0f43eb50-0ad6-5049-8878-b8cdfa34a30a |  | note | • Cl. 204.14(a)(ii) Table 204.141
label | 5cf125d3-4e8e-5d6a-95a2-ef225f61bbd6 |  | note | • Table 204.041
label | c4c5aac7-6b79-54b2-93cd-ff1a1f27bc4d |  | note | – – – – – – – – –
label | 75e93510-668c-5fcb-b59f-b995db9c6b2f |  | note | INSPECTION/TEST METHOD: Verify
label | 2337c4aa-2b85-5503-845c-1a8187e3ade4 |  | note | – – – – – – – – –
label | d4fc7209-fd33-5528-9c72-e78cb964d75b |  | note | RECORD OF CONFORMITY: Permeability Test Records
label | 958c1dc3-dc8d-5f86-8ab2-2b914d3b664e |  | note | – – – – – – – – –
label | 788995cd-e228-5f1e-92e6-17d534340e8d |  | note | TP
label | 73394e22-dedd-5fe7-a82a-6edf97bc1912 |  | note | – – – – – – – – –
label | 35c26bf9-2809-5af0-9f27-043714bbd4ae |  | note | RESPONSIBILITY: Site Engineer
label | a7131f0b-fd46-5ea3-a44e-8d98f04feec1 |  | note | – – – – – – – – –
text | 3d6413ce-9322-5704-8d60-7ce7675ee521 |  | textbox | DATE:
checkpoint-status | ec378261-bd4d-4480-bf7f-327d1d16caf2 |  | checkpoint | 3.8 Material Property Testing (Scale B)
label | 19f9be2f-036d-5c6a-8895-c2f66bb288b8 |  | note | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ede01663-439b-5dc7-a310-bd8ffaf9aa0d |  | note | – – – – – – – – –
label | 7d2f5666-12fa-56a8-bdad-830cff375b56 |  | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
label | 1fac2e8f-b651-5f5e-a7a8-d07c79250910 |  | note | – – – – – – – – –
label | 5b4dbad6-a72f-579c-b111-af2326c865ce |  | note | REFERENCE DOCUMENTS: Cl 204.04, Cl204.14
label | 6e1e347f-1ba3-5a84-8445-b23eae5889e4 |  | note | – – – – – – – – –
label | 945c8c06-c7dc-5968-828d-d0f0fe657c13 |  | note | INSPECTION/TEST METHOD: Verify
label | 15c5f004-4afa-5b7e-ae21-27fd06f4024d |  | note | – – – – – – – – –
label | 7117cb4b-04e7-581c-9096-147b6e599aef |  | note | RECORD OF CONFORMITY: NATA test report
label | 4a749088-88c4-58ea-9160-32b212a79493 |  | note | – – – – – – – – –
label | 2388df8c-7543-5f18-876d-6ff197c83e32 |  | note | TP
label | 07fa3398-d1e2-5273-9546-638635d33f79 |  | note | – – – – – – – – –
label | f1049b43-3218-5cf7-9b48-93f60e4fbeac |  | note | RESPONSIBILITY: Site Engineer
label | dd748573-4f69-5af9-ab7d-fd1d0f977f22 |  | note | – – – – – – – – –
text | 912db884-e931-5b12-896d-b7a1a49d6baf |  | textbox | DATE:
checkpoint-status | 1a34e863-c5eb-4e49-9ca2-992ed2696136 |  | checkpoint | 3.9 Survey Conformance
label | 1f45b53b-73f5-5740-8857-6c822944110d |  | note | FREQUENCY: Each lot
label | 453cc4d3-d630-5264-9091-2478b0faa4a5 |  | note | – – – – – – – – –
label | e884e892-5461-57a4-b621-a20331fbfa37 |  | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
label | 263d3854-2b10-5efd-af9e-f4cc9b324fd3 |  | note | • Scale B: Range x = +5,-25
label | b4b972cb-5c61-5c5c-976c-6b4cf1fff429 |  | note | • Max S = 15mm
label | e2d9c394-0fb7-5b50-a651-35351db6e307 |  | note | • 40 measurements per lot
label | f0d40df4-8b63-5f73-840c-db5fa453275b |  | note | – – – – – – – – –
label | 4173ee7b-7f34-57ce-9805-f0371ad379bc |  | note | REFERENCE DOCUMENTS: 204.03
label | 5177530f-3579-56ce-8aa9-80d9d1abfda5 |  | note | – – – – – – – – –
label | 09549b90-b2e0-5acb-bdfe-c92623f0abd3 |  | note | INSPECTION/TEST METHOD: Survey conformance point
label | 8eff97a8-cb55-5a8c-9ca2-678edd8e2bf1 |  | note | – – – – – – – – –
label | df718ebd-c036-524f-b777-0f340e6428ac |  | note | RECORD OF CONFORMITY: Survey report, Lot Register
label | d30ab738-e895-52b3-9eca-3a434fc59d3f |  | note | – – – – – – – – –
label | e88974be-1f76-56b0-958b-1ebde4089467 |  | note | WP, SCP
label | c369c1bc-b529-5a0b-bd71-30ecfce930ae |  | note | – – – – – – – – –
label | 526418c4-ea17-59ac-8dbb-8538db298a99 |  | note | RESPONSIBILITY: Site Engineer & Surveyor
label | 864fd478-58a4-5626-aada-ba82bbecfe61 |  | note | – – – – – – – – –
text | 8cee7dbb-480b-5471-8051-bcde6e2c302a |  | textbox | DATE:
checkpoint-status | ea0511fa-5ce0-485b-863a-8039beddefc6 |  | checkpoint | Final Inspection
label | ceadcb2e-f3e3-5848-a285-85bf14bb5d9f |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | d354d5bf-6871-5303-b8e3-3cdf8e8387d9 |  | textbox | Print Name:
text | 879ed66a-695a-5f61-8f33-4de6bc622019 |  | textbox | Position:
text | d627fd09-06b8-5b11-8e5a-2fcebd7b5189 |  | textbox | Date:
checklist-sectioned | 6fb24073-4612-4e53-8bc1-d451785fe85e |  | checklist | FHC-ITP-009 - Profiling Rev1 | itp |  |  |  | Yes | FHC-ITP-009 - Profiling Rev1 | e5d0165e-3044-4b97-89cd-04699cbba583
checkpoint-group | 69f0293d-4635-46f1-8bcd-b93e795a0081 |  | section | 1 - Preliminary Works
checkpoint-status | f9462b4b-0c95-4003-b344-278d8cc6284a |  | checkpoint | 1.1 Check for correct documentation
label | 330e73e9-3a0a-50ff-858c-91fe2bee6161 |  | note | FREQUENCY: Prior to commencing any activity
label | 436a1692-04d7-514b-aa97-f748641d3dd5 |  | note | – – – – – – – – –
label | a674625f-1804-584b-81b1-e535203d77c3 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 7c9e3791-1683-5b53-a7eb-83f186e7ba13 |  | note | – using the correct and complete set of drawings
label | 1979f499-a2aa-5f44-992c-16b86bfc22bc |  | note | – all drawings are the latest revision
label | a7047f78-a862-55c4-9367-686c83872a10 |  | note | – – – – – – – – –
label | 4c3503d9-e137-5521-8477-f3a84e0a0541 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 2782aec6-348b-5982-b8d6-e9194016748d |  | note | – – – – – – – – –
label | d2678a9e-092e-5a54-b586-013b9df9d148 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | eed79a5e-b7b0-5510-9469-6f800aa581f2 |  | note | – – – – – – – – –
label | b3f175bf-4246-545c-94e5-d5c6aa772289 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8c5652af-818b-5997-abfe-259ec6e1d6fc |  | note | – – – – – – – – –
label | 689c0d58-134c-510a-92e3-219fce98e990 |  | note | HP*
label | da354b42-c5d2-5cc5-9d87-71a5ebf1709d |  | note | – – – – – – – – –
label | f8c18ddb-4cee-56ee-a5cc-be7d8ef4d949 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 50acbc34-65a2-5982-9895-9e62d6c3261a |  | note | – – – – – – – – –
text | db13739a-5f85-5f87-8a51-15071c2274d2 |  | textbox | DATE:
checkpoint-status | 6688f0da-5bc8-4378-b2aa-45fd4bda636b |  | checkpoint | 1.2 Implementation of all measures and controls
label | fd492931-8b69-5702-bb10-b6d3f1f9ff9f |  | note | FREQUENCY: Prior to commencing any activity
label | 43c62598-86ca-5b36-af4b-0ac1546fa700 |  | note | – – – – – – – – –
label | 2c953f87-ed6a-5589-bfdc-5b7b0b7d54a1 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 37a2b6d3-c77f-5670-a0aa-be21cc4d74e1 |  | note | – – – – – – – – –
label | 65b1cc13-2b72-5932-8ff8-11331e2d3115 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | bafe42c4-42e0-5c43-81bd-f7c6bbd2c5e6 |  | note | – – – – – – – – –
label | 7dcbf39d-4583-5078-bf75-aea6278732ee |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f44bd40c-d8f9-5d9d-a3c6-2824a2a43691 |  | note | – – – – – – – – –
label | 38a2886d-a5ee-5507-8c5e-9603771ca57a |  | note | RECORD OF CONFORMITY: This ITP signed
label | 68d113d1-6714-51b5-af9d-69a76dccb495 |  | note | – – – – – – – – –
label | 8424fa29-2e3b-5cb1-84ce-d73ed94d7e0b |  | note | HP*
label | f5c82f50-2d4c-5770-aec5-24d70a336dd3 |  | note | – – – – – – – – –
label | d51793c1-e4c0-5c61-91ff-ad596c823e92 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 1aab2079-fb1f-5b0a-8b4e-dadfade1b441 |  | note | – – – – – – – – –
text | 6e0fb8be-b955-5d8e-a28a-85459f78fd1a |  | textbox | DATE:
checkpoint-group | 85a8660c-2a3d-4dae-955f-21cbcb909db5 |  | section | 2 - Construction Works
checkpoint-status | 4796cf22-ed2e-479b-8402-8be986da596b |  | checkpoint | 2.1 Profiling Works
label | 1099a73f-f8df-5a38-b456-af924cb9adbd |  | note | FREQUENCY: Each lot
label | eba0cee0-e7d0-5506-a953-a07d6b08be97 |  | note | – – – – – – – – –
label | 6c9d8c5d-9bb8-56d7-bf59-1686505aab9c |  | note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
label | 858d2199-b576-502f-86b9-c025b58b442a |  | note | – – – – – – – – –
label | 51e73baf-4958-5d4c-a603-e5a2a92ba936 |  | note | REFERENCE DOCUMENTS: 402.02
label | d82fd3fc-1446-56fa-b540-8829ee591de1 |  | note | – – – – – – – – –
label | 03a36cac-941a-50dd-9233-843217778010 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9db6c544-741b-5b70-b096-d01eeb360802 |  | note | – – – – – – – – –
label | 55237a5a-a01f-5f2a-9590-e498f3b1588d |  | note | RECORD OF CONFORMITY: This ITP signed
label | 24d3cefc-3a5d-51b1-97b4-4064bf1bc704 |  | note | – – – – – – – – –
label | acf8bc04-837c-59dd-9974-62e065c22628 |  | note | WP
label | 0f631d12-de5d-5562-9fa2-e1ebd7459390 |  | note | – – – – – – – – –
label | cc6c07ec-fc6e-5def-b383-399fb119d95d |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | b0a12475-9c04-52c3-852b-ec3a1bc37242 |  | note | – – – – – – – – –
text | fcced668-bedd-5aab-be64-dd48b3cd6f59 |  | textbox | DATE:
checkpoint-status | 08cc5710-5798-4737-a485-566410dbcd6b |  | checkpoint | 2.2 Depth check
label | db73131a-0be9-5764-9b28-ebf5f40e02de |  | note | FREQUENCY: Each lot
label | 1d449daa-13fb-5891-a95e-85e3c4d6dcdf |  | note | – – – – – – – – –
label | d33f41aa-2c5f-52d2-8927-a9b8f5742cac |  | note | ACCEPTANCE CRITERIA: Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed.
label | b54af1ee-b7b9-56c4-96c4-5a4346687e81 |  | note | • After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
label | 947d74c8-86e6-5ac0-96a5-de021771c5dc |  | note | – – – – – – – – –
label | 7f3e3edd-d3bd-58b0-8e3d-fbd3cb058fb8 |  | note | REFERENCE DOCUMENTS: 402.02
label | 5cab79fa-8bf8-5d0a-a342-44a9ae256175 |  | note | – – – – – – – – –
label | c1d316b9-ebaf-5e6b-b6c1-454904832541 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 78316e38-f1e4-5d20-bb30-1d1f46f92978 |  | note | – – – – – – – – –
label | c889a62b-d843-5458-857b-78445d87db74 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ba7cece8-da6d-51db-8c46-49627d2b7762 |  | note | – – – – – – – – –
label | e6e23a33-4516-569c-ba72-078b17a3e2eb |  | note | WP
label | 3b6c6ef7-500c-568f-8fef-b837cd5ec4e4 |  | note | – – – – – – – – –
label | ab6ab7c4-9d09-5e5b-9fc0-3d280795ac92 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | 56d609fc-71c6-5bb0-a008-839e2e0fa4da |  | note | – – – – – – – – –
text | 2aaac270-526b-587a-9f17-bf3dc64525db |  | textbox | DATE:
checkpoint-status | 87c5738b-b219-4759-8f8e-8ba2a88535d9 |  | checkpoint | 2.3 Temporary ramping (longitudinal)
label | 95f9611a-2744-58e2-8751-5cea3490aeb8 |  | note | FREQUENCY: Longitudinal edges
label | 1b02d0c6-0376-5f01-a096-807c5d502735 |  | note | – – – – – – – – –
label | 126efb32-049a-54cf-a7fa-25ceb8cd99f6 |  | note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
label | 27ad8924-5830-5eb1-a8f6-b81a6a7c2ee4 |  | note | – – – – – – – – –
label | 183faba7-98d5-5681-ae9b-11d8b912a4df |  | note | REFERENCE DOCUMENTS: 402.05
label | 28911900-541a-52c8-9345-ca1f93526f81 |  | note | – – – – – – – – –
label | 8ca7c42a-678c-5826-b78a-5935d46f3a1d |  | note | INSPECTION/TEST METHOD: Verify
label | 3275999c-b207-5b94-8db7-4386c1871565 |  | note | – – – – – – – – –
label | d45150d0-3fd0-5c02-9989-ace3f297c87c |  | note | RECORD OF CONFORMITY: This ITP signed
label | f044c9f0-33b6-5e74-836f-677b035f0108 |  | note | – – – – – – – – –
label | dde62919-9e4b-517d-815e-a75689870931 |  | note | WP
label | a36f7cbf-b241-5396-be5a-1355b16c8575 |  | note | – – – – – – – – –
label | 862610d9-fcca-5856-bbb3-db31c453d37c |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | 82ac1268-8993-5f39-b71e-7c53384916c8 |  | note | – – – – – – – – –
text | 65ba2c93-b804-5988-8231-614cecfff502 |  | textbox | DATE:
checkpoint-status | d22bc193-13ab-4c4c-832e-993b0272dbe1 |  | checkpoint | 2.4 Temporary ramping (transverse)
label | b6fc80eb-2dd5-5c31-8d5c-5ee490c71c99 |  | note | FREQUENCY: Transverse Edges
label | bd35881b-db54-5eb9-bbda-a08734fb57d1 |  | note | – – – – – – – – –
label | cd53f918-c4d1-5545-bc73-53d50152dd0a |  | note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
label | 0d1810fa-6109-546a-8c7e-0f32c92d8dcc |  | note | – – – – – – – – –
label | 6df580de-3b43-55d8-8b39-5cc266ab6211 |  | note | REFERENCE DOCUMENTS: 402.05
label | f2adb7ba-2103-5c0e-849d-8e1159deeda8 |  | note | – – – – – – – – –
label | daacf506-7554-5142-8ad7-bd23157f7b06 |  | note | INSPECTION/TEST METHOD: Verify
label | 979e5616-bb44-5356-a456-01d193cae829 |  | note | – – – – – – – – –
label | 1375c4cb-9c1d-5108-a9a6-097999148834 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4ae697ca-7547-5d8a-ad3b-18342d4bda37 |  | note | – – – – – – – – –
label | af4a53f0-f023-58bd-b00c-12f09d725bab |  | note | WP
label | f93ec3ae-3a21-521b-8829-c7b75746876a |  | note | – – – – – – – – –
label | 816a18fc-eab0-51a8-b38b-156f9c26964c |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | a5d460e0-16b3-5bce-93f9-a44e76096c36 |  | note | – – – – – – – – –
text | 92ed54b5-1194-5690-88db-cc1fb74d4c21 |  | textbox | DATE:
checkpoint-status | 4941292c-e115-448c-a512-46682f548f38 |  | checkpoint | Final Inspection
label | e0084c6e-5f02-55b6-90ad-16cf17b68313 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 580e4567-0788-5ecd-90b8-362b27cf218d |  | textbox | Print Name:
text | 3bb2df73-9caa-5b44-a4b6-d04880d828a6 |  | textbox | Position:
text | b29fb01c-6e2f-58b2-8921-55f4e92c402c |  | textbox | Date: