## Precast Delivery Checklist
ConQA Team Notes:
Document Title: |  | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
Check list Description: |  | Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 20/06/2023
ITP created by: |  | Kamel Alshobaki
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team: |  | This Checklist should be used in conjunction with ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
|  |  | Document No.: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | [5 empty] | Revision: | 0
[9 empty] | Date: | 20/06/2023
Item | Task/Activity Description | Reference / ITP Reference | Acceptance Criteria | Pass | Fail | N/A | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | MRPA Sign-off
[7 empty] | Method | Frequency | Category
1 | Materials - Fabrication | IFC Drawings Section 620 Section 701 Section 705 | (1) Precast items manufactured in accordnace with IFC Drawings - Drawing Ref No. _____________________________________ |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket
2 | Materials - Delivery | IFC Drawings Section 620 Section 701 Section 705 | (1) Purchase Order and Material Description and Qtys matches (2) Ensure precast concrete elements are as per IFC Drawings with no damages upon delivery (3) Lifting and Manufacture compliance certification provided - Purchase Order No. __________________________________ |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket Purchase Order
3 | Materials - Manufacture's Certificate of Compliance | IFC Drawings Section 620 Section 701 Section 705 | (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting. |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket Compliance Certificate
4 | Materials - Delivery to site & Storage | IFC Drawings Section 620 Section 701 Section 705 | (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element. (2) Precast elements are unloaded and stored properly on site as per manufacturer's recommendations. |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket
5 | Materials - Others | IFC Drawings Section 620 Section 701 Section 705 | Enter: Additional Comments [free text box] |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket