## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
afca1bda-ebb8-4f91-b56c-cd3f9aa6a653 | checklist | Aluminium |  | Aluminium
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
847a5cf0-1094-46f1-ad4d-2b0c48cc80c1 | checkpoint | Correct size openings
eb1f0018-dd15-4100-91a2-9d8635be7c0c | checkpoint | Correct components used
1ae5137d-1daf-4fc6-92d6-51af5fa4b03d | checkpoint | Fixing to substrate correct
aab79dcb-e448-4eb7-8cfd-11b5e2655270 | checkpoint | Door closes as intended
e02016a5-732d-420c-a89a-fc6792ee2150 | checkpoint | Protection installed
9cf46da4-02c5-44b1-9290-f4fb3c9e02ac | checkpoint | Glazing installed
f1ab18f6-0cdd-4850-9b87-aacc35fb51ba | checkpoint | No damages
82816ef3-e713-4762-a377-3dc279f2f2c3/2 | checklist | Ceilings - Preline |  | Ceilings - Preline
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fde6b77d-01a4-48e7-9ce2-94641bbf38d0 | checkpoint | Ceiling installed to correct height
3d6fef75-fa88-4e41-bd89-0c758f51c595 | checkpoint | Braces installed to spec and correct location
2c89b1c5-52c6-4683-a1cc-aaf068976d24 | checkpoint | Seismic bulkheads installed to spec and location
c1254e5c-4db1-45dc-bd8f-fd46dca5a624 | checkpoint | Ceiling free of damage
4c05b230-9563-4882-b616-4e8ff0b29040 | checkpoint | Fixed perimeter connections to spec
210cc3d9-8568-4720-85ca-fdf4feb077df | checkpoint | Floating perimeter connections to spec
e9175db2-d93e-4c38-bcc2-b744323c0b83 | checkpoint | Two-way setout correct
260788a0-9f2c-40f2-865d-e0cd58f41913 | checkpoint | Two-way square and straight
cc04ff84-7de8-4fe8-9680-f09aec92b3ea | checkpoint | All control and express joints formed
7d66c0ef-45b5-4937-8723-68fb8fa03465 | checkpoint | Ceiling is level/ true
944ece06-938c-4b24-a6cc-c0af2f0ec26f | checkpoint | All bulkheads are straight
20b457e7-f3fe-46e3-aa1c-bc9bd24ae15b | checkpoint | All hatches/ recesses framed and correct size
0f61ed59-4f5f-4b35-b91f-fb1655a9856a | checkpoint | All suspension hangers installed to spec
a67ad843-12cf-5b89-8515-c06fbd3385d7 | checklist | Parapet – Roof framing |  | Parapet – Roof framing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
de4f9100-b144-506e-85c4-cd341134813d | checkpoint | Set out correct
d16688ad-2ad1-5629-b679-f9d3207e50fb | checkpoint | Correct gauge of stud and centres
a1930e7e-7e6e-59b8-ab99-a2ceb0da3395 | checkpoint | Fixing to structure as per design
3670f725-0f93-425d-854c-25fe645bd042 | checklist | Plastering |  | Plastering
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
519cdb52-4082-4c58-add9-b862df9e1b16 | checkpoint | Fire stop to spec
56baf295-2936-422f-8ba5-48f13951219e | checkpoint | Level 4 finish to spec
cf9657db-463e-40f7-85de-37f9592f5d87 | checkpoint | Level 5 finish to spec
00b738e5-6010-49c2-8c3c-836558b60281 | checkpoint | All screws plastered not popped
77ad3020-fea9-4142-b17d-630de2860428 | checkpoint | All external angles installed to spec
e9bcb39b-9e98-4de1-83db-5444cbb5d962 | checkpoint | No visible air bubbles in finish
a5742c2e-99ee-4660-889a-6781e4299b2a | checkpoint | Light check complete
c46eafb8-58ca-4a51-aba4-78c07812cc43 | checkpoint | Ready for painter hand over
517a13dc-a5f6-45d7-98e1-3595fd30694a | checklist | Plastering Handover QA |  | Plastering Handover QA
7d566910-6123-434a-a02f-5570d6fb0903 | section | Details
85451992-f785-4595-a3d0-3a978ac4f284 | checkpoint | All products used as per spec
472bd2e9-e062-4999-92df-7dabac2ae15d | checkpoint | Fire stop to spec
1d333b03-86fc-4b4f-956f-061ded67ec77 | checkpoint | Level 4 finish to spec
6ae74826-859f-46fd-9263-e782ca88f03b | checkpoint | Level 5 finish to spec
fcf35a7b-0f3e-4534-8432-b25c0efcb38e | checkpoint | All screws plastered
2a11245c-bfb0-4e5d-a09f-8989a6c6d102 | checkpoint | All internal / external angles installed to spec
0885f086-ceb0-41d3-82fe-8bc3255cebd5 | checkpoint | No visible air bubbles in finish
937dacc1-2f67-43c2-a80d-4a622b8e368f | checkpoint | Wall straight at ceiling level
70b8465a-9123-44cc-96c2-153ec0ebcefa | checkpoint | Light check complete
d6701a1b-42c6-4132-a6df-be89d214a3d8 | checkpoint | Ready for painter handover
ea19aad9-409b-4456-aaf0-15c3d272aef5/2 | checklist | Walls - Postline |  | Walls - Postline
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
91941834-63b1-4bcc-b16b-e7ed7e63bb91 | checkpoint | Correct linings installed
bfa11a40-370b-4679-a483-79f660974acc | checkpoint | Correct fixings and screw lengths
8dcad85c-60e2-4d9a-83cb-58f48cc6daf9 | checkpoint | Acoustic / Fire sealant installed where required
dc7d6f45-893a-4c93-8c40-f8f70c174649 | checkpoint | No screws in DHT
c8743257-7389-41d1-ad09-5f79093a2545 | checkpoint | Correct Overlap with DHT
8d3c74eb-b3e4-4c8a-bf56-f8865e15f769 | checkpoint | Screws Correct Distance from DHT
d1d2c450-62e3-4751-b321-4c464cb1d048 | checkpoint | Deflection Head Strip Installed
1bd23887-baf5-4844-a041-dd1c449a092a | checkpoint | All sheet joins flush
6e2a8412-55e2-42fb-a1d9-6b9985eaf55f | checkpoint | Correct Sized gap at seismic / expansion plane
347330a9-9bdf-4775-89d0-35fb004eff41 | checkpoint | Flush boxes and penetrations cut correctly
1b045248-8f93-48d9-8613-5d653504da84 | checkpoint | Screws Correct Distance from Joints
77f4ca5b-477c-496e-a2e0-84b90fe588c3 | checkpoint | Screw Depths Correct
455d1d82-d311-4ee2-8dd7-027239edc982 | checkpoint | Fixing Centers Correct
c437b3d1-7f2a-4f3f-beb9-f45c288fedae | checkpoint | Pre-Line Acoustic Sealant Installed
e0956091-c238-4e72-856d-0eb65805c349 | checkpoint | Lining Junction as per drawings
724159c3-7234-4603-8e77-4cbcb9d6b45c | checkpoint | High level Gibbing installed to spec
1719f0d4-46c4-4dbf-9bad-b0579d766af5 | checkpoint | Wall straight at ceiling level
a6e3b83c-8fd9-42d8-8fe2-85767d1bdc65/1 | checklist | Walls - Preline |  | Walls - Preline
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
16f72722-b63a-47fe-b632-9d288d1c4015 | checkpoint | Set out correct
0d01c2b6-8c3f-4885-8b25-6073c31fc4b8 | checkpoint | Correct Stud and centres
4ecadbcf-d368-4a0a-b86f-5bc5c92982ca | checkpoint | Correct screws / Nails
1ac92100-8a19-4817-a4d3-b64af120a58a | checkpoint | Studs un damaged
cc3f7d66-577e-4126-859a-30112f8101ac | checkpoint | Fixings into slab correct
ab6e79b3-c1ef-4c79-bb42-94cdce08d805 | checkpoint | Fixings either side of openings
1b73df4d-45df-4e65-a5af-1146ac73260d | checkpoint | No screw in DHT
96fda4c5-f340-458d-811c-b559b0dba851 | checkpoint | Wall straight at ceiling line
bf60a30f-231e-4eea-af95-10c5e7058ecc | checkpoint | End studs correct at wing walls
8fea763e-86ac-4010-a889-df854f35dee6 | checkpoint | Insulation installed
a9469989-8361-42bb-82fa-7d6cb9c86aee | checkpoint | High level GIB Nogging installed
19c00c99-6943-4862-8e78-5c6b6c494b68 | checkpoint | DHT connection correct
af522e0b-f0d2-4d17-9760-3f1a9dddca17 | checkpoint | Noggs installed to spec