## ChecklistsITCs
Delete rows that aren't applicable to the project, then create the project breakdown and send to CONQA
type | name | values | prefix | postfix
checklist | Site Establishment and Safety Checklist | Pass, Fail
checkpoint | Delivery and goods lift location
checkpoint | Delivery requirements i.e. booking process
checkpoint | On site storage / office location
checkpoint | Site specific restrictions i.e. noise / starting times
checklist | Ductwork Checklist | Pass, Fail, N/A
checkpoint | Ductwork installed as per latest drawing
checkpoint | Inspect ductwork is not damaged. Record and report for any issues
checkpoint | Confirm correct spacing / supports installed
checkpoint | Duct flanges firmly bolted and sealed correctly
checkpoint | Cleats installed as required
checkpoint | Ductwork insulated where required and free of damage
checkpoint | Ductwork restrained for wind/seismic where required
checkpoint | Confirm ductwork joints and seams are sealed
checkpoint | Pops & flex installed as per latest drawing
checkpoint | Correct hanger spacing / supports installed for flex
checkpoint | Flexible duct connections completed correctly
checkpoint | Blade dampers installed as documented and left in the open position
checkpoint | BD pop access panel coordinated and marked
checkpoint | Cushion boxes installed as per latest drawing
checkpoint | Balancing dampers installed as documented and left in the open position
checkpoint | Volume Control Dampers installed as per latest drawing
checkpoint | Motorised dampers installed as per latest drawing / actuator fit off
checkpoint | Smoke dampers installed as per latest drawing / actuator fit off
checkpoint | Damper access panels coordinated and marked
checkpoint | Check all motorised dampers, fire damper and smoke damper are in open position.
Checklist | Drains | Pass, Fail, N/A
checkpoint | Drain trapped where required
checkpoint | Drain pump installed on a gradient/ level
checkpoint | Drain terminates at a tundish
checkpoint | Drain pipe insulated where required
checkpoint | Drains, pump and tundish access for maintenance
checkpoint | Drain pipe is labelled clearly
checklist | ERV Checklist | Pass, Fail, N/A
checkpoint | ERV installed as per latest drawing
checkpoint | Inspect the unit casing is not damaged. Record and report for any issues
checkpoint | Unit is labelled clearly
checkpoint | Unit correctly supported as per documented
checkpoint | Confirm installation of any dampers on the units
checkpoint | Confirm electrical connection to unit
checkpoint | Flexible connections installed
checkpoint | Air filters installed
checkpoint | Check for cleaniness inside the housing
checkpoint | Confirm seismic bracing to requirements
checkpoint | Adequate maintenance clearance maintained
checklist | Split DX Unit Checklist | Pass, Fail, N/A
checkpoint | FCU and condensing units installed as per latest drawing
checkpoint | Inspect the FCU and condensing unit. Record and report for any issues
checkpoint | Unit is labelled clearly
checkpoint | Unit correctly supported as per documented
checkpoint | Confirm safety tray and/ or condensate drain provided to the units and is piped to adjacent waste point
checkpoint | Confirm refrigeration pipework are installed
checkpoint | Confirm refrigeration pipework insulation are installed with adequate support
checkpoint | Confirm correct eletrical connections to the refrigeration system as per wiring schematic
checkpoint | Adequate maintenance and ventilation clearance maintained
checkpoint | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail.
checklist | Fan Checklist | Pass, Fail, N/A
checkpoint | Fan installed as per latest drawing
checkpoint | Inspect the fan. Record and report for any issues
checkpoint | Fan is labelled clearly
checkpoint | Confirm ductwork connections to the fans are correct and include flexible connections
checkpoint | Confirm VSD is installed
checkpoint | Confirm test points, sensors and gauges have been provided and installed as documented
checkpoint | Confirm correct eletrical connections to the fan
checkpoint | Adequate maintenance clearance maintained
checkpoint | Unit complete with acoustic wrapping as per documented
checkpoint | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail.
checklist | Grille Fit-Off Checklist | Pass, Fail, N/A
checkpoint | Confirm grilles type and colour as per schedule
checkpoint | Grilles installed in correct location as per latest duct layout / RCP
checkpoint | Inspect the grille. Record and report for any issues
checkpoint | Grille left clean of fingerprints and caps installed where required
checkpoint | Area left clean/tidy (Any Issues comment below)
checklist | All Subbie Rough-in Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant
label | Pass once all work complete
checklist | All Subbie Fit off & Testing Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant
label | Pass once all work complete
checklist | As Builts Checklist | Complete, Incomplete
button | Update As-Built's of any known changes
checklist | Pipework Testing | Pass, Fail, N/A
checkpoint | Pipe tested and recorded as per Pipe Testing ITP
checkpoint | Pipe pressure test (attach photo)

## TO BUILD - DUCTWORK
Project Breakdown |  | Checklists
PROJECT NAME: EARLY PARENTING CENTRE - HASTINGS
OHS |  | Site Establishment and Safety Checklist
| INPATIENT - Ground Level | Ductwork Checklist
Grille Fit-Off Checklist
| INPATIENT - Roof Level | Ductwork Checklist
| FOH - Ground Level | Ductwork Checklist
Grille Fit-Off Checklist
| FOH - Roof Level | Ductwork Checklist

## TO BUILD - ERV
Project Breakdown |  | Checklists
PROJECT NAME: EARLY PARENTING CENTRE - HASTINGS
OHS |  | Site Establishment and Safety Checklist
| HEX.1 | ERV Checklist
| HEX.2 | ERV Checklist
| HEX.3 | ERV Checklist
| HEX.4 | ERV Checklist

## TO BUILD - FAN
Project Breakdown |  | Checklists
PROJECT NAME: EARLY PARENTING CENTRE - HASTINGS
OHS |  | Site Establishment and Safety Checklist
| EF.1 | Fan Checklist
Ductwork Checklist
Grille Fit-Off Checklist
| EF.2 | Fan Checklist
Ductwork Checklist
Grille Fit-Off Checklist
| EF.3 | Fan Checklist

## TO BUILD - SPLIT DX
Project Breakdown |  | Checklists
PROJECT NAME: EARLY PARENTING CENTRE - HASTINGS
OHS |  | Site Establishment and Safety Checklist
| AC-IP.1 | Split DX Unit Checklist
Drains
| AC-IP.2 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.3 | Split DX Unit Checklist
Drains
| AC-IP.4 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.5 | Split DX Unit Checklist
Drains
| AC-IP.6 | Split DX Unit Checklist
Drains
| AC-IP.7 | Split DX Unit Checklist
Drains
| AC-IP.8 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.9 | Split DX Unit Checklist
Drains
| AC-IP.10 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.11 | Split DX Unit Checklist
Drains
| AC-IP.12 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.13 | Split DX Unit Checklist
Drains
| AC-IP.14 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.15 | Split DX Unit Checklist
Drains
| AC-IP.16 | Split DX Unit Checklist
Drains
| AC-IP.17 | Split DX Unit Checklist
Drains
| AC-IP.18 | Split DX Unit Checklist
Drains
| AC-IP.19 | Split DX Unit Checklist
Drains
| AC-IP.20 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.21 | Split DX Unit Checklist
Drains
| AC-IP.22 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.23 | Split DX Unit Checklist
Drains
| AC-IP.24 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.25 | Split DX Unit Checklist
Drains
| AC-IP.26 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.27 | Split DX Unit Checklist
Drains
| AC-IP.28 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.29 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.30 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.31 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.32 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.33 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.34 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.35 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-IP.36 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| CU.1 | Split DX Unit Checklist
Pipework Testing
| CU.2 | Split DX Unit Checklist
Pipework Testing
| CU.3 | Split DX Unit Checklist
Pipework Testing
| AC-FH.1 | Split DX Unit Checklist
Drains
| AC-FH.2 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-FH.3 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-FH.4 | Split DX Unit Checklist
Drains
| AC-FH.5 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-FH.6 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-FH.7 | Split DX Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| AC-FH.8 | Split DX Unit Checklist
Drains
| AC-FH.9 | Split DX Unit Checklist
Drains
| AC-FH.10 | Split DX Unit Checklist
Drains
| AC-FH.11 | Split DX Unit Checklist
Drains
| AC-FH.12 | Split DX Unit Checklist
Drains
| AC-FH.13 | Split DX Unit Checklist
Drains
| AC-FH.14 | Split DX Unit Checklist
Drains
| AC-FH.15 | Split DX Unit Checklist
Drains
| AC-FH.16 | Split DX Unit Checklist
Drains
| AC-FH.17 | Split DX Unit Checklist
Drains
| AC-FH.18 | Split DX Unit Checklist
Drains
| AC-FH.19 | Split DX Unit Checklist
Drains
| AC-FH.20 | Split DX Unit Checklist
Drains
| AC-FH.21 | Split DX Unit Checklist
Drains
| AC-FH.22 | Split DX Unit Checklist
Drains
| AC-FH.23 | Split DX Unit Checklist
Drains
| AC-FH.24 | Split DX Unit Checklist
Drains
| CU.4 | Split DX Unit Checklist
Pipework Testing
| CU.5 | Split DX Unit Checklist
Pipework Testing
| CU.6 | Split DX Unit Checklist
Pipework Testing
| CU.7 | Split DX Unit Checklist
Pipework Testing

## TO BUILD - ANCILLARIES (hidden)
Project Breakdown |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  | Site Establishment and Safety Checklist
Site QA | EXP-CHW
General Equipment Checklist
EXP-HHW
General Equipment Checklist
CHWT-1-01
General Equipment Checklist
HHWT-1-01
General Equipment Checklist
AFU-CHW
General Equipment Checklist
AFU-HHW
General Equipment Checklist
ADS-CHW
General Equipment Checklist
ADS-HHW
General Equipment Checklist