## struct
resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
Site Establishment and Safety Checklist |  | checklist |  |  | Tier 1: OHS
|  | step |  |  | Tier 1: Site QA
|  | step |  |  | Tier 2: DUCTWORK
|  | step |  |  | Tier 3: LEVEL B1
Ductwork Checklist |  | checklist |  |  | Tier 4: Ductwork
Grille Fit-Off Checklist |  | checklist |  |  | Tier 4: Grille Fit-Off
|  | step |  |  | Tier 3: GROUND LEVEL
Ductwork Checklist |  | checklist |  |  | Tier 4: Ductwork
Grille Fit-Off Checklist |  | checklist |  |  | Tier 4: Grille Fit-Off
|  | step |  |  | Tier 2: PIPEWORK
|  | step |  |  | Tier 3: GROUND LEVEL
Pipework Checklist |  | checklist |  |  | Tier 4: Pipework Checklist
Pipework Testing Checklist |  | checklist |  |  | Tier 4: Pipework Testing
|  | step |  |  | Tier 2: FCU
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.01
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.02
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.03
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.04
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.05
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.06
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.07
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.08
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.09
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.10
Fan Coil Unit Checklist | Drains Checklist | folder-with-checklists |  |  | Tier 3: FCU-G.11
|  | step |  |  | Tier 2: FANS
Fan Checklist |  | checklist |  |  | Tier 3: OAF-B.01
Fan Checklist |  | checklist |  |  | Tier 3: TEF-G.01
Fan Checklist |  | checklist |  |  | Tier 3: GEF-G.01
|  | step |  |  | Tier 2: SPLIT DX
|  | step |  |  | Tier 3: AC-B.01
Split DX Unit Checklist |  | checklist |  |  | Tier 4: Split DX Unit
Drains Checklist |  | checklist |  |  | Tier 4: Drains
|  | step |  |  | Tier 3: CU-B.01
Split DX Unit Checklist |  | checklist |  |  | Tier 4: Split DX Unit
Pipework Testing Checklist |  | checklist |  |  | Tier 4: Pipework Testing
|  | step |  |  | Tier 3: AC-B.02
Split DX Unit Checklist |  | checklist |  |  | Tier 4: Split DX Unit
Drains Checklist |  | checklist |  |  | Tier 4: Drains
|  | step |  |  | Tier 3: CU-B.02
Split DX Unit Checklist |  | checklist |  |  | Tier 4: Split DX Unit
Pipework Testing Checklist |  | checklist |  |  | Tier 4: Pipework Testing
|  | step |  |  | Tier 3: AC-B.03
Split DX Unit Checklist |  | checklist |  |  | Tier 4: Split DX Unit
Drains Checklist |  | checklist |  |  | Tier 4: Drains
|  | step |  |  | Tier 3: CU-B.03
Split DX Unit Checklist |  | checklist |  |  | Tier 4: Split DX Unit
Pipework Testing Checklist |  | checklist |  |  | Tier 4: Pipework Testing