## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d1e97f69-2159-4763-82ce-6f53852aa510 | checklist | ITP-258-CIV-MSS-Rail Delineation Temporary Fencing Rev 0 | itp | ITP-258-CIV-MSS-Rail Delineation Temporary Fencing
b30d5927-aa2a-4175-9daa-a1c419f916b9 | section | 1. Referenced Documentation
e5ec234d-1b1d-42a3-bd1c-3a10dca10cb7 | checkpoint-no-value | Referenced Documentation
a8e7e741-f040-53d6-b884-e7eb519ef698 | note | Document Title: ITP-258-CIV-MSS-Rail Delineation Temporary Fencing
5daf2d2e-70bf-57cf-8826-495db92c3874 | note | ITP Description: Rail Delineation Temporary Fencing for Maidstone St
74ebf3ff-1bb9-5e94-930c-6fdf286d80bd | note | Discipline (e.g. CIV/STR/RAIL): CIV
b0795da0-301f-5bc0-b808-a22e646e127c | note | Revision Number: 0
a96b066d-3712-5ac7-a862-b449f6be2df8 | note | Revision Date: 1/05/2025
04c1c6fe-a5cb-5e17-82ca-1d291b52c1d2 | note | ITP created by: Dan O'Brien
d14fb9ac-5528-55e9-9522-d8f106736f9d | note | ITP approved for use by: Aldrin Guinchoma
ba769a3c-ef1f-55a7-892c-33fe9e8a6d75 | note | 1.1 - Non Dependent
a4f65d4f-4495-505e-82e9-d8e8cc3aa71d | note | Reference - IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025
301f92e4-91d1-46ce-a32d-dc6d99e8f675 | section | 2. Preliminaries-Materials
7d3893ae-ce4b-4572-93ad-920e6f3d6bc3 | checkpoint | 2.1 - Concrete
967bddab-989a-58ff-a014-d3743906042c | note | Reference - IFC Drawings
0e22a410-778b-5489-9550-0eee8a45933c | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
463d1ef1-255c-5bfe-9550-dd8421c26165 | note | Method - Document Review
1b716367-f4ed-5bee-a233-f7f36098ee35 | note | Frequency - Each Mix
c7af3906-0ae0-5057-b4ed-080c26ebba39 | note | Category - HP*
8189423d-5812-5b4d-891a-bf0702722c51 | note | Responsibility - PE
a9938361-823c-5d27-9eaa-879a388a5076 | note | Verifying Documents - This ITP
c6c1c15e-dbd4-5706-a6ed-3c09c80df184 | date | Date Completed:
cd8d2ab8-a0d4-4a6f-8251-6eaecdd47937 | checkpoint | 2.2 - Steel components
f61ace2e-494f-5f41-87f6-b42e49869546 | note | Reference - IFC Drawings AS41000, AS1163
e2ebe6c4-3578-531b-8dce-0e3b6f4c979b | note | Acceptance Criteria - All Steel must comply with Australian Standards.
cde41fe9-275b-5748-a29d-dbc4e4fc31fa | note | ○ Steel section sizes must be checked on site.
f47932f1-206d-5f98-b799-146125e2d135 | note | ○ Steel posts to be CHS with a grade of C250
6dae5f91-b7b5-5aa8-bb79-543683b02433 | note | Method - Document review, Visual and Measure
728d77b2-40be-572c-8582-fe774106e235 | note | Frequency - All elements
c98bffb7-175a-55b1-a07b-7fb6ff871f97 | note | Category - IP
914b4262-0cf3-5cbb-b2f8-052bebf1f2c5 | note | Responsibility - SE/Site Supervisor
4a7450c0-a084-5359-990f-450b81a9919d | note | Verifying Documents - Delivery Dockets
5fefe35e-b7c1-54a8-b9cb-6ff4f707dad1 | date | Date Completed:
b8eda38d-1e6a-458a-9493-800c896ca93e | section | 3. Preliminaries-Documentations
b54abd41-d0ce-4699-9ec5-4874b33118ca | checkpoint | 3.1 - Excavation works
c2e494dd-26a2-567b-8bf0-611c1fe3e96f | note | Reference - IFC Drawings L1-CHE-STD-005
424ba696-9b01-58af-acb2-bba3b291f099 | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements.
43e3c5c9-6bad-55b5-a5ac-eeb35a820977 | note | ○ Follow asset owners guidelines for work around their service.
3b724dee-872e-5039-8265-4a56d7178f04 | note | ○ Excavation must use Non Distructive Digging in close proximity to services
8c06b442-ae56-570a-89c0-52ffbe827d4c | note | Method - Visual
f81bb348-dbb8-5f5a-8041-05fb94dda9a3 | note | Frequency -
dfd44f2e-75b6-5a7c-a7b9-16c12b2b1ac7 | note | Category - IP
a9e0058e-a51f-5336-8918-e390bb6fe64f | note | Responsibility - SE/Site Supervisor
702e81e8-096f-57ce-9fcf-e71e0175a56a | note | Verifying Documents - This ITP
8fdf3b48-a006-50d8-9c20-f6b1900e78a1 | date | Date Completed:
b629eadc-5804-4580-9afc-381cf12b73d7 | section | 4. Pre-construction / Pre-installation Activities
a6cb935a-4aad-42bf-b3d2-95519b27e387 | checkpoint | 4.1 - Survey Set-out
32170596-9996-5e5c-b240-b7c5b900ef76 | note | Reference - IFC Drawings
bf3b2e30-38ec-51ea-a81c-18b91d949dde | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays
f6491261-4bbf-5ea6-bdd9-0fce4671e946 | note | ○ Offset checked against the running edge prior to installation of posts.
51a2d371-a2b4-58c4-8c20-6938b657640b | note | ○ Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
279b33cc-2da8-5c70-9db2-0f100085d02d | note | ○ Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
34a5b179-e29b-5313-8fdc-ec11b4924a0d | note | Method - Measure, Visual inspect
6c09db2b-8528-51f7-9538-22a93b8c8553 | note | Frequency - Each element
11c34bc9-f08f-5732-8c9b-29b3ea46183d | note | Category - IP
b4c63114-1721-578b-a6fd-15f0ff98f679 | note | Responsibility - Surveyor, SE/PE/SPE
d6d49991-8a86-5c5b-80e3-3c805110d515 | note | Verifying Documents - This ITP
df47be1d-60b2-5ea3-845a-455e0e0f5b3a | date | Date Completed:
3053b6ed-d858-4294-9758-72f08ee38928 | checkpoint | 4.2 - Vibration Monitoring
b89d436c-ad3d-5037-8b85-72ab664b0b11 | note | Reference - Worley vibration monitoring plan
36002666-383e-5eff-8d92-4a426232894a | note | Acceptance Criteria - Vibration monitors installed as required in monitoring plan.
7cbf6c73-e611-581b-9b42-aadc811bc350 | note | ○ Vibration at VIVA pipelines not to exceed 10mm/s
d3705057-7652-54e8-93e1-6986bb219a4d | note | Method - Measure
00104225-2343-56a9-a26d-a5806c38835c | note | Frequency - Each element
927714c4-db1c-5465-99b0-9f5c4467dcf4 | note | Category - IP
fa0b1618-46ad-5fa3-aee8-e35e943053eb | note | Responsibility - SE/PE/SPE
ef6f6b0d-66bd-56c1-a830-390ec7cd4318 | note | Verifying Documents - This ITP
17c61e3c-ab59-552f-8d92-858c74b7f047 | date | Date Completed:
9c7a33c5-df87-417d-8cb9-d4ecb503cced | section | 5. Construction / Installation Activities
7b7ca035-54ad-4775-a6f3-1aa1b35c85ed | checkpoint | 5.1 - Ground Conditions
d558d455-9df2-5020-8955-37fcd753ecf5 | note | Reference - IFC Drawings
b84bfa7b-ba8c-500e-b301-8e38d3d11c8f | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
aa2871a2-9c77-57e5-b65c-5b06141e9aea | note | Method - Visual
2cb182c1-d573-568f-ac88-e5e5c51b6df1 | note | Frequency - Each post
b867af5d-fbac-5524-8601-8f13794f03e7 | note | Category - IP
3e09f592-e222-5796-9b31-1edd94c0daef | note | Responsibility - SE/Site Supervisor
098f7710-cae1-5ee3-a853-1f4ca223bc32 | note | Verifying Documents - This ITP
03b2c1e4-d873-53b5-b3be-6a048b936bf2 | date | Date Completed:
57c5f93c-c12b-4bfc-96f1-22df42bfd74d | checkpoint | 5.2 - Post Foundation
b3790331-f2b6-5ff9-9285-0f81be9db427 | note | Reference - IFC Drawings
cc8f33ea-6fb5-565b-a4eb-8a34f4185b35 | note | Acceptance Criteria - Concrete
a7af24e7-2da6-58fa-bc85-1a8e888c98ea | note | — 300mm Dia
865a1a67-1a5d-5e8b-80dc-0d29d9332b59 | note | — 800 mm Depth
6b8c44b4-b5ef-5637-b44f-1ab2c04de962 | note | CHS Sleeve:
0955d0be-52f6-5e0b-9320-f029d2ccf5b4 | note | — Depth 1400
76cee79d-3334-5932-9c1e-1c7fbba8b929 | note | — Other Dimensions as per IFC
7b2210aa-9ff2-52d6-8ac3-fdab18ab20b9 | note | Direct Driven:
98b5ee57-11e2-51e4-b761-505a06458eb6 | note | — 88.9x4 CHS
a20ef889-63ab-508e-aa79-fd2ca49fd281 | note | — Depth: 1400
96c0cb02-9c05-5467-96ff-8165f79c28df | note | Insulated fence near OLE posts:
089be3cb-93f8-5208-8734-04269c6fd94a | note | — 95x65 Truform LVL
30672cb4-320b-5eeb-a65e-e0b221683a09 | note | — Depth 800mm (post embedment 700mm)
139b792e-3a34-58c2-b6c5-63f28dc798c2 | note | — 300mm diameter
0d966fca-2b7d-563b-ba0e-9f409aa22746 | note | Spacings:
ec713574-0153-5eb6-b518-b03ce8243ee0 | note | — Typical: 2700 max
085c0be7-5a92-5160-9426-33268f0730d5 | note | — Gates: 1350
db01712f-ec6f-5c98-8a92-66e43bb237f6 | note | — Refuge: 1200
1f3b8249-290e-517b-9c71-8f40125ec563 | note | Method - Measure
44b5eb9a-11c8-56ac-87c7-0912faabbf58 | note | Frequency - Each footing
d2a47e23-3507-5fdd-b034-bb41d05f0d91 | note | Category - IP
c7ad1105-5372-5766-8829-ff1da28d2045 | note | Responsibility - SE/Site Supervisor
25d859a9-5e93-5561-844b-85b7f2629063 | note | Verifying Documents - Concrete Dockets
5eccd80f-37c8-59d9-8fbf-27fae94fc049 | date | Date Completed:
cab192f5-429d-4a50-80fa-3f3c83fb2b90 | checkpoint | 5.3 - Post Installation
cd681ce9-b967-58ae-903d-508c6ea51848 | note | Reference - IFC Drawings L1-CHE-STD-005
bf470028-e0ba-5511-a3cc-1f4d2a2625eb | note | Acceptance Criteria - Minimum offset 3000mm from centreline of track.
09c4a939-85a3-5d9d-9c84-0b2a88a1d3b4 | note | ○ Minimum 2m offset to existing OLE structures (insulated fence required)
a45969a5-823c-5213-aa0e-47bef95eb55b | note | ○ Maximum post spacing to be 3m
14d022a9-a93c-5430-82a5-aabaafb0cb33 | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
a73d14b9-3b2c-59f6-b7e9-8b8e49e50c1b | note | ○ Max. post height 1800mm above ground level.
49aff54a-6332-5886-b4ad-322491c0ab64 | note | ○ Vertical Tolerance: ±20mm from the design line.
1e8754a7-14e2-5d6c-98e8-63ccd499b2f2 | note | Method - Measure
307ba2c8-ec8c-599a-b934-18e1d79aae05 | note | Frequency - Each post
fd6ae2f1-621d-54a6-8d64-b8eb47fac034 | note | Category - IP
b94c280a-b1d9-598a-bae4-bdc0f09fdc5f | note | Responsibility - SE/Site Supervisor
27c9d2aa-66b6-5cd9-b4c0-fed2bbede3ad | note | Verifying Documents - This ITP
ef4f0635-e943-57d4-bccf-a823bbb7e024 | date | Date Completed:
0b3c0cbf-a5df-414b-a347-0973242bbcaf | checkpoint | 5.4 - Post Installation - insulated fence near OLE structure
5c7ba8e7-f806-5e33-af9d-5a1324be5d64 | note | Reference - IFC Drawings L1-CHE-STD-005
245fb2a8-4474-568c-9281-16ebfa224fde | note | Acceptance Criteria - Minimum offset 4000mm from centreline of track.
115cf64e-4c14-5055-b5cc-43781014d592 | note | ○ Minimum 1m offset to existing OLE structures
922cf335-b90a-56f3-8db7-8b345debab58 | note | ○ Maximum post spacing to be 2.7m
23c1c4cf-b39a-57bf-a0ee-d8ea3e39d1b2 | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
f6232f72-27ac-5b0e-a57a-f0d76943ddcc | note | ○ Max. post height 1800mm above ground level.
3a109598-c898-5eda-beee-1920a4558ea2 | note | ○ Vertical Tolerance: ±20mm from the design line.
0c51a0a1-5487-50df-afea-132f88163c4a | note | Method - Measure
ef0487e6-e81c-532a-8cd8-e857d0f6bb1d | note | Frequency - Each post
e055677a-b1d9-554a-8ce8-2e96a1dcce02 | note | Category - IP
9cd7f530-efe4-5579-a2d4-f19848ab61d7 | note | Responsibility - SE/Site Supervisor
bc58d52f-104b-55ff-902d-106cb217a91e | note | Verifying Documents - This ITP
02807b93-682d-586c-8d1d-93104a2ce8e4 | date | Date Completed:
735e7806-93c6-4b09-980d-97347cc97935 | checkpoint | 5.5 - Chain Wire Mesh Installation
3ad57d51-d4c1-53ad-accb-b890e04da40c | note | Reference - IFC Drawings
3276e5ee-3e98-50b5-97c0-e255863e10a2 | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
6ddd682b-2b0b-5a46-ad5c-9ee3c3411920 | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
50179131-d959-5dee-8e6a-3b6f8ec47df6 | note | Method - Visual
c6aa8c93-3f94-5e1a-8c23-7683da055f4f | note | Frequency - Each element
1da61ce7-4827-5a00-b880-bf3e2de8b588 | note | Category - IP
1d5bc33a-1d8b-54b6-837d-7dac0beab93a | note | Responsibility - SE/Site Supervisor
33ab426b-20bb-5e99-9452-48d4d1861928 | note | Verifying Documents - This ITP
9cf3b7f0-4699-57a5-8617-33bf2c81e259 | date | Date Completed:
0c4f76cc-5706-42eb-867d-e6cf03e52e7e | checkpoint | 5.6 - Bracing
f5219dd5-2890-5a8d-82ef-41fc10b3c708 | note | Reference - IFC Drawings
0aeae59b-9001-5cf1-94da-caed533b03f8 | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
7d56837e-dfb2-5f84-9090-4815f826af43 | note | ○ Bracing to be installed on both sides of the fence at the fence corners
59fcfbeb-243b-56ce-ba0a-afb4a36cd9d8 | note | Method - Visual
201672de-d408-5f68-9ce2-02ff936db4ca | note | Frequency - Each element
c0aa07e3-87fa-5e21-9367-edc3fcf1ed0a | note | Category - IP
6d30352e-d64b-5ea9-997f-69f189f617f6 | note | Responsibility - SE/Site Supervisor
afdabd39-16c6-5aea-9feb-93accdede224 | note | Verifying Documents - This ITP
4137af28-a1ff-5c56-b41f-9b111be13368 | date | Date Completed:
fdcde141-9138-4d89-b307-bea9ef6c8943 | checkpoint | 5.7 - Wire mesh and bracing at OLE posts (insulated fence)
46c6e66f-76d4-540d-a964-7d3f5d934b16 | note | Reference - IFC Drawings
6fe89efd-cdea-53d0-b023-53595842dcb6 | note | Acceptance Criteria - Mesh fence to be PVC coated
ad364aad-a92b-5af4-99cc-c7e22c369404 | note | ○ Bracing with 95x65 truform LVL - fix to post with 2x12G timber batten screws
8d7c4183-64bd-5353-a46f-5a34bf41d6c0 | note | ○ Tension wires to be PVC coated
953a035c-94a3-5fe1-90c2-3377ce7c6a10 | note | ○ Mesh fixed to posts using fence staples at max 200mm spacing
1cf522a5-3e2f-578b-afa6-c51bf1329bfd | note | Method - Visual
508340cf-1852-50bf-a7f4-272daa8c3735 | note | Frequency - Each element
e38b6a57-499a-5387-a3d2-f5612a405f6b | note | Category - IP
ee1e4638-46e0-504b-8908-9df873dee37a | note | Responsibility - SE/Site Supervisor
fc8591b1-5908-55c5-80d7-7ed4f4222444 | note | Verifying Documents - This ITP
7f235e0f-9231-51d2-84af-030ce2bc78d4 | date | Date Completed:
b252e649-e9e0-4cff-ab52-32871f2bf8a0 | checkpoint | 5.8 - Refuge Installation
fbf11d19-e1c4-544b-8e18-fb6273bb2d63 | note | Reference - IFC Drawings
a6d0b2d8-9888-5bcd-8124-f72723b2b825 | note | Acceptance Criteria - Refuge Access to only open from track side.
9661a4d3-1447-513d-b407-936e50ff533e | note | ○ No chain wire mesh to be installed at refuge access.
e4acd58c-37cd-563b-bcf2-3533c6a2fb88 | note | ○ Refuge Access to be located maximum 20m intervals
6cf48143-29db-50f5-9df6-4c99afbe49aa | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
0b4b8292-3965-5f40-aa80-6befb9d979ea | note | Method - Visual
2fb2cfb6-c5d3-5716-8d52-b73a565f5f3c | note | Frequency - Each element
af70bcae-543e-51d6-a358-074ff079ce7c | note | Category - IP
f3e0e1c9-c5b6-5df6-8236-548a374d53d5 | note | Responsibility - SE/Site Supervisor
95c2d7af-459f-5a8d-8c4d-c8cd87cc9320 | note | Verifying Documents - This ITP
0b4e2507-e355-51a8-b7f3-3a4e4fc61cab | date | Date Completed:
c34c7145-0600-419b-a5f1-5b1ecaf30215 | checkpoint | 5.9 - Refuge Signage
f6b1e182-f8d2-5e94-ade7-f3b3a220b70d | note | Reference - IFC Drawings
e87912b2-6464-5240-9d8b-53d65f327d1f | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
4940ad9f-aa25-5018-9eb3-560582cea76a | note | Method - Visual
575ed73a-5b23-551e-9784-7f7f9f9351d5 | note | Frequency - Each element
fb9d979a-8e7d-51eb-b189-0271d3f78f5a | note | Category - IP
009dc2a9-cab4-5a48-b4b4-85aff8485da6 | note | Responsibility - SE/Site Supervisor
095d5d25-ca54-5225-a623-53359e2b2938 | note | Verifying Documents - This ITP
0d9d0a01-7eeb-5244-a6e3-a17ecbed5c76 | date | Date Completed:
a3a50805-960d-4b23-b4d3-449480bc6dc4 | section | 6. Post-construction / Post-installation Activities
141c2044-b4e7-4135-a104-641b66b910ed | checkpoint | 6.1 - Fence Height and Track Clearance
17b44d48-d8be-5ee6-8b3c-e64355d69195 | note | Reference - IFC Drawings
6edbf42c-143b-5812-bb94-d7ad2e41e36e | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
3870fa3b-bbd0-5d32-8c90-21703c288f45 | note | Method - Measure
1899a64f-f296-5f1d-962d-1668817ce3fe | note | Frequency - Each lot
636e2600-6792-5dfb-89df-68b75b8a40d4 | note | Category - IP
5014919b-8412-57d5-851c-3d084025a4bf | note | Responsibility - SE/Site Supervisor
87eeaf9e-a5d4-54b3-9286-f6ffd07b527e | note | Verifying Documents - Survey report
d099666f-be94-51e4-90c9-cfe16c2caff5 | date | Date Completed:
27501c0c-0182-4b24-a1b9-cb7de41f4139 | checkpoint | Final Inspection
81fbc77a-b1d5-5188-b192-23125d1eac79 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fb53e5d9-86ec-548f-8657-03ee7bb1307a | textbox | Name:
878d37e6-793f-5f2b-a526-d20747419764 | textbox | Position:
e453ea52-23ed-572f-93f0-86f2a74deb97 | textbox | Date Completed:
8d1ee2b7-8890-4ed8-acf0-60bfde425fef | signoff | Sign ITP
33e2818a-c0de-401b-a6f2-c588449fb9a5 | checklist | ITP-272-CIV-ADL-Site Clearing and Grubbing Rev 0 | itp | ITP-272-CIV-ADL-Site Clearing and Grubbing
1d481a1b-c2bb-44ce-92f4-59a4b63edfbe | section | 1. Referenced Documentation
2dcea1de-fecc-4c03-a9f8-b0b98b7cd827 | checkpoint-no-value | Referenced Documentation
0304228a-5c28-52c6-8c5a-4992de088a24 | note | Document Title: ITP-272-CIV-ADL-Site Clearing and Grubbing
5d9a7f04-6738-5ac8-aa88-ccace3de2240 | note | ITP Description: ADL-Site Clearing and Grubbing
803da310-8400-576b-bde4-a6ab73ec5996 | note | Discipline (e.g. CIV/STR/RAIL): 272-CIV
08ad79de-74a9-5136-ae18-1079306e0059 | note | Revision Number: 0
39c6eac0-69ba-592e-9beb-d63a72c2fcb1 | note | Revision Date: 20/05/2025
116fac49-f0c5-55d4-bc99-29b203e56c82 | note | ITP created by: Abhi Patel
39943b15-b0d8-5b53-84d4-4904845ad0a0 | note | ITP approved for use by: Aldrin Guinchoma
d077da54-0f62-5813-9714-cc2620af7fea | note | 1.1 - Non Dependent
821b2899-4747-541c-a7b7-b57f971495ad | note | Reference - VicRoads Section 201
deb70b6e-462a-5e29-adaf-5ad23885a2ba | note | 1.2 - Non Dependent
0f479653-1302-5206-a291-35295648d04b | note | Reference - VicRoads Section 204
6108435e-40ab-53be-ba11-765589bdeacf | note | 1.3 - Non Dependent
9c83fd1d-4fe4-5f0c-96de-d7c12f30d659 | note | Reference - IFC Drawings
141cdacc-af6f-4d74-bc7d-c5f06349548d | section | 3. Preliminaries - Documentations
9349d9eb-1146-4dd1-8beb-d6cb3f7a9883 | checkpoint | 3.1 - Environmental Controls
50232dad-5362-5d7c-b5e6-73ff7fc6ed59 | note | Reference - MRPA Environmental Management Plan
f1f10a09-f597-5441-832c-2db629906b7a | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities.
10593464-3a09-527a-b8f9-05f74972fd70 | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
655d3b36-9578-5d66-be08-e94dd2e51a28 | note | Method - Visual
c426a9ec-cfa7-5abb-aab1-e5c527fbf98c | note | Frequency - Where applicable, prior to starting Works
3dd5323f-6402-52a3-8135-2d07ab453f45 | note | Category - WP
ed1b9cb1-eaf4-550d-85cb-71feca85bf50 | note | Responsibility - Supervisor, SE/PE/SPE
83500836-972b-5935-9a91-2d49f5aee3bf | note | Verifying Documents - This ITP Signed-off
bdee3db5-15e9-52a7-8824-1791d7e5e795 | date | Date Completed:
190dfc21-ff0e-4fd0-95e4-238a55ee0078 | checkpoint | 3.2 - Vegetation Removal Permit
8b1e8ba8-ed4e-5e18-94ec-0ed4554176e6 | note | Reference - MRPA Environmental Management Plan
350be7b9-845f-50ca-af30-d0e58fc5e650 | note | Acceptance Criteria - Prior to removing any vegetation or habitat:
39778b84-7e11-5d7b-b84e-aeb4969a1eec | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
601cacc9-8084-5a08-a955-a2461ed7653d | note | ○ A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
4d0f6886-fd52-522b-8b09-defa226f41dc | note | ii. fence and sign all sites nominated as No-Go Zones.
ba1c5186-9e99-5104-b630-63feb42aa9fd | note | Method - Document Review, Visual
4b6a5b61-0c47-52e3-8b46-1d69d6b2c84b | note | Frequency - Where applicable, prior to starting Works
4a7364af-f103-5497-95db-d9470eb016a4 | note | Category - HP*
015b5f3a-b7d7-5701-9be9-fbf977c4f732 | note | Responsibility - Supervisor, SE/PE/SPE
13de2958-80a2-5f88-a965-4c59c2e3f92e | note | Verifying Documents - This ITP Signed-off, Ecologist's Report, Vegetation Removal Permit
3e5d1ccd-899c-5075-8fb4-59ad599c1083 | date | Date Completed:
ea6f5683-587d-42c3-bf67-9f476a9845d1 | section | 4. Pre-Construction Activities
6b75c730-b969-4587-8132-88c18e23b0ce | checkpoint | 4.1 - Survey Set-out / Limits of Work
bdaabaaf-0b68-55cf-be09-53a6e45b8eb1 | note | Reference - IFC Drawings Section 201.03
36cbc574-2e64-5250-98ef-33bd4dd0a4e6 | note | Acceptance Criteria - The limits of clearing and grubbing shall be:
cb153443-4cc1-5ca4-a873-6694f7b4ed8b | note | a. the limits defined on the IFC drawings
e40890de-577e-59e4-944f-ea51c2b89600 | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
8732bfc7-8101-5657-99cd-a8bcc6b0477b | note | c. no more than the width required for completion of the Work under the Contract.
32760a7e-c66e-5744-844d-c115c363180f | note | Method - Measure, Visual
8a609701-09d1-55bf-917c-2b026da0da63 | note | Frequency - Once, prior to starting Works
6b5fa055-a8d4-53d9-9710-4c7363317d0d | note | Category - IP
d1e3f844-2c36-5519-b5b1-b6da74b4f1dc | note | Responsibility - Surveyor, SE/PE/SPE
2361863d-ad23-5f8b-ab2c-63c176c40d69 | note | Verifying Documents - This ITP Signed-off
17b44c63-33ee-53c6-8d0e-c97777077226 | date | Date Completed:
2c23d7c8-56c4-4c6e-803f-412b0bcd6940 | checkpoint | 4.2 - Cultural Heritage and Areas of Significance
dec0a27e-aa39-5a37-a2af-a6292d721c2b | note | Reference - MRPA Environmental Management Plan Section 201.10
990e9588-4d4b-51aa-8781-544b7436fb56 | note | Acceptance Criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
c80ccecc-6ef1-5499-8c9a-fc7b4f92e88d | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
17d35b8f-f4b8-5e51-a4a8-c3eb41ec3f6d | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
bf5bc31d-4f49-5018-b223-e8363e6479e5 | note | Method - Document Review, Visual
55b65ae9-686e-5810-a2ce-3753bf4e80ef | note | Frequency - Where applicable, prior to starting Works
3ca65e7e-e022-53f9-9dd7-92feba8120da | note | Category - HP*
3d70bfb1-b90c-5683-b0f4-180ddfe62a5f | note | Responsibility - Surveyor, SE/PE/SPE
6b41b017-4ffa-5872-a06d-0ef2d34ff0aa | note | Verifying Documents - This ITP Signed-off, Cultural Heritage Report
d8467764-eeae-5d4c-95a0-e6a39b76c4d9 | date | Date Completed:
cb4e7185-4004-4fac-9a5d-5d3333be6b23 | section | 5. Construction Activities
bf08cf07-2898-43ed-b8c8-2948e3396573 | checkpoint | 5.1 - Stripping of Topsoil
e8058611-e783-5d76-9c8e-bf6edf1ede53 | note | Reference - IFC Drawings Section 204.05
0512edc3-8448-55d8-b0bb-e14353814cd9 | note | Acceptance Criteria - Topsoil shall be stripped for the full width of the formation.
dca4e11a-0a2e-507f-8ae0-cc3dbdf7c45e | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
04811ce2-f6e3-52c5-bc07-489f37acdfc0 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
0d8f3679-1593-5e50-8756-a4f0156ba2d8 | note | Method - Visual
6c46bf0b-4b6b-5621-88e9-e237538dfb12 | note | Frequency - Each Site
dc1347ca-09b4-50a0-baf0-63e2904fff7b | note | Category - IP
f093ab9e-ce43-5692-b781-d27a040396a1 | note | Responsibility - Supervisor, SE/PE/SPE
b53f1f37-879f-5f85-8e60-fa316c227a2e | note | Verifying Documents - This ITP Signed-off
3696a439-af98-5a51-801c-630363562062 | date | Date Completed:
b304f65b-2812-4269-b867-75f2e58e7859 | checkpoint | 5.2 - Stockpiling
10d0b188-1f72-5e89-8112-9ed75d76d328 | note | Reference - MRPA Environmental Management Plan Section 204.05
e96869e5-c4ef-5120-b35b-34a81fadef28 | note | Acceptance Criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
34e36a4a-1494-572b-aeb0-126ce574c9f8 | note | ○ If this clearance is not possible,additional protection shall be provided.
e38de41b-6fde-58e4-8217-cbcf7487870a | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
f3a4063b-444e-543a-9bcd-9360a6ca0c20 | note | ○ Topsoil shall be re-spread as soon as practicable.
8f2b3061-2c59-52e1-b142-129b3da25225 | note | Method - Visual
d4e1304b-955f-52f0-8e2e-4193a1900702 | note | Frequency - Where applicable, each Site
6a941ca9-dd97-5788-ae16-564c0abab26a | note | Category - IP
dba322b6-96f3-5017-bfc3-28ea516b48d5 | note | Responsibility - Supervisor, SE/PE/SPE
cbde1aaa-b1ed-5b64-b791-dd2cc888e2e4 | note | Verifying Documents - This ITP Signed-off
83001b0f-dc44-5afe-9297-8f779ad584e4 | date | Date Completed:
c80070ae-3d7a-4c60-a3ca-6d12aa5b7d2d | checkpoint | 5.3 - Abandoned Services
19e349f0-b4c9-5481-95b3-81cf353f4c2c | note | Reference - IFC Drawings Excavation Permit Section 201.05
d6dd85a5-bb24-5d7b-829f-516ca10233bf | note | Acceptance Criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
3ff04773-2e9e-5ff6-b3c2-5ed020d71c52 | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
d8b11319-e95d-5f38-a942-0f20e6b0a992 | note | ○ Decommissioned services to be disposed of in a suitable manner.
c631cfe6-238e-5dbc-88d5-82108c5118c0 | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
df3de554-6f22-520f-9297-c010e83bc50c | note | Method - Visual
da52771e-e381-529d-996d-8cb2b423035a | note | Frequency - Where applicable, each Site
2a0eed87-beca-5398-8df2-2aa26fe51995 | note | Category - IP
fd12a5ba-206d-57f6-b411-2a9eb9fc0eb4 | note | Responsibility - Supervisor, SE/PE/SPE
7ba2db8d-94b1-5179-a703-954747038453 | note | Verifying Documents - This ITP Signed-off
d8e00862-00d0-5396-8342-371479eb970f | date | Date Completed:
65581f34-e9b8-45a9-aa94-43b9c5186ae0 | checkpoint | 5.4 - Clearing of Trees and Vegetation
f29c8fa6-1210-5a18-832b-0f6b96c81230 | note | Reference - IFC Drawings Section 201.04
a94490c3-a622-57ab-a59a-5b82a17a94ad | note | Acceptance Criteria - Clearing work shall not be undertaken outside of the specified limits of work.
9e4f9a45-e584-5fb8-9c13-1d3745aa7970 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
53b041e4-49fc-5a81-8f3c-4512b0c2dab9 | note | Method - Visual
ae13d428-a88b-52f5-a046-23829b9d4a97 | note | Frequency - Where applicable, each Site
da482118-5634-5345-8102-428a756cbc2f | note | Category - IP
e9e44eba-9cad-5a5a-b171-48d6a32d9fec | note | Responsibility - Supervisor, SE/PE/SPE
df6408b2-5676-5b79-92c8-a0ccd20934c7 | note | Verifying Documents - This ITP Signed-off
ee0df769-2d36-5630-b489-ba59c9e89a15 | date | Date Completed:
93cc9b35-a4dc-4908-8f04-23c2667960fc | checkpoint | 5.5 - Grubbing of Vegetation
81140d34-fac4-5afd-8d25-2cb9cff1a7e8 | note | Reference - IFC Drawings Section 201.05, Section 201.06
f7d59364-ffeb-5665-aa23-aba692210aef | note | Acceptance Criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
94a78537-63b3-5896-aa5d-eaf595ca112a | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
8c70d6fd-a9a8-500e-80dd-35acabdd6f21 | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
5f730986-8ebc-51c0-9417-503bfa415497 | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
2d563ee8-7caf-575c-b180-493166f37294 | note | Method - Visual
8466bf8e-3070-583c-88dc-637f77e0f214 | note | Frequency - Where applicable, each Site
e44901fd-a67e-567e-8a16-7fdcc662e239 | note | Category - IP
092fafc4-4138-5453-8c49-95b88824dd05 | note | Responsibility - Supervisor, SE/PE/SPE
86e47296-3b72-53c7-b61f-498f23d96610 | note | Verifying Documents - This ITP Signed-off
1867753c-3a1f-50fe-9a44-1e913c8d45c0 | date | Date Completed:
e865c5c1-2de6-4052-ba68-fd28a5c11ca5 | section | 6. Post-construction Activities
cc9694a5-e125-42ce-8ade-a88c03a8aeb2 | checkpoint | 6.1 - Disposal of Materials & Vegetation
cd136eb4-493b-528b-8fd4-f92377535f94 | note | Reference - Section 201.07
17fd15d9-3110-59ec-9b42-21d11e29cd2c | note | Acceptance Criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
e2908b28-30d3-5f41-928c-d05c05a65b43 | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
eef9689a-bf7a-531e-8b16-169d9292fded | note | ○ Tree trunks and large branches shall be removed from the site.
711e6a9b-e164-5d31-a694-8b3f54a88321 | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
0ecf6eae-fbe4-52b2-9d35-3408e3a0b3ae | note | ○ Attach: Delivery Dockets (for Items sent off Site)
2ddca178-19cf-52a4-9f19-9454dbac8f39 | note | Method - Visual
f26e030e-ce22-5b3a-8515-4f9a5e28cf07 | note | Frequency - Where applicable, each Site
dc43f60d-3013-5f9c-bd6e-6d577bd765b2 | note | Category - IP
95005841-82a2-5679-b5f4-f023623d788e | note | Responsibility - Supervisor, SE/PE/SPE
7faf3292-e1ae-557b-b3fc-4c89bc215f42 | note | Verifying Documents - This ITP Signed-off
286e5179-cac9-50ae-8393-a704f1d8d730 | date | Date Completed:
d6cf56b3-f0b8-413e-a41a-1472f7f2b002 | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
19633775-6046-5f87-b36e-0a88f6883573 | note | Reference - MRPA Quality Management Plan
993c6894-f31c-59c4-bf72-78097faf7abc | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
2dd0f9d0-55f4-59c1-a992-e56269bb75fe | note | Method - Document Review
4cff97e3-c3c5-5d12-a681-699afb18302f | note | Frequency - Once, prior to closure of this lot / element / Work area
4043a6ea-620c-53e6-88d6-752237f2d38e | note | Category - HP*
62122b52-4018-545a-bd34-caa02decf478 | note | Responsibility - SE/PE/SPE
2202cfac-f70c-500f-8e55-2991a81e7604 | note | Verifying Documents - This ITP
2fd12520-acb8-53be-90e4-c660671f8e24 | date | Date Completed:
51c2f1dd-5cca-445d-9060-35a8b2a64cbd | checkpoint | Final Inspection
7518e5a7-78a2-5697-8f58-ae36ed3a0d54 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2d5ee97f-d4ea-5365-80f1-835f976493fe | textbox | Name:
18babd2e-723b-521c-b42c-52317e7a4beb | textbox | Position:
2212ad70-7de5-5d1a-b0bc-ec03c823a613 | textbox | Date Completed:
778bb575-d48c-45eb-8edd-8c711f97c659 | signoff | Sign ITP
c51f959f-5e83-4e17-bff3-3284a14639f9 | checklist | ITP-273-CIV-ADL-Subgrade Preparation - Road Rev 0 | itp | ITP-273-CIV-ADL-Subgrade Preparation - Road
09dcb07a-8973-4bca-9067-e543401238c1 | section | 1. Referenced Documentation
353d9ccb-e890-4e08-9f76-1640db00d350 | checkpoint-no-value | Referenced Documentation
dd73eff8-f9e5-5c9f-ad8d-094277ca9ad3 | note | Document Title: ITP-273-CIV-ADL-Subgrade Preparation - Road
6b8824ce-1fa0-5bea-ab9a-a23aaecdaa8f | note | ITP Description: ADL-Subgrade Preparation - Road
25e11c32-9e88-5d2d-91e5-d66fb48a909a | note | Discipline (e.g. CIV/STR/RAIL): 273-CIV
ec4d66f9-cf25-5053-a2d8-66c915522cad | note | Revision Number: 0
af7f1121-429c-50bc-8688-c1831de41824 | note | Revision Date: 22/05/2025
9c9aedc7-e900-569f-b412-ae8052a1b34d | note | ITP created by: Abhi Patel
146f2023-6543-5a37-9863-a409add392e4 | note | ITP approved for use by: Aldrin Guinchoma
b4f54757-6daa-5e6b-afec-219505314848 | note | 1.1 - Non Dependent
a1d96ea8-4bea-53db-98d1-49b8d46f921e | note | Reference - VicRoads Section 204
9d1699e6-023c-5bea-b1fc-8b6ae4fbcda7 | note | 1.2 - Non Dependent
101c7c17-8eb0-5f23-bcb3-7ccfd11d0c31 | note | Reference - VicRoads Section 173
a4425afd-17b5-4ea1-8f49-d52972a48ef5 | section | 2. Preliminaries-Materials
7e63927a-923c-44dc-99cd-973137c02a17 | checkpoint | 2.1 - Material Approval
401ea3f0-e3cb-557b-a3ae-140ea64f59f4 | note | Reference - VR 204.04 (C)
9e8e3ce5-d5a1-50d5-973c-e9a18cd038df | note | Acceptance Criteria - Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
5be372c0-ac7d-5982-b71d-3d961e955d75 | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
6de095b9-276e-5453-b6d0-5a581dbc35d4 | textbox | Enter: Teambinder Material Approval number
563615e1-a1e2-5673-bceb-d0d674d38659 | note | Method - Document Review
67b7a7d3-006b-5669-ba24-2b7af89c6641 | note | Frequency - Once, for each mix material
1807d235-555f-5da7-a7e4-663d765f7fe6 | note | Category - HP*
cc9bef30-22fc-520b-860c-2ff3a2900dfc | note | Responsibility - Nominated Authority
cc4df168-3646-5800-bda5-7fa5e654bea8 | note | Verifying Documents - Teambinder Material Approval
391b00d8-65cb-5ffa-bd59-79b5cf1719b0 | date | Date Completed:
3e64166a-cc93-445e-a977-1d2bcd75998c | section | 3. Preliminaries-Documentations
c85e0726-c626-495a-9490-c3f523e2bfd9 | checkpoint-no-value | 3.1 - Non Dependent
71793db7-9512-4007-972c-61411aa8bb5f | section | 4. Pre-construction / Pre-installation Activities
4a897bd9-8e37-48f5-b988-95ac8530d249 | checkpoint | 4.1 - Survey Set-Out
95e5f64f-96cf-54d5-897f-9aab9a634901 | note | Reference - IFC Drawings
9872fa3a-670d-5919-a11c-1df3222368f0 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
c4365c10-b811-5ea8-9107-7ce0cf79d2f6 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
cf6c600f-8d8b-5c8c-8858-cadccf334e33 | note | Method - Verify
82b64af2-36aa-5491-b63d-9d0e582cc22e | note | Frequency - Prior to commencement of excavation
ddbc0ba6-6861-58b6-ac37-acd5ae798d20 | note | Category - IP
d30a99e6-beb9-581a-b97c-324e3acff50c | note | Responsibility - SE/Surveyor
de7214b3-52fa-534a-aa2e-a8b29e856800 | note | Verifying Documents - This ITP
a12a8f39-ccb8-5876-b74d-8b374a68cc2d | date | Date Completed:
88230224-1661-42ed-843a-af4e0ba8feb0 | section | 5. Construction / Installation Activities
49fa9fb5-affa-480e-b861-769b656f8d5c | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
277a8236-fa47-5abf-a13c-17ea63841617 | note | Reference - Section 204.06 (C), Section 204.06 (e) IFC Drawings
554b40ee-e934-52f2-807a-c4456c716319 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
60953a9a-fd91-5268-aac4-8e527499ed1f | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
971cf373-dfe3-5493-9818-9ac2a0e0eb38 | note | ○ Assigned CBR ≥ 2.5%
179943fd-50bc-565b-88f8-8170abe65ea6 | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
0628f244-e236-5bbd-a25f-864043592a94 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
0837b73d-7bfc-5d6e-9de9-d1f9e0b6197f | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
c07b012c-5f40-509d-b50d-fb4e695e9c5d | note | ○ Attach: Laboratory testing Verification:
5ba6cbc8-261f-5159-a0b2-ee76af06aab6 | textbox | Enter: Type A fill Lot Number:
f4c66724-8290-5bc2-a06c-88664c5305a9 | note | Method - Verify-Document Review
8254bf9a-5dec-564b-8850-02aaf3d5b533 | note | Frequency - Each lot
145c758e-6fd2-57f8-a944-3274b8550fe7 | note | Category - HP
1fdde727-56a5-5ebc-a083-1a91bc83cbaf | note | Responsibility - Nominated Authority
0c7614f7-1daf-57aa-b704-bd66fdca6dbe | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
8374593b-f874-56c6-8cbc-89341e6146fc | date | Date Completed:
e309c0f8-cb58-4e8e-9fd5-3f17f18d5daf | signoff | AUTHORITY HOLDPOINT
e8d1e764-d40e-4828-b6b7-91ced75ea20a | checkpoint | 5.2 - Material classified as silt
c21c4d96-721e-5fcf-b4c5-2b57222b24ec | note | Reference - Section 204.04 (b)
43ad4088-6c77-58d3-9f7a-fe303c84d7e1 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
9cb35d49-1ab2-59c9-8b2b-c20450cec117 | note | Method - Document Review
57e8136c-97ad-5632-bb21-251d9adcce61 | note | Frequency - Prior to commencing
dd1ee55e-b89f-53e8-afc4-d1d730b91851 | note | Category - HP
2c7823e2-9c7f-59c1-b35f-c0de91ca06bb | note | Responsibility - Nominated Authority
7ef8a81d-8994-5803-9974-38f2ee02d1d9 | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
65e16d0a-73bb-5cc3-a53a-b23843ee360e | date | Date Completed:
dfb4e3f7-35ba-481a-b35e-7db8d2cf4a27 | signoff | AUTHORITY HOLDPOINT
1b80955a-ad3f-4e45-ae76-223fbeff6939 | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
4a7f018d-8ae6-5bcf-943e-519f7872018a | note | Reference - Section 204.06 (f)
5cce6b65-6efa-506d-ace0-4852b7d59468 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
350c2cef-b316-5f4d-a86e-e984038c14ee | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
99cc2acd-6118-52a1-913c-f10dacc0be1f | note | Method - Site Inspection/ Document Review
5a35f4eb-a85b-5471-a199-2df2ddd64614 | note | Frequency - Prior construction of the regulating layer
66bcafad-e065-5a95-8a3c-7749046b4008 | note | Category - HP
f57eb615-ae9b-576f-8133-bec845a90a73 | note | Responsibility - Nominated Authority
54c42940-3163-5db9-abd8-29f9c470eeb0 | note | Verifying Documents - This ITP
24ccf69a-72b1-52e6-afd1-db2535981ac3 | date | Date Completed:
bb4a6ad9-c8c0-4af6-9615-05d638a70e42 | signoff | AUTHORITY HOLDPOINT
402eec62-32c4-47b1-a377-ec490ac58d07 | checkpoint | 5.4 - Unsuitable Material
20066514-5d00-55f2-a4b6-3d45da1f5006 | note | Reference - Section 204.07 (d)
47cd6f98-5066-5734-992d-a79f6de97a21 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
48eb0ade-ce97-5fdd-ae8a-7641018aab78 | note | Method - Visual inspection
5af9ac17-d923-5362-abb3-c7d008423866 | note | Frequency - Each lot
f6c7fbeb-073d-5c79-a572-f21ac2dd986a | note | Category - HP
a3d1fb95-62c5-5038-9048-cf0774092955 | note | Responsibility - Nominated Authority
79bfd0ed-c17e-5a2b-bbdf-b53185ee71e0 | note | Verifying Documents - This ITP
11c2b495-fde8-5dd4-abd9-69c18590d41a | date | Date Completed:
5fdd4def-bd13-494d-ac56-6a9632393938 | signoff | AUTHORITY HOLDPOINT
db2e8e51-802d-4773-ae50-194d0fc0fc37 | checkpoint | 5.5 - Groundwater
a2bcf881-cb3a-5e4b-b78c-4771b141ed5a | note | Reference - Section 204.06 h)
faac3644-a61f-59f2-b37d-6727145cb4c4 | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
21080e1e-1b7f-5eb6-af18-d13db8274485 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
71e524e6-0d90-5bbe-99aa-0fa9a8d0f7b3 | note | Method - Visual inspection
4a338b20-2665-553a-8ac7-c950dc35c6af | note | Frequency - Each lot
220947a7-28ad-5c87-bd79-c34846b27fc9 | note | Category - HP
80d7e92a-de01-5613-b38d-5c29ca54af5a | note | Responsibility - Nominated Authority
aaf18eae-9f73-592f-9938-b61cd473e1fb | note | Verifying Documents - This ITP
b9a9163b-efc4-565c-bb28-3b6963c58075 | date | Date Completed:
dbc38a4b-af68-4f27-a745-ea35e8dce07d | signoff | AUTHORITY HOLDPOINT
adb32f4f-5e4d-4870-9bff-49a69b3b4f9d | checkpoint | 5.6 - Cut to Fill Zones
4f51c306-5033-548b-a790-dd5f61def9fe | note | Reference - Section 204.06 g)
b4254336-d112-5897-8544-44011fcfa945 | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
fd23b02b-8b72-550b-8f83-00785814e1fb | note | Method - Site Inspection
436d5b16-7171-5ff4-8865-876feac40239 | note | Frequency - Each lot
0f540ed0-8c65-5aa3-91f7-fadfc85f5686 | note | Category - IP
c0ef740b-a329-5da3-a753-137450861e9b | note | Responsibility - SE/Site Supervisor
ee0a9013-9c8c-55dc-8c13-cb21c8eb93de | note | Verifying Documents - Sign ITP
85505d1d-36c8-502c-bee2-7fbeff0097c7 | date | Date Completed:
71d2a16a-feae-4a72-949d-cb07f2b75b27 | checkpoint | 5.7 - Proof Roll
6817d6e3-ac9f-58e2-9e0b-141b20fdf5dc | note | Reference - Section 173
2e379c93-2b67-5f83-a37c-a12afa0e981c | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
cdcf98ed-1ed7-5e98-8a4f-2a22d6347c97 | note | Method - Visual inspection
cfce6d4a-56fc-5b0c-b4dd-9c19b20ebf16 | note | Frequency - Each lot
94fcb228-3945-5c7a-9272-ec1b16b9b660 | note | Category - HP
401d65b0-9e70-59cc-9489-2884412f5fcb | note | Responsibility - Nominated Authority
e66225e5-fd35-5f0c-916a-1910a413d304 | note | Verifying Documents - This ITP
99c7415c-1b39-522d-84e2-1b7851872b4c | date | Date Completed:
84c3217a-5be7-41be-9c6f-58e8db8ba844 | signoff | AUTHORITY HOLDPOINT
27caee17-76f6-49b6-9d3d-a53e25a8049f | checkpoint | 5.8 - Compaction Testing
adc517dc-9eae-5278-a185-43216197cfbe | note | Reference - Table 204.131
28025764-95c6-5c93-9a19-e52bdd08c316 | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
3281946c-27cc-50d1-8a3e-357bd8eca62e | note | ○ Ripped and re-compacted material below Cut Floor Level
c12cb1d3-9ce1-5359-862a-6a8981841002 | note | ○ Scale A: Characteristic Density Ratio 99%.
b4c2a007-9c7b-5141-97ec-ea61285a8d7e | note | ○ Scale B: Characteristic Density Ratio 98%.
998a5270-5f02-595c-b5b2-4da343ab181f | note | ○ Scale C: Mean Value of Density Ratio: 100%
a8dd6b73-6ada-52d8-bfd4-18d54b04a1a5 | note | ○ Attach: Compaction Test Result:
430bc580-e1ef-5dea-983a-b8c97796cbd7 | note | Method - Document Review
92f2960e-bc20-5157-9bc2-135fc56dfaa1 | note | Frequency - Each lot
b98f798d-602d-50f3-a018-6749deea3d92 | note | Category - IP
c19d1b18-fa0d-502d-af00-925e0af8ecba | note | Responsibility - PE/SE
557d34be-b86b-5abe-966e-6d38dcce97c7 | note | Verifying Documents - Sign ITP, Attach Test Report
9debf407-f104-5561-88f2-951f96d2812a | date | Date Completed:
1e64fe55-7aef-4c9e-b1a4-ec7d432bd401 | checkpoint | 5.9 - Post Compaction Material Property Testing
94b88f3e-5330-52de-9849-88719e8514e7 | note | Reference - Section 204.04 (C), Section 204.14 (a) and Table 204.141 For Scal A, Section 204.14 (b) for Scale B IFC Drawings
213ece8f-14d8-5a33-a2c4-e066da23611b | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
491e71bd-323e-52b6-a444-ba5f00286f69 | note | Scale A:
783c0188-8849-5764-bf5d-3f6aca99bfb5 | note | — CBR and Swell as per IFC for design packge:
60b85037-d86d-5e78-83f7-cdd51ca2a2ce | note | — MRP-DPK-087-00-CDR-0002-0
c3abf1ea-f7a2-5a47-bfa5-fc698a67817b | note | — as per table VR 204.141
460e207f-4e05-51eb-9ae8-e524e13ff2ef | note | Scale B:
1c90c618-e86a-5e94-bcb8-0cbd41bf76b1 | note | — CBR and Swell as per IFC for design packge:
26729c03-6f9c-51af-bda1-3bcc4963ce4a | note | — MRP-DPK-087-00-CDR-0002-0
67900d4a-00bb-518c-afc7-4e56dd647485 | note | First Lot for Max Particle Dimension:
89df4476-c4e2-5b1f-b831-c9ca23dda715 | note | — After compaction Type B material shall have a maximum particle dimension of not more than:
915a4c60-0c85-503f-bd48-ecfaad6705fe | note | — 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
be39bb0b-e5a2-57c5-aa57-1eb32857c2f6 | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
a78136dc-3368-53f8-8aab-7e2b81e97c36 | note | ○ Attach: Post compaction test results:
5f4547b3-28dd-5987-ac63-06849e0be2cb | note | Method - Review Document
a809a2b1-a46c-57f4-b013-2869b9662448 | note | Frequency - Refer to Section 204
181eaece-e6a8-5bdd-b75a-029c8bc010ba | note | Category - IP
dc97c7bb-7a87-53a7-b931-753707f0dc6c | note | Responsibility - PE/SE
7201b939-c2e1-5ca2-a2a4-fa977a0fad1e | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
015a5371-5854-5451-aa46-39915541876c | date | Date Completed:
a05cb6bb-3ca7-4ac2-acaf-952af70bb34f | section | 6. Post Construction Activities
95e3c3b0-f72e-4b6b-85f9-0a7448432d7c | checkpoint | 6.1 - Survey Conformance
b27ea5df-064f-5eb5-be92-ce8f49f35436 | note | Reference - VicRoads 204.03f,g and h
638029b3-d4c5-5412-90b2-e6887dfcbdfd | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
050a1922-498f-55b5-8021-af0df7a77ed5 | note | Level tolerances (Scale A):
8017308e-fc44-5ff1-a67f-bf4a9fae2619 | note | — Range x = +5, -15mm
59239228-4857-5ba2-aa90-20df6c04ad3c | note | — Max S = 12 mm
2a350467-b9a6-5261-93b3-6bbcc2b61024 | note | — 80 measurements per lot
a13d987d-67b3-5a63-8996-63da65948161 | note | Level tolerances (Scale B):
e7e7c431-0754-5028-b6d6-224984b17783 | note | — Range x = +5, -25mm
e513662e-39bb-5ecd-9b9c-360552e4234f | note | — Max S = 15 mm
f724a1ae-8408-505e-8ebb-b3b607663d06 | note | — 40 measurements per lot
e3597c80-96e2-55e9-ac64-d38639473da1 | note | Level tolerances (Scale C):
0088500d-e7b9-5e34-8469-404cd700783a | note | — Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
0f69a527-db3e-572a-9751-d5f9c9bb435b | note | Method - Review Document
f8ed9129-e75d-5f49-b56c-1d7ccae75e34 | note | Frequency - Each lot
36ea462c-b60b-5b88-8925-9676c3a3e3da | note | Category - SCP
4c03fb61-cf9f-5c3e-b253-aea3eb615ff7 | note | Responsibility - SE/Surveyor
bb85935c-5f59-5ab5-b5a6-727463762666 | note | Verifying Documents - Sign ITP, Attach Survey Report
085979d8-bc45-5d74-bb4d-ec35c60fce72 | date | Date Completed:
0e3f5524-22f6-41c6-8c94-efe664b1b126 | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
830383a5-2e93-53a2-8ebc-9a7601cb52e9 | note | Reference - MRPA Quality Management Plan
4eef6a52-0ed0-556d-9349-6af7339a32bb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
53012d27-49c1-5773-8928-b6f4b9f20d4b | note | Method - Document Review
2a34738e-37e3-598a-846d-f6a740bc1dcf | note | Frequency - Once, prior to closure of this lot / element / Work area
5cb1a495-db76-57ee-a6ed-1063b011070b | note | Category - HP*
3fb07e5c-2dcb-5d6c-ac45-1533c281b376 | note | Responsibility - SE/PE/SPE
3b067177-c33b-5e19-9a0f-dae7cad63358 | note | Verifying Documents - This ITP
6d6fc070-d3e0-5dca-92ae-43d05ef97963 | date | Date Completed:
e4fd4f10-809b-433a-ada2-443787145b9f | checkpoint | Final Inspection
3dcb02a7-f241-5521-ba17-5e66126cdee6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
03b8855f-d544-5048-9161-15eca2ce1754 | textbox | Name:
57bae9cb-a95a-5350-ae61-7fc2b36b0fc8 | textbox | Position:
f75c926d-e085-56c7-a192-0b66f21bc43f | textbox | Date Completed:
a8dad709-a2c0-4a76-b8db-b76042c49be4 | signoff | Sign ITP
ef1fd386-7fe5-4e65-8d0a-16adff7a9349 | checklist | ITP-274-CIV-ADL-Type A Fill - Road Rev 0 | itp | ITP-274-CIV-ADL-Type A Fill - Road
b255144d-456a-4b49-a127-b49e87dacde9 | section | 1. Referenced Documentation
5c04fd0b-8f67-4951-b06f-2abe83ba3e43 | checkpoint-no-value | Referenced Documentation
69d40f4a-f4eb-5362-8e8e-87b811015b80 | note | Document Title: ITP-274-CIV-ADL-Type A Fill - Road
e6f7b97c-0521-5180-a006-bfbb4d1cac9e | note | ITP Description: ADL-Type A Fill - Road
7524b109-bbf4-5d01-be4c-c41b750095cb | note | Discipline (e.g. CIV/STR/RAIL): 274-CIV
9dc1d6a5-80f6-5d32-9c98-71af2a967513 | note | Revision Number: 0
48abbf27-2e59-543c-893f-313bf8e3fe0b | note | Revision Date: 22/05/2025
c5ff1a73-7cb3-538f-b98b-dfc093e01eda | note | ITP created by: Abhi Patel
52ab9c68-e673-5af1-a7cb-387fd4bc4f0d | note | ITP approved for use by: Aldrin Guinchoma
dd758b6f-4221-58ec-9ba7-038198ae80e1 | note | 1.1 - Non Dependent
bf92bb9c-0b79-57de-b7d9-5ae3212cc247 | note | Reference - IFC Drawings
3dedf8d7-508e-5a5e-8aeb-c682afe3ccb3 | note | ○ VicRoads Standard Section 176
54685c05-fb4c-5463-8b7f-b946a778ba46 | note | ○ VicRoads Section 204
89524db5-1d8b-535f-8dd8-da157a5fd62f | note | ○ Code of Practice RC500.20
3b285dc1-20f4-5cc2-948d-8cc4ce11c985 | note | ○ Code of Practice RC500.5
28f09aa6-3215-4f17-a1cc-d6160c606d61 | section | 2. Preliminaries-Materials
b2023879-f5a8-481f-81ee-205f438692e9 | checkpoint | 2.1 - Material Conformance
25e3f916-dd85-5004-98a3-ee28309f7181 | note | Reference - Section 204.04 b) Table 204.041
07da9808-e588-5dd9-a8ca-65d513bb65af | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
7cdbba44-1e0f-5660-b9b6-1f3c091ca658 | note | Type A Material shall meet the followingPOST FIELD COMPACTION requirements as follows:
2db0c205-c362-5829-87cd-36922906e47e | note | ○ Assigned CBR≥ 6%
7e59fc7c-5ee3-5ed3-8eab-97e574da2252 | note | ○ Swell ≤ 1.5%
3c681f8f-4c93-5f67-a493-28a4aa065fb2 | note | ○ Permeability ≤ 5X10-9 m/s
0340d306-3f17-5df4-bd35-997d560d5aa6 | note | ○ Grading:
cad3fc56-0601-5423-9d94-96fae71a2126 | note | — 75.0mm 100%
e7acfa9b-d930-53b5-a652-df4176ed79ef | note | — 4.75mm 40-80%
0d6529c0-a4e1-5bee-80e7-2fbcda05943a | note | — 0.075mm 10-40%
f474ad2f-2f9a-5eb6-8087-17c9ac5bbf79 | note | ○ PI Range: 6 to 25
1d3fc829-3712-57ad-ab24-2484297e0561 | note | ○ PI x %passing o.425 mm: 1000 max
1773d91c-e4f8-50a9-b5e9-0091417c4844 | textbox | Reference: Material approval in Teambinder:
fb1f15b7-01d5-5827-916e-d561afd89b33 | note | Method - Document Review
d64f9b80-b081-541b-9022-540620abd294 | note | Frequency - Once, for each material type
cee71ede-5e53-5113-889f-1e2878801d1c | note | Category - HP*
d860668e-95ba-5fe7-9c14-fc19baffee62 | note | Responsibility - SE/Nominated Authority
0dc6d567-730e-5043-a8a9-4426668caa22 | note | Verifying Documents - Teambinder Material Approval
73892107-66b8-523b-b07f-bbad6b57170a | date | Date Completed:
d2e8517e-c3a3-4471-8644-15839e913df4 | section | 3. Preliminaries-Documentations
1ee92118-3cec-4997-b30a-bc9e24cdd9fe | checkpoint | 3.1 - Pre-Commencement of Fill Works
8413f968-2dfe-5f2f-bbd6-df5f9a3dfcd4 | note | Reference - Section 204.10 (b)
bc768997-fb07-509e-80a1-440c83dbb75b | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
ce0e6bb2-9610-5a56-a29b-520d30a8a861 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
d99b3d56-048e-588c-a712-d91ac6bcdefa | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
a0ca7931-a39c-542e-91f1-9a43124e1c4f | textbox | Reference: Subgrade Preparation Lot Number:
37dc2bff-8bc2-54d8-85f6-5e71f6e6b383 | note | Method - Visual Inspection
26260b12-4f10-5cc9-b7a1-ede2bdf24fd6 | note | Frequency - Prior to commencement of fill works
0a188b95-8416-5997-8969-35d83eb8d962 | note | Category - HP
26f1578f-3dbf-5abf-9695-991eb97c391e | note | Responsibility - Nominated Authority
8bb38338-9015-5a5f-afea-27c3764eca12 | note | Verifying Documents - This ITP
efec891c-9fd5-5c8f-941d-ea76581cfde8 | date | Date Completed:
8b89ba69-61c0-48b2-8e82-ad30168e6017 | signoff | AUTHORITY HOLDPOINT
10be6132-444e-4d6e-aa65-9ac01df8a553 | section | 4. Pre-construction / Pre-installation Activities
381cb864-de16-4f7e-9a27-e2604718c047 | checkpoint | 4.1 - Survey Set Out
d5b2a507-4962-5bc8-a5dc-3e25e89c5a5f | note | Reference - Design Drawings
4dfea471-4c77-56ba-ba58-62225ea83191 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
67ed877a-a3cc-58ea-974c-dfb3d1e30a60 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
dbf38148-395d-5021-aa7f-d6e660e47724 | note | Method - Visual Inspection
c4a3649e-7122-5ee0-b1c4-4bf6fb0e3e35 | note | Frequency - Each lot prior to commencement
3868e0b6-e248-5b01-ac61-71fd2c2ee616 | note | Category - HP*
f5a356f3-8f2b-57b0-9b5b-caac3da8b2b8 | note | Responsibility - PE
59f12a0b-2011-558f-8181-7e38fe76413e | note | Verifying Documents - Signed ITP, Lot Map
ac6b7ac8-a32b-533f-8674-a90592152114 | date | Date Completed:
efc42326-494a-49b6-be35-b23050065a7c | section | 5. Type A Fill/Verge Activities
5db8d518-4dc0-45c0-83b0-006359072682 | checkpoint | 5.1 - Placing of Fill
0a34e2dd-b48f-5ee8-a3a7-aea7cb9d44b7 | note | Reference - Section 204.10
cf188989-4903-5e8c-bed5-6a2b783bf2fd | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
590a8db8-2ab9-5582-9ced-cf2b44294447 | note | Method - Visual
3c71d492-51be-5c8a-8996-d0fac2877dc8 | note | Frequency - Each Lot
a9a047ab-1da5-57e9-ab7c-8552c384ce31 | note | Category - WP
17da9fa7-b4f0-540a-894c-6269c7b37b6e | note | Responsibility - SE/Site Supervisor
7dd1148c-63de-5582-9c24-289f46c95d4e | note | Verifying Documents - Sign ITP
b491327d-a46d-59e6-9c8a-3963a22b95c9 | date | Date Completed:
1afb1947-5e15-4393-bb6e-c358dd9ff7fc | checkpoint | 5.2 - Test Roll
d349d95b-0797-588b-a6c7-2bf807599b49 | note | Reference - Section 173.03, Section 204.12
ef33aea0-ae70-5af6-bcb4-f20ced431020 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
207d8726-c8ad-5667-acf2-30fceba9f662 | note | Method - Test Roll as per 173.03
c6f6f299-4b55-5cbe-a049-bdad2b63271f | note | Frequency - Each Lot/Layer
78948789-addb-58e8-bff1-84f3a1cdcd8d | note | Category - HP
cde06611-d731-5bb6-8bc6-56d05d13d15a | note | Responsibility - Nominated Authority
61f3c70f-badf-5c2d-9131-b201eef9497f | note | Verifying Documents - Sign ITP
b8150c7a-d73c-54c9-bb7d-001bf47e7654 | date | Date Completed:
ce141adc-7179-41bd-9d87-84cc21ae5d7a | signoff | AUTHORITY HOLDPOINT
7f91f3f1-f5a1-4b4b-9392-6f665eb94544 | checkpoint | 5.3 - Compaction Testing
5876232a-95b3-5106-b032-58b075ffbeeb | note | Reference - Table 204.131, Section 204.14 c) Table 204.142
6e5f679f-5f9e-54dd-bfda-70f97dc56dea | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
4e4cd477-88e6-5d6b-8b76-f84777e10ee4 | note | ○ Standard Compactive Effort
e4b3285a-ffdd-505c-9de5-d35638d6e54d | note | — For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
694f8604-ad6b-527b-89aa-45d5c4d78b2a | note | ○ Compaction and Moisture content
a9edeb5c-a0aa-57f1-9d59-f931c3106cea | note | — Scale A: Characteristic Density Ratio 99%.
1f1ead93-5b42-5224-8ba6-17105e1d4161 | note | — Scale B: Characteristic Density Ratio 98%.
d24d3c9d-f20d-53fd-a67b-2521be404b89 | note | — Scale C: Mean Value of Density Ratio: 100%
59830395-80d9-50cd-810d-98a7b23fc473 | note | ○ Lot size - the leser of one day's production or 5,000sqm
c0ed5831-8f8a-5d99-b8b7-a07f1b89eef1 | note | ○ ATTACH: COMPACTION TEST RESULTS
2aa09247-598f-5cc2-99dc-f11c3975bbd8 | note | Method - Review Document
3c14dd10-a3b3-5dc8-a3d5-2ec3b6ba3176 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
a88009a2-176f-5dc5-af62-4e3d719b8cf5 | note | Category - IP
d8f35a2f-c087-5e52-91bc-f36450ec2bfa | note | Responsibility - SE/Site Supervisor
53c06543-0074-51a4-b898-c5491eaa8fdd | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
c8b578f9-d612-5575-94bd-aceec0ede687 | date | Date Completed:
09c26bbb-7c6b-4720-bbe6-959708bc825d | checkpoint | 5.4 - Preparation of final surface
b976650a-b2af-5c6a-b759-78f80564c9e7 | note | Reference - Section 204.15, 204.03 (g)
80ebf7d7-1a1a-5658-98c7-1a134ce9febc | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
5a4d791d-75cf-5358-bcd4-329ae9cdfdb1 | note | Method - Measure
05ccb54a-154f-5ac1-96a8-96610aca2997 | note | Frequency - Top layer
d8442e34-4a68-5844-a7a8-64422f6bc658 | note | Category - IP
e18d1329-2dc5-510a-8c98-3232a2ea071f | note | Responsibility - SE/Site Supervisor
59db97c1-d5aa-5b3c-b04a-eee6339cd112 | note | Verifying Documents - Signed ITP
1cfcc00d-0029-53a4-9b07-3a7eb40fbff9 | date | Date Completed:
9a2a2f0b-c560-417b-9b3e-4fc879f4bb41 | section | 6. Post-construction Activities
c888484e-9c63-44b7-a5d7-490dcd723dfd | checkpoint | 6.2 - Survey Conformance
af71c676-f0e1-5aa9-b98c-38c2f0832552 | note | Reference - VicRoads 204.03f,g and h
997a8af5-c284-58e5-a835-89d1723d0882 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
ce132242-302d-5e96-91d7-2da31abaf8f1 | note | ○ Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
17f0adfb-63ee-57ef-8301-b145ed4c1a5e | note | Method - Document Review
b76e1871-e357-5977-b51d-e69b224088f3 | note | Frequency - Top of Type A/Verge
f8e955e6-d5da-50b1-83ba-1ae0d3d823e3 | note | Category - IP
80b217e6-4e10-51f8-8bb6-b764c158e926 | note | Responsibility - Surveyor, SE/PE/SPE
16754cfc-22d9-5049-9a72-56e5661b17e2 | note | Verifying Documents - This ITP, Survey Conformance Report
37afd066-a92a-52e1-a648-92898e5eda3e | date | Date Completed:
f3c836f0-341a-45f0-a87d-b0f0a4984f6a | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
d6401255-312b-5a57-8a60-fda2e0dd80de | note | Reference - MRPA Quality Management Plan
c4244885-9f7b-58d0-8844-2a6dc8e37a3c | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
3d017004-de8c-5102-8cb9-8f3d4cd472d2 | note | Method - Document Review
6f1a76ea-1c7c-5465-ba2d-0dac163e9572 | note | Frequency - Once, prior to closure of this lot / element / Work area
8897ae7d-5c1f-5e13-a156-5b233813b2e2 | note | Category - HP*
324fef95-7474-588d-9e6e-764bfb35d4f5 | note | Responsibility - SE/PE/SPE
fcda5bf3-9325-54c6-8a73-0565dd2278b1 | note | Verifying Documents - This ITP
ad3f92d1-b71e-5869-ae19-37cf41d6b98f | date | Date Completed:
a363750a-b312-4572-85b3-b24bab0eee62 | checkpoint | Final Inspection
c4318869-28ab-5977-82be-5e99c25ce3b8 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a7de28b7-e2d0-526f-91df-873727bb71d0 | textbox | Name:
b393fd46-a04a-52b6-8161-f3958e4cbaa5 | textbox | Position:
40049ab7-4d14-5bbb-b6bb-a6d5eac5c7c5 | textbox | Date Completed:
9ea54448-fdb6-4615-8efb-acbdfde340c3 | signoff | Sign ITP