## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-284-CIV-ADL-Stormwater Drainage | itp |  |  |  |  | ITP-284-CIV-ADL-Stormwater Drainage Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-284-CIV-ADL-Storm water drainage ITP
label | ITP Description: ADL-Storm water drainage ITP
label | Discipline (e.g. CIV/STR/RAIL): 284-CIV
label | Revision Number: 0
label | Revision Date: 12/06/2025
label | ITP created by: Abhi Patel
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 701
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 705
label | 1.3 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries-Materials
checkpoint | 2.2 - Drainage Flexible Pipes
label | Reference - Section 701.08
label | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
checkpoint | 2.3 - Precast Drainage Pit
label | Reference - Section 705.07, Section 705.04, Section 705.09
label | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
checkpoint | 2.4 - Cast in Place Drainage Pit
label | Reference - Section 705.06 IFC Drawings
label | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
checkpoint | 2.5 - Drainage Pit - Step Irons
label | Reference - Section 705.04, Section 705.12
label | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
checkpoint | 2.6 - Drainage Bedding Material
label | Reference - Section 701.09
label | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
checkpoint | 2.7 - Drainage Backfill Material
label | Reference - Section 701.09, Section 701.19
label | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Pits - installation
label | Reference - IFC Drawings VR 701, VR 705
label | Acceptance Criteria - All the pits for this separable package are installed and respecting Lots are closed
label | Method - Document review
label | Frequency - Eachdrainage separable package
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.1 - Pipes - installation
label | Reference - IFC Drawings VR 701, VR 705
label | Acceptance Criteria - All the pipe runs for this separable package are installed and respecting Lots are closed
label | Method - Document review
label | Frequency - Each drainage separable package
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Flushing & CCTV
label | Reference - Section 701.28, Section 701.30
label | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | Method - Record Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP, CCTV Reports
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - As Built Survey
label | Reference - Section 701.10
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP, As Built Survey Report
date | Date Completed:
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.3 - Repairs to Damaged Pipes
label | Reference - Section 701.31
label | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | — cracks wider than 0.5 mm
label | — spalling of concrete
label | — exposed reinforcement
label | — joints that are not fully engaged.
label | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
label | — longitudinal cracks greater than 2 mm
label | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | — circumferential cracks around part of the circumference with width greater than 4 mm
label | — penetrations with area greater than 400 mm2
label | — pipe joints that are separated.
label | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs | [5 empty] | CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs Rev 0
section | Details
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs
label | Checklist Description: Material delivery inspection-Precast Pits and RCPs
label | Discipline (e.g. CIV/STR/RAIL): 003-Civil
label | Revision Number: 0
label | Revision Date: 6/12/2023
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
checkpoint | 1 - Delivery Details
label | Reference -
label | Acceptance Criteria - Enter: Delivery Docket Number: [Free text box]:
textbox | Enter: Delivery Date:
textbox | Enter: Element ID (s):
label | ○ Attach: Delivery Docket and packaging Slip
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 2 - Packaging Inspection-Quantity
label | Reference -
label | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | Method - Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 3 - Packaging Inspection-Delivery Contents
label | Reference -
label | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 4 - Packaging Inspection-Birth Certificate
label | Reference -
label | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
label | ○ Precast components are to be marked on the birth certificate.
label | ○ Cast date and lot are to be marked on the birth certificate.
label | Method - Document Review
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 5 - Packaging Inspection-Transport
label | Reference -
label | Acceptance Criteria - Is the condition of packaging acceptable.
label | ○ Precast items are protected from damage during the transport
label | Method - Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 6 - Fault IDs:
label | Reference -
label | Acceptance Criteria - For each precast type delivered, check for the following:
label | 1 - Identification markings match the Precast type
label | 2 - Precast Pit fabricated as per drawings - inverts size.
label | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
label | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
label | 5 - Precast Pits - Inverts coliding.
label | 6 - Precast Pits and RCPs - Inspect for Cracks.
label | 7 - Precast Pits and RCPs - Inspect for Spalling/Damage to concrete surface.
label | 8 - Precast Pits and RCPs - Inspect for Exposed Reinforcement.
label | 9 - Precast Pits and RCPs - Inspect for correct Lifting mechanism.
label | 10 - RCPs - Inspect rubber rings
label | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
label | Method - Visual, Measure
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 1
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 2
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 3
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 4
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 5
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation | [5 empty] | CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
label | Checklist Description: ADL-Stormwater Drainage Pipes Installation
label | Discipline (e.g. CIV/STR/RAIL): 017-CIV
label | Revision Number: 0
label | Revision Date: 12/06/2025
label | ITP created by: Abhi Patel
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 - Non Dependent
label | Reference - VR 701
label | 1.2 - Main ITP
label | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
label | Acceptance Criteria - This ITP Should be used in Conjunction with ITP-284-CIV-ADL-Stormwater Drainage ITP
textbox | Enter: Main ITP Teambinder Lot Number
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Bedding
label | Reference - VR 701
label | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
checkpoint | 2.2 - Backfill Material
label | Reference - VR 701
label | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
checkpoint | Stabilized Sand
label | Reference - VR 701
label | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Subcontractor QA Submissions and ITP
label | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
label | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | ○ ATTACH: Subcontractor Signed ITP
label | Method - Document Review
label | Frequency - Each Lot (in case undertaken by subcontractor)
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
section | 4. Pre-construction Activities
checkpoint | 4.1 - Survey Set-Out-
label | Reference - 710.1
label | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ○ The culverts constructed shall be constructed true to line and level.
label | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
label | Method - Survey, Measure
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - This ITP, Main Lot Map
date | Date Completed:
section | 5. Construction Activities
checkpoint | 5.1 - Trench Excavation
label | Reference - VR 701.15
label | Acceptance Criteria - For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
label | ○ Horizontal Clearance to wall of trench
label | Pipe Culverts:
label | ○ 300mm<Horizontal clearance for corrugated metal culverts<1000mm
label | ○ 300mm<Horizontal clearance for other Pipe culverts<600mm
label | Box Culverts:
label | ○ 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
label | Method - Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Trench Base
label | Reference - VR 701.15
label | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant
label | Method - Visual
label | Frequency - Each Lot
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Bedding-Placement and compaction
label | Reference - VR 701.16, VR 701.20 (a)
label | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | — 100 mm where D < 1500 mm
label | — 200 mm where D ≥ 1500 mm
label | ○ Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
label | Method - Visual, Measure
label | Frequency - Each Lot
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Laying pipes-Bedding conformity
label | Reference - VR 701.17
label | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
label | ○ Laying of pipes or box culverts shall commence from the downstream end.
label | Method - Visual
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Pipe Laying
label | Reference - VR 701.16, VR 701.17
label | Acceptance Criteria - Laying of pipes or box culverts shall commence from the downstream end.
label | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
label | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
label | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
label | Method - Visual
label | Frequency - Each Pipe
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Pipe Joints and rotation
label | Reference - VR 70.18
label | Acceptance Criteria - All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
label | Method - Visual
label | Frequency - Each Pipe
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.7 - Conformity with drawings
label | Reference - VR 701.10
label | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ○ ATTACH: Survey Report
label | Method - Measure
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | 5.8 - Backfill-Under area to be paved
label | Reference - VR 701.19 (a) i
label | Acceptance Criteria - Culvert under area to be paved
label | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
label | Method - Visual
label | Frequency - Each Lot
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5. 9 - Backfill-Under area not to be paved
label | Reference - VR 701.19 (a) ii
label | Acceptance Criteria - The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
label | Method - Visual
label | Frequency - Each Lot
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.10 - Backfilling with cement stabilised sand
label | Reference - VR 701.19 ( c)
label | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
label | Method - Visual
label | Frequency - Each Lot
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.11 - Backfill Placement
label | Reference - VR 701.20
label | Acceptance Criteria - backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | Method - Visual
label | Frequency - Each Lot
label | Category - SP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.12 - Backfill Compaction
label | Reference - VR 701 (b)
label | Acceptance Criteria - 20% of all bedding/Backfill layers for each culvert shall be tested.
label | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
label | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | Method - Test
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Compaction and Moisture content tests
label | Reference - VR 701.20
label | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
label | ○ Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | ○ ATTACH: Compaction and Moisture content test results:
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - Test Results
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | CHK-018-CIV-ADL-Stormwater Drainage Pits Installation | [5 empty] | CHK-018-CIV-ADL-Stormwater Drainage Pits Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
label | Checklist Description: ADL-Stormwater Drainage Pits Installation
label | Discipline (e.g. CIV/STR/RAIL): 018-CIV
label | Revision Number: 0
label | Revision Date: 12/06/2025
label | ITP created by: Abhi Patel
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 - Non Dependent
label | Reference - VR 701
label | 1.2 - Main ITP
label | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
label | Acceptance Criteria - This ITP Should be used in Conjunction with ITP-284-CIV-ADL-Stormwater Drainage ITP
textbox | Enter: Main ITP Teambinder Lot Number
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Bedding
label | Reference - VR 701
label | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
checkpoint | 2.2 - Backfill Material
label | Reference - VR 701
label | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Subcontractor QA Submissions and ITP
label | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
label | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications..
label | ○ ATTACH: Subcontractor Signed ITP
label | Method - Document Review
label | Frequency - Each Lot (in case undertaken by subcontractor)
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
section | 5. Construction Activities
checkpoint | 3.1 - Survey Set Out
label | Reference - VR 701.10
label | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Pit Excavation
label | Reference - VR 705.05
label | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - Excavation Foundation
label | Reference - VR 705.05
label | Acceptance Criteria - Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
label | ○ > 80mm for clay foundations
label | ○ > 150mm for rock foundations
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.4 - Jointing
label | Reference - VR 705.11
label | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.5 - Shaping of Floor
label | Reference - VR 705.13
label | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.6 - Step Irons
label | Reference - VR 705.12
label | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.7 - Fitting of Covers
label | Reference - VR 705.17
label | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | ○ Height shall be within 10mm of the design level
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.8 - Backfilling Around Drainage Pits
label | Reference - VR 705.18
label | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Placement of Pit-Conformity with drawings
label | Reference - VR 701.10
label | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ○ ATTACH: Survey Report
label | Method - Measure
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP