## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-285-STR-CPD- Coloured Surface Treatment (Omni Grip) | itp |  |  |  |  | ITP-285-STR-CPD- Coloured Surface Treatment (Omni Grip) Rev 1
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-285-STR-CPD-Coloured Surface Treatment (Omni Grip)
label | ITP Description: CPD-Coloured Surface Treatment (Omni Grip)
label | Discipline (e.g. CIV/STR/RAIL): 285-STR
label | Revision Number: 1
label | Revision Date: 13/06/2025
label | ITP created by: Andrew Carlini
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - Vicroads Section 431 April 2018
label | 1.2 - Non Dependent
label | Reference - Vicroads Section 175 November 2019
label | 1.3 - Non Dependent
label | Reference - Vicroads Section 721 Feburary 2017
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Primer and Binder Product Details
label | Reference - Vicroads 431.03
label | Acceptance Criteria - The contractor shall submit the following details for the primer and binder product to be used to the Superintendent prior to works beginning:
label | (i) priming materials type and source
label | (ii) binder type and source
label | (iii) manufacturer's recommendations/instructions for priming material supply and placement
label | (iv) manufacturer's recommendations/instructions for binder mix quantities and tolerances on mixing components
label | (v) manufacturer's recommendations/instructions for mixing of binder and components
label | (vi) manufacturer's recommendations/instructions for pot life of binder, i.e. time of mixing to time of spreading
label | (vii) manufacturer's recommendations/instructions for placement of binder including application rates and tolerances and placement temperatures
label | (viii) manufacturer's recommendations/instructions for curing
label | (ix) manufacturer's recommendations/instructions for accelerants (if applicable)
label | (x) manufacturer's recommendations/instructions for supply and placement of protective sealers
label | (xi) type of coloured pigment.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Per Material
label | Category - IP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material certificate
date | Date Completed:
checkpoint | 2.2 - Aggregate Product Details
label | Reference - Vicroads 431.03
label | Acceptance Criteria - The contractor shall submit the following details for the aggregate product to be used to the Superintendent prior to works beginning:
label | (i) aggregate type, source and gradation
label | (ii) manufacturer's or Contractor’s recommendations/instructions for placement of aggregate including spread rate
label | (iii) Polished Stone Value (PSV) – aggregates shall have a minimum PSV of 54.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Per Material
label | Category - IP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material certificate
date | Date Completed:
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Product performance documentation
label | Reference - Vicroads 431.04
label | Acceptance Criteria - Documented evidence of satisfactory performance over at least 5 years for the coloured surface treatment in a heavy urban traffic environment shall be provided with the Tender. The documentation may include references from clients, details of sites with the coloured surface treatment, evidence of texture with time, evidence of skid resistance with time, evidence of colour retention with time, evidence of durability with time.
label | ○ The Superintendent may request additional information regarding performance of the proposed coloured surface treatment and shall determine if the documented evidence is satisfactory. Only products with satisfactory documented evidence will be considered for award of the works.
label | ○ The Superintendent may require a sample of the material to be provided. The sample shall be a minimum size of 300 mm x 300 mm which is representative of the material to be applied.
label | ○ Acceptance of the documented evidence and acceptance of the proposed coloured surface treatment does not guarantee the performance of the coloured surface treatment, and does not relieve the Contractor from any performance requirements.
label | ○ Restricted use of untried products on a trial basis shall be subject to the approval of the Superintendent.
label | Method - Document Review
label | Frequency - Per Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release, PCCP Accreditation
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - Surface preparation
label | Reference - Vicroads 431.07
label | Acceptance Criteria - The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | ○ The area around making area is also clean to avoid tracking into the marking area
label | ○ Removal of existing unsound, obsolete or redundant pavement markings
label | ○ Removal of any foreign materials and debris within reasonable limits.
label | ○ All liftring mechanisms and joins between the lid and frame shall be masked and protected such that te coloured surface treatment does not impede lifting and replacing lids
label | Method - Measure, Visual, Document Review
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Redundant pavement / unsuitable marking markers removal
label | Reference - Vicroads 431.07
label | Acceptance Criteria - Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.3 - Set out the works for installation of pavement markings
label | Reference - Vicroads 431.08
label | Acceptance Criteria - Coloured surface treatments shall not be placed until the Superintendent agrees that the prepared road surface is ready for surfacing
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5. Construction Activities
checkpoint | 5.1 - Application of Coloured Surface Treatment
label | Reference - Vicroads 431.08
label | Acceptance Criteria - Check conditions for application of coloured surfface treatment.
label | (i) Priming Materials and binder installed as per manufacturer’s recommendations. Application rate for shall be provided to the Superintendent
label | (ii) Binder and Aggregate shall ve spread to provide a uniform thickness over the site
label | (iii) The pavement tempreture shall be measured and recorded at least every 2 hours during the works
label | (iv) The same materials used with those nominated in the certifications.
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Clean up
label | Reference - Vicroads 431.10
label | Acceptance Criteria - Superintendent shall agree the site is neat, tidy and free of excess aggregate prior to opening to traffic.
label | (i) All excess materials shall be removed from the site and disposed in accordance with EPA Requirements
label | (ii) All masking shall be removed prior to opening the site to traffic
label | (iii) Excess aggregate shall be removed from finished surface prior to opening to the site to traffic.
label | (iv) All materials which become loose after inital clean-up shall be removed 24 hours, 3 days and 14 days after placement
label | Method - Visual /Site Inspection
label | Frequency - Per Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-construction Activities
checkpoint | 6.1 - Uniform Finish
label | Reference - Vicroads 431.11
label | Acceptance Criteria - Coloured surface treatments shall provide a visually uniform surface with uniform aggregate retention, and be free from delamination, stripping and areas of wear/scuffing.
label | Method - Visual /Site Inspection
label | Frequency - Per lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.2 - Surface Texture
label | Reference - Vicroads 431.11 (a)
label | Acceptance Criteria - Acceptance of work for surface texture shall be based on visual assessment, noting a lot shall be the lesser of one day's production or each 500m2
label | Method - Visual /Site Inspection
label | Frequency - Per lot When applicable
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.3 - Skid Restistance
label | Reference - Vicroads 431.11 (b)
label | Acceptance Criteria - The Superintendent may require that the work be tested and assesed for skid resistance using one of the following methods:
label | (i) SCRIM: The length of the entire site shall be tested using SCRIM ® in the left and right wheel paths in every through traffic lane of the site. The site shall be tested within 4 weeks of initial placement, and within 8 weeks prior to the end of the defects liability period. The Superintendent may undertake additional skid resistance testing of the site at any time during the defects liability period. The skid resistance of the coloured surface treatment shall be a minimum of 0.55 sfc at any time during the defects liability period
label | (ii) Portable Pendulum Friction Tester: The coloured surface treatment shall be tested using a pendulum friction tester in accordance with AS 4663 – Wet method. Each lot shall have 5 randomly selected test locations selected in accordance with VicRoads test method RC316.10 – Selection of test sites within a lot. Each lot shall achieve a minimum mean British Pendulum Number (BPN) of 55 with no individual test location having a BPN of less than 50 at any time during the defects liability period.
label | ○ Attach: Either report from Testing Method for skid resistance
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per lot When applicable
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.4 - Colour
label | Reference - Vicroads 431.11 (c)
label | Acceptance Criteria - The colour of the finished surface shall be a Rating 3 Approximate Match (or better) with one of the following Australian Standard 2700 2011 colours as listed in Table 431.111.
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per lot When applicable
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.5 - Maintenace and Repairs
label | Reference - Vicroads 431.12
label | Acceptance Criteria - The Contractor shall be responsible for monitoring and maintenance of the coloured surface treatment from the time of placement, until the end of the defects liability period.
label | ○ Areas of delamination less than 0.01 m2 are not required to be repaired, unless the total of defective areas exceeds 1% of the total area. Areas of defect shall be agreed with the Superintendent. Defective areas of coloured surface treatment shall be squared up and removed and replaced.
label | ○ Repairs shall be undertaken within 4 weeks of notification by the Superintendent. Urgent repairs shall be started onsite within 24 hours of notice by the Superintendent.
label | ○ The Contractor shall advise the Superintendent in writing of the proposed treatment for any repairs before undertaking the work
label | Method - Visual /Site Inspection
label | Frequency - Per lot When applicable
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.6 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP