## Health and Safety
Health and Safety
type | name | values
checklist | Health and Safety
section | Site Activities
checkpoint | SSSP docs have been submitted to main contractor
checkpoint | SSSP docs hard copy is held in Site Office
checkpoint | SSSP docs have been approved and signed off by Main Contractor | Photo required
checkpoint | Subcontractor site inductions complete | Photo required
checkpoint | Subcontractor has read and signed onto all Task Analysis | Photo required
checkpoint | Subcontractor Licences have been veiwed and are upto date | Photo required
checkpoint
checkpoint
checkpoint
section | Elevated Work Platforms
checkpoint | Correct EWP has been delivered fit for purpose
checkpoint | EWP daily checklists have been completed | Photo required
checkpoint | Working area for EWP has been inspected and is flat and level. Clear of obstructions | Photo required
checkpoint
section | Construction Type
checkpoint | Working at Heights
checkpoint | General Construction - Walls
checkpoint | General Construction - Ceiling
checkpoint | General Construction - Roof
checkpoint | General Construction - Room
checkpoint | General Construction - Demolition
checkpoint | General Construction - Ambient Room
checkpoint | General Construction - Cool Room
checkpoint | General Construction - Freezer Room
checkpoint | General Construction - Clean Room
checkpoint | General Construction - Repair Work

## Deliveries
Deliveries
type | name | values
checklist | Deliveries
section | Site Review
checkpoint | Subcontractor have discussed and agreed with Main Contractor an appropriate Truck Route for delveries. | Photo required
checkpoint | Subcontractor have discussed and agreed with Main Contractor an appropriate Material Lay Down area. | Photo required
checkpoint | Material access point into site / work face has been arranged and agreed
checkpoint | Material picking slips matchdelivery dockets | Photo required
checkpoint | Material has arrived undamaged | Photo required
checkpoint | Material has been unloaded and placed in laydown area undamaged | Photo required
checkpoint
section | Laydown Area
checkpoint | Area is Flat and Level for unloading material | Photo required
checkpoint | Packs of Panel are inside undercover | Photo required
checkpoint | Packs of Panel are outside exposed to the weather | Photo required
checkpoint | Material has been stored in an area that is clear and safe from other workers | Photo required
section | Machine Operator
checkpoint

## Project Specs
Project Specifications
type | name | values
checklist | Panel Specifications
section | Panel Core Type
checkpoint | XFLAM Panel | Photo required
section | Panel Thickness
checkpoint | 50mm | Photo required
checkpoint | 100mm | Photo required
checkpoint | 150mm | Photo required
section | Panel Profile
checkpoint | Flat / Flat | Photo required
section | Panel Colour
checkpoint | Titania | Photo required
section | Aluminiumm Extrusion Size and Finish
checkpoint | 40x40 Angles | Photo required
checkpoint | 50x50 Angles | Photo required
checkpoint | 70x50 Angles | Photo required
checkpoint | Mill Finish Extrusion | Photo required
section | Construction Type
checkpoint | Standard Build | Photo required
section | Drawings
checkpoint | Architecture IFC Drawings have been provided to Subcontractor | Photo required

## C&C Freezer Coolroom
C&C Freezer
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build
checkpoint | Pit depth is correct
checkpoint | Pit is dry | Photo required
checkpoint | Pit edges are smooth and level | Photo required
checkpoint | Pit Threshold has been boxed out and is correct | Photo required
checkpoint | Pit is square and as per drawing
checkpoint | Ceiling supports have been installed correctly | Photo required
checkpoint | Layflat has been correctly layed with Mastic | Photo required
checkpoint | F-Mould has been correctly fixed over Layflat with Mastic | Photo required
checkpoint | F-Mould fixings are at the correct centres
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated Panel Installation
checkpoint | F-Mould has been mastic bed sealed ready for panel installation | Photo required
checkpoint | Panel has veen prepared in readiness for installation - Mastic applied to slip joins | Photo required
checkpoint | Panel has been prepared in readiness for installation - Steel skin removed at base | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Underfloor build - Insulation Install
checkpoint | Heated cables have been installed to the correct spacing | Photo required
checkpoint | Correct sand depth has been achieved | Photo required
checkpoint | Polythene has been installed and taped correcly | Photo required
checkpoint | Underfloor insulation has been installed correcly | Photo required
checkpoint | Building panel has been installed correcly
hold point | Project Manager to sign off | Signature required
section | Completed Works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded Damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Bakery Freezer
Bakery Freezer
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build
checkpoint | Pit depth is correct
checkpoint | Pit is dry | Photo required
checkpoint | Pit edges are smooth and level | Photo required
checkpoint | Pit Threshold has been boxed out and is correct | Photo required
checkpoint | Pit is square and as per drawing
checkpoint | Ceiling supports have been installed correctly | Photo required
checkpoint | Layflat has been correctly layed with Mastic | Photo required
checkpoint | F-Mould has been correctly fixed over Layflat with Mastic | Photo required
checkpoint | F-Mould fixings are at the correct centres
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated Panel Installation
checkpoint | F-Mould has been mastic bed sealed ready for panel installation | Photo required
checkpoint | Panel has veen prepared in readiness for installation - Mastic applied to slip joins | Photo required
checkpoint | Panel has been prepared in readiness for installation - Steel skin removed at base | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Underfloor build - Insulation Install
checkpoint | Heated cables have been installed to the correct spacing | Photo required
checkpoint | Correct sand depth has been achieved | Photo required
checkpoint | Polythene has been installed and taped correcly | Photo required
checkpoint | Underfloor insulation has been installed correcly | Photo required
checkpoint | Building panel has been installed correcly
hold point | Project Manager to sign off | Signature required
section | Completed Works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded Damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Seafood Freezer
Seafood Freezer
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build
checkpoint | Pit depth is correct
checkpoint | Pit is dry | Photo required
checkpoint | Pit edges are smooth and level | Photo required
checkpoint | Pit Threshold has been boxed out and is correct | Photo required
checkpoint | Pit is square and as per drawing
checkpoint | Ceiling supports have been installed correctly | Photo required
checkpoint | Layflat has been correctly layed with Mastic | Photo required
checkpoint | F-Mould has been correctly fixed over Layflat with Mastic | Photo required
checkpoint | F-Mould fixings are at the correct centres
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated Panel Installation
checkpoint | F-Mould has been mastic bed sealed ready for panel installation | Photo required
checkpoint | Panel has veen prepared in readiness for installation - Mastic applied to slip joins | Photo required
checkpoint | Panel has been prepared in readiness for installation - Steel skin removed at base | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Underfloor build - Insulation Install
checkpoint | Heated cables have been installed to the correct spacing | Photo required
checkpoint | Correct sand depth has been achieved | Photo required
checkpoint | Polythene has been installed and taped correcly | Photo required
checkpoint | Underfloor insulation has been installed correcly | Photo required
checkpoint | Building panel has been installed correcly
hold point | Project Manager to sign off | Signature required
section | Completed Works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded Damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Butchery Freezer
Butchery Freezer
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build
checkpoint | Pit depth is correct
checkpoint | Pit is dry | Photo required
checkpoint | Pit edges are smooth and level | Photo required
checkpoint | Pit Threshold has been boxed out and is correct | Photo required
checkpoint | Pit is square and as per drawing
checkpoint | Ceiling supports have been installed correctly | Photo required
checkpoint | Layflat has been correctly layed with Mastic | Photo required
checkpoint | F-Mould has been correctly fixed over Layflat with Mastic | Photo required
checkpoint | F-Mould fixings are at the correct centres
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated Panel Installation
checkpoint | F-Mould has been mastic bed sealed ready for panel installation | Photo required
checkpoint | Panel has veen prepared in readiness for installation - Mastic applied to slip joins | Photo required
checkpoint | Panel has been prepared in readiness for installation - Steel skin removed at base | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Underfloor build - Insulation Install
checkpoint | Heated cables have been installed to the correct spacing | Photo required
checkpoint | Correct sand depth has been achieved | Photo required
checkpoint | Polythene has been installed and taped correcly | Photo required
checkpoint | Underfloor insulation has been installed correcly | Photo required
checkpoint | Building panel has been installed correcly
hold point | Project Manager to sign off | Signature required
section | Completed Works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded Damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## General Freezer
General Freezer
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build
checkpoint | Pit depth is correct
checkpoint | Pit is dry | Photo required
checkpoint | Pit edges are smooth and level | Photo required
checkpoint | Pit Threshold has been boxed out and is correct | Photo required
checkpoint | Pit is square and as per drawing
checkpoint | Ceiling supports have been installed correctly | Photo required
checkpoint | Layflat has been correctly layed with Mastic | Photo required
checkpoint | F-Mould has been correctly fixed over Layflat with Mastic | Photo required
checkpoint | F-Mould fixings are at the correct centres
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated Panel Installation
checkpoint | F-Mould has been mastic bed sealed ready for panel installation | Photo required
checkpoint | Panel has veen prepared in readiness for installation - Mastic applied to slip joins | Photo required
checkpoint | Panel has been prepared in readiness for installation - Steel skin removed at base | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Underfloor build - Insulation Install
checkpoint | Heated cables have been installed to the correct spacing | Photo required
checkpoint | Correct sand depth has been achieved | Photo required
checkpoint | Polythene has been installed and taped correcly | Photo required
checkpoint | Underfloor insulation has been installed correcly | Photo required
checkpoint | Building panel has been installed correcly
hold point | Project Manager to sign off | Signature required
section | Completed Works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded Damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Seafood Coolroom
Seafood Coolroom
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build - Base components and ceiling supports
checkpoint | Concrete Slab has been sweeped clean | Photo required
checkpoint | Concrete Nib is level and straight
checkpoint | Set out of room is as per drawings
checkpoint | Structural Steel is true and plumb
checkpoint | Ceiling supports have been installed correctly
checkpoint | Base channel have been siliconed sealed and fixed at correct centres
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres
checkpoint | Insulated panel has been inspected and is free from damage ready to install
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Base angles have been siliconed bed sealed ready for panel installation | Photo required
checkpoint | Panel has been prepared in readiness for installation - step cut | Photo required
checkpoint | Panel has been prepared in readiness for installation - mitre cut | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Main build - Penetrations
checkpoint | Doors have been marked out correctly | Photo required
checkpoint | Windows have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
checkpoint
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Bakery Coolroom
Bakery Coolroom
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build - Base components and ceiling supports
checkpoint | Concrete Slab has been sweeped clean | Photo required
checkpoint | Concrete Nib is level and straight
checkpoint | Set out of room is as per drawings
checkpoint | Structural Steel is true and plumb
checkpoint | Ceiling supports have been installed correctly
checkpoint | Base channel have been siliconed sealed and fixed at correct centres
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres
checkpoint | Insulated panel has been inspected and is free from damage ready to install
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Base angles have been siliconed bed sealed ready for panel installation | Photo required
checkpoint | Panel has been prepared in readiness for installation - step cut | Photo required
checkpoint | Panel has been prepared in readiness for installation - mitre cut | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Main build - Penetrations
checkpoint | Doors have been marked out correctly | Photo required
checkpoint | Windows have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
checkpoint
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Deli Coolroom
Deli Coolroom
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build - Base components and ceiling supports
checkpoint | Concrete Slab has been sweeped clean | Photo required
checkpoint | Concrete Nib is level and straight
checkpoint | Set out of room is as per drawings
checkpoint | Structural Steel is true and plumb
checkpoint | Ceiling supports have been installed correctly
checkpoint | Base channel have been siliconed sealed and fixed at correct centres
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres
checkpoint | Insulated panel has been inspected and is free from damage ready to install
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Base angles have been siliconed bed sealed ready for panel installation | Photo required
checkpoint | Panel has been prepared in readiness for installation - step cut | Photo required
checkpoint | Panel has been prepared in readiness for installation - mitre cut | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Main build - Penetrations
checkpoint | Doors have been marked out correctly | Photo required
checkpoint | Windows have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
checkpoint
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Butchery Holding Room
Butchery Holding Room
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build - Base components and ceiling supports
checkpoint | Concrete Slab has been sweeped clean | Photo required
checkpoint | Concrete Nib is level and straight
checkpoint | Set out of room is as per drawings
checkpoint | Structural Steel is true and plumb
checkpoint | Ceiling supports have been installed correctly
checkpoint | Base channel have been siliconed sealed and fixed at correct centres
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres
checkpoint | Insulated panel has been inspected and is free from damage ready to install
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Base angles have been siliconed bed sealed ready for panel installation | Photo required
checkpoint | Panel has been prepared in readiness for installation - step cut | Photo required
checkpoint | Panel has been prepared in readiness for installation - mitre cut | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Main build - Penetrations
checkpoint | Doors have been marked out correctly | Photo required
checkpoint | Windows have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
checkpoint
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Butchery Coolroom
Butchery Coolroom
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build - Base components and ceiling supports
checkpoint | Concrete Slab has been sweeped clean | Photo required
checkpoint | Concrete Nib is level and straight
checkpoint | Set out of room is as per drawings
checkpoint | Structural Steel is true and plumb
checkpoint | Ceiling supports have been installed correctly
checkpoint | Base channel have been siliconed sealed and fixed at correct centres
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres
checkpoint | Insulated panel has been inspected and is free from damage ready to install
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Base angles have been siliconed bed sealed ready for panel installation | Photo required
checkpoint | Panel has been prepared in readiness for installation - step cut | Photo required
checkpoint | Panel has been prepared in readiness for installation - mitre cut | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Main build - Penetrations
checkpoint | Doors have been marked out correctly | Photo required
checkpoint | Windows have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
checkpoint
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Produce Coolroom
Produce Coolroom
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build - Base components and ceiling supports
checkpoint | Concrete Slab has been sweeped clean | Photo required
checkpoint | Concrete Nib is level and straight
checkpoint | Set out of room is as per drawings
checkpoint | Structural Steel is true and plumb
checkpoint | Ceiling supports have been installed correctly
checkpoint | Base channel have been siliconed sealed and fixed at correct centres
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres
checkpoint | Insulated panel has been inspected and is free from damage ready to install
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Base angles have been siliconed bed sealed ready for panel installation | Photo required
checkpoint | Panel has been prepared in readiness for installation - step cut | Photo required
checkpoint | Panel has been prepared in readiness for installation - mitre cut | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Main build - Penetrations
checkpoint | Doors have been marked out correctly | Photo required
checkpoint | Windows have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
checkpoint
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## General Coolroom
General Coolroom
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has reviewed and accepts area handed over from Mian Contractor
section | Base build - Base components and ceiling supports
checkpoint | Concrete Slab has been sweeped clean | Photo required
checkpoint | Concrete Nib is level and straight
checkpoint | Set out of room is as per drawings
checkpoint | Structural Steel is true and plumb
checkpoint | Ceiling supports have been installed correctly
checkpoint | Base channel have been siliconed sealed and fixed at correct centres
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres
checkpoint | Insulated panel has been inspected and is free from damage ready to install
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Base angles have been siliconed bed sealed ready for panel installation | Photo required
checkpoint | Panel has been prepared in readiness for installation - step cut | Photo required
checkpoint | Panel has been prepared in readiness for installation - mitre cut | Photo required
checkpoint | Panel has been installed plumb and level | Photo required
checkpoint | Panel mitres have been formed correctly | Photo required
checkpoint | Correct size "step cut" has been formed | Photo required
checkpoint | Panel connections / joins have been foamed correctly | Photo required
section | Main build - Penetrations
checkpoint | Doors have been marked out correctly | Photo required
checkpoint | Windows have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
checkpoint
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Produce Prep Area
Produce Prep Area
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has been reviewed and accepts area handed over to them from Main Contractor | Photo required
checkpoint | Insulated panel had been inspected and is free from damage
section | Base build - Base components and ceiling supports
checkpoint | Concrete slab has been sweeped clean
checkpoint | Concrete nib is level and straight | Photo required
checkpoint | Set out of room is as per drawings | Photo required
checkpoint | Set out of doors and openings have completed and are as per drawings | Photo required
checkpoint | Structural steel is true and plumb
checkpoint | Ceiling supports have been installed correctly | Photo required
checkpoint | Base channel has been siliconed sealed and fixed at correct centres | Photo required
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres | Photo required
checkpoint | All third party services have been installed and are ready for panel installation to commence
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Insulated panel has been inspected and is free from damage ready to install | Photo required
checkpoint | Base channel / angles have been siliconed bed sealed, ready for panel installation to commence | Photo required
checkpoint | Insulated panel has been installed plumb
checkpoint | Corners have been formed neat and tidy
checkpoint | Mid-span fixings have been installed at the correct height and centers as per specifications | Photo required
checkpoint | Perimter angles have been installed neat and tidy with correct fixings and centers | Photo required
section | Main build - Penetrations
checkpoint | Doors sizes have been marked out correctly | Photo required
checkpoint | Window sizes have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required

## Butchery Prep Area
Butchery Prep Area
type | name | values
checklist | Pre-Construction
section | Build area / work face
checkpoint | Subcontractor has been reviewed and accepts area handed over to them from Main Contractor | Photo required
checkpoint | Insulated panel had been inspected and is free from damage
section | Base build - Base components and ceiling supports
checkpoint | Concrete slab has been sweeped clean
checkpoint | Concrete nib is level and straight | Photo required
checkpoint | Set out of room is as per drawings | Photo required
checkpoint | Set out of doors and openings have completed and are as per drawings | Photo required
checkpoint | Structural steel is true and plumb
checkpoint | Ceiling supports have been installed correctly | Photo required
checkpoint | Base channel has been siliconed sealed and fixed at correct centres | Photo required
checkpoint | Angles (to form channel) have been silicone bed sealed and fixed at correct centres | Photo required
checkpoint | All third party services have been installed and are ready for panel installation to commence
hold point | Project Manager to sign off | Signature required
section | Main build - Insulated panel installation
checkpoint | Insulated panel has been inspected and is free from damage ready to install | Photo required
checkpoint | Base channel / angles have been siliconed bed sealed, ready for panel installation to commence | Photo required
checkpoint | Insulated panel has been installed plumb
checkpoint | Corners have been formed neat and tidy
checkpoint | Mid-span fixings have been installed at the correct height and centers as per specifications | Photo required
checkpoint | Perimter angles have been installed neat and tidy with correct fixings and centers | Photo required
section | Main build - Penetrations
checkpoint | Doors sizes have been marked out correctly | Photo required
checkpoint | Window sizes have been marked out correctly | Photo required
checkpoint | Penetrations have been marked out correctly | Photo required
checkpoint | Fire sprinklers have been marked out correctly | Photo required
hold point | Project Manager to sign off | Signature required
section | Completed works
checkpoint | Internal panels surfaces have been inspected and no damage has been found | Photo required
checkpoint | All interior angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | Ceiling panels have been inspected and no damage has been found | Photo required
checkpoint | Ceiling panel fixings have been installed correctly and all fixings are at the correct centers | Photo required
checkpoint | All windows have been fitted and all fixings have been fitted | Photo required
checkpoint | All doors have been fitted and all fixings have been fitted | Photo required
checkpoint | All Sealant work has been completed and is neat and tidy | Photo required
checkpoint | All penetrations have been cut, flashed and siliconed sealed | Photo required
checkpoint | All external angles / flashings have been installed correctly and all fixings have been fitted | Photo required
checkpoint | External panels surfaces have been inspected and no damage has been found | Photo required
section | Recorded damage
checkpoint | Panel damage (during installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damage (after installation) has been identified and reported to main contractor | Photo required
checkpoint | Panel damge has been repaired and evidence of such recorded with main contractor | Photo required
section | Variation to contract
checkpoint | Variation has been requested by main contractor | Photo required
hold point | Project Manager to approve | Signature required
checkpoint | Variation has been completed | Photo required
hold point | Project Manager to sign off | Signature required