## General
SECTION 1 – GENERAL DETAILS
Project Name: | Ōtaki to Levin Saftey Improvements | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | [6 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 6581 | [5 empty] | C | Check | ER | Cust. Representative | Luke Cameron | LC
Area/ Sub-System: | Ōtaki to Levin State Highway 1 |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: |  |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | Glen Flint | GF
ITP Description: | Covers all inspection points pre, during and post construction of the insitu cast concrete structures | [5 empty] | I | Inspection | PM | Project Manager | Sam Christensen | SC
Discipline: | Concrete | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 Relevant specs as detailed in TS1 | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | For construction drawings : | [5 empty] | S | Subcontractor | SP | Supervisor
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Sam Christensen |  |  | Date: | 2023-08-08 |  | W | Witness Point | SV | Surveyor | Andre Wilkes | AW
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Tipping |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Drainage
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection
[7 empty] | Key | By | Checked (PM Initial) | Date
11 | Drainage | Final Sign Off | All below requirements are met and approved by CR | Referenced Item numbers as below | Once post construction | Hold Point | H | ER
11.1 | Materials
11.1.1 | Plant Mix Concrete | Mix Design Review | Meets Project TS 1 412.2 requirements and relevant mPa as required on drawings | Manufacturers Certificate | Prior to Pour | Review | R | ER
11.2 | Construction - In accordance with NZTA F/3 & NZS 3725
11.2.1 | Pre-Pour Inspection _ NIB, Kerb & Dish Channel | Onsite Inspection and testing: Witnessed Proof Roll Clegg Testing | Proof Roll shows no undue movement in Subbase Clegg Results > 20 String Lines inspected by engineer onsite and approved. | Site Inspection Sheet and Clegg Record | Once prior to each pour | Hold Point | H | PM/ER
| Pre-Pour Inspection _ Roundabout & Central Island | Onsite Visual Inspection | Visual Inspection of prepped surface showing tight uniform surface. All Subbase Pavement requirements passed as per ITP 4 | Site Inspection Sheet and ITP Requirements | Once prior to each pour | Hold Point | H | PM/ER
11.2.2 | Pre-Pour Reinforcing & boxing Inspection | On-Site Visual Inspection | Reinforcing to be placed as per design with applicable cover as per TS1 and relevant specifications. Boxing to be set to design to ensure correct grade as per design. | Site Inspection Sheet | Once prior to each pour | Hold Point | H | PM/ER
11.2.3 | Material Delivery | Maintain a delivery record for each batch of ready mixed concrete delivered to the works | Concrete Dockets provided showing product delivered matches design as required. | Concrete Truck Docket | Per Truck | Witness Point | W | PM/PS
11.2.3 | Concrete Joints | Onsite Visual Inspection | Construction/contraction joints to be constructed as per design and TS1 Specifications. Machine laid kerb and channel - Contraction Joints formed every 5m. Saw cutting within 24hours. Concrete Island Infills - Contraction Joints formed every 5m. | Site Inspection Sheet | Post Construction | Witness Point | W | PM/PS/ER
11.2.4 | Survey As-Built | Review of Data | As-Builts show construction as per design, within tolerences set out in TS1 and relevant specifications. | As-Built 3d Data File | Post Construction | Hold Point | H | PM/PS/ER
11.2.5 | Post Construction Inspection | On-Site Visual Inspection | Finished concrete to be uniform and free of defects. Concrete Island Infill shall have a Class U5 Broomed Finish | Site Inspection Sheet | Post Construction | Hold Point | H | PM/ER
11.3 | Material Testing
11.3.1 | Control tests from concrete plant | Project Technical Specification 13.10.7.4 & NZS 3104 | Test result by Ready-mix supplier | Prior concreting | Throughout Construction | Hold Point | H | SE
11.3.2 | Compressive strength Test | Project Technical Specification 13.10.7.4 & NZS 3112 | Test Results from IANZ registered Laboratory. Cast in Channels: >20MPa Machine Laid Kerb and Channel: >25MPa Concrete Island Infill: >20Pa | During concreting | One test per 50m3 | Hold Point | H | SE
11.3.3 | Slump Test | Project Technical Specification 13.10.7.4 & NZS 3112:Part 1 | Test Results from IANZ registered Laboratory. | During concreting | One test per 50m3 | Hold Point | H | SE
COMMENTS
[5 empty] | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: