## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 11 - Concrete | itp |  |  |  |  | F2LSIP - ITP 11 - Concrete | 77404007-858c-45f3-9ca7-5124c893aeec
section | 11 - Drainage
checkpoint | Drainage
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by CR
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 11.1 - Materials
checkpoint | 11.1.1 - Plant Mix Concrete
label | Inspection Point: Quality Control Activity - Mix Design Review
label | Acceptance Criteria - Meets Project TS 1 412.2 requirements and relevant mPa as required on drawings
label | Verifying Document - Manufacturers Certificate
label | Frequency - Prior to Pour
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 11.2 - Construction - In accordance with NZTA F/3 & NZS 3725
checkpoint | 11.2.1 - Pre-Pour Inspection _ NIB, Kerb & Dish Channel
label | Inspection Point: Quality Control Activity - Onsite Inspection and testing:
label | ○ Witnessed Proof Roll
label | ○ Clegg Testing
label | Acceptance Criteria - Proof Roll shows no undue movement in Subbase
label | ○ Clegg Results > 20
label | ○ String Lines inspected by engineer onsite and approved.
label | Verifying Document - Site Inspection Sheet and Clegg Record
label | Frequency - Once prior to each pour
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.2.1 - Pre-Pour Inspection _ Roundabout & Central Island
label | Inspection Point: Quality Control Activity - Onsite Visual Inspection
label | Acceptance Criteria - Visual Inspection of prepped surface showing tight uniform surface. All Subbase Pavement requirements passed as per ITP 4
label | Verifying Document - Site Inspection Sheet and ITP Requirements
label | Frequency - Once prior to each pour
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.2.2 - Pre-Pour Reinforcing & boxing Inspection
label | Inspection Point: Quality Control Activity - On-Site Visual Inspection
label | Acceptance Criteria - Reinforcing to be placed as per design with applicable cover as per TS1 and relevant specifications.
label | ○ Boxing to be set to design to ensure correct grade as per design.
label | Verifying Document - Site Inspection Sheet
label | Frequency - Once prior to each pour
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.2.3 - Material Delivery
label | Inspection Point: Quality Control Activity - Maintain a delivery record for each batch of ready mixed concrete delivered to the works
label | Acceptance Criteria - Concrete Dockets provided showing product delivered matches design as required.
label | Verifying Document - Concrete Truck Docket
label | Frequency - Per Truck
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM/PS
checkpoint | 11.2.3 - Concrete Joints
label | Inspection Point: Onsite Visual Inspection
label | Acceptance Criteria - Construction/contraction joints to be constructed as per design and TS1 Specifications. Machine laid kerb and channel - Contraction Joints formed every 5m. Saw cutting within 24hours. Concrete Island Infills - Contraction Joints formed every 5m.
label | Verifying Document - Site Inspection Sheet
label | Frequency - Post Construction
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM/PS/ER
checkpoint | 11.2.4 - Survey As-Built
label | Inspection Point: Quality Control Activity - Review of Data
label | Acceptance Criteria - As-Builts show construction as per design, within tolerences set out in TS1 and relevant specifications.
label | Verifying Document - As-Built 3d Data File
label | Frequency - Post Construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/PS/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.2.5 - Post Construction Inspection
label | Inspection Point: Quality Control Activity - On-Site Visual Inspection
label | Acceptance Criteria - Finished concrete to be uniform and free of defects. Concrete Island Infill shall have a Class U5 Broomed Finish
label | Verifying Document - Site Inspection Sheet
label | Frequency - Post Construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 11.3 - Material Testing
checkpoint | 11.3.1 - Control tests from concrete plant
label | Inspection Point: Quality Control Activity - Project Technical Specification 13.10.7.4 & NZS 3104
label | Acceptance Criteria - Test result by Ready-mix supplier
label | Verifying Document - Prior concreting
label | Frequency - Throughout Construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.3.2 - Compressive strength Test
label | Inspection Point: Quality Control Activity - Project Technical Specification 13.10.7.4 & NZS 3112
label | Acceptance Criteria - Test Results from IANZ registered Laboratory. Cast in Channels: >20MPa Machine Laid Kerb and Channel: >25MPa Concrete Island Infill: >20Pa
label | Verifying Document - During concreting
label | Frequency - One test per 50m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.3.3 - Slump Test
label | Inspection Point: Quality Control Activity - Project Technical Specification 13.10.7.4 & NZS 3112:Part 1
label | Acceptance Criteria - Test Results from IANZ registered Laboratory.
label | Verifying Document - During concreting
label | Frequency - One test per 50m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT