## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 04 - Pavements | itp |  |  |  |  | F2LSIP - ITP 04 - Pavements | dde760f8-2901-4394-8805-5dda7f5353e6
section | 4.0 - Pavements
checkpoint | Pavements
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by CR
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 - Source Properties as per NZS 4407
checkpoint-no-status | Source Properties as per NZS 4407
label | Acceptance Criteria - Subbase AP65
checkpoint | 4.1.1 - Crushing Resistance Test 3.10
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Under a load of 100 kN less than 10% fines passing 2.36mm sieve size shall be produced
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.1.2 - Weathering Quality Index Test Test 3.11
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - AA, AB, AC, BA, BB, or CA
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.1.3 - Soaked CBR Test Test 3.15
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - CBR ≥ 80%
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.2 - Production Properties as per NZS 4407
checkpoint-no-status | Production Properties as per NZS 4407
label | Acceptance Criteria - Subbase AP65
checkpoint | 4.2.1 - Quality of Fines - SE 3.6 - CI 3.5 - PI 3.4
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - SE ≥ 25, CI ≤ 3, PI ≤ 6
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.2.2 - Broken Face Content Test 3.14
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 60% by weight shall have two or more broken faces.
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.2.3 - Particle Size Distribution Test 3.8.1
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - As per Table to A506.2.1
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 4.3 - Source Properties as per NZTA M-4
checkpoint-no-status | Source Properties as per NZTA M-4
label | Acceptance Criteria - Basecourse AP40
checkpoint | 4.3.1 - Crushing Resistance Test 3.1
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Under 130kN load < 10% fines passing 2.36mm sieve.
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per 10,000m3
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.3.2 - Weathering Quality Index Test 3.11
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - AA,AB,BA,BB,CA
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per 10,000m3
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.3.3 - California Bearing Ratio Test 3.15
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Not less than 80%
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per 10,000m3
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 4.4 - Production Properties as per NZTA M-4
checkpoint-no-status | Production Properties as per NZTA M-4
label | Acceptance Criteria - Basecourse AP40
checkpoint | 4.4.1 - Quality of Fines - SE 3.6 - CI 3.5 - PI 3.4
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - SE ≥ 40, CI ≤ 3, PI ≤ 5
label | Verifying Document - IANZ Lab Report
label | Frequency - Lot Size =
label | ○ < 400m2 = 2 Samples
label | ○ 400 to 1500m2 = 3 Samples
label | ○ 1500 to 4000m3 = 4 Samples
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.4.2 - Broken Face Content Test 3.14
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - 19mm - 37.5mm - NOT LESS THAN 70%
label | ○ 9.5mm - 19.0mm - NOT LESS THAN 70%
label | ○ 4.75mm - 9.5mm - NOT LESS THAN 70%
label | Verifying Document - IANZ Lab Report
label | Frequency - Lot Size =
label | ○ < 400m2 = 2 Samples
label | ○ 400 to 1500m2 = 3 Samples
label | ○ 1500 to 4000m3 = 4 Samples
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.4.3 - Particle Size Distribution Test 3.8.1
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - As per NZTA M/4 AP40 PSD Requirements
label | Verifying Document - IANZ Lab Report
label | Frequency - Lot Size =
label | ○ < 400m2 = 2 Samples
label | ○ 400 to 1500m2 = 3 Samples
label | ○ 1500 to 4000m3 = 4 Samples
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 4.5 - Pavement Construction
checkpoint-no-status | Pavement Construction
label | Acceptance Criteria - Require formal sign off record of previous layer prior to placment of next layer. DNZ to develop sign off sheet or approval system of work.
checkpoint | 4.5.1 - Visual inspection of final trimmed subgrade surface
label | Inspection Point: Quality Control Activity - Pre pavement construction visual inspection
label | Acceptance Criteria - Entire surface to be firm, uniform and smooth.
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM & ER
checkpoint | 4.5.2 - Survey Setout
label | Inspection Point: Quality Control Activity - Height Check
label | Acceptance Criteria - Check to ensure pegs are still sitting at correct height from initial set out. Target MDD to be approved prior to Construction. Lab MDD Reports to be submitted for Approval.
label | Verifying Document - Visual
label | Frequency - Prior to subbase construction
label | Inspection Type - Check
label | Inspection: Key - C
label | Inspection: By - SV
checkpoint | 4.5.3 - Subbase Compaction
label | Inspection Point: Quality Control Activity - NDM - Dry Density
label | Acceptance Criteria - Mean DD ≥ 95% of MDD, Minimum DD ≥ 92% of MDD
label | Verifying Document - IANZ Lab & Report, NDM Report
label | Frequency - MDD to be determind per 5000m2 of material laid.
label | ○ Compacted layer to be tested in 1000m2 lots, at randomly generated locations.
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.4 - Subbase Deflection
label | Inspection Point: Quality Control Activity - Benklemen Beam Test
label | Acceptance Criteria - Maximum Deflections of not more than (see surfacing notes)
label | Verifying Document - IANZ Report and Truck Weightbridge Docket (where applicable)
label | Frequency - 10m Intervals - alternating wheel paths
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.5 - Level Compliance
label | Inspection Point: Quality Control Activity - Survey As-built
label | Acceptance Criteria - Subbase level to be within +5mm / - 25mm of design
label | Verifying Document - 20m Survey Cross Sections
label | Frequency - 20m Cross Sections
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM & ER
checkpoint | 4.5.6 - Basecourse Compaction
label | Inspection Point: Quality Control Activity - NDM - Dry Density
label | Acceptance Criteria - Mean DD ≥ 98% of MDD, Minimum DD ≥ 95% of MDD
label | Verifying Document - IANZ Lab & Report, NDM Report
label | Frequency - MDD to be determind per 5000m2 of material laid.
label | ○ Compacted layer to be tested in 1000m2 lots, at randomly generated locations.
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.7 - Basecourse Deflections
label | Inspection Point: Quality Control Activity - Benklemen Beam Test
label | Acceptance Criteria - Only Required if subbase BB not completed - Engineer to advise target
label | Verifying Document - IANZ Report and Truck Weightbridge Docket (where applicable)
label | Frequency - 10m Intervals - alternating wheel paths
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.8 - Final Surface Shape & Levels
label | Inspection Point: Quality Control Activity - Straight Edge, Survey As-built
label | Acceptance Criteria - Pavement shall not deviate greater than 10mm under a 3m straight edge.
label | ○ No area of pavement shall pond water where grade is greater than 1%.
label | ○ Pavement to be within +15mm / -5mm of design levels (or +/- 5mm against the lip of a channel)
label | Verifying Document - Straight Edge Sheet, Site Inspection Form, 20m Survey Cross Sections
label | Frequency - Once per construction area, 20m Cross Sections
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.9 - Final Surface Visual Inspection
label | Inspection Point: Quality Control Activity - Onsite Surface Inspection
label | Acceptance Criteria - Shall present a swpet, tightly consolidated surface in which:
label | ○ Large aggregate is exposed to the surface & held in place with a matrix of smaller agregates.
label | ○ Smaller aggregate is held in place by fines material
label | ○ Matrix does not displace under normal trafficing or sweeping.
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT