## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 06 - Road Barriers | itp |  |  |  |  | F2LSIP - ITP 06 - Road Barriers | 7dde947d-7988-4d6c-a73d-2cadca3f7556
section | 6.0 - Barriers
checkpoint | Barriers
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by ER
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 6.1 - Construction
checkpoint | 6.1.1 - Documentation Review
label | Inspection Point: Quality Control Activity - Review
label | Acceptance Criteria - All barrier componants comply to the relevant specification as per NZTA M23.
label | Verifying Document - Manufacturers Certificates
label | Frequency - Once per supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER/PM
section | 6.2 - Construction
checkpoint | 6.2.1 - Design Revision as required
label | Inspection Point: Quality Control Activity - Design submission & review
label | Acceptance Criteria - Engineer to review and approve
label | Verifying Document - Revised design NTE/NTC
label | Frequency - Once per design revision.
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 6.2.2 - Barrier set out & review
label | Inspection Point: Quality Control Activity - Site inspection
label | Acceptance Criteria - Engineer to review barrier setout onsite and approve.
label | Verifying Document - Ste inspection form
label | Frequency - Once per barrier string
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - ER/PM
checkpoint | 6.2.3 - Anchor Block Construction
label | Inspection Point: Quality Control Activity - Site Inspection
label | Acceptance Criteria - Engineer to inspect excavated foundation prior to anchor block pour.
label | Verifying Document - Site inspection form
label | Frequency - Once per anchor block
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.4 - Concrete Work
label | Inspection Point: Quality Control Activity - Site Inspection
label | Acceptance Criteria - Concrete works shall be constructed to the line and levels detailed on the drawings, and finished to a smooth suface with no significant cracks, spalling or exposed reinforcing.
label | ○ Concrete dockets to be provided to engineer.
label | Verifying Document - Site inspection form
label | Frequency - Once per barrier string
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - ER/PM
checkpoint | 6.2.5 - Marker posts, reflectors and signage
label | Inspection Point: Quality Control Activity - Site inspection
label | Acceptance Criteria - Edge marker posts to be installed along w-beam at standard spacing intervals
label | ○ Wire rope barriers to have reflectorised top caps every 3rd post.
label | ○ Leading end terminals to have Hazard/width marker where required
label | ○ Wire rope barrier leading end terminals installed with RD6L signage
label | Verifying Document - Site inspection form
label | Frequency - Once per barrier string
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER/PM
checkpoint | 6.2.6 - WRB Pull Test
label | Inspection Point: Quality Control Activity - Witnessed pull test
label | Acceptance Criteria - No visual damage to occur to posts or foundation as a result of the pull test. Any damage is to be rectified prior to sign off & string retested.
label | Verifying Document - Site inspection form
label | Frequency - Minimum one test / 100m
label | Inspection Type - Witness Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.7 - W-Beam Inspection
label | Inspection Point: Quality Control Activity - Check Sheet
label | Acceptance Criteria - Contractor to provide end terminal check sheet signed by a suitably qualified person. Construction Review and Audit Form (RSHDS4) filed in QA File.
label | Verifying Document - Barrier Inspection form
label | Frequency - One per end terminal
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - ER
checkpoint | 6.2.8 - As-Built
label | Inspection Point: Quality Control Activity - Survey As-Built
label | Acceptance Criteria - As-built to show Barrier constructed as per design and within tolerences as per m23
label | Verifying Document - As-Built Data
label | Frequency - Once Per String
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT