## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 07 - Sealing | itp |  |  |  |  | F2LSIP - ITP 07 - Sealing | d425488c-c498-4445-a3c2-36f0aeca200a
section | 7.0 - Sealing
checkpoint | Sealing
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by ER
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.1 - Bitumen Approval
checkpoint | 7.1.1 - NZTA M1: 2022: Bitumen Material Approval
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Bitumen/binder compliant with NZTA M/1 - Table 5.1
label | Verifying Document - Manufacturers Certificate
label | Frequency - Minimum 5 working days prior to construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.2 - Source Properties
checkpoint | 7.2.1 - NZTA M6: 2022: 4.2 Crushing Resistance
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Maximum of 10% fines shall be produced under a load of 230kN.
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2.2 - NZTA M6: 2022: 4.3 Weathering Resistance
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - The aggregate shall have a quality index of AA or BA
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2.3 - NZTA M6: 2022: 4.4 Weak Particles Test
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Note - only required if source properties are disputed.
label | ○ The aggregate shall have a maximum of 1% of unsound materials
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2.4 - NZTA M6: 2022: 4.6 Polished Stone Value
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Polished Stone Value (PSV) - compliant with NZTA M6: 2022: 4.6 & project requirements
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.3 - Production Properties
checkpoint-no-status | Production Properties
label | Acceptance Criteria - Grade 2, 3 & 4 Chip
checkpoint | 7.3.1 - NZTA M6: 2022: 5.1 Cleanness
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Cleaness of aggregate samples compliant with NZTA M6: 2022 5.2 Cleanness
label | – – – – – – – – – – – – – – – – – – – – –
label | Chip Grade ¦¦ Minimum Cleaness Value
label | – – – – – – – – – – – – – – – – – – – – –
label | 2 ¦¦ 89
label | 3 ¦¦ 87
label | 4 ¦¦ 85
label | 5 ¦¦ Report only
label | 6 ¦¦ Report only
label | – – – – – – – – – – – – – – – – – – – – –
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | ○ 1 test per < 100m3;
label | ○ 2 tests per 100-500m3; or
label | ○ 3 tests per > 500m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3.2 - NZTA M6: 2022: 5.2 Size and Shape
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Size and Shape of Aggregate Particles compliant with NZTA M6: 2022: 5.2 Size and Shape
label | – – – – – – – – – – – – – – – – – – – – –
label | Grade of Chip ¦¦ ALD (mm) ¦¦ % of Least Dimensions Within 2.5mm of ALD ¦¦ AGD/ALD Ratio ¦¦ % Passing 4.75mm Sieve ¦¦ % With at Least Two Broken Faces
label | – – – – – – – – – – – – – – – – – – – – –
label | 2 ¦¦ 9.5 - 12.0 ¦¦ 65 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 3 ¦¦ 7.5 - 10.0 ¦¦ 70 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 4 ¦¦ 5.5 - 8.0 ¦¦ 75 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 5 ¦¦ Report ¦¦ Report ¦¦ Report ¦¦ Report ¦¦ Report
label | – – – – – – – – – – – – – – – – – – – – –
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | ○ 1 test per < 100m3;
label | ○ 2 tests per 100-500m3; or
label | ○ 3 tests per > 500m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.4 - Production Properties
checkpoint-no-status | Production Properties
label | Acceptance Criteria - Grade 5 & 6 Chip
checkpoint | 7.4.1 - NZTA M6: 2022 5.3 PSD
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Particle Size Distribution compliant with NZTA M6: 2022 5.1 Table 4
label | – – – – – – – – – – – – – – – – – – – – –
label | Siege Size (mm) ¦¦ Percentage Passing Sieve (Grade 5 :: Grade 6)
label | – – – – – – – – – – – – – – – – – – – – –
label | 13.2 ¦¦ 100 :: -
label | 9.5 ¦¦ 95 - 100 :: 100
label | 6.7 ¦¦ - :: 95 - 100
label | 4.75 ¦¦ 0 - 8 :: -
label | 2.36 ¦¦ 0 - 2 :: 0 - 15
label | 0.300 ¦¦ 0 :: 0 - 8
label | – – – – – – – – – – – – – – – – – – – – –
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | ○ 1 test per < 100m3;
label | ○ 2 tests per 100-500m3; or
label | ○ 3 tests per > 500m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.5 - Pre-Construction
checkpoint-no-status | Pre-Construction
label | Acceptance Criteria - Require formal sign off record of previous layer prior to placment of next layer. DNZ to develop sign off sheet or approval system of work. Bitumen distributors shall possess a current Certificate of Compliance with the BCA E/2 Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
checkpoint | 7.5.1 - Chipseal Design Submission
label | Inspection Point: Quality Control Activity - Design Review
label | Acceptance Criteria - Designer to approve sealing design, prior to sealing.
label | Verifying Document - NTC confirming acceptance
label | Frequency - Once per seal design
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.5.2 - Pre-seal Inspection
label | Inspection Point: Quality Control Activity - Visual Site Inspection
label | Acceptance Criteria - Basecourse/Subbase (Membrane seal) - To be prepped to a tight, uniform surface, swept to remove any dust and other foreign objects.
label | ○ Prime or previous seal - Full surface swept with a power broom to remove excess chip and any other foreign material. The Contractor shall give the Engineer 24 hours’ notice of its intention to seal
label | Verifying Document - Site Inspection Form
label | Frequency - Prior to construction of sealing coat
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.5.3 - Pre-seal testing
label | Inspection Point: Quality Control Activity - Degree of Saturation test TNZB/02 Clause 12
label | Acceptance Criteria - Compliant as per TNZ B/02 Clause 12 DOS at each of minimim 5 points < 70%
label | Verifying Document - Testing results
label | Frequency - Minimum 5 tests per 1000m2
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.6 - Construction
checkpoint | 7.6.1 - Working Temperature Prior to Spraying
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying shall be carried out when the pavement surface temperature is below 10 degrees C.
label | Verifying Document - Sealing Checklist
label | Frequency - Prior to Spraying
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.2 - Application rate for Bituminous Seal
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Sprayed Rate measured compliant with the Approved Seal Design
label | Verifying Document - Sealing Checklist
label | Frequency - Per spray run
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.3 - Chip Spread Rate
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Sealing Records showing compliant spread rate of the chips based on C0213.5;TNZ P/3: 1995-21 Cl. 28
label | Verifying Document - Sealing Checklist
label | Frequency - 1 test per chip grade per 2,000m2 seal constructed
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.4 - Rolling Requirements
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Sealing Records showing compliant rolling requirements based on C0213.5;TNZ P/3: 1995-22 ROLLING
label | Verifying Document - Sealing Checklist
label | Frequency - Per Shift
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.5 - On Site Checks - Post PTR and Brooming
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Surface Compliant and Surplus chip removed
label | Verifying Document - Sealing Checklist
label | Frequency - Prior to construction of next layer/ Prior removal of the temporary speed restriction signs
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER