## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 09 - Road Signs | itp |  |  |  |  | F2LSIP - ITP 09 - Road Signs | 2224a125-ff69-492e-a112-d6879ab63ecb
section | 9.0 - Road Signs
checkpoint | Road Signs
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by ER
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 9.1 - Materials
checkpoint | Materials / Retroreflective Requirements / Contractor's Signposts Design
label | Inspection Point: Quality Control Activity - Pre Installation - Compliance Check
label | Acceptance Criteria - All materials to comply with relevent clause under TNZ P24 2020
label | ○ The minimum standard of retroreflection for signs shall be as detailed in Table 810.2 in the technical specifications
label | – – – – – – – – – – – – – – – – – – – – –
label | TABLE 810.2: MINIMUM STANDARD OF SIGN RETROREFLECTION
label | SIGN TYPE ¦¦ STANDARD OF RETROREFLECTION
label | – – – – – – – – – – – – – – – – – – – – –
label | All signs with white or yellow backgrounds, such as regulatory parking and permanent warning signs ¦¦ Class 400
label | All RG5 "Stop", RG6 "Give Way", RG-6R "Roundabout Give Way", RG-17 "Keep Left", and RG-17.1 "Keep Left Twin Disc" signs ¦¦ Class 900
label | All other regulatory signs ¦¦ Class 400
label | All ground-mounted information signs with a red, green, brown or blue background (guide, motorist service, and tourist signs) ¦¦ Class 400
label | All Overhead Signs ¦¦ Class 900
label | Chevron sign boards and single chevrons ¦¦ Class 400
label | Panels with white background for black-on-white signs with less than 30% black on the sign face ¦¦ Class 100
label | Belisha discs and red and white banded railway crossing cross-buck poles ¦¦ Class 400
label | Permanent warning signs and chevrons as instructed by the Engineer ¦¦ Fluorescent signs
label | – – – – – – – – – – – – – – – – – – – – –
label | ○ The contractor shall design all signposts, poles and foundations in accordance to NZTA P4: 2020 and submit to the Engineer for Information and Review a month prior to installation.
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/PS/ER
section | 9.2 - Installation
checkpoint | 9.2.1 - Delivery / Confirm Services
label | Inspection Point: Quality Control Activity - Inspection upon delivery
label | Acceptance Criteria - Signs to be checked for any damage upon delivery, return to manufacturer if damaged. The Contractor shall confirm the location of all underground services within the vicinity of a ground-mounted sign prior to its erection.
label | Verifying Document - Delivery Checklist
label | Frequency - Once Per Delivery
label | Inspection Type - Check
label | Inspection: Key - C
label | Inspection: By - PM/PS
checkpoint | 9.2.2 - Positioning & Orientation
label | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | Acceptance Criteria - Positioning & Orientation to comply to TNZ P24 2020 Clause 7.3 & 7.4
label | Verifying Document - Site Checklist Form
label | Frequency - Once per sign installation
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/PS/ER
checkpoint | 9.2.3 - Sign Support Selection
label | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | Acceptance Criteria - Supports to comply as per TNZ P24 2020 - Table 7.1
label | Verifying Document - Site Checklist Form
label | Frequency - Once per sign installation
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/PS/ER
checkpoint | 9.2.4 - Foundations / Construction Records
label | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | Acceptance Criteria - Foundations to comply as per TNZ P24 2020 Clause 7.7 Foundations. The contractor is to maintain construction records of each sign that clearly show that all posts, poles and foundation details comply with the requirements of the specification.
label | Verifying Document - Site Checklist Form
label | Frequency - Once per sign installation
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/PS/ER
checkpoint | 9.2.5 - Daytime Survey
label | Inspection Point: Quality Control Activity - Post construction survey
label | Acceptance Criteria - (a) The actual sign face is free of environmental soil such as mildew or lichen growth
label | (b) No physical damage has affected or risked sign face readability and or sign integrity
label | (c) No vegetation or other structure impedes line of sight or visibility to the sign face
label | (d) The sign is free of any graffiti or the aftermath of previous poor cleaning action
label | (e) Sign supports and foundations are sound and maintain correct sign presentation
label | (f) The need for the sign still exists – for example a speed reduction has not negated the need for a
label | posted curve warning speed
label | (g) Confirming that the physical sign and its structure remain suitable for purpose or note that some repair should be undertaken
label | (h) Any fluorescent sign, deemed to require a higher level of day time visibility through its fluorescing colour feature, maintains a satisfactory performance e.g. Signs for active users (schools, pedestrians, cyclists).
label | Verifying Document - Survey Checklist
label | Frequency - Once per completed section of works
label | Inspection Type - Inspection
label | Inspection: Key - Inspection
label | Inspection: By - PM/ER
checkpoint | 9.2.6 - Nighttime Survey
label | Inspection Point: Quality Control Activity - Post construction survey
label | Acceptance Criteria - (a) Overall any sign or part of a traffic sign (eg guide sign), especially when set in a disadvantaged position, is performing suitable for purpose, exhibiting an even level of retroreflectivity across the face of the sign to ensure that an appropriate level of readability is achieved across the entire sign throughout the approach
label | (b) The orientation of the sign face is such that no specular (mirror) retroreflection creates an over bright glare effect that interferes with sign recognition/readability
label | (c) At the threshold of retroreflectivity the traffic sign presents a level of visibility that ensures a driver becomes aware the sign is present – before actual readability is possible
label | (d) That any previous maintenance completed during daylight hours has not damaged retroreflectivity at night – for example poor graffiti cleaning
label | (e) Traffic signs remain fully effective and suitable for the purpose for which they were installed
label | Verifying Document - Survey Checklist
label | Frequency - Once per completed section of works
label | Inspection Type - Inspection
label | Inspection: Key - Inspection
label | Inspection: By - PM/ER