## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 02 - Earthworks | itp |  |  |  |  | F2LSIP - ITP 02 - Earthworks | 1359cf13-a212-41f0-9cf0-19408f27f11e
section | 2 - Earthworks
checkpoint | Earthworks
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by CR
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 2.1 - Source Properties Imported Fill
checkpoint | 2.1.1 - Bearing Strength
label | Inspection Point: Quality Control Activity - Sampled from truck or stockpile onsite as per NZS4402 clasue 1.6.3 & 1.6.4
label | Acceptance Criteria - CBR > 40 as per NZS4402
label | ○ Note: For Hard Fill CBR, the target CBR is determined by trhe following formula:The tests shall consist of 4-day soaked CBRs carried out to NZS 4402. If the sample mean is C and the standard deviation is s then C must not be less than 40 + 1.3s.
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per stockpile
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 2.1.2 - Weathering Resistance
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - QI = AA, AB, AC, BA, BB, CA, CB as per NZS4407 1991 Test 3.11
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per stockpile
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 2.1.3 - Grading Limits
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Grading within envelope as per table 302.2.3 (Technical Specifications) Tested in accordance with NZS4407 1991 Test 3.8.1
textbox | Maximum Material Particle size:
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per stockpile
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 2.2 - Construction
checkpoint | 2.2.1 - Topography Survey
label | Inspection Point: Quality Control Activity - Pre-Cut/Fill Survey
label | Acceptance Criteria - Within Design Expectations
label | Verifying Document - Survey Data
label | Frequency - Once per construction area
label | Inspection Type - Action
label | Inspection: Key - A
label | Inspection: By - SV
checkpoint | 2.2.2 - Survey Set out
label | Inspection Point: Quality Control Activity - Onsite Setout
label | Acceptance Criteria - Survey have setout using pegs or similar, the location of the pavement in regards to horizontal and vertical alignment, as per design. Existing surface to be surveyed for quantity measurements prior to topsoil strip, prior to cut or fill and after completion of Cut or Fill.
label | ○ Note: Prior to Cut and Fill Operation, Site Clearance and Topsoil stripping is required.
label | ○ NZTA F/1: Clause 3 - Clearing
label | ○ Clearing shall include complete removal from the site of trees, logs, scrub, grass, roots, and other vegetation fences (if any) and debris. All material removed shall become the property of the Contractor and disposed in a safe and legal mannner. Burning of rubbish & vegetation is not permitted at any time; irrespective of Local Authority permission.
label | ○ NZTA F/1: Clause 4 Topsoiling - Removal depth100mm thick. Only Topsoil under the footprint of works shall be removed.
label | 4. REMOVAL OF TOPSOIL
label | 4.1 Topsoil shall be removed within the limits of the earthworks. Care shall be taken during the removal to avoid contamination of the topsoil.
label | 4.2 Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. The Contractor shall control all stockpiling operations oto ensure the maximum utilisation of each area.
label | Verifying Document - N/A
label | Frequency - As required
label | Inspection Type - Action
label | Inspection: Key - A
label | Inspection: By - SV
checkpoint | 2.2.3 - Visual inspection of final trimmed subgrade surface
label | Inspection Point: Quality Control Activity - Pre pavement construction visual inspection
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM & ER
checkpoint | 2.2.4 - Compaction (granular)
label | Inspection Point: Quality Control Activity - Proof Roll
label | Acceptance Criteria - Surface impression not greater than:
label | ○ 7mm for bulk fill
label | ○ 5mm for subgrade fill
label | ○ Using 11t Smooth Drum Roller or equivalent.
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.5 - Compaction (Non-granular)
label | Inspection Point: Quality Control Activity - Wet density measure
label | Acceptance Criteria - See TNZ F-1 1997 Clause 10.5.2 Non Granular Material
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.6 - California Bearing Ratio
label | Inspection Point: Quality Control Activity - DCP Testing
label | Acceptance Criteria - Equivalent CBR value of ≥ 2%
label | Verifying Document - DCP Test Report
label | Frequency - TBD by Engineer
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.7 - Surface Finish Tolerances
label | Inspection Point: Quality Control Activity - Straight edge, as-built and inspection
label | Acceptance Criteria - No point varying more than 30mm on a 3m straight edge laid parallel to centreline, or x-section camber board at 90° to centreline. No ponding where design slope ≥ 2%
label | ○ RL Tolerence = +0 - 30mm from design
label | ○ Survey data / As-built drawings to be submitted to engineer.
label | ○ The subgrade surface shall not pond water, where the design slope of the subgrade is 2% or steeper.
label | Verifying Document - Straight Edge form, as-built survey data, visual inspection
label | Frequency - TBD by Engineer
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.8 -
label | Inspection Point: Quality Control Activity - Subgrade Testing and Improvement
label | Acceptance Criteria - The in-situ subgrade shall be:
label | – Tested with Dynamic Cone Penetrometer (DCP) as out in Section 505.2.3
label | – Proof roll as per the requirements as out in Section 505.2.4
label | Acceptance of the subgrade shall be confirmed by the Engineer and shall be based on achieving a minimum CBR of 6%.
label | Where DCP tests show areas less than the design CBR, these areas shall be treated by undercutting the subgrade and replacing with:
label | ○ AP65 subbase quality material (4% ≤ CBR < 6%), and
label | ○ AP65 subbase quality material and a Class 1 Geotextile with triaxial geogrid on top of the subgrade (2% ≤ CBR < 4%).
label | The undercut requirements, if a minimum CBR of 6% is no achieved, for the SH01N widening is shown in Table A505.2.1.
label | Verifying Document - IANZ Lab Report
label | Frequency - Each layer constructed.
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT