## 004 Trench & Backfill
TRENCHING AND BACKFILLING
Nominate Equipment or Works associated with this ITC | [12 empty] | Page 1 of 1
ITP No : |  | 001 |  | ITP Item No: |  | 3.2 |  | Job No: |  | Area:
Dwg No:
Dial before dig permit No: | [10 empty] | OK | NA | NCR raised
No | Confirm following items comply with requirements | [11 empty] | Major | Minor
Prior to excavation :
Stage / Section location:
1 | Mark out route as per electrical services drawings
2 | Potholing/Service Locations - mark-up all documentation identifying any service clashes Co-ordinate with other trades i.e. civil, hydraulic, comms Route and dimensions agreed with Principal Contractor
HOLD POINT
3 | Obtain excavation permit from Principal Contractor
During excavation
4 | Confirm signs / safety barriers in place
5 | Confirm trenching is correct - Size / Alignment / Depth (Use Datum Points)
Prior to backfilling:
HOLD POINT
6 | Confirm the completion of QA_TEM_005_Underground Conduit Installation has not raised any non-conformances Confirm suitability of proposed backfill Check compaction and frequency requirements Confirm layers being replaced i.e., geotextile fabric, road base, general fill
During and after backfilling, check that :
7 | Cable marker tape is correct (Type & Depth)
8 | Survey points for as built documentation has been completed
9 | Route markers installed
10 | Compaction is correct - refer to specification
11 | Route markers are correct
12 | Soil is properly removed
13 | Cable protection installed
On completion
14 | Layer clean fill
15 | Co-ordinate compaction tests as required with Principal Contractor
16 | Surface reinstatement to agreed standard
Associated documents:
Comments:
Minor NCR's raised |  |  |  |  | YES | NO | N/A | Have all NCR's been finalised ?
[8 empty] | YES |  | NO |  |  | N/A
Major NCR's raised |  |  |  |  | YES | NO | N/A
Accepted By |  |  | Name (Print) |  |  | Signature |  |  | Position |  | Date
Q Electrical
PM Review
Client (If Applicable)