## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Sewer Progress
| Scope |  |  | Sewer
Rows
|  | Sewer Main | grouping | sewer main
|  | Lot 1 - New-1/1 East | dynamic | lot 1 - new-1/1 east | sewer main | Sewer
|  | Lot 1 - New-1/1 Centre | dynamic | lot 1 - new-1/1 centre | sewer main | Sewer
|  | Lot 1 - New-1/1 West | dynamic | lot 1 - new-1/1 west | sewer main | Sewer
|  | Lot 2 - New-1/1 East | dynamic | lot 2 - new-1/1 east | sewer main | Sewer
|  | Lot 2 - New-1/1 Centre | dynamic | lot 2 - new-1/1 centre | sewer main | Sewer
|  | Lot 2 - 2/1-3/1 | dynamic | lot 2 - 2/1-3/1 | sewer main | Sewer
|  | Lot 3 - 4/1-5/1 | dynamic | lot 3 - 4/1-5/1 | sewer main | Sewer
|  | Lot 4 - 5/1-6/1 | dynamic | lot 4 - 5/1-6/1 | sewer main | Sewer
|  | Lot 5 - 8/1-7/1 | dynamic | lot 5 - 8/1-7/1 | sewer main | Sewer
|  | Lot 6 - 11/1-10/1 | dynamic | lot 6 - 11/1-10/1 | sewer main | Sewer
|  | Lot 7 - 1/3-E/3 | dynamic | lot 7 - 1/3-e/3 | sewer main | Sewer
|  | Lot 8 - 2/1-1/2 | dynamic | lot 8 - 2/1-1/2 | sewer main | Sewer
|  | Lot 9 - 2/1-3/1 | dynamic | lot 9 - 2/1-3/1 | sewer main | Sewer
|  | Lot 10 - 3/2-2/2 | dynamic | lot 10 - 3/2-2/2 | sewer main | Sewer
|  | Lot 11 - 1/4-2/4 | dynamic | lot 11 - 1/4-2/4 | sewer main | Sewer
|  | Road Crossings | grouping | road crossings
|  | Lot 12 - 1/1-2/1 | dynamic | lot 12 - 1/1-2/1 | road crossings | Sewer
|  | Lot 13 - 4/1-HC/1A | dynamic | lot 13 - 4/1-hc/1a | road crossings | Sewer
|  | Lot 14 - 5/1-HC/1B | dynamic | lot 14 - 5/1-hc/1b | road crossings | Sewer
|  | Lot 15 - 6/1-HC/1C | dynamic | lot 15 - 6/1-hc/1c | road crossings | Sewer
|  | Lot 16 - 7/1-HC1/D | dynamic | lot 16 - 7/1-hc1/d | road crossings | Sewer
|  | Lot 17 - 8/1-HC/1E | dynamic | lot 17 - 8/1-hc/1e | road crossings | Sewer
|  | Lot 18 - 9/1-HC/1F | dynamic | lot 18 - 9/1-hc/1f | road crossings | Sewer
|  | Lot 19 - 9/1-10/1 | dynamic | lot 19 - 9/1-10/1 | road crossings | Sewer
|  | Lot 20 - 1/2-1/4 | dynamic | lot 20 - 1/2-1/4 | road crossings | Sewer
|  | Lot 21 - 2/2-HC/2A | dynamic | lot 21 - 2/2-hc/2a | road crossings | Sewer
|  | Manholes | grouping | manholes
|  | New | dynamic | new | new | Sewer
|  | 1/1 | dynamic | 1/1 | 1/1 | Sewer
|  | 2/1 | dynamic | 2/1 | 2/1 | Sewer
|  | 3/1 | dynamic | 3/1 | 3/1 | Sewer
|  | 6/1 | dynamic | 6/1 | 6/1 | Sewer
|  | 9/1 | dynamic | 9/1 | 9/1 | Sewer
|  | 1/2 | dynamic | 1/2 | 1/2 | Sewer
|  | 3/2 | dynamic | 3/2 | 3/2 | Sewer
|  | 1/4 | dynamic | 1/4 | 1/4 | Sewer
Columns
|  | Trench Compaction Tests - Test Location plan provided |  | Test Location plan provided | Trench Compaction Tests
|  | Trench Compaction Tests - No trench base tests required | No trench base tests required | Test Location plan provided | Trench Compaction Tests
|  | Trench Compaction Tests - No trench base tests provided | No trench base tests provided | Test Location plan provided | Trench Compaction Tests
|  | Trench Compaction Tests - No backfill tests required | No backfill tests required | Test Location plan provided | Trench Compaction Tests
|  | Trench Compaction Tests - No backfill tests provided | No backfill tests provided | Test Location plan provided | Trench Compaction Tests
|  | Trench Compaction Tests - Target HILF Density | Target HILF Density | Test Location plan provided | Trench Compaction Tests
|  | Trench Compaction Tests - Densities Compliant |  | Densities Compliant | Trench Compaction Tests
|  | Manhole Compaction Tests - Test Location plan provided |  | Test Location plan provided | Manhole Compaction Tests
|  | Manhole Compaction Tests - No MH base tests required | No MH base tests required | Test Location plan provided | Manhole Compaction Tests
|  | Manhole Compaction Tests - No MH base tests provided | No MH base tests provided | Test Location plan provided | Manhole Compaction Tests
|  | Manhole Compaction Tests - No backfill tests required | No backfill tests required | Test Location plan provided | Manhole Compaction Tests
|  | Manhole Compaction Tests - No backfill tests provided | No backfill tests provided | Test Location plan provided | Manhole Compaction Tests
|  | Manhole Compaction Tests - Target HILF Density | Target HILF Density | Test Location plan provided | Manhole Compaction Tests
|  | Manhole Compaction Tests - Densities Compliant |  | Densities Compliant | Manhole Compaction Tests
|  | Manhole Compaction Tests - Manhole base DCP tests |  | Manhole base DCP tests | Manhole Compaction Tests
|  | Vacuum Tests - Manholes - Photos & documents |  | Attach and relevant photos & documents | Vacuum Tests - Manholes
|  | Vacuum Tests - Manholes - No Tests required | No Tests required | Attach and relevant photos & documents | Vacuum Tests - Manholes
|  | Vacuum Tests - Manholes - No Tests provided | No Tests provided | Attach and relevant photos & documents | Vacuum Tests - Manholes
|  | Vacuum Tests - Manholes - All Tests Passed |  | All Tests Passed | Vacuum Tests - Manholes
|  | Ovality - Photos & documents |  | Attach and relevant photos & documents | Ovality
|  | Ovality - No Tests required | No Tests required | Attach and relevant photos & documents | Ovality
|  | Ovality - No Tests provided | No Tests provided | Attach and relevant photos & documents | Ovality
|  | Ovality - All Tests Passed |  | All Tests Passed | Ovality
|  | Ovality - CCTV Sewer |  | CCTV Sewer | Ovality
|  | Destructive Welds - Photos & documents |  | Attach and relevant photos & documents | Destructive Welds
|  | Destructive Welds - No Tests required | No Tests required | Attach and relevant photos & documents | Destructive Welds
|  | Destructive Welds - No Tests provided | No Tests provided | Attach and relevant photos & documents | Destructive Welds
|  | Destructive Welds - All Tests Passed |  | All Tests Passed | Destructive Welds
|  | Concrete Compaction Tests - Photos & documents |  | Attach and relevant photos & documents | Concrete Compaction Tests
|  | Concrete Compaction Tests - No Tests required | No Tests required | Attach and relevant photos & documents | Concrete Compaction Tests
|  | Concrete Compaction Tests - No Tests provided | No Tests provided | Attach and relevant photos & documents | Concrete Compaction Tests
|  | Concrete Compaction Tests - All Tests Passed |  | All Tests Passed | Concrete Compaction Tests
|  | Material Compliance - Bedding material certifcation |  | Bedding material certifcation | Material Compliance
|  | Material Compliance - Pipe certification |  | Pipe certification | Material Compliance
|  | Material Compliance - Concrete mix design (thrust blocks & trench stops) |  | Concrete mix design (thrust blocks and trench stops) | Material Compliance
|  | Contractor's Accreditations - PE Welding |  | PE Welding accreditation | Contractor's Accreditations
|  | Contractor's Accreditations - PVC pipe installation course |  | PVC pipe installation course | Contractor's Accreditations
|  | Contractor's Accreditations - Century Plus |  | Century Plus accreditation | Contractor's Accreditations
|  | Contractor's Accreditations - Certifed Construction package from Construction Certifier |  | Certifed Construction package from Construction Certifier | Construction inspections
|  | As Constructed - Red Line Markups - All water & sewer mains |  | All water and sewer mains have been shown | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - No major departures from design on drawings |  | No major departures from the design shown on the drawings | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - All details/notes/legend updated to reflect "As constructed" |  | All details, notes and legend have been updated to reflect "As constructed" | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - As constructed stamps (Eng & Survey) on all drawings |  | As constructed stamps (Eng and Survey) shown on all drawings | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - Correct Lot Layout |  | Correct Lot Layout shown | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - New and existing road names |  | New and existing road names shown | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Existing sewer/water infrastructure |  | Existing sewer/water infrastructure shown | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Engineer's Stamp |  | Engineer's Stamp | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Surveyor's stamp |  | Surveyor's stamp | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Unitywater title block |  | Unitywater title block | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Unitywater drawing number |  | Unitywater drawing number | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Linetypes/text height as per SEQ Code |  | Linetypes/text height as per SEQ Code | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Legend on plan |  | Legend on plan | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - PSM/Datum on plans |  | PSM/Datum on plans | As Constructed - Drafting Generally
|  | As Constructed - Sewer - All sewer lines shown |  | All sewer lines are shown | As Constructed - Sewer
|  | As Constructed - Sewer - Sewer Structures |  | Sewer Structures | As Constructed - Sewer
|  | As Constructed - Sewer - Property connections - HCs shown for every lot |  | Property connections - HCs shown for every lot | As Constructed - Sewer
|  | As Constructed - Sewer - Hole" vs "Shaft" attribute correct |  | Hole" vs "Shaft" attribute correct | As Constructed - Sewer
|  | As Constructed - Sewer - Diameter (600, 1050, 1200 etc) | Diameter (600, 1050, 1200 etc) | Hole" vs "Shaft" attribute correct | As Constructed - Sewer
|  | As Constructed - Sewer - Precast Vs Cast insitu | Precast Vs Cast insitu | Hole" vs "Shaft" attribute correct | As Constructed - Sewer
|  | As Constructed - Sewer - Maintenance Structures: |  | Maintenance Structures: | As Constructed - Sewer
|  | As Constructed - Sewer - Pipes |  | Pipes | As Constructed - Sewer
|  | As Constructed - Sewer - Diameter (150,225 etc) checked | Diameter (150,225 etc) checked | Pipes | As Constructed - Sewer
|  | As Constructed - Sewer - Joint Type (RRJ, Weld etc) Checked | Joint Type (RRJ, Weld etc) Checked | Pipes | As Constructed - Sewer
|  | As Constructed - Sewer - Type (Bend, dead plate, branch etc) | Type (Bend, dead plate, branch etc) | Pipes | As Constructed - Sewer
|  | As Constructed - Sewer - Material (PVC-U, PE etc) checked | Material (PVC-U, PE etc) checked | Pipes | As Constructed - Sewer
|  | As Constructed - Sewer - Fittings/Connections: |  | Fittings/Connections: | As Constructed - Sewer
|  | As Constructed - Sewer - Diameter (100mm, 150mm etc) | Diameter (100mm, 150mm etc) | Fittings/Connections: | As Constructed - Sewer
|  | Qualities & Testing - Material Qualities |  | Material Qualities | Qualities & Testing
|  | Qualities & Testing - Concrete test reports for each manhole & bridging slab |  | Concrete test reports for each manhole and bridging slab if required | Qualities & Testing
|  | Qualities & Testing - Vacuum testing of each sewer line/manhole/poo pit |  | Vacuum testing of each sewer line, manhole and poo pit | Qualities & Testing
|  | Qualities & Testing - Ovality testing for each sewer line |  | Ovality testing for each sewer line. | Qualities & Testing
|  | Qualities & Testing - CCTV report for each line |  | CCTV report for each line | Qualities & Testing
|  | Qualities & Testing - Inspection reports (A&C) |  | Inspection reports (A&C) | Qualities & Testing
|  | Qualities & Testing - Compaction Testing |  | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Test Lift | Test Lift | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Test completed (Date) | Test completed (Date) | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Tested By | Tested By | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Docket # | Docket # | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Test Result % | Test Result % | Compaction Testing | Qualities & Testing