## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Watermain Progress
| Scope |  |  | Watermain
Rows
|  | Group 2- RC Driveway 01 | dynamic | group 2- rc driveway 01 | Watermain
|  | Group 4- RC Lot 7&19 | dynamic | group 4- rc lot 7&19 | Watermain
|  | Group 8- RC Lot 17 | dynamic | group 8- rc lot 17 | Watermain
|  | Group 15- RC Lot 38 | dynamic | group 15- rc lot 38 | Watermain
Columns
|  | As Constructed - Red Line Markups - All water & sewer mains shown |  | All water and sewer mains have been shown | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - No major departures from design shown on drawings |  | No major departures from the design shown on the drawings | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - All details/notes/legend updated to reflect "As constructed" |  | All details, notes and legend have been updated to reflect "As constructed" | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - As constructed stamps (Eng & Survey) shown on all drawings |  | As constructed stamps (Eng and Survey) shown on all drawings | As Constructed - Red Line Markups
|  | As Constructed - Red Line Markups - Correct Lot Layout shown |  | Correct Lot Layout shown | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - New & existing road names shown |  | New and existing road names shown | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Existing sewer/water infrastructure shown |  | Existing sewer/water infrastructure shown | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Engineer's Stamp |  | Engineer's Stamp | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Surveyor's stamp |  | Surveyor's stamp | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Unitywater title block |  | Unitywater title block | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Unitywater drawing number |  | Unitywater drawing number | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Linetypes/text height as per SEQ Code |  | Linetypes/text height as per SEQ Code | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - Legend on plan |  | Legend on plan | As Constructed - Drafting Generally
|  | As Constructed - Red Line Markups - PSM/Datum on plans |  | PSM/Datum on plans | As Constructed - Drafting Generally
|  | As Constructed - Water - All Mains are shown |  | All Mains are shown | As Constructed - Water
|  | As Constructed - Water - All mains dimensioned from Bdy |  | All mains dimensioned from Bdy | As Constructed - Water
|  | As Constructed - Water - All mains size, Class & length |  | All mains size, Class and length shown | As Constructed - Water
|  | As Constructed - Water - All SV |  | All SV shown | As Constructed - Water
|  | As Constructed - Water - All FH |  | All FH shown | As Constructed - Water
|  | As Constructed - Water - Fittings All Bend |  | Fittings All Bend shown | As Constructed - Water
|  | As Constructed - Water - All Tee shown (inc size) |  | All Tee shown (inc size) | As Constructed - Water
|  | As Constructed - Water - Water meter to each lot |  | Water meter to each lot shown | As Constructed - Water
|  | As Constructed - Water - Road crossings (inc size, class & length) |  | Road crossings (inc size, class and length) | As Constructed - Water
|  | As Constructed - Water - Property Connections |  | Property Connections | As Constructed - Water
|  | As Constructed - Water - ADAC File checked against visual drawings for consistency |  | ADAC File checked against visual drawings for consistency | As Constructed - Water
|  | As Constructed - Water - XML report reviewed & compliant |  | XML report has been reviewed and is compliant | As Constructed - Water
|  | As Constructed - Water - Diameter (25mm) Checked |  | Diameter (25mm) Checked | As Constructed - Water
|  | As Constructed - Water - Water Service:Class checked (PN16) |  | Water Service:Class checked (PN16) | As Constructed - Water
|  | As Constructed - Water - Material (PE) | Material (PE) | Water Service:Class checked (PN16) | As Constructed - Water
|  | As Constructed - Water - Diameter | Diameter | Water Service:Class checked (PN16) | As Constructed - Water
|  | As Constructed - Water - Material | Material | Water Service:Class checked (PN16) | As Constructed - Water
|  | As Constructed - Water - Pipes: |  | Pipes: | As Constructed - Water
|  | As Constructed - Water - Class | Class | Pipes: | As Constructed - Water
|  | As Constructed - Water - Joint (RRJ) | Joint (RRJ) | Pipes: | As Constructed - Water
|  | As Constructed - Water - Valves: |  | Valves: | As Constructed - Water
|  | As Constructed - Water - Type (Gate, Knife etc) | Type (Gate, Knife etc) | Valves: | As Constructed - Water
|  | As Constructed - Water - Diameter | Diameter | Valves: | As Constructed - Water
|  | As Constructed - Water - Hydrants: Spring Checked |  | Hydrants: Spring Checked | As Constructed - Water
|  | As Constructed - Water - Serial numbers included | Serial numbers included | Hydrants: Spring Checked | As Constructed - Water
|  | As Constructed - Water - Meters: Manufacturer Checked |  | Meters: Manufacturer Checked | As Constructed - Water
|  | As Constructed - Water - Fittings: |  | Fittings: | As Constructed - Water
|  | As Constructed - Water - Body size/diameter | Body size/diameter | Fittings: | As Constructed - Water
|  | Trench Backfill - Photos & documents |  | Attach and relevant photos & documents | Trench Backfill
|  | Trench Backfill - No Tests required | No Tests required | Attach and relevant photos & documents | Trench Backfill
|  | Trench Backfill - No Tests provided | No Tests provided | Attach and relevant photos & documents | Trench Backfill
|  | Trench Backfill - All Tests Passed |  | All Tests Passed | Trench Backfill
|  | Trench Backfill - Pressure Test passed |  | Pressure Test passed | Trench Backfill
|  | Trench Backfill - Destructive Weld Tests |  | Destructive Weld Tests | Trench Backfill
|  | Bacteriological test - Chlorination Certificate provided |  | Chlorination Certificate provided | Bacteriological test
|  | Bacteriological test - Chloro/Bacto report provided |  | Chloro/Bacto report provided | Bacteriological test
|  | Bacteriological test - F10045 - Water Quality Commission |  | F10045 - Water Quality Commission | Bacteriological test
|  | Construction Compliance - Material Compliance |  | Material Compliance | Construction Compliance
|  | Construction Compliance - Contractor's Accreditations |  | Contractor's Accreditations | Construction Compliance
|  | Construction Compliance - Construction inspections |  | Construction inspections | Construction Compliance
|  | Qualities & Testing - Material Qualities |  | Material Qualities | Qualities & Testing
|  | Qualities & Testing - Hydrostatic pressure test per stage/substage split |  | Hydrostatic pressure test per stage or substage is split | Qualities & Testing
|  | Qualities & Testing - Water meter register to include number & reading for each water meter |  | Water meter register to include number and reading for each water meter | Qualities & Testing
|  | Qualities & Testing - Destructive testing if HDPE used |  | Destructive testing if HDPE is used | Qualities & Testing
|  | Qualities & Testing - Inspection reports (A&C) |  | Inspection reports (A&C) | Qualities & Testing
|  | Qualities & Testing - Concrete reports for each thrust block |  | Concrete reports for each thrust block | Qualities & Testing
|  | Qualities & Testing - Compaction Testing |  | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Test Lift | Test Lift | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Test completed (Date) | Test completed (Date) | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Tested By | Tested By | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Docket # | Docket # | Compaction Testing | Qualities & Testing
|  | Qualities & Testing - Test Result % | Test Result % | Compaction Testing | Qualities & Testing