## Site QA Sheet
30-01-24 V0
342 Sydenham Rd | Work Zones | Work Lots | Work Elements | Checklists pulled from (Master Checklists Tab)
Folder Tier - 1 | Folder Tier - 2 | Folder Tier - 3 | Folder Tier - 3 | Folder Tier - 4
Site QA | Block A | Lot 01 | Inground Plumbing Installation | Authority Main to Meter Installation
Site QA | Block A | Lot 01 | Inground Plumbing Installation | Drainage Installation (In-ground)
Site QA | Block A | Lot 01 | Inground Plumbing Installation | Water Service Installation (In-ground)
Site QA | Block A | Lot 01 | Inground Plumbing Installation | Gas Service Installation (In-ground)
Site QA | Block A | Lot 01
Site QA | Block A | Lot 01 | Rough-in Plumbing Installation | Waste & Vent Installation
Site QA | Block A | Lot 01 | Rough-in Plumbing Installation | Water Service Installation (Rough-ins)
Site QA | Block A | Lot 01 | Rough-in Plumbing Installation | Gas Service Installation (Rough-ins)
Site QA | Block A | Lot 01
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Toilet & Cistern Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Wash Basin & Tapware Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Shower & Tapware Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Bath & Tapware Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Kitchen Sink & Tapware Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Washer Machine Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Laundry Trough & Tapware Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Tundish Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Hose Tap Installation
Site QA | Block A | Lot 01 | Fit-off Plumbing Installation | Gas Appliance Installation
Site QA | Block A | Lot 01
Site QA | Block A | Lot 01 | Hot Water Unit Installation | Water Heating, Boiling, Chilling, Unit Installation
Site QA | Block A | Lot 01
Site QA | Block A | Lot 01 | Testing | Testing Drainage Pipework (Air Test)
Site QA | Block A | Lot 01 | Testing | Testing Drainage Pipework (Water Test)
Site QA | Block A | Lot 01 | Testing | Testing Water Pipework (Water Test)
Site QA | Block A | Lot 01 | Testing | Testing Gas Service (Air Test)
Site QA | Block A | Lot 01
Site QA | Block A | Lot 01 | Commissioning | Commission Fixture Group
Site QA | Block A | Lot 01 | Commissioning | Commission Hot Water Generating Plant
Site QA | Block A | Lot 01 | Commissioning | Commission Reduced Pressure Zone Device
Site QA | Block A | Lot 02 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 03 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 04 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 05 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 06 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 07 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 08 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 09 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 10 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 11 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 12 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 13 | Repeat folder structure as above | Repeat checklists as above
Site QA | Block A | Lot 14 | Repeat folder structure as above | Repeat checklists as above
Site QA
Site QA | Block B | Lot 15 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 16 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 17 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 18 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 19 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 20 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 21 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 22 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 23 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 24 | Repeat folder structure as above | Repeat checklists as above
Site QA
Site QA | Block C | Lot 25 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 26 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 27 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 28 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 29 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 30 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 31 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 32 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 33 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 34 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 35 | Repeat folder structure as above | Repeat checklists as above
Site QA
Site QA | Block D | Lot 36 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 37 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 38 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 39 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 40 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 41 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 42 | Repeat folder structure as above | Repeat checklists as above
Site QA
Site QA | Block E | Lot 43 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 44 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 45 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 46 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 47 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 48 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 49 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 50 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 51 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 52 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 53 | Repeat folder structure as above | Repeat checklists as above
Site QA |  | Lot 54 | Repeat folder structure as above | Repeat checklists as above
z | z | z |  | z | z | z

## MCL Index
| Type | Name | Values | Prefix | Postfix
Checklist 240122
1 | checklist | Add New Task
2 | checklist | Drainage Installation (In-ground)
3 | checklist | Stack & Vent Installation
4 | checklist | Waste & Vent Installation
5 | checklist | Cast-in Waste & Vent
6 | checklist | Downpipe & Overflow Installation
7 | checklist | Pump Line Installation
8 | checklist | Suction Line Installation
9 | checklist | Authority Main to Meter Installation
10 | checklist | Water Service Installation (In-ground)
11 | checklist | Water Service Installation (Mains/Risers)
12 | checklist | Water Service Installation (Rough-ins)
13 | checklist | Backflow Prevention Device Installation
14 | checklist | Water Meter Installation
15 | checklist | Gas Service Installation (In-ground)
16 | checklist | Gas Service Installation (Mains/Risers)
17 | checklist | Gas Service Installation (Rough-ins)
18 | checklist | Penetration Installation
19 | checklist | Toilet & Cistern Installation
20 | checklist | Urinal & Cistern Installation
21 | checklist | Wash Basin & Tapware Installation
22 | checklist | Shower & Tapware Installation
23 | checklist | Bath & Tapware Installation
24 | checklist | Kitchen Sink & Tapware Installation
25 | checklist | Washer Machine Installation
26 | checklist | Laundry Trough & Tapware Installation
27 | checklist | Tundish Installation
28 | checklist | Hose Tap Installation
30 | checklist | Gas Appliance Installation
32 | checklist | Cleaners Sink & Tapware Installations
33 | checklist | Water Heating, Boiling, Chilling, Unit Installation
34 | checklist | Plant & Equipment Installation
35 | checklist | Testing Drainage Pipework (Air Test)
36 | checklist | Testing Drainage Pipework (Water Test)
37 | checklist | Testing Water Pipework (Water Test)
38 | checklist | Testing Gas Service (Air Test)
39 | checklist | Commission Drainage Pump Station
40 | checklist | Commission Water Pressure Pump Set
41 | checklist | Commission Rain Water Pressure Pump Set
42 | checklist | Commission Water Storage Tank
43 | checklist | Commission Hot Water Generating Plant
44 | checklist | Commission Rain Water Diversion Valve
45 | checklist | Commission Thermostatic Mixing Valves
46 | checklist | Commission Reduced Pressure Zone Device
47 | checklist | Commission Fixture Group
| z | z | z | z | z

## Master Checklists
| Type | 342 Sydenham Road, Sydenham | Values | Prefix | Postfix
Checklist Resources - Updated 30/01/2024
1 | checklist | Add New Task
1 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
1 | checkpoint | New task checked off (add brief description of this task) | Yes, No, N/A
1
2 | checklist | Drainage Installation (In-ground)
2 | checkpoint | Mark this checkpoint 'FAIL' if you think this task should be a variation or additional scope of works. If ok mark as 'Pass' | Yes, No, N/A
2 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
2 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
2 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
2 | checkpoint | Check for damage & leaks | Yes, No, N/A
2 | checkpoint | Check materials & joining methods | Yes, No, N/A
2 | checkpoint | Check alignments & levels | Yes, No, N/A
2 | checkpoint | Check bedding & clearances | Yes, No, N/A
2 | checkpoint | Check connections to pits, tanks, etc | Yes, No, N/A
2 | checkpoint | Check covers, venting & conduits to pits, tanks, etc | Yes, No, N/A
2 | checkpoint | Check pipework & traps are clear of debris | Yes, No, N/A
2 | checkpoint | Check inspection openings | Yes, No, N/A
2 | checkpoint | Check open ends are sealed | Yes, No, N/A
2 | checkpoint | If trench is to be left open, make sure pipe can not float | Yes, No, N/A
2 | checkpoint | Check pipe trench marking tape (if specified) | Yes, No, N/A
2 | checkpoint | Check trench backfill & compaction | Yes, No, N/A
2 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
2
3 | checklist | Stack & Vent Installation
3 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
3 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
3 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
3 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
3 | checkpoint | Check for damage & leaks | Yes, No, N/A
3 | checkpoint | Check materials & joining methods | Yes, No, N/A
3 | checkpoint | Check alignments & levels | Yes, No, N/A
3 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
3 | checkpoint | Check expansion joints and anchor points | Yes, No, N/A
3 | checkpoint | Check inspection openings | Yes, No, N/A
3 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
3 | checkpoint | Check open ends are sealed | Yes, No, N/A
3 | checkpoint | Check acoustic insulation (if specified) | Yes, No, N/A
3 | checkpoint | Check pipe labelling | Yes, No, N/A
3 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
3 | checkpoint | Check roof vent pipes weather proofing is complete | Yes, No, N/A
3 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
3
4 | checklist | Waste & Vent Installation
4 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
4 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
4 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
4 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
4 | checkpoint | Check for damage & leaks | Yes, No, N/A
4 | checkpoint | Check materials & joining methods | Yes, No, N/A
4 | checkpoint | Check alignments & levels | Yes, No, N/A
4 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
4 | checkpoint | Check expansion joints and anchor points | Yes, No, N/A
4 | checkpoint | Check in-wall fixture mounting brackets | Yes, No, N/A
4 | checkpoint | Check in-wall waste pipes & vents | Yes, No, N/A
4 | checkpoint | Check inspection openings | Yes, No, N/A
4 | checkpoint | Check pipework & traps are clear of debris | Yes, No, N/A
4 | checkpoint | Check open ends are sealed | Yes, No, N/A
4 | checkpoint | Check acoustic insulation (if specified) | Yes, No, N/A
4 | checkpoint | Check pipe labelling | Yes, No, N/A
4 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
4 | checkpoint | Check roof vent pipes weather proofing is complete | Yes, No, N/A
4 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
4
5 | checklist | Cast-in Waste & Vent
5 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
5 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
5 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
5 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
5 | checkpoint | Check for damage & leaks | Yes, No, N/A
5 | checkpoint | Check materials & joining methods | Yes, No, N/A
5 | checkpoint | Check alignments & levels | Yes, No, N/A
5 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
5 | checkpoint | Check pipework & traps are clear of debris | Yes, No, N/A
5 | checkpoint | Check open ends are sealed | Yes, No, N/A
5 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
5
6 | checklist | Downpipe & Overflow Installation
6 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
6 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
6 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
6 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
6 | checkpoint | Check for damage & leaks | Yes, No, N/A
6 | checkpoint | Check materials & joining methods | Yes, No, N/A
6 | checkpoint | Check alignments & levels | Yes, No, N/A
6 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
6 | checkpoint | Check expansion joints and anchor points | Yes, No, N/A
6 | checkpoint | Check connection to roof & floor outlets | Yes, No, N/A
6 | checkpoint | Check inspection openings | Yes, No, N/A
6 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
6 | checkpoint | Check open ends are sealed | Yes, No, N/A
6 | checkpoint | Check acoustic insulation (if specified) | Yes, No, N/A
6 | checkpoint | Check pipe labelling | Yes, No, N/A
6 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
6 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
6
7 | checklist | Pump Line Installation
7 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
7 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
7 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
7 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
7 | checkpoint | Check for damage & leaks | Yes, No, N/A
7 | checkpoint | Check materials & joining methods | Yes, No, N/A
7 | checkpoint | Check alignments & levels | Yes, No, N/A
7 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
7 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
7 | checkpoint | Check open ends are sealed | Yes, No, N/A
7 | checkpoint | Check pipe labelling | Yes, No, N/A
7 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
7 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
7
8 | checklist | Suction Line Installation
8 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
8 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
8 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
8 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
8 | checkpoint | Check for damage & leaks | Yes, No, N/A
8 | checkpoint | Check materials & joining methods | Yes, No, N/A
8 | checkpoint | Check alignments & levels | Yes, No, N/A
8 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
8 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
8 | checkpoint | Check open ends are sealed | Yes, No, N/A
8 | checkpoint | Check pipe labelling | Yes, No, N/A
8 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
8 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
8
9 | checklist | Authority Main to Meter Installation
9 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
9 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
9 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
9 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
9 | checkpoint | Check for damage & leaks | Yes, No, N/A
9 | checkpoint | Check materials & joining methods | Yes, No, N/A
9 | checkpoint | Check alignments & levels | Yes, No, N/A
9 | checkpoint | Check bedding & clearances | Yes, No, N/A
9 | checkpoint | Check valve connections | Yes, No, N/A
9 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
9 | checkpoint | Check pipe trench marking tape (if specified) | Yes, No, N/A
9 | checkpoint | Check trench backfill & compaction | Yes, No, N/A
9 | checkpoint | Check water meter assemblies | Yes, No, N/A
9 | checkpoint | Check RPZD assemblies | Yes, No, N/A
9 | checkpoint | Check pipe labelling | Yes, No, N/A
9 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
9
10 | checklist | Water Service Installation (In-ground)
10 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
10 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
10 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
10 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
10 | checkpoint | Check for damage & leaks | Yes, No, N/A
10 | checkpoint | Check materials & joining methods | Yes, No, N/A
10 | checkpoint | Check alignments & levels | Yes, No, N/A
10 | checkpoint | Check bedding & clearances | Yes, No, N/A
10 | checkpoint | Check valve connections | Yes, No, N/A
10 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
10 | checkpoint | Check open ends are sealed | Yes, No, N/A
10 | checkpoint | Check pipe trench marking tape (if specified) | Yes, No, N/A
10 | checkpoint | If trench is to be left open, make sure pipe can not float | Yes, No, N/A
10 | checkpoint | Check trench backfill & compaction | Yes, No, N/A
10 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
10
11 | checklist | Water Service Installation (Mains/Risers)
11 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
11 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
11 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
11 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
11 | checkpoint | Check for damage & leaks | Yes, No, N/A
11 | checkpoint | Check crimp fittings | Yes, No, N/A
11 | checkpoint | Check materials & joining methods | Yes, No, N/A
11 | checkpoint | Check alignments & levels | Yes, No, N/A
11 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
11 | checkpoint | Check expansion joints and anchor points | Yes, No, N/A
11 | checkpoint | Check valves & meter assemblies | Yes, No, N/A
11 | checkpoint | Check valves & meter assemblies fixings & brackets | Yes, No, N/A
11 | checkpoint | Check hot water pipe clips & thermal insulation (if specified) | Yes, No, N/A
11 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
11 | checkpoint | Check for cross connections | Yes, No, N/A
11 | checkpoint | Check open ends are sealed | Yes, No, N/A
11 | checkpoint | Check pipe labelling | Yes, No, N/A
11 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
11 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
11
12 | checklist | Water Service Installation (Rough-ins)
12 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
12 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
12 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
12 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
12 | checkpoint | Check for damage & leaks | Yes, No, N/A
12 | checkpoint | Check crimp fittings | Yes, No, N/A
12 | checkpoint | Check for cross connections | Yes, No, N/A
12 | checkpoint | Check alignment & levels | Yes, No, N/A
12 | checkpoint | Check materials & joining methods | Yes, No, N/A
12 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
12 | checkpoint | Check TMV/TV | Yes, No, N/A
12 | checkpoint | Check mixer bodies & lugged elbows | Yes, No, N/A
12 | checkpoint | Check in-wall pan & cistern brackets | Yes, No, N/A
12 | checkpoint | Check noggings for future fixture | Yes, No, N/A
12 | checkpoint | Check sharp edge pipe protection | Yes, No, N/A
12 | checkpoint | Check heat trace (if specified) | Yes, No, N/A
12 | checkpoint | Check hot water pipe clips & thermal insulation (if specified) | Yes, No, N/A
12 | checkpoint | Check pipe colour coding | Yes, No, N/A
12 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
12 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
12
13 | checklist | Backflow Prevention Device Installation
13 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
13 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
13 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
13 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
13 | checkpoint | Check for damage & leaks | Yes, No, N/A
13 | checkpoint | Check materials & joining methods | Yes, No, N/A
13 | checkpoint | Check alignments & levels | Yes, No, N/A
13 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
13 | checkpoint | Check pressure relief pipe to tundish | Yes, No, N/A
13
14 | checklist | Water Meter Installation
14 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
14 | text | Meter Type:
14 | text | Meter Number:
14 | text | Meter Location:
14 | text | Meter Size:
14 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
14 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
14 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
14
15 | checklist | Gas Service Installation (In-ground)
15 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
15 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
15 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
15 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
15 | checkpoint | Check for damage & leaks | Yes, No, N/A
15 | checkpoint | Check materials & joining methods | Yes, No, N/A
15 | checkpoint | Check alignments & levels | Yes, No, N/A
15 | checkpoint | Check bedding & clearances | Yes, No, N/A
15 | checkpoint | Check valve connections | Yes, No, N/A
15 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
15 | checkpoint | Check open ends are sealed | Yes, No, N/A
15 | checkpoint | Check pipe trench marking tape (if specified) | Yes, No, N/A
2 | checkpoint | If trench is to be left open, make sure pipe can not float | Yes, No, N/A
15 | checkpoint | Check trench backfill & compaction | Yes, No, N/A
15 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
15
16 | checklist | Gas Service Installation (Mains/Risers)
16 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
16 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
16 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
16 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
16 | checkpoint | Check for damage & leaks | Yes, No, N/A
16 | checkpoint | Check materials & joining methods | Yes, No, N/A
16 | checkpoint | Check crimp fittings | Yes, No, N/A
16 | checkpoint | Check alignments & levels | Yes, No, N/A
16 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
16 | checkpoint | Check valves & meter assemblies | Yes, No, N/A
16 | checkpoint | Check valves & meter assemblies fixings & brackets | Yes, No, N/A
16 | checkpoint | Check pipework is clear of debris | Yes, No, N/A
16 | checkpoint | Check for cross connections | Yes, No, N/A
16 | checkpoint | Check open ends are sealed | Yes, No, N/A
16 | checkpoint | Check pipe labelling | Yes, No, N/A
16 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
16 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
16
17 | checklist | Gas Service Installation (Rough-ins)
17 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
17 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
17 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
17 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
17 | checkpoint | Check for damage & leaks | Yes, No, N/A
17 | checkpoint | Check crimp fittings | Yes, No, N/A
17 | checkpoint | Check for cross connections | Yes, No, N/A
17 | checkpoint | Check alignment & levels | Yes, No, N/A
17 | checkpoint | Check materials & joining methods | Yes, No, N/A
17 | checkpoint | Check clip spacing & pipe separation | Yes, No, N/A
17 | checkpoint | Check lugged elbows | Yes, No, N/A
17 | checkpoint | Check noggings for future fixture | Yes, No, N/A
17 | checkpoint | Check sharp edge pipe protection | Yes, No, N/A
17 | checkpoint | Check pipe colour coding | Yes, No, N/A
17 | checkpoint | Check floor/wall penetration fire proofing | Yes, No, N/A
17 | checkpoint | Testing by approved method has been complete (must provide test pressure photos) | Yes, No, N/A
17
18 | checklist | Penetration Installation
18 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
18 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
18 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
18 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
18 | checkpoint | Check for damage & missing penos | Yes, No, N/A
18 | checkpoint | Check penetration sizes, locations & finished levels are corrrect | Yes, No, N/A
18 | checkpoint | Check fire collars types & ratings are correct | Yes, No, N/A
18 | checkpoint | Check blank sleeves are correct | Yes, No, N/A
18 | checkpoint | Check cast-in outlets location & finished levels are correct | Yes, No, N/A
18 | checkpoint | Check open ends are sealed | Yes, No, N/A
18
19 | checklist | Toilet & Cistern Installation
19 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
19 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
19 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
19 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
19 | checkpoint | Check for damage or leaks | Yes, No, N/A
19 | checkpoint | Check level & alignment | Yes, No, N/A
19 | checkpoint | Check mini stops | Yes, No, N/A
19 | checkpoint | Check flexible connections are not twisted or kinked | Yes, No, N/A
19 | checkpoint | Check button assembly is securely fitted | Yes, No, N/A
19 | checkpoint | Check seat & lid function | Yes, No, N/A
19 | checkpoint | Check special DDA accessories (if applicable) | Yes, No, N/A
19 | checkpoint | Check operation, controls & remote sensors | Yes, No, N/A
19 | checkpoint | Check trap is clear of debris | Yes, No, N/A
19 | checkpoint | Check caulking | Yes, No, N/A
19
20 | checklist | Urinal & Cistern Installation
20 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
20 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
20 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
20 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
20 | checkpoint | Check for damage or leaks | Yes, No, N/A
20 | checkpoint | Check level & alignment | Yes, No, N/A
20 | checkpoint | Check mini stops | Yes, No, N/A
20 | checkpoint | Check flexible connections are not twisted or kinked | Yes, No, N/A
20 | checkpoint | Check button assembly | Yes, No, N/A
20 | checkpoint | Check operation, controls & remote sensors | Yes, No, N/A
20 | checkpoint | Check trap is clear of debris | Yes, No, N/A
20 | checkpoint | Check caulking is correct | Yes, No, N/A
20
21 | checklist | Wash Basin & Tapware Installation
21 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
21 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
21 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
21 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
21 | checkpoint | Check for damage or leaks | Yes, No, N/A
21 | checkpoint | Check level & alignment | Yes, No, N/A
21 | checkpoint | Check mini stops | Yes, No, N/A
21 | checkpoint | Check flexible connections are not twisted or kinked | Yes, No, N/A
21 | checkpoint | Check special DDA accessories (if applicable) | Yes, No, N/A
21 | checkpoint | Check waste & trap connections | Yes, No, N/A
21 | checkpoint | Check operation, controls & remote sensors | Yes, No, N/A
21 | checkpoint | Check trap is clear of debris | Yes, No, N/A
21 | checkpoint | Check caulking | Yes, No, N/A
21
22 | checklist | Shower & Tapware Installation
22 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
22 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
22 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
22 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
22 | checkpoint | Check for damage or leaks | Yes, No, N/A
22 | checkpoint | Check level & alignment | Yes, No, N/A
22 | checkpoint | Check wall plates, mixers & diversion valves | Yes, No, N/A
22 | checkpoint | Check outlets, wall rails & hand showers | Yes, No, N/A
22 | checkpoint | Check special DDA accessories (if applicable) | Yes, No, N/A
22 | checkpoint | Check waste & trap connections | Yes, No, N/A
22 | checkpoint | Check operation & controls | Yes, No, N/A
22 | checkpoint | Check floor grate level & alignment | Yes, No, N/A
22 | checkpoint | Check trap is clear of debris | Yes, No, N/A
22 | checkpoint | Check caulking | Yes, No, N/A
22
23 | checklist | Bath & Tapware Installation
23 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
23 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
23 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
23 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
23 | checkpoint | Check for damage or leaks | Yes, No, N/A
23 | checkpoint | Check level & alignment | Yes, No, N/A
23 | checkpoint | Check wall plates, mixers & diversion valves | Yes, No, N/A
23 | checkpoint | Check outlets, wall rails & hand showers | Yes, No, N/A
23 | checkpoint | Check special DDA accessories (if applicable) | Yes, No, N/A
23 | checkpoint | Check waste & trap connections | Yes, No, N/A
23 | checkpoint | Check operation & controls | Yes, No, N/A
23 | checkpoint | Check floor grate level & alignment | Yes, No, N/A
23 | checkpoint | Check trap is clear of debris | Yes, No, N/A
23 | checkpoint | Check caulking | Yes, No, N/A
23
24 | checklist | Kitchen Sink & Tapware Installation
24 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
24 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
24 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
24 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
24 | checkpoint | Check for damage or leaks | Yes, No, N/A
24 | checkpoint | Check level & alignment | Yes, No, N/A
24 | checkpoint | Check mini stops | Yes, No, N/A
24 | checkpoint | Check flexible connections are not twisted or kinked | Yes, No, N/A
24 | checkpoint | Check waste & trap connections | Yes, No, N/A
24 | checkpoint | Check dishwasher waste & water connections | Yes, No, N/A
24 | checkpoint | Check stop valves for future connections are capped | Yes, No, N/A
24 | checkpoint | Check operation & controls | Yes, No, N/A
24 | checkpoint | Check trap is clear of debris | Yes, No, N/A
24 | checkpoint | Check caulking | Yes, No, N/A
24
25 | checklist | Washer Machine Installation
25 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
25 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
25 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
25 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
25 | checkpoint | Check for damage or leaks | Yes, No, N/A
25 | checkpoint | Check level & alignment | Yes, No, N/A
25 | checkpoint | Check mini stops are correct | Yes, No, N/A
25 | checkpoint | Check wall tundish & waste connections | Yes, No, N/A
25 | checkpoint | Check stop valves are capped | Yes, No, N/A
25 | checkpoint | Check operation & controls | Yes, No, N/A
25
26 | checklist | Laundry Trough & Tapware Installation
26 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
26 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
26 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
26 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
26 | checkpoint | Check for damage or leaks | Yes, No, N/A
26 | checkpoint | Check level & alignment | Yes, No, N/A
26 | checkpoint | Check mini stops | Yes, No, N/A
26 | checkpoint | Check flexible connections are not twisted or kinked | Yes, No, N/A
26 | checkpoint | Check waste & water connections | Yes, No, N/A
26 | checkpoint | Check stop valves for future connections are capped | Yes, No, N/A
26 | checkpoint | Check operation & controls | Yes, No, N/A
26 | checkpoint | Check trap is clear of debris | Yes, No, N/A
26 | checkpoint | Check caulking | Yes, No, N/A
26
27 | checklist | Tundish Installation
27 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
27 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
27 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
27 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
27 | checkpoint | Check for damage or leaks | Yes, No, N/A
27 | checkpoint | Check level & alignment | Yes, No, N/A
27 | checkpoint | Check waste & trap connections | Yes, No, N/A
27 | checkpoint | Check trap is clear of debris | Yes, No, N/A
27
28 | checklist | Hose Tap Installation
28 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
28 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
28 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
28 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
28 | checkpoint | Check for damage or leaks | Yes, No, N/A
28 | checkpoint | Vacuum breaker fitted | Yes, No, N/A
28 | checkpoint | Check pipe colour coding | Yes, No, N/A
28
30 | checklist | Gas Appliance Installation
29 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
30 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
30 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
30 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
30 | checkpoint | Check for damage or leaks | Yes, No, N/A
30 | checkpoint | Check level & alignment is correct | Yes, No, N/A
30 | checkpoint | Check surrounding wall material is fire rated | Yes, No, N/A
30 | checkpoint | Check distance from cook-top to range hood complies with manufacturer specification | Yes, No, N/A
30 | checkpoint | Check surrounding walls to closest burner distance complies with manufacturer specification | Yes, No, N/A
30 | checkpoint | Check flexible connections are not twisted or kinked | Yes, No, N/A
30 | checkpoint | Check gas isolation valve | Yes, No, N/A
30 | checkpoint | Check gas pressure regulator | Yes, No, N/A
30 | checkpoint | Check operation & controls | Yes, No, N/A
30
32 | checklist | Cleaners Sink & Tapware Installations
30 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
32 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
32 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
32 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
32 | checkpoint | Check for damage or leaks | Yes, No, N/A
32 | checkpoint | Check level & alignment | Yes, No, N/A
32 | checkpoint | Check tapware for fit & function | Yes, No, N/A
32 | checkpoint | Check wall brackest & fixings | Yes, No, N/A
32 | checkpoint | Check bucket grate | Yes, No, N/A
32 | checkpoint | Check waste & trap connections | Yes, No, N/A
32 | checkpoint | Check trap is clear of debris | Yes, No, N/A
32 | checkpoint | Check caulking | Yes, No, N/A
32
33 | checklist | Water Heating, Boiling, Chilling, Unit Installation
33 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
33 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
33 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
33 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
33 | checkpoint | Check for damage or leaks | Yes, No, N/A
33 | checkpoint | Check level & alignment | Yes, No, N/A
33 | checkpoint | Check mini stops | Yes, No, N/A
33 | checkpoint | Check isolation valves & non-return valves | Yes, No, N/A
33 | checkpoint | Check pressure reduction valve (if specified) | Yes, No, N/A
33 | checkpoint | Check flexible connections are not twisted or kinked | Yes, No, N/A
33 | checkpoint | Check waste & water connections | Yes, No, N/A
33 | checkpoint | Check operation & controls | Yes, No, N/A
33 | checkpoint | Check water temperatures are as specified | Yes, No, N/A
33
34 | checklist | Plant & Equipment Installation
32 | checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation. If no variation mark as 'N/A'. You must still proceed with the following checks | Yes, No, N/A
34 | checkpoint | Plant & Equipment Installation checked off as below
34 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
34 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
34 | checkpoint | Installation & materials were used in accordance with manufacturer requirements | Yes, No, N/A
34 | checkpoint | Check for damage & leaks | Yes, No, N/A
34 | checkpoint | Check tundishes are correct | Yes, No, N/A
34 | checkpoint | Check electrical power is available | Yes, No, N/A
34 | checkpoint | Check BMS is available | Yes, No, N/A
34
35 | checklist | Testing Drainage Pipework (Air Test)
35 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
35 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
35 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
35 | checkpoint | Check installation is clean and ready for testing | Yes, No, N/A
35 | checkpoint | Apply air test as per AS/NZS-3500 (Provide test process photos) | Yes, No, N/A
35
36 | checklist | Testing Drainage Pipework (Water Test)
36 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
36 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
36 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
36 | checkpoint | Check installation is clean and ready for testing | Yes, No, N/A
36 | checkpoint | Apply water test as per AS/NZS-3500 (Provide test process photos) | Yes, No, N/A
36
37 | checklist | Testing Water Pipework (Water Test)
37 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
37 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
37 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
37 | checkpoint | Check installation is clean and ready for testing | Yes, No, N/A
37 | checkpoint | Apply water test as per AS/NZS-3500 (Provide test process photos) | Yes, No, N/A
37
38 | checklist | Testing Gas Service (Air Test)
38 | checkpoint | Installation complies with current AS/NZS-5600 | Yes, No, N/A
38 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
38 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
38 | checkpoint | Check installation is clean and ready for testing | Yes, No, N/A
38 | checkpoint | Apply air test as per AS/NZS-5600 (Provide test process photos) | Yes, No, N/A
38
39 | checklist | Commission Drainage Pump Station
39 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
39 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
39 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
39 | checkpoint | Check lifting rails & chains | Yes, No, N/A
39 | checkpoint | Check water level sensor set points | Yes, No, N/A
39 | checkpoint | Check pump motor rotation | Yes, No, N/A
39 | checkpoint | Check dry pump fault | Yes, No, N/A
39 | checkpoint | Check low water level fault | Yes, No, N/A
39 | checkpoint | Check high water level fault | Yes, No, N/A
39 | checkpoint | Check auto pump roll-over | Yes, No, N/A
39 | checkpoint | Check pump package operational set points | Yes, No, N/A
39 | checkpoint | Check control panel display & set points | Yes, No, N/A
39 | checkpoint | Check fault warning alarms | Yes, No, N/A
39 | checkpoint | Check BMS connection as specified | Yes, No, N/A
39 | checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint | Yes, No, N/A
39
40 | checklist | Commission Water Pressure Pump Set
40 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
40 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
40 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
40 | checkpoint | Check water supply fault | Yes, No, N/A
40 | checkpoint | Check pump motor rotation | Yes, No, N/A
40 | checkpoint | Check dry pump fault | Yes, No, N/A
40 | checkpoint | Check auto pump roll-over | Yes, No, N/A
40 | checkpoint | Check pump package operational set points | Yes, No, N/A
40 | checkpoint | Check control panel display & set points | Yes, No, N/A
40 | checkpoint | Check fault warning alarms | Yes, No, N/A
40 | checkpoint | Check BMS connection as specified | Yes, No, N/A
40 | checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint | Yes, No, N/A
40
41 | checklist | Commission Rain Water Pressure Pump Set
41 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
41 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
41 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
41 | checkpoint | Check water supply fault | Yes, No, N/A
41 | checkpoint | Check pump motor rotation | Yes, No, N/A
41 | checkpoint | Check dry pump fault | Yes, No, N/A
41 | checkpoint | Check auto pump roll-over | Yes, No, N/A
41 | checkpoint | Check ultra violet lamps | Yes, No, N/A
41 | checkpoint | Check filters & backwash | Yes, No, N/A
41 | checkpoint | Check back-up water supply | Yes, No, N/A
41 | checkpoint | Check pump package operational set points | Yes, No, N/A
41 | checkpoint | Check control panel display & set points | Yes, No, N/A
41 | checkpoint | Check fault warning alarms | Yes, No, N/A
41 | checkpoint | Check BMS connection as specified | Yes, No, N/A
41 | checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint | Yes, No, N/A
41
42 | checklist | Commission Water Storage Tank
42 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
42 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
42 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
42 | checkpoint | Check valves are fully open | Yes, No, N/A
42 | checkpoint | Check water level sensor set points | Yes, No, N/A
42 | checkpoint | Check tank fill valve | Yes, No, N/A
42 | checkpoint | Check low level fault | Yes, No, N/A
42 | checkpoint | Check high level fault | Yes, No, N/A
42 | checkpoint | Check passive over-flow | Yes, No, N/A
42 | checkpoint | Check statutory warning signage | Yes, No, N/A
42 | checkpoint | Check control panel display & set points | Yes, No, N/A
42 | checkpoint | Check BMS connection as specified | Yes, No, N/A
42 | checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint | Yes, No, N/A
42
43 | checklist | Commission Hot Water Generating Plant
43 | checkpoint | Installation complies with current AS/NZS-3500 & AS/NZS-5600 | Yes, No, N/A
43 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
43 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
43 | checkpoint | Check valves are fully open | Yes, No, N/A
43 | checkpoint | Check water filters are clean | Yes, No, N/A
43 | checkpoint | Check gas supply | Yes, No, N/A
43 | checkpoint | Check circulating pumps | Yes, No, N/A
43 | checkpoint | Check flue operation | Yes, No, N/A
43 | checkpoint | Check system auto start | Yes, No, N/A
43 | checkpoint | Check flow & return temperatures | Yes, No, N/A
43 | checkpoint | Check control panel display & set points | Yes, No, N/A
43 | checkpoint | Check BMS connection as specified | Yes, No, N/A
43 | checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint | Yes, No, N/A
43
44 | checklist | Commission Rain Water Diversion Valve
44 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
44 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
44 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
44 | checkpoint | Check valve operation | Yes, No, N/A
44 | checkpoint | Check valve defaults to storm-water if no power or tank full | Yes, No, N/A
44 | checkpoint | Check control panel display & set points | Yes, No, N/A
44 | checkpoint | Check BMS connection as specified | Yes, No, N/A
44 | checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint | Yes, No, N/A
44
45 | checklist | Commission Thermostatic Mixing Valves
45 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
45 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
45 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
45 | checkpoint | Check water temperature does not exceed 45°C (Provide photo) | Yes, No, N/A
45
46 | checklist | Commission Reduced Pressure Zone Device
46 | checkpoint | Installation complies with current AS/NZS-3500 | Yes, No, N/A
46 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
46 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
46 | checkpoint | Commissioning by certified persons only | Yes, No, N/A
46 | checkpoint | Check valves are fully open | Yes, No, N/A
46 | checkpoint | Check inlet water pressure does not exceed manufacturer specification | Yes, No, N/A
46 | checkpoint | Check outlet water pressure is as per manufacturer specification | Yes, No, N/A
46 | checkpoint | Check exhaust tundish drain sized to accept a full flush | Yes, No, N/A
46 | checkpoint | Provide the commissioning report & all plant documentation to this checkpoint | Yes, No, N/A
46
47 | checklist | Commission Fixture Group
47 | checkpoint | Installation complies with current AS/NZS-3500 or AS/NZS-5600 | Yes, No, N/A
47 | checkpoint | Installation complies with current drawings & specifications | Yes, No, N/A
47 | checkpoint | Installation & materials were used, comply with manufacturer requirements | Yes, No, N/A
47 | checkpoint | Check for any damage, leaks or missing components | Yes, No, N/A
47 | checkpoint | Check level & alignment of all fixtures | Yes, No, N/A
47 | checkpoint | Check all fixtures, seats & covers are securely fastened | Yes, No, N/A
47 | checkpoint | Check all valves are fully open | Yes, No, N/A
47 | checkpoint | Check all flexible connections are not twisted or kinked | Yes, No, N/A
47 | checkpoint | Check for water for cross connections | Yes, No, N/A
47 | checkpoint | Check fixture wastes & connections | Yes, No, N/A
47 | checkpoint | Check pipework & all traps are clear of debris | Yes, No, N/A
47 | checkpoint | Check AAV is installed to correct height | Yes, No, N/A
47 | checkpoint | Check future connection water valves are securely capped | Yes, No, N/A
47 | checkpoint | Check TV do not exceed 50°C | Yes, No, N/A
47 | checkpoint | Check TMV do not exceed 45°C | Yes, No, N/A
47 | checkpoint | Check dishwasher function | Yes, No, N/A
47 | checkpoint | Check gas valves & regulators | Yes, No, N/A
47 | checkpoint | Check all gas burner functions | Yes, No, N/A
47 | checkpoint | Check balcony hose tap | Yes, No, N/A
47 | checkpoint | Check balcony floor grate & downpipe | Yes, No, N/A
47 | checkpoint | Check all fixtures & tapware are operating as specified | Yes, No, N/A
47 | checkpoint | Confirm area has been left clean | Yes, No, N/A
47
| z | z | z | z | z