## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Q11 Penetrations Checklist |  |  |  |  | Yes | Q11 Penetrations Checklist | 2637a3f6-9b6a-43dc-9586-1996a2a9aa25
checkpoint-status |  |  | checkpoint | Drawings are marked for construction, are the latest revision and are entered on drawing register
checkpoint-status |  |  | checkpoint | Drawings have been submitted and approved by structural engineer.
checkpoint-status |  |  | checkpoint | Penetration has been set out as per drawings, form ply or conduits installed and secured in place
checkpoint-status |  |  | checkpoint | Penetrations have been fire sealed as per project requirements
checkpoint-status |  |  | checkpoint | Certificate for fire rating has been issued to the client
checkpoint-status |  |  | checkpoint | Final as Installed drawings have been drafted and submitted for approval
checklist-flat |  |  | checklist | Q07 Light Control Function Checklist |  |  |  |  | Yes | Q07 Light Control Function Checklist | 2ca98a21-d2a6-4bec-8443-40593be3fb81
checkpoint-status |  |  | checkpoint | Enter details below
text | 62e75ee1-6ccb-51c9-a8d8-98c7ddcfbecf |  | textbox | Motion Type
text | 55572266-19b1-5a99-bf79-9d35f77ce026 |  | textbox | Detection Function Operation
text | ed1a5cf5-0342-56fc-a2c5-505901b0e8a8 |  | textbox | Operation Time
text | 2b5af246-e09d-5589-ae2a-8faccca4eaaa |  | textbox | Switching Type
text | 49ec909d-5955-5d97-90d3-ceacef431019 |  | textbox | Daylight Harvest Function
checklist-flat |  |  | checklist | Q10 Master Antenna System Checklist |  |  |  |  | Yes | Q10 Master Antenna System Checklist | 4ce375c4-b343-44ce-9678-1232e7cd991b
checkpoint-status |  |  | checkpoint | Drawing is marked for construction, is the latest revision and is entered on the drawing register Drawing has been transmitted to subcontractor/supplier
checkpoint-status |  |  | checkpoint | Shop drawings for MATV system have been approved by consultant and issued for construction
checkpoint-status |  |  | checkpoint | The Master Antenna system is fully installed, and all floor and wall penetrations are completely sealed
checkpoint-status |  |  | checkpoint | As installed documents are kept up to date for the complete Master Antenna system
checkpoint-status |  |  | checkpoint | The complete Master Antenna system is fully tested, commissioned, and certified by subcontractor
checkpoint-status |  |  | checkpoint | Final as Installed drawings have been drafted and submitted for approval
checklist-flat |  |  | checklist | Q06 General Area Rough-in and Fit-off Checklist |  |  |  |  | Yes | Q06 General Area Rough-in and Fit-off Checklist | 506dfaf7-f0bd-44a6-aaa6-cb1dc7e52c3a
checkpoint-status |  |  | checkpoint | Lighting
checkpoint-status |  |  | checkpoint | Power
checkpoint-status |  |  | checkpoint | Data
checkpoint-status |  |  | checkpoint | Switchboard
checkpoint-status |  |  | checkpoint | Sub-Mains
checkpoint-status |  |  | checkpoint | Cable Tray
checkpoint-status |  |  | checkpoint | Security
checkpoint-status |  |  | checkpoint | NBN
checklist-flat |  |  | checklist | Apartment Rough In / Fit Off Checklist |  |  |  |  | Yes | Apartment Rough In / Fit Off Checklist | 588afc30-74cc-44ce-bc88-177631966f78
checkpoint-status |  |  | checkpoint | L1 - Lighting
checkpoint-status |  |  | checkpoint | L2 - Smoke Detector
checkpoint-status |  |  | checkpoint | P1 - General Power
checkpoint-status |  |  | checkpoint | P2 - Oven
checkpoint-status |  |  | checkpoint | P3 - General Power
checkpoint-status |  |  | checkpoint | P4 - Washing Machine/Dryer
checkpoint-status |  |  | checkpoint | P5 - AC
checkpoint-status |  |  | checkpoint | Purchaser Changes: Motorised Blinds, AC
checkpoint-status |  |  | checkpoint | Kitchen Led strip
checkpoint-status |  |  | checkpoint | Laundry LED & SW
checkpoint-status |  |  | checkpoint | Switches
checkpoint-status |  |  | checkpoint | 2 ways
checkpoint-status |  |  | checkpoint | Fan Plug Base
checkpoint-status |  |  | checkpoint | Lights
checkpoint-status |  |  | checkpoint | Switchboard
checkpoint-status |  |  | checkpoint | DATA/NBN
checkpoint-status |  |  | checkpoint | MATV
checkpoint-status |  |  | checkpoint | Submain
checkpoint-status |  |  | checkpoint | Coax Lead In
checklist-flat |  |  | checklist | Q03 Cast In Conduit Checklist |  |  |  |  | Yes | Q03 Cast In Conduit Checklist | 6d87d523-ead2-44cf-9619-8a6a1ad3d011
checkpoint-status |  |  | checkpoint | Drawings are marked for construction, are the latest revision and are entered on drawing register
checkpoint-status |  |  | checkpoint | All conduit is installed to correct positions, is the correct size, is securely glued, saddled, tied in position and the ends sealed for in slab conduits
checkpoint-status |  |  | checkpoint | All concealed conduit runs have been marked up on draft as installed drawings prior to concrete being poured Concrete pour has been observed to ensure conduits have not been damaged
checkpoint-status |  |  | checkpoint | Final as installed drawings have been drafted and submitted for approval
checklist-flat |  |  | checklist | Fire Rating Checklist |  |  |  |  | Yes | Fire Rating Checklist | 7af414b5-bb06-4a9b-9d07-648196ac182e
checkpoint-status |  |  | checkpoint | Header Penetration (Internal & External)
checkpoint-status |  |  | checkpoint | Room Penetrations
checkpoint-status |  |  | checkpoint | Labelling And Photos
checklist-flat |  |  | checklist | Q09 Main Switchboard Checklist |  |  |  |  | Yes | Q09 Main Switchboard Checklist | 7c15f023-2b8b-4663-923a-185900822886
checkpoint-status |  |  | checkpoint | Schematic drawings are marked for construction, are the latest revision and are entered on drawing register
checkpoint-status |  |  | checkpoint | Space has been checked and proposed switchboard will fit
checkpoint-status |  |  | checkpoint | Shop drawings have been submitted and approved by the client
checkpoint-status |  |  | checkpoint | Switchboard has been manufactured, factory inspection tests have been completed and switchboard is approved for delivery to site
checkpoint-status |  |  | checkpoint | Main switchboard has been delivered to site, installed, and bolted together
checkpoint-status |  |  | checkpoint | All connections have been tested, all penetrations have been sealed and certificate of electrical safety has been submitted Inspection has been booked
checkpoint-status |  |  | checkpoint | Inspection is completed Supply authority has energised the main switchboard
checkpoint-status |  |  | checkpoint | Final as Installed drawings have been drafted and submitted for approval
checklist-flat |  |  | checklist | Kapitol Group Acknowledgement Of Works |  |  |  |  | Yes | Kapitol Group Acknowledgement Of Works | 850034da-0740-4342-b985-aa952dc477c7
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgement of works being completed
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Q05 Distribution Boards Checklist |  |  |  |  | Yes | Q05 Distribution Boards Checklist | 8ad531d4-3dd5-42fe-b2c1-afc9d9133efd
checkpoint-status |  |  | checkpoint | Drawings are marked for construction, are the latest revision and are entered on drawing register
checkpoint-status |  |  | checkpoint | Available space has been checked and proposed distribution boards will fit
checkpoint-status |  |  | checkpoint | Shop drawings have been submitted and approved Available space has been re-checked and boards will fit
checkpoint-status |  |  | checkpoint | Switchboard has been manufactured, factory inspection tests have been completed and switchboard is approved for delivery to site
checkpoint-status |  |  | checkpoint | Switchboard has been installed All connections have been checked, all penetrations have been sealed, all outgoing circuits are safe for energizing
checkpoint-status |  |  | checkpoint | Distribution board and outgoing circuits have been tested Testing records have been completed Certificate of electrical safety has been submitted
checkpoint-status |  |  | checkpoint | Distribution Board and final sub-circuits have been energised
checkpoint-status |  |  | checkpoint | Final as Installed drawings have been drafted and submitted for approval
checklist-flat |  |  | checklist | Q08 Lightning Protection Checklist |  |  |  |  | Yes | Q08 Lightning Protection Checklist | 9c76eb18-ce15-4e06-a972-e515b09c82ea
checkpoint-status |  |  | checkpoint | Drawing is marked for construction, is the latest revision, has been transmitted to subcontractor/supplier and is entered on the drawing register
checkpoint-status |  |  | checkpoint | The lightning protection system has been coordinated with the builder, the subcontractor, and the Consultant Final details have been transmitted to subcontractor/supplier
checkpoint-status |  |  | checkpoint | As installed documents and test, results are kept up to date for the complete lightning protection system
checkpoint-status |  |  | checkpoint | The lightning protection system is fully installed, and all floor and wall penetrations are completely sealed
checkpoint-status |  |  | checkpoint | The complete lightning protection system is fully tested and commissioned to the satisfaction of all concerned
checkpoint-status |  |  | checkpoint | Final as Installed drawings have been drafted and submitted for approval
checklist-flat |  |  | checklist | Q12 Underground Conduit Checklist |  |  |  |  | Yes | Q12 Underground Conduit Checklist | 9db36d62-fa95-4886-a544-76b9e384c73d
checkpoint-status |  |  | checkpoint | Drawing is marked for construction, is the latest revision and is entered on the drawing register
checkpoint-status |  |  | checkpoint | Trench has been set-out and excavated to the required depth
checkpoint-status |  |  | checkpoint | All conduit is installed to correct positions, is the correct size, is securely glued, and the ends sealed for in ground conduits
checkpoint-status |  |  | checkpoint | The in-ground conduit is covered with a layer of coarse crushed stone which is compacted
checkpoint-status |  |  | checkpoint | Marker tape placed on top of compacted coarse crushed stone The trench is backed filled and compacted
checkpoint-status |  |  | checkpoint | All concealed conduit runs have been marked up on draft as installed drawings prior to concrete being poured
checkpoint-status |  |  | checkpoint | Final as installed drawings have been drafted and submitted for approval
checklist-flat |  |  | checklist | Q02 Busduct Checklist |  |  |  |  | Yes | Q02 Busduct Checklist | a00df454-eb8d-4003-9653-4881789387e7
checkpoint-status |  |  | checkpoint | Shop drawings have been submitted Available space has been checked and busduct will fit penetration drawing is correct
checkpoint-status |  |  | checkpoint | Busduct has been manufactured, factory inspection tests have been completed and busduct is approved for delivery to site
checkpoint-status |  |  | checkpoint | Busduct delivery has been checked for all correct components Electrical riser is weather sealed
checkpoint-status |  |  | checkpoint | Level of duct has been installed All joints have been checked and bolts torqued to spec
checkpoint-status |  |  | checkpoint | Sub mains from busduct to meter panel have been installed All connections have been checked
checkpoint-status |  |  | checkpoint | Busduct supply and sub mains have been isolated following the isolation procedure
checkpoint-status |  |  | checkpoint | Busduct and sub mains have been tested Testing records have been completed Certificate of electrical safety has been submitted
checkpoint-status |  |  | checkpoint | Busduct and final sub mains have been energised
checkpoint-status |  |  | checkpoint | Penetrations have been sealed
checklist-flat |  |  | checklist | Q04 Consumer Mains Including Main Earth Checklist |  |  |  |  | Yes | Q04 Consumer Mains Including Main Earth Checklist | ebefcf12-c069-4124-a43a-b901fc165fb8
checkpoint-status |  |  | checkpoint | Drawings are marked for construction, are the latest revision and are entered on drawing register
checkpoint-status |  |  | checkpoint | Earth stake position have been confirmed Full co-ordination of cable route is complete Cable sizes, lengths and configuration have been finalised
checkpoint-status |  |  | checkpoint | Substation phase configuration and supply capacity has been confirmed with the supply authority
checkpoint-status |  |  | checkpoint | Cable ladder, earth stake, cables, main earth, earth bond and equipment earthing has been installed
checkpoint-status |  |  | checkpoint | Consumers mains have been terminated inside substation and the main switchboard
checkpoint-status |  |  | checkpoint | All connections have been tested Certificate of electrical safety has been submitted Inspection has been booked
checkpoint-status |  |  | checkpoint | Inspection is completed Supply authority has energised consumers mains
checkpoint-status |  |  | checkpoint | Final as Installed drawings have been drafted and submitted for approval