## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Installation of Conduit Stub-up's | [5 empty] | ASI-OP-OP-ITP-0041 Conduit Stub-Ups Rev 3
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check & confirm all required permits are in place and approved.
label | Quality Control Activity - R
label | Verify Documents - Permit Requirement’s
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 1.2 - Check & confirm the latest drawings and specifications are being referenced.
label | Quality Control Activity - M
label | Verify Documents - Drawings and specifications
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 1.3 - Check & confirm all plant and materials are available to complete the works and are fit for purpose.
label | Quality Control Activity - R
label | Verify Documents - Site Supervision
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - N/A
textbox | Comments:
checkpoint | 1.4 - Check & confirm all required qualified labour is available to complete the work.
label | Quality Control Activity - R
label | Verify Documents - Site Supervision
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - N/A
textbox | Comments:
section | 2.0 - Installation Works
checkpoint | 2.1 - Check & confirm the drawings details against the actual location.
label | Quality Control Activity - M
label | Verify Documents - Survey and ITS-0119
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 2.2 - Install Conduit Stub-Up’s as per the locations requirements.
label | Quality Control Activity - R
label | Verify Documents - Specification and ITS-0119
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 2.3 - Secure conduit stub-ups in position as per drawings / requirements.
label | Quality Control Activity - R
label | Verify Documents - Specification and ITS-0119
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 2.4 - Install cables through Conduit Stub-Ups and secure / tie as required.
label | Quality Control Activity - R
label | Verify Documents - TBA
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 2.5 - Install cable ID tags on both sides of conduit stub-up as required.
label | Quality Control Activity - R
label | Verify Documents - TBA
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 2.6 - Grout seal conduit stub-ups as required.
label | Quality Control Activity - R
label | Verify Documents - Specification and ITS-0119
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
section | 3.0 - Verification of Installation
checkpoint | 3.1 - Verify the installation is as per the latest drawings and requirements.
label | Quality Control Activity - M
label | Verify Documents - Specification, drawings and ITS-0119
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 3.2 - Complete survey of conduit stub-ups as / if required.
label | Quality Control Activity - M
label | Verify Documents - Survey and ITS-0119
label | Inspection Authority: Contractor - M
label | Inspection Authority: Engineer - M
label | Inspection Authority: Client - M
textbox | Comments:
checkpoint | 3.3 - Back-Fill with 5% stabilized sand
label | Quality Control Activity - R
label | Verify Documents - Specification and ITS-0119
label | Inspection Authority: Contractor - M
label | Inspection Authority: Engineer - M
label | Inspection Authority: Client - R
textbox | Comments:
section | 4.0 - Completion / Hand-Over
checkpoint | 4.1 - Complete As Built drawings as required.
label | Quality Control Activity - R
label | Verify Documents - Specification and ITS-0119
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 4.2 - Complete all documentation as required and hand-over as required to client.
label | Quality Control Activity - R
label | Verify Documents - Site requirements and ITS-0119
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 4.3 - Check and confirm all permits have been relinquished.
label | Quality Control Activity - Permit
label | Verify Documents - Site Supervision & Permit Requirement’s
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - N/A
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | FINAL ACCEPTANCE (All verifying documents completed, reviewed and accepted)
textbox | CONTRACTOR - NAME:
textbox | CONTRACTOR - TITLE:
textbox | CONTRACTOR - DATE:
textbox | ENGINEER - NAME:
textbox | ENGINEER - TITLE:
textbox | ENGINEER - DATE:
textbox | COMPANY - NAME:
textbox | COMPANY - TITLE:
textbox | COMPANY - DATE:
holdpoint | SIGN