## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Excavation and Backfill | [5 empty] | ASI-OP-OP-ITP-0044 Excavation Rev 3
section | 1.0 - APPROVALS AND OTHER PRELIMINARY REQUIREMENTS
checkpoint | 1.1 - Completion and required Approval of all required Permits.
label | Quality Control Activity - R
label | Verify Documents - Client’s Permits
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 1.2 - Review SWMS ( Safe Work Method Statement )
label | Quality Control Activity - R
label | Verify Documents - SWMS
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 1.3 - Develop / Review and have approved the Traffic Management Plan (if required).
label | Quality Control Activity - R
label | Verify Documents - TMP
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 1.4 - Confirm JHA’s etc. are completed and signed by all persons required.
label | Quality Control Activity - R
label | Verify Documents - JHA
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 1.5 - Confirm latest drawings are being referenced.
label | Quality Control Activity - R
label | Verify Documents - Drawings
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 1.6 - Confirm trench routing has been surveyed.
label | Quality Control Activity - R
label | Verify Documents - Survey
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 1.7 - Confirm location of designated waste disposal area.
label | Quality Control Activity - R
label | Verify Documents - Disposal Area
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 1.8 - Confirm all environmental controls are in place.
label | Quality Control Activity - R
label | Verify Documents - Enviro Plan
label | Inspection Authority: Contractor - M
label | Inspection Authority: Engineer - M
label | Inspection Authority: Client - M
textbox | Comments:
section | 2.0 - Preparation Works
checkpoint | 2.1 - Confirm all plant and equipment is available, is site approved and fit for purpose.
label | Quality Control Activity - R
label | Verify Documents - Visual & Permits
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 2.2 - Confirm trench route has been walk-down and survey pegs confirmed.
label | Quality Control Activity - R
label | Verify Documents - Survey & drawings
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 2.3 - Confirm all safety barricading and signage is available.
label | Quality Control Activity - R
label | Verify Documents - Barricades/ signs
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - N/A
textbox | Comments:
checkpoint | 2.4 - Confirm all safety bulletins have been issued.
label | Quality Control Activity - R
label | Verify Documents - Safety
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - M
textbox | Comments:
section | 3.0 - Excavation Works
checkpoint | 3.1 - Check and confirm all required signage and safety barricading is erected.
label | Quality Control Activity - R
label | Verify Documents - Visual
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 3.2 - Verify required trench depth and width prior to commencing.
label | Quality Control Activity - R
label | Verify Documents - Spec and drawings
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 3.3 - Excavate trench removing and separating excavated materials that will be unsuitable for backfilling.
label | Quality Control Activity - R
label | Verify Documents - Material grading
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - M
textbox | Comments:
checkpoint | 3.4 - Remove and dispose of unsuitable materials to designated disposal area.
label | Quality Control Activity - R
label | Verify Documents - Disposal
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - M
textbox | Comments:
checkpoint | 3.5 - Continually Erect safety signs and barricading along trench route as required.
label | Quality Control Activity - R
label | Verify Documents - HS&E
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 3.6 - Request client inspection of excavated trench system when excavation is completed.
label | Quality Control Activity - R
label | Verify Documents - Client Inspection Sheet
label | Inspection Authority: Contractor - H
label | Inspection Authority: Engineer - H
label | Inspection Authority: Client - W
textbox | Comments:
section | 4.0 - 1st Sand Bedding (if required)
checkpoint | 4.1 - Install 1st layer of sand bedding as required and have inspected by client’s representative.
label | Quality Control Activity - R
label | Verify Documents - Client Inspection Sheet
label | Inspection Authority: Contractor - H
label | Inspection Authority: Engineer - H
label | Inspection Authority: Client - W
textbox | Comments:
section | 5.0 - 2nd Sand Bedding (if required)
checkpoint | 5.1 - Install 2nd layer of sand bedding after installation of services is completed and have inspected by client.
label | Quality Control Activity - R
label | Verify Documents - Client Inspection Sheet
label | Inspection Authority: Contractor - H
label | Inspection Authority: Engineer - H
label | Inspection Authority: Client - W
textbox | Comments:
section | 6.0 - Backfill
checkpoint | 6.1 - Commence backfill with 5% stabilized sand in layers as per the relevant site requirements and specification.
label | Quality Control Activity - R
label | Verify Documents - Client Inspection Sheet
label | Inspection Authority: Contractor - M
label | Inspection Authority: Engineer - M
label | Inspection Authority: Client - M
textbox | Comments:
checkpoint | 6.2 - Complete compaction requirements as per the relevant site requirements and specification.
label | Quality Control Activity - R
label | Verify Documents - Client Inspection Sheet
label | Inspection Authority: Contractor - M
label | Inspection Authority: Engineer - M
label | Inspection Authority: Client - M
textbox | Comments:
checkpoint | 6.3 - Install polymer Protection Tiles (if required) as per the relevant site requirements and specification.
label | Quality Control Activity - R
label | Verify Documents - Visual Inspection
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 6.4 - Install Warning Tape (if required) as per the relevant site requirements and specification.
label | Quality Control Activity - R
label | Verify Documents - Visual Inspection
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 6.5 - Install route markers (if required) as per the relevant site requirements and specification.
label | Quality Control Activity - R
label | Verify Documents - As required
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 6.6 - Remove all surplus excavated materials to the approved disposal area.
label | Quality Control Activity - R
label | Verify Documents - Disposal
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 6.7 - Complete final grade of excavated area and clean up.
label | Quality Control Activity - R
label | Verify Documents - Visual inspection with Client
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - M
textbox | Comments:
section | 7.0 - Documentation
checkpoint | 7.1 - Complete all required documentation and get signed off by client.
label | Quality Control Activity - R
label | Verify Documents - Documentation
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 7.2 - Complete As Built drawings as required.
label | Quality Control Activity - R
label | Verify Documents - Documentation
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
checkpoint | 7.3 - Complete all survey data as required.
label | Quality Control Activity - R
label | Verify Documents - Survey
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - R
textbox | Comments:
section | 8.0 - Hand-Over
checkpoint | 8.1 - Walk – Down work area with client.
label | Quality Control Activity - R
label | Verify Documents - Client
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | 8.2 - Hand area back to client.
label | Quality Control Activity - R
label | Verify Documents - Hand-over
label | Inspection Authority: Contractor - R
label | Inspection Authority: Engineer - R
label | Inspection Authority: Client - W
textbox | Comments:
checkpoint | FINAL ACCEPTANCE (All verifying documents completed, reviewed and accepted)
textbox | CONTRACTOR - NAME:
textbox | CONTRACTOR - TITLE:
textbox | CONTRACTOR - DATE:
textbox | ENGINEER - NAME:
textbox | ENGINEER - TITLE:
textbox | ENGINEER - DATE:
textbox | COMPANY - NAME:
textbox | COMPANY - TITLE:
textbox | COMPANY - DATE:
holdpoint | SIGN