## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-009-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0009 - Unbound Pavements
section | Lot Information
checkpoint | 1.0 Lot Information
textbox | Lot Created On
textbox | Lot Opened On
textbox | Work Commenced On
dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
textbox | From and To Chainage
dropdown | Construction Element | PAVI - Paving
dropdown | Activity | SUC4 - Subbase - Class 4
dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
textbox | Engineer Responsible
textbox | comments
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
note | - - - - - - - - -
note | Reference Documents: PMP Inductions Register
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of conformity: Site induction signed.
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.2 - Check that current revision drawings are being used
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
note | - - - - - - - - -
note | Reference Documents: Project Drawings / Drawing Register
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of conformity: Latest Revision Drawings
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
note | - - - - - - - - -
note | Reference Documents: EMP, Site induction, Project Specification Cl. 1200.03
note | - - - - - - - - -
note | Inspection / Test Method: Document review & Site inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
note | Frequency: Prior to commencing
note | - - - - - - - - -
note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
note | - - - - - - - - -
note | Reference Documents: Project General Specsefication Cl.1125.07 Health and Safety Coordination Plan
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: SWMS(s) signed
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 1.5 - Crushed Rock Mix design
note | Frequency: Prior to Commencing Work
note | - - - - - - - - -
note | Acceptance Criteria: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Cl.812.04
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: Mix Design VicRoads Approval
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
note | Responsibility: Superintendent
signoff | HOLD POINT AUTHORITY
checkpoint | 1.6 - Excavation Permit issued
note | Frequency: Prior to Commencing Work
note | - - - - - - - - -
note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
note | - - - - - - - - -
note | Reference Documents: Excavation Permit
note | - - - - - - - - -
note | Inspection / Test Method: Document review & Site inspection
note | - - - - - - - - -
note | Record of conformity: Excavation Permit #
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 1.7 - Traffic Management (When required)
note | Frequency: Prior to Commencing Work
note | - - - - - - - - -
note | Acceptance Criteria: Approved TMP and MOA
note | - - - - - - - - -
note | Reference Documents: TMP
note | - - - - - - - - -
note | Inspection / Test Method: Document review & Site inspection
note | - - - - - - - - -
note | Record of conformity: Approved TMP & MOA
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility: Site Engineer
section | 2 - Placing Fill
checkpoint | 2.1 - Transverse Joints
note | Frequency: Check prior to placing material
note | - - - - - - - - -
note | Acceptance Criteria: * Material should be spread to minimize number of joints. * Transverse joints shall be offset from one layer to next by not less than 2 metres * Transverse joints shall be offset from one layer to the next by not less than 2 m.
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Cl.304.07 (a, b & c)
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 2.2 - Longitudinal Joints
note | Frequency: Check prior to placing material
note | - - - - - - - - -
note | Acceptance Criteria: * Material should be spread to minimize number of joints. * longitudinal joints shall be offset from one layer to the next by not less than 150 mm. * longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Cl.304.07 (a, d & e)
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 2.3 - Lot Size
note | Frequency: Check prior to placing material
note | - - - - - - - - -
note | Acceptance Criteria: A single lot shall be considered a single layer of 4000m2 or one day's production in a single layer, whichever is lesser. For pavement construction, any lot that has a surface area less than 500 m2 may be treated as a small area and tested in accordance with Section 173.
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Cl.304.08 (b)(ii & iv) Table 304.111
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 2.4 - Proof Roll
note | Frequency: After placing material
note | - - - - - - - - -
note | Acceptance Criteria: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Cl.304.08(b)(iv) Cl. 173
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
note | Responsibility: Site Engineer & Superintendent
signoff | HOLD POINT AUTHORITY
section | 3 - Testing and Inspection
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
note | Frequency: Prior to Testing
note | - - - - - - - - -
note | Acceptance Criteria: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Table 204.161 VicRoads Specification Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
note | - - - - - - - - -
note | Inspection / Test Method: Document Review/ Site Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.2 - Modified Compactive Effort
note | Frequency: As per 3.1
note | - - - - - - - - -
note | Acceptance Criteria: Characteristic Value of Density Ratio for Subbase:- > 98.0% for Scale A and >97.0% for Scale B. For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six.
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Cl. 304.08 (b) (iii) Table 304.081
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Test Records
note | - - - - - - - - -
note | TP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.3 - Permeability Testing
note | Frequency: As per 3.1
note | - - - - - - - - -
note | Acceptance Criteria: Class 4 Crushed rock max 5x10^-9 m/sec. Class 3 Crushed rock max 5x10^-7 m/sec Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051
note | - - - - - - - - -
note | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.051
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Test Records from Supplier
note | - - - - - - - - -
note | TP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.4 - Post-compaction Plasticity Index
note | Frequency: After compaction
note | - - - - - - - - -
note | Acceptance Criteria: Post-compaction Plasticity Index must comply with the requirement of table 3040.053. Class 3: 0 < PI < 10.
note | - - - - - - - - -
note | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.053
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Test Records from Supplier
note | - - - - - - - - -
note | TP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.5 - Post- compaction Grading
note | Frequency: After compaction
note | - - - - - - - - -
note | Acceptance Criteria: The post compaction grading shall comply with the requirements of table 304.101
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Cl. 304.10 Table 304.101
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Test Records from Supplier
note | - - - - - - - - -
note | TP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.6 - Test Requisition
textbox | Test Requested on
textbox | Location
dropdown | Material Type | Type A,Type B,See comments
dropdown | Material Source | Holcim,Boral,See comments
tickbox | Compaction Test (Standard)
tickbox | Compaction Test (Modified)
tickbox | Maximum Particle Test
tickbox | CBR/Swell Test
tickbox | PI Test
tickbox | Permeability Test
tickbox | Grading
tickbox | Moisture
tickbox | See comments
textbox | Test Level/ Layer
signoff | Test Requisition
checkpoint | 3.7 - Survey Level
note | Frequency: At completion
note | - - - - - - - - -
note | Acceptance Criteria: Scale A: Minimum number of measurements per lot: 80 for Upper — Upper Subbase: Mean + 4mm to -8mm wit a maximum Standard Deviation of 8mm — Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm — Base: Mean +- 5 with a maximum Standard Deviation of 8mm
note | - - - - - - - - -
note | Reference Documents: VicRoads Specification Table 304.061 Table 304.062
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Test Records
note | - - - - - - - - -
note | TP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Name:
textbox | Position:
textbox | Date:
textbox | Work Completed On:
signoff | Add Signature
section | Lot Verification
checkpoint | Lot Verification.
dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
textbox | Other:
dropdown | Lot Status | OUTSTANDING, CLOSED
textbox | Lot Closed On
textbox | comments