## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B | 3111f2df-fd4d-4607-ba81-ecbd85e8df1e
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Work Lot
label | f8fa8744-13b2-595c-98cc-5859150f61f7 |  | note | Ref docs - 173.02 204.03 (h) Table 204.142
label | d1ea8105-ee7f-591a-8a11-cf1e60ef4236 |  | note | • Quality Management Plan
label | 39a8c9d4-027d-5918-a9d9-4f96876e37ba |  | note | • Lot Diagram
label | f7650654-fefc-5b5e-bfb4-1486c27d2111 |  | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works.
label | 6c69807b-c950-5009-b94a-9b772664fe74 |  | note | • Lot diagram to be provided clearly marking up extents of lot area.
label | 1ef85644-cc9d-512f-a208-6d9367fc4fea |  | note | • Work Lot open on TeamBinder.
label | a27b5b57-cf0a-5840-a13e-ec109c455015 |  | note | • Lot size with no more than one day’s production or a maximum of 10000m² for Type B Material.
label | e043f336-5a94-5ae2-a395-e00c15916d1f |  | note | • In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
button | 4aa1afbb-375c-5a7e-ac1a-5fda953d13ee |  | button | Has all of the above been completed and approved? | Yes, No
label | 51e77f8a-25a9-54bc-8d9c-b1377033a817 |  | note | Freq - Prior to start of works
label | 02f07382-4226-50c2-9891-8c218a386800 |  | note | Key - R S
label | dd7a00e0-c420-5602-bfe6-856a64eb27da |  | note | Resp - SE
checkpoint-group |  |  | section | 2.0 Set Out
checkpoint-status |  |  | checkpoint | 2.1 - Set Out Survey Completed
label | 118def92-7ae8-52bd-b7c1-ea6f3cef4ac3 |  | note | Ref docs - VR Clause 204.03 (a)
label | 083d1f38-9c86-5175-acba-f078f9465f9c |  | note | • IFC Drawings
label | a87b551f-99f5-5e2e-9c83-fffacbde0053 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
button | df6f0577-1631-5a38-b0c9-16f6c114cbaf |  | button | Has all of the above been completed and approved? | Yes, No
label | 2407d0e7-d52d-5181-b4d3-0a9dfcebc940 |  | note | Freq - Each Lot
label | 81be863e-484c-5078-a26c-f7cc0949fd96 |  | note | Key - R
label | 46a738c1-b9ef-55d1-ad30-b8cea37b6831 |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Placement of Type B Material
checkpoint-status |  |  | checkpoint | 3.1 - Underlying Layer Conformance
label | b966ac30-4021-58e8-9e25-53ac22743838 |  | note | Ref docs - VR Clause 204.10(b)
label | ba0c806a-d3c7-541e-84c9-293c5fbc20e7 |  | note | • Construction Document
label | c2e911ac-2517-550e-b6cf-2ee6d603ead6 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
button | ce35b749-8589-5479-aaaa-09f337926ce6 |  | button | Approval to proceed granted? | Yes, No
label | 3ae8b7f8-b3ce-5e26-a4ea-1591f1f2da2a |  | note | Freq - Each Lot
label | 080bd78e-71c7-5906-9172-209d89051cb9 |  | note | Key - H W
label | 7f8fcd2a-aeaf-592d-9fc2-a1e2cf1a8454 |  | note | Resp - SE
label | c1db7b92-6c3d-5126-864a-5d73143de71c |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Placing Geotextiles (if applicable)
label | bd08aef2-18fe-5935-9b33-534f3172ffee |  | note | Ref docs - VR Clause 210.05 Table PS3020.071
label | bed0d4e8-4bf8-5135-9c69-31ce505ae231 |  | note | • IFC Drawing
label | 7b201fa8-bc5e-5218-a9b7-ff88bbdbd546 |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent.
label | e2e69e54-079b-54e8-bf2a-853bfcdc9f85 |  | note | • Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with
label | 1d76b062-9cf5-56bb-ac26-05353f135e50 |  | note | • imperfections shall not be used.
label | 7deae25b-6a43-55c8-9c0a-e03d78545609 |  | note | • All joints shall be overlapped or sewn in accordance with the Geotextile Record.
label | fc7d1e8e-a611-5846-ad63-1d9f6fb5cc32 |  | note | • Geotextiles shall be covered by filling within 48 hours of placement.
button | efbf72a2-32fa-5bdb-8151-f91635077240 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 4230b240-da06-57b7-8733-02e0bd3e58a6 |  | note | Freq - Each Lot
label | f71b7a78-d185-54bb-83f8-b325c08f3afd |  | note | Key - H W
label | d2abe9c9-ff8b-577d-93b9-10d97343b4c1 |  | note | Resp - SE
label | e2d84bd3-e837-54b6-bea5-809ee533cb13 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Placing Subsurface Drainage
label | c2034b4b-82fc-5d1f-8cf5-18254a913649 |  | note | Ref docs - 1630-P200-SYM-TPW-RPT-0001 Appendix B – Table 5
label | b412a3a4-e44c-569c-83cc-e43719c8b8c1 |  | note | Acceptance criteria - Subsurface drainage mat to be prepared in accordance with drawings.
label | ac42204d-bfaa-5ef5-92af-13c35b074e8f |  | note | • Superintendent to review and approve prior to placement of any fill on top of subsurface drainage mat.
button | a2d77c7f-be3a-53b5-b980-46659f5d2cca |  | button | Approval to proceed granted? | Yes, No
label | f7afb9f1-9e7e-5743-945b-18b0c379a85a |  | note | Freq - Each Lot
label | 58de0113-ad2f-5738-b895-9d8385cd944c |  | note | Key - H
label | d81479cd-00a9-57e4-a8a6-fc50ebd29eea |  | note | Resp - SE
label | fb6c1e43-1fa9-51aa-9b3f-c6167f221205 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Placing of Fill
label | 7439b7b5-66df-50e3-a649-1a765a24b725 |  | note | Ref docs - VR Clause 204.10(d)
label | 28d26d1c-81e3-58b0-bc4d-813f00975d6d |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm.
label | 3a6b356c-7c7b-51c3-969e-8aa27e959b17 |  | note | • Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
label | d507a032-f181-5036-a2fb-f8af3dd72c5f |  | note | • Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material.
label | 381e8f85-d34e-5ad1-9948-f65d4724db91 |  | note | • Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
label | f3d345ed-beab-5838-a56e-0c928bd4059b |  | note | • Material shall be compacted at minimum moisture ratio of 80%
button | 1d3d8f53-25e9-51be-9fe7-3d1bf0212b2e |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | fb1fd68f-3689-503a-b2a3-30945ae7f1aa |  | note | Freq - Once Each Lot
label | 29ec73c8-0132-5f84-9ad3-f1bf427e7307 |  | note | Key - W
label | b13ab224-53ee-563a-b31a-33929358dc63 |  | note | Resp - SE
button | 39e98d6a-206b-5c8c-82e8-bac451523eb6 |  | button | Verification Records: Layer Thickness at least every three layers | Yes, No
button | 62a26d3f-43b1-577c-9147-fe002ce00bf6 |  | button | Material Compliance Certificates & Material Approval Register | Yes, No
button | 696f9d87-dbb7-5d5e-8a53-0560a3efb911 |  | button | VicRoads registration of recycled material blend (if applicable) | Yes, No
checkpoint-status |  |  | checkpoint | 3.5 - Keyed Fill Layers
label | 104e13ea-72e4-50b7-9030-c40ac7450b5f |  | note | Ref docs - VR Clause 204.10(c) 204.10(d)
label | d2dc909a-758d-540a-b4b6-7ab223f911c2 |  | note | • Construction Document
label | e9791f4e-7e59-56c9-ab57-d49d73cfbe7d |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
label | 38f8450d-1e00-59b9-8d76-7e00e071fde9 |  | note | • Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | 314a6108-2574-5fbc-90da-06ab1b524735 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | b107da41-6929-541f-a597-a3e3252f3b38 |  | note | Freq - Once Each Lot
label | 4a29c030-b1ba-5c93-9e80-70926b846973 |  | note | Key - W
label | e6df2306-34ae-55bf-99f5-166ca6cd7ffc |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Test Roll of Type B fill layer
label | 983500ac-6324-5b1f-a3a5-760b49f65ccf |  | note | Ref docs - VR Clause 204.12 173.03
label | 03ab576d-3c63-5c45-8e37-c69b63ee2ebc |  | note | • Construction Document (Test roll Procedure in specification 173.03)
label | 8ac0100a-3cc4-57a2-827d-242ef2f85a73 |  | note | • 1630-P200-SYM-GEO-DPK-0001 Table 43
label | 8ab6705a-6931-59b9-9435-644477ea4b54 |  | note | Acceptance criteria - Test Roll in accordance with Section 173.
label | e1633663-4a1e-5a62-a78a-21738e56505f |  | note | • Surface shall withstand test rolling without visible deformation or springing.
label | 4ac2db4a-8b83-5c58-9a16-585bedd8a7e1 |  | note | • Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass.
label | 217b824b-a26a-5a00-abd7-1baf1c824518 |  | note | • Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted.
label | a7733f88-456d-5861-80a7-2e93b24c4b8e |  | note | • The Contractor shall provide for the Superintendent to be present during all test rolling.
button | f64f483a-3116-5b3d-ae5e-aa37eff088d4 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 556c15b4-11ee-5cc9-9646-7e5f97ac3de3 |  | note | Freq - Each Lot
label | f5f7fc49-1b7b-574b-9239-8fa3c633c878 |  | note | Key - H
label | a9a6ac68-cd7e-5fc4-b44c-c149f6efeed3 |  | note | Resp - SE
label | b5e1d91b-8b4a-5833-b93c-4bbff796da76 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Geotechnical Analysis
checkpoint-status |  |  | checkpoint | 4.1 - CBR/Swell – Initial Testing
label | 91bfb728-5fdd-56b5-9e6b-ac3930a0339c |  | note | Ref docs - VR Clause 204.04(c) PS3020.05 (c)(v)
label | 98ae63c7-d3ea-549d-a559-f013517b318d |  | note | Acceptance criteria - First lot tested to determine assigned CBR and Swell:
label | ac9f9e30-d565-5a74-9fdf-c652b63fbf0f |  | note | • CBR ≥ 2.5%
label | 40712dda-c500-5516-a3be-ee59d7a2ffb7 |  | note | • Swell < 2.5%
label | c8fd70c5-d39f-5296-8304-b8ba47b10ce4 |  | note | • If swell exceeds 2.5%, material shall be classified as expansive. Raise RFI and request approval from Superintendent to use material.
label | 74cdb9ed-6770-53e7-b2a8-6609f5dccd6f |  | note | Freq - Each Lot
label | 62941524-c285-5027-9c3c-e3c947cef67d |  | note | Key - R
label | 7c85ecca-e400-55e4-9984-6aa85352f368 |  | note | Resp - SE
button | 5af2ccd3-3031-5d0a-b331-4d94cd946b32 |  | button | NATA Test Report: CBR and Swell | Yes, No
checkpoint-status |  |  | checkpoint | 4.2 - Compaction Testing / Moisture Testing
label | 7c0ba699-a638-5e26-b8a7-5e1c5d91cb62 |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) Table PS3020.072
label | 365f91d9-d18a-5119-932e-47785f1bf2d3 |  | note | Acceptance criteria - All areas of the job will be considered as scale A.
label | 212572ac-70c5-508f-b9ca-53060fd99d7a |  | note | • Scale A Testing: HWKR Rd, Princes Freeway, All Freeway Interchange Ramps, All other arterial roads.
label | 7ee65017-459d-559c-b479-746fda37da19 |  | note | • Scale B Testing: All other local roads, SUP.
label | 2f174dd1-5828-59a2-b6eb-a3fb2d21dade |  | note | • Type B material placed within 400 mm of top of Type B material: 99% (Scale A)
label | 63df42a2-8de3-5d69-a0f4-cb1441ceb73b |  | note | • Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A)
label | 12c0681f-8950-55a5-af8d-bed53a51f43f |  | note | • Type B material placed within 400 mm of top of Type B material: 98% (Scale B)
label | c17b1b5c-307a-5be3-b77d-618e417bcd29 |  | note | • Type B Material placed more than 400 mm below top of Type B Material: 95% (Scale B)
label | 1c49a7b5-13e6-5104-9d8c-e51023541254 |  | note | • Type B material is to be tested as per table 201.142. And should meet the moisture content requirements as per VR204.
label | 4c4325f5-a2eb-595c-aeb8-4fa5fa196f09 |  | note | • >70% for any material within 150mm of subgrade.
label | 6864dc93-2ff2-597b-be3e-333a8a6e0ea7 |  | note | • >80% for all material below cut floor level.
button | 93d15fb4-c8bf-5773-9678-b2b60d35f8fb |  | button | Have the results been achieved? | Yes, No
label | ba39e6a5-b6fb-5ab4-8cd9-d92b0271b339 |  | note | Freq - Each Lot
label | b654dc38-3ff9-58b6-ba21-8539363b5c51 |  | note | Key - R
label | 9c6d5e95-5e1e-5d3e-a0ff-48acaa61cc9e |  | note | Resp - SE
button | 15761318-036d-54de-a751-fa8d2dd404c5 |  | button | NATA Test Report: Compaction | Yes, No
checkpoint-status |  |  | checkpoint | 4.3 - Material Requirements
label | 44b65fdc-6368-5473-9181-924946fa2b1c |  | note | Ref docs - VR Clause Table 204.041
label | 4379448b-b6d0-523c-895a-3a8037cefebd |  | note | Acceptance criteria - Maximum Particle Distribution (MPD) ≤ 150 mm within 400 mm of Top of Type B. or MPD ≤ 40mm at depths greater than 400 mm below the top of Type B material.
button | e93b3fa0-8dfe-5d84-97ec-8c2e52a68c6c |  | button | Have the results been achieved? | Yes, No
label | 2114a86e-059c-513d-8ac6-c29e058925f5 |  | note | Freq - Each Lot
label | f1bf0faf-db49-5dfa-aa54-d6a4039fe6f3 |  | note | Key - R
label | c6f2522f-598b-54ce-9292-02bb59549387 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.4 - LL and PI Testing
label | d76fb0de-d97d-5ad8-bb27-d9cad57deddc |  | note | Ref docs - VR Clause Table 204.141 Table 204.142 173.04(d)
label | b43e6d06-8615-5fbf-9c35-94e547b16dad |  | note | Acceptance criteria - LL and comparison of PI against LL, (identification of silt) is required for Type B Material. Initial testing is 1 Test per 2 lots.
button | 2d8a3c83-32fb-5e62-945e-811f84c8e672 |  | button | Have the results been achieved? | Yes, No
label | 8a87e1fc-e8f2-5058-b430-c4a92ab6be0a |  | note | Freq - Each Lot
label | a074bc31-e9e7-5db8-9466-23e5ee89dbed |  | note | Key - R
label | a1a2e96e-f8cb-5c9f-8320-4dd0eb3b590d |  | note | Resp - SE
button | 5e59158b-3225-586c-ba9a-0f1a244dfb02 |  | button | NATA Test Report: LL, PI | Yes, No
checkpoint-status |  |  | checkpoint | 4.5 - Reduced Frequency Post compaction testing of initial lots.
label | c1479262-f6af-5c15-8091-aea0aeeec38f |  | note | Ref docs - VR Clause 204.14 – Table 204.141 PS3020.07 (f)
label | 6ca61033-2d69-5dfe-b061-4ac3da306207 |  | note | Acceptance criteria - Test initial lot for CBR/Swell.
label | 6a5f862d-a29f-5c5d-8c92-8c70cd03c944 |  | note | • Test initial 3 lots for compaction.
label | 3dc0e1e8-ee11-519d-9fd4-64846fc3338b |  | note | • Once material and work have achieved the specified requirements in the first test. And;
label | 8e90521c-245d-5507-83d5-0d8399de7d38 |  | note | • Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
label | c146e570-2dc6-55a0-aa24-a0e65def17fa |  | note | • If Reduced frequency has been granted, the testing can be conducted at the following frequency.
label | 90769965-a46f-5dcf-b97c-69c6347f2a09 |  | note | • 1 test per every 8 lots for CBR/Swell
label | 85d87464-9a88-5dac-968c-3ab7b678f556 |  | note | • 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing.
label | 6d34f96d-4895-5b35-bb0b-e076b5114d76 |  | note | • 1 test per 4 lots of LL and comparison of PI against LL.
button | 98404032-c260-52f1-b2c1-d684e7b4d057 |  | button | Has the criteria been achieved? | Yes, No
label | 62c7bb6b-86dc-5ec1-8058-f1017a9a105a |  | note | Freq - Each Lot
label | 6f56bbda-c8a8-5593-bcd7-98839f3d65c7 |  | note | Key - R
label | 6610f325-093b-5730-a0b6-f5990129546b |  | note | Resp - SE
label | 2ad28cee-3061-52a9-ac78-8535637aa9a9 |  | note | SI Key - R
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
label | d1345fae-145b-5b0d-af14-74c5227c0a94 |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | e7ab7d81-c896-592e-a99b-d0cc763d63c6 |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements.
label | af2cb4d9-359c-50dd-a958-2d376315462b |  | note | Scale A: 80 measurements per lot
label | e697266b-9e3a-583d-a9ca-703f6478ac6e |  | note | Mean +5 / -15 mm Max Std Dev. 12 mm
button | 57eed39e-620e-516e-b12b-e8601eb7111f |  | button | Does the final product conform to the above criterial? | Yes, No
label | 7e3734b0-d44c-5430-8d10-c4df18b361a7 |  | note | Freq - Each Lot
label | ffd92195-084d-576a-8f26-dcf60131aafc |  | note | Key - R
label | 5ef8ba29-032e-54b5-8b18-6f3446dd71a6 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 02eb49a0-3f89-5637-8bf6-d42b2315dec8 |  | note | Ref docs - VR Clause 204.15
label | 6a9e98f9-e1dd-5121-9cbe-fa3007557e1c |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
label | a5e66414-f1c3-501d-b611-fd5fb5a245dd |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | acd96646-20c0-58e3-a7d7-c8045e83f782 |  | button | Does the final product conform to the above criterial? | Yes, No
label | b8d92a8d-0ee1-5320-a7f5-11f9adcbe01a |  | note | Freq - Each Lot
label | 23697983-92a5-572a-bc45-af87969c195b |  | note | Key - R
label | b58f0636-5780-500d-b5bf-0f358a1ecf94 |  | note | Resp - SE
checkpoint-group |  |  | section | 6.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 6.1 - Test Reports
label | 1c5e28cd-b7a9-5172-831f-e6eeb8f870fb |  | note | Ref docs - DoT Specs
label | 9825c7b4-8b07-5800-a59a-a24f61edc366 |  | note | Acceptance criteria - All Test reports received and reviewed
label | e650331a-449c-5697-a402-dd04edaeca4b |  | note | Freq - Each Lot
label | 0a39f398-8347-5ff8-91c6-4028ececdb48 |  | note | Key - R
label | a835032b-54f1-5e3d-9bc4-434f31806b21 |  | note | Resp - SE
label | 301e79f9-cc24-5399-b011-84686b184546 |  | note | NATA Endorsed Test Reports
checkpoint-status |  |  | checkpoint | 6.2 - Product Non-Conformance
label | 7e067f12-75f7-5cb1-998c-30bec7510d73 |  | note | Ref docs - QMP
label | 87a3287c-1139-5a79-9f05-8820e0e93eb5 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 4fb2e3d3-112c-5769-a2e0-0987651e0f94 |  | note | Freq - Each Lot
label | a4f426b2-0b77-53c9-b298-95adbd8fcf6a |  | note | Key - R
label | 5948400e-70e1-5ca6-a1ff-bc0bb4eed080 |  | note | Resp - PE
label | 922db5e6-793c-5502-a517-9305dd6a331e |  | note | NCR reports
checkpoint-status |  |  | checkpoint | Works complete
text | e6466221-d572-56f8-8d61-0f15daf79e56 |  | textbox | Name:
text | feb18dff-780e-5219-a3ec-35f990bceeec |  | textbox | Position:
text | 12d106e1-c754-517c-9452-b660a99ce2a7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot conforms
text | 44cafff3-cf30-576b-bff4-110e03ffad77 |  | textbox | Name:
text | 60877274-ee3d-5e63-92f7-3ba3635121bd |  | textbox | Position:
text | 3027fa8d-93f4-5bb4-92a6-7bebfac36889 |  | textbox | Date lot closed:
text | 74f59420-8cdf-5e5f-b6ea-5437550ab3dd |  | textbox | NCR/s no. raised:
text | 2267fbfb-5bb1-5148-a955-6fbd41ccbbf6 |  | textbox | Date NCR closed for this lot:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing | a073e436-6148-4f4e-a1cf-0ac516489764
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Lot
label | 1aeaacd4-4230-5865-95c7-c87b67f2f725 |  | note | Ref docs - 1200.15 (b) (i) (B)
label | 3051c949-737e-5f17-91d2-d04bc948cd17 |  | note | Acceptance criteria - Clearly mark out lot and extents.
label | 25f3fbd6-318a-5d65-a217-61e8af37ca55 |  | note | • All No-Go Zones must be protected by temporary fencing and signage visible.
label | e9c9eb16-22e5-521a-bc5f-0ef130232142 |  | note | • All fencing of No-Go Zones must be:
label | ecddb32e-7a18-5e98-9fa4-a7143532f8b8 |  | note | a. erected a minimum of 1 metre beyond the boundary of the habitat to be protected, at the Tree Protection Zone or as directed by the Superintendent;
label | 99495e62-1c44-50e3-a545-ba563cb4783e |  | note | b. at minimum, constructed of star picket and paraweb with two wire supports. The star pickets must be 1.3m in height, installed to a height of 1m above ground level and the paraweb must be installed to ensure a minimum 30cm gap is available between the bottom of the fence and existing ground to allow for fauna movement;
label | a255df34-f2a2-559a-b045-2a60203e192a |  | note | c. communicated by signage installed on the temporary fencing at intervals no less than 10 metres apart stating ‘Environmental No-Go Zone – no unauthorised access’;
label | ab6a4518-209c-5efe-a7cc-1e738598fe04 |  | note | d. installed prior to commencement of works in the immediate area, in accordance with the relevant approved SEP; and
label | 568faa27-ea5e-5522-bef7-dc75982fd353 |  | note | e. retained in place for the duration of construction activities.
button | a2ec6a87-7d84-5ed9-bab7-5201a648016d |  | button | Has all of the above been completed? | Yes, No, N/A
label | 7f7c9a1b-c030-5997-9f37-8956a46d8830 |  | note | Freq - Prior to start of works
label | 9c7638ba-17e3-58a3-af91-d967e4e51e98 |  | note | Key - R
label | 067a77d9-060a-5143-8e55-8390c0ede22c |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.2 - Works required inside a No-Go Zone
label | b489b33a-e894-50f7-8c1c-b138239e478a |  | note | Ref docs - 1200.15 (b) (i) (B)
label | 613ac238-8319-5ae0-baa9-1f3b3f5eeabc |  | note | Acceptance criteria - No works are to occur inside any No-Go Zones, except for where the following process is followed:
label | 33ed54e1-e28e-55b9-95ba-c4d1e621de57 |  | note | • Before commencement, where works have potential to impact flora and fauna protected by a No Go Zone, the Superintendent has been provided a report to the requirements of 1200.15 (b) (i) (B) for approval 5 days before the proposed Delivery Activities and it has been approved by the Superintendent.
button | 15ca0b7e-2e78-5caa-ba28-68615285b53b |  | button | Has all of the above been completed? | Yes, No, N/A
label | fd935c82-b7e1-511d-95d2-b9ab84e2b6d4 |  | note | Freq - Prior to start of works
label | 6062c4de-3b5a-53d8-9a15-607b5b08d0c9 |  | note | Key - H
label | 35c3e5ec-38f5-54bc-805b-6060b8b9eaea |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - MRPV Vegetation Removal Permit
label | 688d3eca-247d-5a7a-b7b8-acf90a952cce |  | note | Ref docs - Vegetation Removal Permit / PS3020.07 (a) (ii)
label | fde1cadf-b659-5684-bfc1-d3340246aa53 |  | note | Acceptance criteria - Sign off by the Project and MRPV Environmental Representatives. This is to be reviewed by the Superintendent prior to removal and provided to Environmental team
button | f732ba0c-e9fd-5929-8e92-7c4091da8c37 |  | button | Has all of the above been completed? | Yes, No, N/A
label | f04de08a-0d34-5f7f-9f75-010c0a684c1a |  | note | Freq - Prior to start of works
label | 28124040-ea02-55df-9758-54259c361318 |  | note | Key - H
label | 4164726a-ef54-5049-9e7b-ce07d6c2dd95 |  | note | Resp - SE
label | e12ed4c0-a438-59c1-86cf-80df686a891c |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Design Documents Required
label | 7a32c4b3-012d-5891-8c3f-6e4e4dcc2985 |  | note | Ref docs - 1170.11
label | 8eada7fd-3d79-5a74-9c08-5df5768ef2a7 |  | note | Acceptance criteria - For site clearing and grubbing, the documents needed are:
label | 91c9385b-5359-5c43-a9da-ef3460a5a3a4 |  | note | (1) marked up drawings that relate to the design Documents and clearly define the scope of the Enabling Works;
label | 1e81eec6-8f15-5f5c-96a7-05ff41dfdfab |  | note | (2) any relevant Construction Specification for the Enabling Works.
label | 134cdc22-d059-503f-95b4-726cd717a2f7 |  | note | (3) a drawing showing environmental approval boundaries, activity areas and no-go zones.
label | 949dfb55-f788-516a-bea0-33cd437f9916 |  | note | (4) evidence that any required design related Approvals have been obtained; and
label | 930838fc-ee73-52da-a4f3-110030ccbd87 |  | note | (5) a list of all required Approvals.
button | 49215191-82bf-5cc2-a396-a1097e7b6353 |  | button | Has all of the above been completed? | Yes, No, N/A
label | a4351caf-6e81-58c2-87f7-9de342889914 |  | note | Freq - Prior to start of works
label | 2d7967b9-2b34-5465-8cca-1414d010d9a1 |  | note | Key - R
label | 5e2e08d1-b6a0-5a8c-8fa1-940b8205ec90 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.5 - Site Environmental Protection Plan
label | 367059b9-87d4-5293-8214-cc1b1896b2e4 |  | note | Acceptance criteria - Site Environmental Protection Plans and Site Erosion Control Plans have been reviewed and approved for works.
button | 7cb6d97e-008a-5996-ae1c-4ac9c740634b |  | button | Has all of the above been completed? | Yes, No, N/A
label | ca28ac44-81ad-53ff-8340-97003323e7b2 |  | note | Freq - Prior to start of works
label | f05f6b68-5a07-5a7a-9a38-16fdfd9a754e |  | note | Key - R
label | b255601b-3441-565f-8dcf-7097fb3bd442 |  | note | Resp - ENV REP
checkpoint-group |  |  | section | 2.0 Pre-Clearing activities
checkpoint-status |  |  | checkpoint | 2.1 - Pre-Clearing Identification
label | f66c08f7-26a3-517d-ae71-f8951f49cea7 |  | note | Ref docs - 1200.15 (b)(i)(C)
label | 9c6418f7-b248-5d60-b799-c0428e265a01 |  | note | Acceptance criteria - No less than 7 days prior clearing, an ecologist has certified that all habitat trees are clearly identified and marked with flagging tape or survey, consistent with the Design Documents and permits and approvals.
label | 406073f9-3636-543a-87ce-c92a9517220b |  | note | • Any salvageable timber suitable for reuse to be identified and marked for stockpiling, for it to be reused after clearing.
button | 5caee50c-1dbc-59b4-9134-0420fc38c384 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 304ca1c1-bddc-51d7-8579-614c4c345df5 |  | note | Freq - 7 days prior to proposed clearing
label | 330062aa-d495-5ed1-879e-a331e5e98d40 |  | note | Key - H
label | 5529ab32-761a-5984-9cda-c5b862cf7d98 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.2 - On-site inspection
label | cea5e880-ea3b-5e8b-a0cf-4ef27cdbeaca |  | note | Ref docs - 1200.15 (b)(i)(C) (4)
label | 92af811b-f0a9-5f25-80f6-2041775eaec1 |  | note | Acceptance criteria - Prior to removal of vegetation, site inspection to be arranged with the Superintendent and other authorities to confirm the requirements of Sections 1200.15(b)(i)(C)(1) and 1200.15(b)(i)(C)(2) have been achieved.
label | ad722b5e-4838-5ef2-9c69-15b7464a267b |  | note | • All Approvals are in place and the ecologist is always on site, ready to perform further inspections in accordance with Sections 1200.15(b)(i)(C)(3) and 200.15(b)(i)(C)(5).
button | f703935d-b0ce-532b-bf92-62ede504562d |  | button | Has all of the above been completed? | Yes, No, N/A
label | 36b866cc-9670-5900-8449-ff775a11fea8 |  | note | Freq - Prior to clearing
label | 4b0be976-fa55-5a73-bd16-9cb2a8040ce4 |  | note | Key - H
label | a5b589a5-762b-54c6-bece-ffe2e79061d1 |  | note | Resp - SE
label | 0ffbca66-b115-56c7-a6a8-344f4fafb2bd |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Onsite Clearing and Grubbing
checkpoint-status |  |  | checkpoint | 3.1 - Clearing
label | 8134fbe5-5f9c-51f4-bd1e-2285ba293755 |  | note | Ref docs - VR201.04 1200.15 (b)(i)(C) (5)
label | d1885acc-e2cf-5908-b8a8-3421c18841c4 |  | note | Acceptance criteria - Only non-habitat trees can be removed during the first stage of clearing. Habitat trees can then be removed after approvals have been received and a minimum of 24 hours after the removal of non-habitat trees.
label | 594387f3-cff1-5e29-a205-8c94f69f8f87 |  | note | • Prior to commencing of clearing each day, the ecologist appointed should inspect the area for signs of wildlife.
button | a62414e5-2aa4-57ef-9f46-a24733e6905f |  | button | Has all of the above been completed? | Yes, No, N/A
label | 4aa2dad0-7550-59a2-9b40-919a3fc12b34 |  | note | Freq - Each lot
label | 071f9452-f9ef-53f3-99c2-8969f5ddbef9 |  | note | Key - H
label | ac43cedc-ca20-5277-a6c4-84b94bf60f88 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.2 - Grubbing
label | 765705e2-d463-523b-bf79-b23f0f2c2dc1 |  | note | Ref docs - VR201.05
label | 3810f854-6779-5953-ab9d-554d9449e3f9 |  | note | Acceptance criteria - In areas where excavation will be undertaken, all vegetation shall be grubbed as per the requirements of VR 201.05 and early works – subgrade improvement design package
label | dd370420-f1e0-525b-9fb0-3482980c504d |  | note | • Holes resulting from grubbing shall be backfilled with similar material and compacted to same degree as surrounding material.
label | 43af75e3-6205-5bef-b9c0-c92da9f71132 |  | note | Freq - Each Lot
label | a32fc915-ab09-535b-88b4-4d9f9083db34 |  | note | Key - R
label | 942823a9-3770-57c2-8ed8-76b6d4c64c91 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.3 - Clearing at Culvert Sites
label | 17166604-6bf8-5a47-9f4b-549277092086 |  | note | Ref docs - VR201.06
label | 38cd2420-f39d-52ff-880b-d69a58f4dc70 |  | note | Acceptance criteria - Any trees or stumps with 10m of any portion of a proposed culvert having a waterway area greater than 6m^2 shall be cleared and grubbed in accordance with the requirements of VR201.
button | 81f3b80b-3665-5499-8b7d-4b029a1c3143 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b7364ca5-7ef3-5fd9-a367-9c26af473400 |  | note | Freq - Each lot
label | 1c9aa83b-f83f-567a-92a7-7302c41c5b5d |  | note | Key - R
label | b3d7b60a-53ce-548d-9229-0c85a8d738dd |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.4 - Flora and fauna handling and removal
label | 0c8b1649-bc7c-5328-a8c4-e66f8b8cd5af |  | note | Ref docs - 1200.15 (b)(i)(F)
label | 20c690c6-6455-580f-83a5-255e8110b13d |  | note | Acceptance criteria - The Superintendent must be notified if any significant flora and fauna is found, and an ecologist must identify and provide advice on what to do with the found flora or fauna.
label | 41c59073-a4f0-542b-b774-185ac0f50271 |  | note | • The Superintendent must notify Environmental representative of any flora and fauna found.
button | 6558365f-04f5-5525-b8ca-9e3ada2a8c59 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b015d1ac-2a3a-56ce-a752-5179739c3397 |  | note | Freq - Each lot
label | 6666619e-77af-539b-9be1-17089105176c |  | note | Key - I
label | b4508b45-159e-50f2-807f-3125fb7945ff |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Identified habitat
label | a3eaf210-473b-532b-9b97-c7d2ffb028de |  | note | Ref docs - VR201.10 1200.15
label | db02926b-aa92-5b12-a5c3-e8b948bf7818 |  | note | Acceptance criteria - Trees with hollows can only be removed during initial clearing, if hollow is occupied, the section is to be left and cut after clearance from the ecologist and a minimum of 24 hours after removal of non-habitat trees in the area.
button | 4eaa7fc3-187b-5524-8023-442f29334217 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 50ba95ab-ea75-5cd3-8271-fe53b2ea3dd8 |  | note | Freq - Each lot
label | 0fe09c78-873c-5e1c-b893-7946aa42f93f |  | note | Key - I
label | 9529233f-363e-52e5-a5d0-61fbf76aed4f |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Reuse of Material
label | 5ed6226d-b06c-5add-a9fe-05feddd7d5e0 |  | note | Ref docs - 1200.15 (b)(i)(G)
label | 19593e4e-2458-5263-8699-2530c500b7fb |  | note | Acceptance criteria - Seek and adopt where practical reuse opportunities for vegetation felled during the vegetation clearing operations. Reuse may include:
label | 9bb6ebc9-c4d7-59ad-b1e7-68d766c755b3 |  | note | a. retention of sections of a branch/trunk with hollows;
label | 2b188504-37fe-5e54-bc82-0af88263820c |  | note | b. habitat logs on the ground in revegetation sites;
label | 66b7bdcf-916b-57de-a73f-48746ce61f44 |  | note | c. placement as in-stream habitat with the appropriate approval of the relevant Catchment Management Authority; or
label | 63009fc2-485d-513a-97c2-645a99b9c12f |  | note | d. timber for furniture construction
label | d25265f3-e945-5cd5-8707-e2d067632433 |  | note | e. Mulch provided to Council, local schools, or to landscaping facilities
label | e9746773-2157-53de-9d93-5ee8925d70ab |  | note | Update tree removal/retention register
button | c0c4fd5b-50cf-5eee-9858-233bc7904da5 |  | button | Has all of the above been completed? | Yes, No, N/A
label | f25cfa97-395d-5c6a-938e-144f2ff692ce |  | note | Freq - Each lot
label | 51b7f521-36ee-53b7-9930-8dfb665e33b3 |  | note | Key - R
label | c1c1495d-0590-541c-b1c1-16d8fa3d64cc |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.7 - Disposal of Material
label | 22ab1f51-be06-59d3-8723-6a067c3cd4de |  | note | Ref docs - VR201.07 VR177.I2 PS3020.07 (a)
label | 5c8edeb8-5436-5716-b9ad-7eec55c24b3d |  | note | Acceptance criteria - No removal of noxious weeds from the site. Identify and undertake treatment of declared noxious weeds prior to the commencement of any ground disturbing activities.
label | 8ad52fd6-9afe-5a69-8a56-b25741efabe5 |  | note | • The disposal of these materials shall be in accordance with the CEMP and its sub plans
button | 15f8667e-f158-5a0e-b0b5-bb8f79ea6243 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b9bbbd28-46a5-55c2-90e6-b420a0b67e94 |  | note | Freq - Each lot
label | e67357d3-d70a-5557-a6c5-0724d4b43a7b |  | note | Key - R
label | 91f63033-9c44-5f27-99e0-db12236e6a7d |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.8 - Salvage of Vegetation
label | 23549aac-89ad-5bee-b6eb-0969e80f2ae1 |  | note | Ref docs - VR201.11
label | 72147322-28e1-51bc-b978-03f241399063 |  | note | Acceptance criteria - Salvaging any plants as well as collecting cuttings and available seed from areas of native vegetation on site to be completed where applicable
button | e2ce4a55-26c2-5287-aa10-7edb1b48adf0 |  | button | Has all of the above been completed? | Yes, No, N/A
label | ec6acecb-2efe-5060-8553-6bc607710bf8 |  | note | Freq - Each Lot
label | 41cb47bd-0387-50d8-bf7b-8cc6dc6e4fb5 |  | note | Key - R
label | 5e022082-44cf-5f79-8775-0d23395d8ead |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Product Non-Conformance
label | 19c26434-6dc1-59af-bc98-36adc0c0cfcc |  | note | Ref docs - CQMP
label | 9518b3f4-350e-5fcf-84bb-20dc7d9bfd0a |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 414be1e4-dd58-514e-9aa9-3aa236908911 |  | note | Freq - Each lot
label | 95c40cbe-2f04-5cfb-9ea7-46afacf4e933 |  | note | Key - R
label | 346b6282-08c5-5e82-b865-5a52190fbf88 |  | note | Resp - SE
text | 1de4e1b9-6e81-5c1e-937e-83f3b62d4ca2 |  | textbox | NCR No:
boolean | 3d042604-f802-5c13-9d3a-f5a67dd771c1 |  | tickbox | NCR reports
checkpoint-status |  |  | checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
label | ffc76c0f-2b8b-558d-b0d7-dae9d6812bed |  | note | Ref docs - CQMP Lot Records
label | e10d2619-880b-51f6-88de-945be30924e0 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | b2e3f48d-5616-5f85-8bbf-b937b6eacd62 |  | note | Freq - Each lot
label | a5c3681d-7870-5675-a7cf-b69ac24a35a6 |  | note | Key - R
label | d049f055-3bb5-56ce-a1ed-2ee1e25ae8ea |  | note | Resp - SE
boolean | 7f5d42cd-6f2a-5cfd-8273-f23af83651c5 |  | tickbox | Completed Checklist (if applicable) and reports and other compliance records attached.
checkpoint-status |  |  | checkpoint | Works complete
text | b6cae550-0803-5228-a7c2-2435c6ef9d43 |  | textbox | Name:
text | ecebb617-f0b0-50c9-8b17-5f08b95a2bc6 |  | textbox | Position:
text | 70847307-3131-528f-9492-99a9b779b584 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot conforms
text | 943bb270-c14d-5aed-b800-5ed14cd21f4c |  | textbox | Name:
text | 98450938-7c27-5cfd-8229-478e2b9e454b |  | textbox | Position:
text | 1587c337-cbcb-52c2-a695-d8ae1dbb010e |  | textbox | Date lot closed:
text | 7b2113f2-6c5b-58f1-805a-99576113cde3 |  | textbox | NCR/s no. raised:
text | e9ba59c4-d4ec-5bae-86c0-824b62dca42d |  | textbox | Date NCR closed for this lot:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping |  |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping | e9007ad5-8686-4cfd-9689-41b829945f13
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Commencement of Work
label | 354d4795-24bc-5065-8ceb-48d5e3a49155 |  | note | Ref docs - VR Clause 160.C1 General condition of Contract
label | 3604b9c5-db0f-5d37-a313-662a65afb029 |  | note | Acceptance criteria - Works shall not commence on site before the following documents have been submitted:
label | a2f3cb45-2f2e-558f-87ca-453e0f657632 |  | note | a. Evidence of public liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
label | b51d1b8c-0fe0-5d99-988d-5917794f9d27 |  | note | b. Third party property damage insurance in accordance with Clause 160.G1
label | 3cbaafe7-b65f-5a84-bc10-df42fc0ce6fd |  | note | c. Health and Safety Management Plan
label | a8777f84-cd15-5f8b-8fed-a7c578cf98ab |  | note | d. Construction Environmental Management Plan
label | cf0d5e50-678a-5153-8ffd-8e63e15a55b2 |  | note | e. Traffic Management Strategy and Traffic Management Plans for the initial works
button | 746ebbb4-4050-5c7c-8aab-a3fcc36b41fc |  | button | Has all of the above been completed and approved? | Yes, No, N/A
label | e8c3a184-a8f4-5272-82a3-11f5dea72b87 |  | note | Freq - Once (Pre-Start)
label | 845c6684-e4f9-5b0f-96c7-708a92b78f54 |  | note | Key - H
label | 20dac91e-ef6e-5e5e-8ffa-37400f1d0c16 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.2 - Safety
label | 7a23205e-ea04-5fa3-a339-47099e0014fe |  | note | Ensure that the following items have been actioned:
label | 506daf4b-2b5b-5461-b76e-2deb8d233501 |  | note | – SWMS if applicable
label | db56b86d-dd2a-5c0d-8616-70e7154f0a5b |  | note | – Plant Pre-start Inspection
label | 74cc66f9-a7d3-5537-8b90-da6b26d58931 |  | note | – Service locations identified
label | e259a063-05a4-5fce-b555-74d63f2b37b0 |  | note | – Traffic Management Plans (if required)
label | ae7dad5d-55d6-59e5-85a1-6c367e033a24 |  | note | – All staff inducted
label | 3a8d747a-73a3-505b-8cf3-26dc7f6edd17 |  | note | Ref docs - SMP
label | 1816e80a-be2c-51f4-8aee-18c55bc75588 |  | note | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
label | dee25c15-d2ac-5739-b2c0-77eea97b7d3b |  | note | • Plant inspections completed and entered.
label | c62750c2-7eb0-57c7-9fba-87e3ac98b376 |  | note | • TSA training completed. Pre-work briefings completed.
label | cb573129-8244-5126-9ccc-1b4800a0b520 |  | note | • Service Diagrams available and services located.
button | 79e64d44-a089-5c6e-93be-28bfd9b1dfea |  | button | Has all of the above been completed and approved? | Yes, No, N/A
label | febd9e82-8f5c-5dd2-9ee2-7e81ee54d9c5 |  | note | Freq - Once (Pre-Start)
label | ee3953d9-ce56-5d09-976a-87495b0e7567 |  | note | Key - H
label | 1b23ae50-05d4-5551-94b1-2fbef3c6c41e |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - Survey Set-out and TBM’s
label | ab550148-a0da-5865-99b3-d3e81ed2fbb7 |  | note | Ref docs - IFC Drawing
label | 858b8e46-6323-5fe7-a78a-8195315895fa |  | note | Acceptance criteria - Record existing and established TBMs. Survey set out including frame, benchmark, and recovery points in place.
button | 802b698e-9f4f-585f-b64c-44224b503f97 |  | button | Has all of the above been completed? | Yes, No, N/A
label | aee3ad6f-2789-54a5-beb7-2ae34e363e63 |  | note | Freq - Prior to start of Works
label | d6d6148a-cec1-5c75-b757-64ca8569ac01 |  | note | Key - H
label | 53102884-5190-5c72-a305-f4f39aa0d7eb |  | note | Resp - SE SV
checkpoint-group |  |  | section | 2.0 Construction
checkpoint-status |  |  | checkpoint | 2.1 - Topsoil Stripping
label | 03a4e44f-00e7-590a-964e-4a5cf4e4d3b4 |  | note | Ref docs - VR Clause 204.05
label | 3f3044d0-c5aa-5ac0-b809-7b89e63c19ef |  | note | Acceptance criteria - Topsoil is to be stripped to an appropriate depth removing surface topsoil in a way to leave the surface evenly graded and free draining.
label | 15fb0719-dda3-5219-ace4-567c2462ac1e |  | note | • Topsoil to be reused onsite is to be stockpiled in an agreed location. All stockpiles shall be maintained in a neat, well-shaped state capable of shedding water.
button | bd1542f0-e364-5995-a1b7-863fbd73b1cb |  | button | Has all of the above been completed? | Yes, No, N/A
label | ced33ea1-69fb-507b-af7d-0a4409b70308 |  | note | Freq - Each Lot
label | c2bcb800-d535-535b-8057-62e1f7c6cc63 |  | note | Key - R
label | fd2cc638-f59c-5f2b-893d-c5783f77ef81 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.2 - Site Excavation
label | b78056f9-eb0a-5953-b395-d43fab4429df |  | note | Ref docs - VR Clause 204.06
label | d4271cca-3256-59a3-a32d-4c9a5f196de4 |  | note | Acceptance criteria - Prior and during excavation work, the Superintendent will be notified to inspect all material encountered for material classification, subject to verification by laboratory testing.
label | 4f018ea4-fbff-5c2f-a722-eb4288acda14 |  | note | • The areas of rock subgrade shall be presented to the Superintendent for acceptance.
button | 45a75409-28f4-56a0-99fb-520c552a9c37 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 7e4bce7f-f710-50ec-9fac-f027c0f60c90 |  | note | Freq - Each lot & Each possession
label | 8fda29b4-19e6-5859-b55b-dfa2005a36f1 |  | note | Key - H I S
label | d01857fa-f4df-5ae3-a305-843bef5f790e |  | note | Resp - SE
label | aaceb6b1-ca28-551b-b1aa-5769126f56df |  | note | SI Key - H
button | 5b40de0e-8bf9-5546-926f-8a9aa495d6aa |  | button | NATA Test Reports (as required): | Yes, No
label | 1cf12cc2-6220-5484-bd49-926f5a34381c |  | note | – CBR and Swell
label | c9b0127c-747e-5e54-94d2-853610702616 |  | note | – PI
label | 0a2d5c34-5aad-5ac8-9078-ba4347fce6e4 |  | note | – Permeability
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Groundwater / Seepage (if applicable)
label | 3dbca08e-003d-5324-adf5-0c8ea834c548 |  | note | Ref docs - VR Clause 204.06 (h)
label | 26145cf0-a388-5b28-bb51-e7b5aca2fa02 |  | note | Acceptance criteria - If groundwater or seepage is encountered, notify the Superintendent, and create a course of proposed action.
label | 4da4d0d2-4596-5db3-88a2-de1794556e17 |  | note | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
button | 11ff03e0-5769-5659-8555-fa91069a1d5c |  | button | Has all of the above been completed? | Yes, No, N/A
label | 8bbcd9ee-fac7-5547-851c-99d46787a713 |  | note | Freq - Each lot & Each possession
label | c9c30a26-d7ea-5272-8bdf-6dcc3c20cb89 |  | note | Key - H I S
label | 69ab45c6-0d80-5d75-914b-74d5750af34a |  | note | Resp - SE
label | 2ca9c33b-0b10-5043-a676-00b29b77b27a |  | note | SI Key - H
text | f140015f-9544-5a17-acbf-c61c6962d731 |  | textbox | Dewatering Permit No.:
button | 1eeb59c8-7cb9-5cb0-b222-fad81728a2b3 |  | button | Written Approval from Authorities | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Treatment of Unsuitable Materials (if applicable)
label | 71e5f216-2ecc-5d84-842c-f6a2ac75ff92 |  | note | Ref docs - VR Clause 204.07 (d)
label | d7503594-bcb2-5ad7-a828-3b3fd3b71809 |  | note | Acceptance criteria - If unsuitable material is encountered, submit proposal for in-situ treatment or excavation and replacement with conforming material.
button | 4d8cc251-9c73-5622-bbc3-5c2224d5b4ce |  | button | Has all of the above been completed? | Yes, No, N/A
label | 8fbc0d1b-cea8-58ca-a282-ffd65476b0e3 |  | note | Freq - Each lot & Each possession
label | 43e8fa9a-3acb-52d6-9c1c-d09bec99a386 |  | note | Key - H
label | 8dde038c-78af-589e-843f-02cfcbd813a7 |  | note | Resp - SE
label | 7d8fb756-d231-5a81-8cc0-11f22a3054a0 |  | note | SI Key - H
button | 1d4e1dea-25a1-55fc-b1f5-75b147ced990 |  | button | Survey Report (Extent of Area) | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Treatment of Cut / Rock Subgrade
checkpoint-status |  |  | checkpoint | 3.1 - Treatment of Rock Subgrade
label | dc46f4b8-3f7f-50a3-96fb-35a3211330b0 |  | note | Ref docs - VR Clause 204.06 (f)
label | cfd6d02c-6f33-5584-a11f-7ace2d67d67b |  | note | Acceptance criteria - Where rock exists in a cut below subgrade level but within the designed capping or selected material layer:
label | c2df1d1f-3a42-5db2-96ea-162d40546085 |  | note | • Excavate minimum 150 mm below subgrade level in all areas on which pavement is to be placed.
label | 8c02cdf2-f17c-502a-be42-aed6f00afbbc |  | note | • Remove loose material and soil from the rock floor.
label | 674927fe-90ce-524f-8824-85cfb305ffa4 |  | note | • Any resulting depressions lower than 150 mm below subgrade level shall be cleaned of loose material and backfilled with 20 mm Class 3, 3% cement treated crushed rock and compacted as specified.
label | 719f4a96-b270-510c-9f4f-d35d8b04f122 |  | note | ○ Present the above to Superintendent for inspection.
label | b5bcad0f-4589-5ff7-8f23-0b4282dc02bc |  | note | ○ Contractor is to submit details of any necessary adjustments to the subsurface drainage design, including transverse subsurface drainage at all interfaces to the Superintendent for inspection and review.
button | 73479a87-bdf1-52bb-857d-d3c85d9c1426 |  | button | Has all of the above been completed? | Yes, No, N/A
label | f425aa4b-24b9-5544-a64a-9a5784477d35 |  | note | Freq - Each lot & Each possession
label | e7a44e25-8613-5538-a8b7-f99f4214f978 |  | note | Key - H W S
label | 45af8726-8d29-58ba-966a-713b42c2caa0 |  | note | Resp - SE
label | 13aca8c9-2d27-50df-8239-4077197e6400 |  | note | SI Key - H
button | defeafc4-308c-58f0-9355-502284218a09 |  | button | Evidence of VicRoads Registered Mix | Yes,No
button | a04b5e9c-55e7-5571-be53-98d640a71176 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Regulating Layer for Rock Subgrade
label | e53644c0-6d45-5e79-861b-0b04ee49d2b9 |  | note | Ref docs - VR Clause 204.06
label | e2bd0d62-8680-552e-a466-bf615aa7814e |  | note | Acceptance criteria - Following inspection of rock subgrade by Superintendent, place 150 mm regulating layer of Class 4, 20 mm Crushed to subgrade level in lieu of the specified capping or selected material.
button | d0c31cfb-3e79-58f4-901d-21b3e64bc8b1 |  | button | Has all of the above been completed? | Yes, No, N/A
label | e7c25b1e-c2d2-5f8a-a416-663bb3fcd878 |  | note | Freq - Each lot & Each possession
label | a8085c19-1495-599b-8707-612a219a19aa |  | note | Key - W S
label | abf77ff0-fb0c-5b8a-b6f8-bf1fb1404819 |  | note | Resp - SE
button | e74dfb76-bfac-5a95-9f1d-e178756c5065 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
checkpoint-status |  |  | checkpoint | 3.3 - Testing In-situ Material in Cuts
label | d19e9362-2436-5eda-ae14-ede3d36d21d7 |  | note | Ref docs - VR Clause 204.07 PS3020.05 (c)
label | 95eb85db-9635-5592-9cc1-d069d0d51eaa |  | note | Acceptance criteria - Undertake 1 Lot test initially to determine Assigned CBR and % swell for in-situ material in cuts within 400 mm below capping layer.
label | 52b3800a-aa7b-5ee2-aa3a-c7f196ed4b55 |  | note | • Where the assigned CBR and % swell conform to the requirements of Cl. 204.04, seek the Superintendents ’s approval for minimum frequency of testing.
label | f1f02e00-9f19-5fc3-8c4f-c1bd673cddad |  | note | • Assigned CBR must be equal to or greater than 2.5% and must be no more than 10%.
label | e053a484-9e84-5867-8c77-46baf3f19112 |  | note | • Assigned percent swell must be less than 2.5%
label | 121ff1b6-5ce9-5c25-92fc-2f4e85cdb1fb |  | note | • Where Superintendent approves minimum testing frequency, proceed to conduct 1 single CBR and % swell test to confirm Assigned CBR and swell every 4 lots.
label | 8f7e6ba2-7a09-5f72-a268-279d9c46ed42 |  | note | • Where unsuitable material is encountered on site, the contractor shall submit proposed treatment plan to the superintendent for evaluation.
button | 1f310865-f0a2-52a5-b9ed-5efd69f1e4de |  | button | Has all of the above been completed? | Yes, No, N/A
label | dd19ff20-4c7e-5d4a-823c-347e77f704d1 |  | note | Freq - Each lot & Each possession
label | f170c8e9-9499-5195-9231-865b5afabea1 |  | note | Key - W S
label | 8eef8029-68cd-56b8-ba0d-9eba64294b96 |  | note | Resp - SE
button | bb76e712-5fea-51b3-8e86-c3431ca52423 |  | button | NATA Test Report: CBR and Swell | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Treatment of Cut (if applicable)
label | 13c7d6eb-566e-5ef5-bb11-40514a98c06b |  | note | Ref docs - VR Clause 204.06 (e)(ii) 204.10 (b) 204.12
label | 263ff6d1-d670-512e-8edf-ef5704dd79f2 |  | note | Acceptance criteria - The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm.
label | 188662a4-b8b1-5771-90ee-cea6ff90ca0f |  | note | • Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with Type B material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
button | f41ef56a-f579-5fc9-8fb5-67f5e62d5d07 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 419ed413-bd9e-513b-9b3c-2991b7a7eb06 |  | note | Freq - Each lot & Each possession
label | 4c934a84-3d28-534b-a5e5-0d3bfdfc260e |  | note | Key - W S
label | 7c0c504e-9ce1-5648-a1f2-2d83830fa3e5 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Compaction and Moisture Requirements (material of nominal size < 40 mm)
label | 4c0558d5-2dbf-5e33-ab3f-9e01534fef0c |  | note | Ref docs - VR Clause 204.13 (para 1) 204.13 (b) 204.15
label | 3702e6a1-eeee-50c3-a15a-d8364f238983 |  | note | Acceptance criteria - Undertake 6 tests per lot (except for small lots).
label | 309dbdf3-8fbd-55b6-a17d-f48bc67df3b5 |  | note | • Ripped and re-compacted material below CFL: minimum CDR 99% (Scale A)
label | 3667c525-8d48-50ab-8bf2-e05dea9f1d10 |  | note | • Top 150 mm of areas where fill is to be constructed: minimum CDR 97% (Scale A)
label | 9b2aa876-1447-5483-8302-1e4033166390 |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer above.
label | ba086768-31c2-586b-ab0c-c1a2512ae333 |  | note | • The moisture ratio shall be determined using the material which passes the 37.5 mm sieve, where the material contains less than 20% oversize material. If the material contains more than 20% oversize material, the moisture ratio shall be determined using an alternative method in accordance with the appropriate test method or Code of Practice.
button | a00c3d9c-a330-5e2d-8552-a6a903d9b73e |  | button | Has all of the above been completed? | Yes, No, N/A
label | 6d090dd2-21ba-5777-bd0d-ac8bd55d2bbf |  | note | Freq - Each lot & Each possession
label | c96f9750-b33f-5913-b71c-aa56b3318804 |  | note | Key - W S
label | fc8c429f-b71a-5759-a225-a5e156c3bfe1 |  | note | Resp - SE
button | a7baaf89-94d3-5839-bb11-92b0bb04e593 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
checkpoint-status |  |  | checkpoint | 3.6 - Compaction and Moisture Requirements (material of nominal size > 40 mm)
label | e5713da6-0202-59df-af38-1c0a212b7f4d |  | note | Ref docs - VR Clause 204.13 204.15
label | 6cf35207-f719-54ef-b24b-3f022973a7d6 |  | note | Acceptance criteria - All fill material and material below the Cut Floor Level shall be compacted at minimum moisture ratio of 80%. Place and compact material in accordance with approved procedure.
label | 534cd735-9926-5ca2-9608-4c4c2083f12a |  | note | • Any unstable areas detected by test rolling shall be rectified. Where unstable areas exceed 20% of the area being test rolled, the whole of the area shall be ripped, re compacted as specified above, and re-presented for test rolling.
button | 81f8a26a-fe89-5a8b-a9ca-f2341f7935fa |  | button | Has all of the above been completed? | Yes, No, N/A
label | 2e18ad7f-1650-55a5-b7f3-65dd92bf69db |  | note | Freq - Each lot & Each possession
label | f4e77a1f-07b9-52c0-9e3b-423c7293c460 |  | note | Key - W S
label | 158c3fef-8bbc-5cc5-a262-e3092516f966 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.7 - Surface Level Conformity – Fills and Prepared Surfaces
label | 517b58a4-cd13-5202-8843-6f3b7574a963 |  | note | Ref docs - VR Clause 204.03 (a),(b),(c),(d),(e),(f),(g),(i),(j) & (K)204.15
label | 02c6bd54-5239-5c37-aad6-a14a6cb8337e |  | note | • VR Clause 204.12
label | cfb65c17-b056-5982-829b-cc270e587283 |  | note | Acceptance criteria - Where capping and/or selected material is to be placed above the Cut Floor Level to subgrade level, the level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
label | fbf2949c-b9e7-54dd-af5e-7e3808610224 |  | note | • Where capping and/or selected material is not required, the Cut Floor Level shall be prepared to the appropriate tolerance for the subgrade. (See figure 1)
button | f016296c-c9bd-5b5d-81ef-1bec01e06269 |  | button | Has all of the above been completed? | Yes, No, N/A
label | caa8cc8a-1fdb-5daa-8da8-9452cc75dd47 |  | note | Freq - Each lot & Each possession
label | 7564ccc7-b44d-5cfe-b858-b2ac681a997b |  | note | Key - I S
label | bbbfc94f-2aab-592f-b3c8-54ee7d519da1 |  | note | Resp - SE
button | 35b12cf9-d6c0-5325-b11e-3655abe375c3 |  | button | Survey Conformance Report | Yes,No
label | 20ebf3e3-187e-5847-8a80-e4664a75c3f0 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | ff889095-5a80-596a-a74b-79eb81ad4af3 |  | note | Figure 1.
label | 6a8f1ba9-79e5-5c88-895c-c9da96f415b2 |  | note | Table 204.031 Minimum Number of Level Measurements and Tolerances
label | 10a3701e-7be7-5be0-90e7-afaaf9e3788b |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 6ad71462-cf0c-5bc3-a17c-90ab6eee099c |  | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̄ Range (mm) ¦¦ Tolerance: Maximum S (mm)
label | 4d49f4e8-d7cf-5442-9426-aecb66c4a12a |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | ac3dd7ba-e12c-5f27-9962-f711f8795fcf |  | note | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
label | e5d5aea4-adcf-5f14-bc61-7f0cf0f51121 |  | note | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
label | 3f744d3b-386b-5cea-811d-03e65d832e8f |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | c05453e2-8510-56b5-a1eb-923c899e0ef1 |  | note | Notes:
label | 33378fdf-1b0e-5fd7-8cdb-a743c5ed8561 |  | note | 1. x̄ is the mean value of all level readings taken in the lot
label | 16c761b7-d084-5b00-9c03-a81db5facd61 |  | note | 2. S is the standard deviation of all level readings taken in the lot
label | 1c6d8b14-6eb4-5370-82d4-acb374136121 |  | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
checkpoint-status |  |  | checkpoint | 3.8 - Test Rolling
label | 2df1ed7a-3f9e-58de-b541-ecf8f1e8736a |  | note | Ref docs - VR Clause 204.12
label | faa97184-a15a-5b06-8759-5d9da28419c4 |  | note | Acceptance criteria - Test Roll in accordance with Section 173.
label | ed057fd5-5646-5b6a-9feb-760dff8e743f |  | note | • The Contractor shall provide for the Superintendent to be present during all test rolling.
label | 6ae69317-d944-5705-8af1-20894256f4a4 |  | note | • Surface shall withstand test rolling without visible deformation or springing.
button | eef470b0-9d49-5204-8b25-964221af9fb7 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 97ded3ae-34a4-5064-88ae-58153bfec0cf |  | note | Freq - Each lot & Each possession
label | 74e0d21d-c552-5dd5-8465-4f0fecfcd990 |  | note | Key - W S
label | e140ed56-b79d-53b2-af93-0280d4428121 |  | note | Resp - SE
label | d6c70eda-971c-5781-873d-f941dc7d37e5 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Maintenance of Cut Floor Level
label | 9af9148c-76ed-5486-a207-1cac2fa80380 |  | note | Ref docs - VR Clause 204.15
label | d8a339f5-31c1-52e8-8467-959132686604 |  | note | Acceptance criteria - Visual inspection to confirm that surface is produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | f255f7c2-6ec4-5ab2-8b00-7fba0f541756 |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
button | d95886ac-6dd2-5c23-bf60-eb9187c5d993 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 760cbdd4-bfdc-5752-9a96-43f97ab9e2b2 |  | note | Freq - Each lot & Each possession
label | 3191d04f-9a5c-5e78-8b04-6f8163cd31af |  | note | Key - W S
label | 263b4dfa-edd6-5a13-895e-2a655efa064d |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Test Reports
label | b190ccef-1ea1-5964-b59e-b33ae19a291e |  | note | Ref docs - VIC Roads Specifications
button | 34232b75-da6c-53e2-aa25-51ae3844ab67 |  | button | Acceptance criteria - All Test reports received and Reviewed. | Yes, No, N/A
label | 530678c3-b60d-5b84-9051-7a5f5e02cf74 |  | note | Freq - Each lot
label | 81302774-d031-5f9e-a3af-dfadc79a9982 |  | note | Key - R
label | 43cb3c08-fa9a-598c-948a-863187ae379b |  | note | Resp - SE
button | 34b18927-742a-556e-a974-7efc3474d1ce |  | button | NATA Endorsed Test Reports | Yes,No
checkpoint-status |  |  | checkpoint | 4.2 - Product Non-Conformance
label | 440ede72-b716-5c21-b481-e8ce125fb51d |  | note | Ref docs - CQMP
button | 544e2d5c-6070-56a9-b017-a94410256f62 |  | button | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable) | Yes, No, N/A
label | d272dd55-8d73-5999-b921-4232ad0bd0ae |  | note | Freq - Each lot
label | f12d9070-98c4-5e5e-a9e5-d393f6675078 |  | note | Key - R
label | a2764a93-086b-5613-9770-d9e227ba285c |  | note | Resp - SE
text | 406a12de-d985-508a-acf6-f29296fe8f43 |  | textbox | NCR No:
button | 25b65892-8b52-5646-87e1-0abb1a91f2ce |  | button | NCR reports | Yes,No
checkpoint-status |  |  | checkpoint | Works complete
text | 8e6f2020-9965-51d1-adb2-8ae0a80cefde |  | textbox | Name:
text | 7bed400d-0a9e-59d7-9ad4-87b46aac7d68 |  | textbox | Position:
text | 7a803878-0079-5057-8bbb-6262cf2fae33 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot conforms
text | a74f3555-06d7-5e38-8363-7f4c430d1281 |  | textbox | Name:
text | 5e2ef7f6-7cf3-5492-a301-2380d87e28c6 |  | textbox | Position:
text | 113a78f1-49dd-5b7d-90ff-ad2a466ffac1 |  | textbox | Date lot closed:
text | 1d89c42d-b4aa-546e-8b47-a1e3dae6a789 |  | textbox | NCR/s no. raised:
text | 8f7af5ee-580c-5db9-8da3-3c219248d580 |  | textbox | Date NCR closed for this lot:
holdpoint |  |  | signoff | Sign ITP