## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | FADX-ITP-009 (FTC-05) FACTORY FABRICATION | itp |  |  |  | Yes | Factory ITP | a6095cd7-b3eb-40f2-9e85-f02de0de3b78
checkpoint-status |  |  | checkpoint | Check the delivery docket and compliance certificate is available upon receiving raw material
label | 625a6472-170b-5b8a-b1d8-bd1b14a74db4 |  | note | Responsibility: FACADEX
label | e12f7655-b4b4-5b16-8a90-f92f1308b256 |  | note | – – – – – – – – –
label | e693ceb0-08e7-5e0a-8c24-5386ecc817fd |  | note | Acceptance Criteria: Production manager to sign off
label | 148dd441-5bbb-58e1-9ef0-33ae5fa7e88a |  | note | – – – – – – – – –
text | 9e6a368e-157b-594a-b5b9-7de7cb2ab33e |  | textbox | Shop Drawing number:
text | d03267a3-eca2-55a5-b14f-25a89466a084 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Shop Drawings/Engineering and Samples approved for fabrication
label | c095b0a7-1ea3-5f3a-b0d2-dd0adadb5333 |  | note | Responsibility: FACADEX
label | f2bc06a8-7a19-5410-975b-4da196add95c |  | note | – – – – – – – – –
label | e1fc7442-3a21-5b66-b181-76d459ec5517 |  | note | Acceptance Criteria: Production manager to sign off
label | c6a00730-1d67-5e6f-a7b3-e278aef71ac2 |  | note | – – – – – – – – –
text | 82fbf331-9419-5a72-bc22-99a12bbc9f4d |  | textbox | Shop Drawing number:
text | bcb1fab9-06dc-5f78-97cf-824fa170af2d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections as per approved shop drawings
boolean | df63a612-63eb-537b-95ad-7982b2e4fe7e |  | tickbox | (1) Welded (need to provide welding documents
boolean | 146eb661-9a86-5f78-bfd0-08a3224cb073 |  | tickbox | (2) Bolted, classify the bolt type (nug, TF or TB)
boolean | 012f7906-72c6-593e-ac23-ce283c4f7a34 |  | tickbox | (3) Other
text | 03bb9270-8b12-5082-b43e-5d40bf4b40d1 |  | textbox | Other - Please specify:
label | 5448e12d-6ae1-5582-b516-e9a0293fcbbd |  | note | – – – – – – – – –
label | c71b2087-fc4b-5279-80c6-09cdf4870df7 |  | note | Responsibility: FACADEX
label | 12a8cd21-d0ac-539b-bc84-68b6ca68a221 |  | note | – – – – – – – – –
label | 87653685-391f-5b7d-9ad1-407b00f71bbf |  | note | Acceptance Criteria: Production manager to sign off
label | f06ff1ae-cdb4-5678-b844-519bd9e1376f |  | note | – – – – – – – – –
text | a6aedff2-80d2-52f8-9abf-0336a22ec233 |  | textbox | Shop Drawing number:
text | f2880cc8-fcf3-5426-99c5-9c32bbb67596 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm & check finish as per approved Shop Drawings
boolean | 2e11a29b-de07-58c3-ab4c-bea6470cf6d7 |  | tickbox | (1) Paint (check TDS)
boolean | f00db8d0-c784-5027-8dd3-9d70aafc33c3 |  | tickbox | (2) Powder coat (check warranty certificate)
boolean | 31d709c0-9080-50a2-bd2b-f0fc64be6e7b |  | tickbox | (3) Other
text | f50cfc1f-45cb-56c8-bfb0-1a143258277d |  | textbox | Other - Please specify:
label | 84197aa8-0b8e-5173-9082-d7788330ff73 |  | note | – – – – – – – – –
label | 5acde4d6-e455-5089-adb9-018f9d579791 |  | note | Responsibility: FACADEX
label | 9a7c2926-1949-5b80-87f7-33b87c53ba83 |  | note | – – – – – – – – –
label | 01d7b329-6531-5ba2-bb0f-3bde7478939c |  | note | Acceptance Criteria: Production manager to sign off
label | 0d949a47-3f81-5cd3-8ca9-6339638f3db7 |  | note | – – – – – – – – –
text | a77c9985-e79a-5321-a9e8-10b4a55020fd |  | textbox | Shop Drawing number:
text | 5f4b51c9-82a6-59a9-98c5-1572b5b6c05e |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Check Panel size and dimensions against drawing
label | 089915be-6a44-5ea8-a3b5-78598a0bcabc |  | note | Responsibility: FACADEX
label | c9c3c6da-bb8d-5be8-b8bf-866bf66376f1 |  | note | – – – – – – – – –
label | 844a8e96-a882-5230-8989-840db35a7b46 |  | note | Acceptance Criteria: Factory QA to sign off
label | 46e8cb6d-c406-59a6-affe-21786eb9b0d4 |  | note | – – – – – – – – –
text | 64f99acc-9937-5d51-a8c0-72901eaf8500 |  | textbox | Shop Drawing number:
text | 02456bf1-2136-5b3f-aa60-6029454b810a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check Diagonal dimension to ensure odd shape panel are done correctly
label | 2b5026e7-58c1-5ec8-98c0-b77138403305 |  | note | Responsibility: FACADEX
label | 9bc09515-0f24-5576-8e6e-4671498ba077 |  | note | – – – – – – – – –
label | 632381a2-e2dd-53d2-8a71-6dd0636185ba |  | note | Acceptance Criteria: Factory QA to sign off
label | e585d8ef-2ef4-507a-8abd-9fc43fd3cff6 |  | note | – – – – – – – – –
text | 6bc488d3-bed5-52f1-9dbe-9cab7a5d6786 |  | textbox | Shop Drawing number:
text | ce95dc34-0e5f-54b5-be2c-6fa349d5a6d1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA check delivery docket and receipt from the painter
label | 3c6b7ea5-d9d3-5e7d-a361-c3ed557707e3 |  | note | Responsibility: FACADEX
label | caa27e4a-b513-5943-b441-20a7058e182a |  | note | – – – – – – – – –
label | 94c2b28f-cb9e-5813-8a98-d9b809877e7d |  | note | Acceptance Criteria: Factory QA to sign off
label | c404aae8-ad8a-548c-b5ac-f933f97bf1ef |  | note | – – – – – – – – –
text | 325ee6ad-59b8-5de7-a5dd-364581f24100 |  | textbox | Shop Drawing number:
text | fbf0cff9-9fee-5730-aca7-9bde59f3027d |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Check Frame dimension against Shop Drawings check Factory QA to sign off
label | 1fca1036-de02-5c97-af8b-4652d3b5ce1d |  | note | Responsibility: FACADEX
label | 95b618f2-cf1a-5742-9094-73ce83d5a560 |  | note | – – – – – – – – –
label | 78dfa871-7fad-5fb5-948b-5be63042328a |  | note | Acceptance Criteria: Factory QA to sign off
label | a76a9cdd-54b2-5011-94d0-54ce84296956 |  | note | – – – – – – – – –
text | d046c2c9-fc9b-5ef2-a111-cfb615af71b3 |  | textbox | Shop Drawing number:
text | 26da131b-33e0-5136-81a6-850897c34f09 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check the finished frame is Square and plumb with bracket attached (if applicable)
label | cf0ffb69-97e4-5225-a3bb-a93f6be914ed |  | note | Responsibility: FACADEX
label | c62e1012-c334-5cdd-ae06-337e60e7c830 |  | note | – – – – – – – – –
label | d13cb2ba-1efb-58a6-81e4-65f304ff62a7 |  | note | Acceptance Criteria: Factory QA to sign off
label | a5ed0f30-c5d0-5106-9a85-cae2f9114042 |  | note | – – – – – – – – –
text | 108a7134-20e9-545c-98aa-07f98dad7819 |  | textbox | Shop Drawing number:
text | a082d7a3-da1b-528b-a7a5-d81a6c2fe852 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the Crash rail has been fabricated to drawing and attached to the frame of the module
label | b626b1d5-263e-5d73-a155-1e0221dba21c |  | note | Responsibility: FACADEX
label | ed39c058-b5ad-5a73-93a0-60a6e386d25c |  | note | – – – – – – – – –
label | 4257a763-d50c-5a4a-9ddd-36dbf4215ec9 |  | note | Acceptance Criteria: Factory QA to sign off
label | 36ff2fb9-7c03-571f-97b6-817b856c23d5 |  | note | – – – – – – – – –
text | 36fdb0e0-4547-559c-ab46-80a25463113b |  | textbox | Shop Drawing number:
text | af0abd3f-00a8-5054-93c5-13efeebc75b7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if external grow cable has been installed into the correct location (if applicable)
label | aa8e7e88-695f-5929-ab6a-fa0349d62f4e |  | note | Responsibility: FACADEX
label | f1aa88ed-3fb4-5a1a-90c6-5f40e9fa8487 |  | note | – – – – – – – – –
label | 451dd017-d135-57c2-8ef7-bc428f692c8a |  | note | Acceptance Criteria: Factory QA to sign off
label | fa0e2c84-533d-52d2-af03-2b8d59a86b87 |  | note | – – – – – – – – –
text | d85d2319-2534-52d4-95c6-0b177c231847 |  | textbox | Shop Drawing number:
text | fbfc3207-36bc-58ea-9672-bd84517ec7b1 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Installed finished panels to the frame, and spilt batten been locked with silicone
label | 32ddbfb1-9744-5283-bfb1-c205323f3bba |  | note | Responsibility: FACADEX
label | 7272fdf1-bb74-504b-ac35-06a153da4d43 |  | note | – – – – – – – – –
label | 476b4383-cadb-5d4d-b1f3-834388fa22cb |  | note | Acceptance Criteria: Factory QA to sign off
label | d4c32353-24af-596d-8e8c-3d8b5d06bc56 |  | note | – – – – – – – – –
text | 9a69d348-7c57-5136-87b4-bcdb3c541a53 |  | textbox | Shop Drawing number:
text | 97b91c12-e470-5e46-a683-12099655090b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Horizontal cladding shall have a minimum slope of 1:15 and shall be sloped away from visible vertical façade areas to prevent staining
label | 5d5c9719-5188-5782-9c36-9ee7a673505d |  | note | Responsibility: FACADEX
label | 024029c0-dbb7-5e3d-afd7-ac021e849a08 |  | note | – – – – – – – – –
label | 52a96a66-2b6e-5440-9d9b-f6faf4eb3d90 |  | note | Acceptance Criteria: Factory QA to sign off
label | 6f6ebbcd-275f-5266-993a-81cd07b82652 |  | note | – – – – – – – – –
text | 8458c018-434a-5534-a1e6-a61b51043315 |  | textbox | Shop Drawing number:
text | de605846-770f-5e4e-a4fa-9416064223f8 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | No defects/scratch/dents/distortion/crack (visual) on the finish
label | ce1d0570-8d41-546c-b52d-81a071196868 |  | note | Responsibility: FACADEX
label | 7fe1ddbc-dee5-5131-967b-716a359439c5 |  | note | – – – – – – – – –
label | 6f4522e7-6909-5cf6-a386-118f73f0eead |  | note | Acceptance Criteria: Factory QA to sign off
label | c948b176-d30d-56cb-bf80-b613ff574d73 |  | note | – – – – – – – – –
text | 2fb185a6-b2f7-5735-8fb7-2025d2491f9f |  | textbox | Shop Drawing number:
text | d8de6fb4-0dc7-5c14-a771-71e9a94e0b36 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is Fabricated item labelled as per drawing
select | 20fb3171-6c7f-59e0-94d7-cb88ce7ba0c6 |  | dropdown |  | YES - Label ID, NO
label | b043ddd2-3573-5dde-b93e-a2deeb10acd8 |  | note | – – – – – – – – –
label | 7ce2282e-a2f2-5c7e-a878-3d759cba29cd |  | note | Responsibility: FACADEX
label | d7828805-0d4b-5859-a906-6198046fa530 |  | note | – – – – – – – – –
label | 1b2f77cc-77c5-5e32-9e70-f3fcd9c04e4b |  | note | Acceptance Criteria: Factory QA to sign off
label | d4602960-64ae-5d8c-bb23-f37771debccb |  | note | – – – – – – – – –
label | 7b4af7a0-7de9-55e5-b052-b663a9b59d96 |  | note | Shop Drawing number: N/A
text | ec97bdeb-3b0f-5aac-85c1-5e9dfd0c617e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
select | c1860120-9306-58d3-afbb-2a2ff7a1b148 |  | dropdown |  | Yes,No
label | 58ac6d08-91c8-57cd-936f-5a212c386a77 |  | note | – – – – – – – – –
label | a276da2a-0639-5dc7-b5be-5009a98412cf |  | note | Responsibility: FACADEX
label | fb6ec0bd-7a2e-5830-af06-424f60d1b536 |  | note | – – – – – – – – –
label | 329d8472-32c6-5b4d-97e2-6fec6c509d6b |  | note | Acceptance Criteria: Factory QA to sign off
label | d6bf0815-a081-5261-8ba5-c74060a73751 |  | note | – – – – – – – – –
text | 461f8763-466d-5661-9a5c-0d07fa6e0a32 |  | textbox | Shop Drawing number:
text | 11c3db2d-bde7-59dc-85e6-4f650bed8ad2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Lifting Lugs holes has been drilled on the frames
label | f86ee5e6-322c-580e-8aac-806d0c70ff65 |  | note | Responsibility: FACADEX
label | 215a0cbf-6b97-550c-8213-378e2146daa9 |  | note | – – – – – – – – –
label | 6b57f1ad-da9c-52d7-bfc4-a1afe1a0dbd9 |  | note | Acceptance Criteria: Factory QA to sign off
label | f1a5213d-ade9-5e05-9200-522300c16399 |  | note | – – – – – – – – –
text | 36c42502-437b-5fe1-8db8-105aa10d658d |  | textbox | Shop Drawing number:
text | c53dbe18-d384-523a-b512-258efdfe101c |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Prevent direct contact between incompatible metals, and between green hardwood or chemically treated timber and aluminium or coated steel
label | cc6414b1-ef97-5183-b60c-f569709e4505 |  | note | Responsibility: FACADEX
label | 178967f4-8405-5156-821a-f1b4b1e081fa |  | note | – – – – – – – – –
label | 7d6df5ea-4aaa-5fe8-a078-79681f7b4394 |  | note | Acceptance Criteria: Factory QA to sign off
label | bab38f7d-a826-5282-abb9-077e36e9250b |  | note | – – – – – – – – –
text | d673a6e3-fd6b-576f-9363-dfb99f6febff |  | textbox | Shop Drawing number:
text | 48b973ef-3200-5236-95c6-b51f159b01b4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Pack onto the stillage for delivery after completion of all above
label | e8dbe55d-be3d-5b32-906b-b1e269c63e8e |  | note | Responsibility: FACADEX
label | 51e0af72-5d6a-515f-8bf2-5a206c9ba063 |  | note | – – – – – – – – –
label | 9d3ebd54-b35f-5c69-8678-30e54fb5b6b4 |  | note | Acceptance Criteria: Factory QA to sign off
label | 187c4d8e-f37a-5f98-b6c5-b902a335751b |  | note | – – – – – – – – –
text | fdc320c1-52b6-5b0e-9937-4c4e57a70fd4 |  | textbox | Shop Drawing number:
text | d7bbeb39-b321-56e7-af21-d1a70f4ce70d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 6e59265d-a5ff-5a6d-a194-30dc5b3231e2 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
label | 27b00249-4140-5af4-8451-a0333b378eab |  | note | Ensure the product was done base on the design complying AS standards including the following where applicable
label | 0f4db547-3000-5a9d-9a8e-f12f988c4276 |  | note | • AS1562.1 Clause 5.5 (Resistance to wind pressures)
label | 09d3fd3c-903b-5ecc-8a36-3d824afdd48c |  | note | • AS1530.1 (Combus􀆟bility)
label | 446bd1f4-0dce-54db-ad0d-83488b2b9ed4 |  | note | • AS5637.1 (Fire Hazard Proper􀆟es)
label | 30b50adb-99aa-51ae-8a94-d9ea489c3e78 |  | note | • A S1530.4 (Fire resistance level)
label | ef5424ba-fbe8-571d-9949-751778ee698a |  | note | • A S2904 (Flashings)
text | f9a7d293-3a48-530f-b1f0-0f7749099f2c |  | textbox | Lead Fabricator – Checklist Completed:
text | 6c95c88e-4636-5f50-a655-2d40bdb28650 |  | textbox | Date / Time:
text | e302f4b5-7212-5a71-b527-a59f6ea25cda |  | textbox | Factory Manager – Checklist Completed:
text | 0d48b999-7129-5b8a-8231-1fe84ea1838b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-flat |  |  | checklist | FADX-ITP-008-2 (FTC-05) SITE INSTALLTION - CLADDING | itp |  |  |  | Yes | Site ITP | b397a6d7-cca5-48f1-8861-bed4b54052ac
checkpoint-status |  |  | checkpoint | Multiplex - IFC Drawings Shop Drawings Approval
label | 375dc2e4-6c4c-5cb2-bc5d-8534b49a3c3f |  | note | Responsibility: Multiplex
label | 42a48771-55c5-598d-91b6-863e2cbfd6c6 |  | note | – – – – – – – – –
label | 9b1ac2f3-630a-591b-b466-d18bf4ecd894 |  | note | Acceptance Criteria: Multiplex Sign Off
label | 82d0d0d1-5db8-5fc9-9184-0e7540cb4f53 |  | note | – – – – – – – – –
text | 7db3fb7a-af22-5372-bd7a-e96d2a57a759 |  | textbox | Reference Document AS1562.1-1992
text | 1b9f4d29-1c4e-555a-82cf-7183d1831882 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Multiplex - Material Approval
label | a3ca32ff-d6ad-5c41-9098-cfbc48d55b0f |  | note | Responsibility: Multiplex
label | 2ad41f74-9e3d-5ac4-8cdc-d86ec848ba74 |  | note | – – – – – – – – –
label | b0d84d74-d2f5-5e71-b91f-ea86c01fcb3b |  | note | Acceptance Criteria: Multiplex Sign Off
label | 5ffcd931-5cf4-5f1f-b19e-f82fd74792d6 |  | note | – – – – – – – – –
text | 3b9a6dc3-ee0d-53ce-9dbd-a05be19b048b |  | textbox | Reference Document AS1562.1-1992
text | e41fa686-4e5c-5469-82ac-17f62c0e5fdd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials - check materials meet Aust Stand AS1562.1-1992 and are supplied as ordered and specified for the project
label | 2262002c-4168-5315-aafc-d96c04ab95ee |  | note | Responsibility: Facadex
label | 0246b43e-2645-572e-8fb7-d153169ab1ea |  | note | – – – – – – – – –
label | 77aaccf4-d297-58aa-9003-644689b85104 |  | note | Acceptance Criteria: Facadex sign off - Site Supervisior
label | a177932d-c09e-5da4-8839-c6952480f31a |  | note | – – – – – – – – –
text | 4a75fa36-531d-5ffb-8c2c-96c8b9622192 |  | textbox | Reference Document AS1562.1-1992
text | c96f8371-4a3b-59a0-8aa4-d33f19088f91 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Multiplex - Materials inspection upon delivery and prior to installation
label | 75d6e21b-8588-542f-b3d2-a64dc2634d08 |  | note | Responsibility: Multiplex
label | 7b596a9a-24a6-5e22-9966-d352fa30a225 |  | note | – – – – – – – – –
label | 8b2747ab-71fd-5502-8a22-d0ef77f635fe |  | note | Acceptance Criteria: Multiplex Sign off AS1562.1-1992
label | 79bf3255-45d5-573a-9031-70d59fca297d |  | note | – – – – – – – – –
text | f246091e-d37d-5552-9c12-0252deebe8df |  | textbox | Reference Document AS1562.1-1992
text | 60735879-4169-58e1-88e8-f40dde0616af |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check Structure is level and plumb prior to commencing subframing for wall cladding
label | 9524b9c7-63bc-5c7b-818f-c32a0dc32f2f |  | note | Responsibility: Facadex/MPX
label | 74e66e39-2c89-5f87-9b82-5fc62dd3ce87 |  | note | – – – – – – – – –
label | f1a13bb0-f134-5c80-beac-9fc83f6e1228 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | a89e956f-5906-5a75-a9ab-495a5a3c2489 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 434e3cd0-53f3-52e5-abf5-984563f51355 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 871f8509-3732-5463-9bd6-0cba8fbe1cb3 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | b0ca7f48-f976-52fd-a4fb-0bd7836c1976 |  | note | Expansion & Contraction:
label | a54c81c2-8e5b-5d19-8bd8-582956a98abc |  | note | +/- 3mm @ every 1000mm in length & height
label | 9977885a-32d2-5d09-82c7-4cc130a1470d |  | note | – – – – – – – – –
text | 12d2166e-c7a8-5128-9fa2-2700f3668593 |  | textbox | Reference Document AS1562.1-1992
text | d9a13fbf-14b6-53c7-ba26-f01c8a126c4a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Site Installation – Grid lines established and RL by MPX
label | 10de62b0-d21a-5b66-b826-4f9de2a8880f |  | note | Responsibility: Facadex
label | 8e748471-2120-5f17-a2ed-98aa7c94a094 |  | note | – – – – – – – – –
label | c1030b1c-1ef5-5c7c-a5b2-db4a71e3524f |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 0f123567-9b21-5878-955f-884a2e069b84 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ef6ee5d4-83da-5b6e-b165-2751a3d79cf2 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | f540c3f1-39b0-5001-a9c7-dd1786455fb2 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 5e6634a7-c085-5f37-9e0d-94ad957b4bbd |  | note | Expansion & Contraction:
label | 91654a4f-f42f-5dc3-b6ef-db9c1506acc0 |  | note | +/- 3mm @ every 1000mm in length & height
label | fde3cd3d-7199-5ca4-8cd6-c7b71b6a0d10 |  | note | – – – – – – – – –
text | a5232d9b-6440-549c-8cef-c1fff5d0a899 |  | textbox | Reference Document AS1562.1-1992
text | 26129f59-0496-5e3f-b967-88cb6f00ecb2 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Site Installation – Installation: SHS framing and Cladding including all capping and flashings Sealing and Cauking
label | 2027faa3-75b2-50e2-aafc-ab30106d4128 |  | note | Responsibility: Facadex/MPX
label | aeeaf1e1-bb26-5445-b45c-3c02a173c7cb |  | note | – – – – – – – – –
label | 9e2e4995-f43f-596d-a712-f11b61b2cb0f |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | b8609cdc-42af-5c25-912a-b5ef31aeb78b |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 2a3ad29b-8465-5c5d-a49d-baec46460396 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 3238d4ba-b63a-55b7-9ef7-f8d3b4e1a351 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 4b0b18fd-d4dd-572b-b41d-68a29845a115 |  | note | Expansion & Contraction:
label | 47377dd8-c21c-51d2-bf28-797274ccddb6 |  | note | +/- 3mm @ every 1000mm in length & height
label | 2001a949-448b-5498-991e-18679c6789fb |  | note | – – – – – – – – –
text | 8e7bf28a-b761-5401-ac45-883b0b3e2531 |  | textbox | Reference Document AS1562.1-1992
text | f7bed550-c060-5c8d-82e7-4656733ee043 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Site Installation – Ensure the internal crash rail and external Grow cable are installed correctly
label | 134c248f-2736-5444-a497-bc4641c18556 |  | note | Responsibility: Facadex/MPX
label | 709803c3-6dc8-5aa0-baf2-2426e13ebabf |  | note | – – – – – – – – –
label | 1015d656-9055-5ade-8df0-3bb0f9be9bc2 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 788c1ff0-057a-57cc-8604-d1ede3a3f3a7 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 01f6c101-fa8c-51d4-8812-896233ea2a24 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | e718c60e-6e6b-5edb-bb5f-c17fcf1ca434 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 5d797ec5-f75a-5672-b6e0-fc4c1e9ea78c |  | note | Expansion & Contraction:
label | feaee893-ab8e-5e2a-8662-7cca3ee5b017 |  | note | +/- 3mm @ every 1000mm in length & height
label | a3f528e7-8f80-5efd-9b7a-643152d5df96 |  | note | – – – – – – – – –
text | 684c500e-4435-5381-af49-636b08eb7934 |  | textbox | Reference Document AS1562.1-1992
text | 9012a517-235f-5637-acfb-4ecca4dfd618 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed wall with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 6f834f74-6fa6-5a9e-8995-5b9f698b95a6 |  | note | Responsibility: Facadex /MPX
label | 114e2e95-8358-5f71-8ab5-f8912cdbe934 |  | note | – – – – – – – – –
label | 556c8d59-28c7-51f1-a3e4-e42f5fd1b22a |  | note | Acceptance Criteria: Defect notification via Teambnder or Builder email
label | eb2c966a-429e-5d1a-ac6f-1952c0eb8a4c |  | note | Evidence of close out / rectification.
label | 2b806cf2-9380-52aa-ae43-d239d9021d89 |  | note | (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type).
label | 6b9f4dff-268f-52cd-8adc-55a0451e224c |  | note | – – – – – – – – –
text | 9928bf78-7a90-5c53-bcc3-06b651c83fcf |  | textbox | Reference Document AS1562.1-1992
text | ec61ee3d-70f5-5daa-8085-b0bb913c9e79 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | d89b27f3-504f-5ba3-bdb9-656dcb803596 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 24abdced-38bb-585e-9c5c-536d049a75d1 |  | textbox | Foreman – Checklist Completed:
text | 96623418-9a82-5076-8999-415ce8fe869d |  | textbox | Date / Time:
text | 8abc786a-1847-505a-ad0e-f29b38a5f540 |  | textbox | Coordinator – Checklist Completed:
text | 76a9a240-b5c4-59dc-ace1-25efc7d609c3 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed