## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CLD-214 Lysaght Spandek - Cladding Building D Panel Site ITP | itp |  |  |  |  | CLD-214 Lysaght Spandek - Cladding Building D Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Cladding Panels installed to manufacturers specifications
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Cladding Panels checked for paint scratches post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | 0.55mm colorbond flashing has been installed to the gap to the strcutrue
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-214 Lysaght Spandek - Cladding Building D (North Wall Double 50 Top Hat) ITP | itp |  |  |  |  | CLD-214 Lysaght Spandek - Cladding Building D (North Wall Double 50 Top Hat) ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | 50mm vertical top hat has been set out and installed to steel frames with #12 tek screws@500 crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | 50mm horizontal top hat has been set out and installed to vertical top hat with #12 tek screws@500crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Packers has been used to ensure the top hat frame is plumb for lysaght spandek panels to be cladded on.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-214 Lysaght Spandek - Cladding Building D Factory ITP | itp |  |  |  |  | CLD-214 Lysaght Spandek - Cladding Building D Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-506 Deflection Head Site ITP | itp |  |  |  |  | CLG-506 Deflection Head Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials (Deflection head/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Deflection head installed as per shop details and location
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Correct size of deflection head has been installed to allow enough depth to outcome the tolerance of the slab.
label | Responsibility: Facadex
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Ensure the deflection head installed was not bended or deformed.
label | Responsibility: Facadex
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-506 Factory ITP | itp |  |  |  |  | CLG-506 Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-514 Bridge Factory ITP | itp |  |  |  |  | CLG-514 Bridge Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-514 Steel Bracket Underside Site ITP | itp |  |  |  |  | CLG-514 Steel Bracket Underside Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials (steel bracket/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Bracket installed as per shop details and location
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Ensure the correct steel bracket has been installed to the desinated spot along the underside of the pre-camped bridge
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria:
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Ensure the steel bracket installed was not bended or deformed.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria:
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-506 Cladding ITP | itp |  |  |  |  | CLG-506 Cladding ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Cladding Panels installed to manufacturers specifications
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Cladding Panels checked for paint scratches post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-514 Cladding Panel ITP | itp |  |  |  |  | CLG-514 Cladding Panel ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Cladding Panels installed to manufacturers specifications
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Cladding Panels checked for paint scratches post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-514 Site Subframing ITP | itp |  |  |  |  | CLG-514 Site Subframing ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Truss Framing underside of the bridge installed as per shop details
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Truss Framing aligned finished level and plumb
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Top hat to primiry steel (side) or to truss frame (underside) installed and leveled for panel installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-506 Z450 Steel Frame ITP | itp |  |  |  |  | CLG-506 Z450 Steel Frame ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Truss Framing installed as per shop details
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Truss Framing aligned finished level and plumb (height adjusted with deflaction head)
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Top hat to the truss frame installed and leveled for panel installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | ○ Expansion & Contraction:
label | +/- 3mm @ every 1000mm in length & height
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign off only once agreed that wall is defect free
label | – – – – – – – – –
textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed