## Resources
type | name | values | prefix | postfix
checklist | 51.01 - Environmental Management Systems | itp
section | Details
checkpoint | Environmental Management Plan (Construction) submitted in accordance with Conditions of Contract.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS51 Cl 6.3
checkpoint | Works shall not commence until the Environmental Management Plan (Construction) has been assessed for suitability by the Administrator and approved.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS51 Cl 6.3
signoff | HOLD POINT
checkpoint | Amendments to the Environmental Management Plan (Construction) to be submitted on a monthly bases for assessment of suitability by the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS51 Cl 6.4
signoff | HOLD POINT
checkpoint | Enviromental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Superintendent on a monthly basis.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl 7
checkpoint | Environmental records are to be included in the Quality Records under the Contract. Records and registers shall be made available to the Administrator upon request.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS51 Cl 7.3
signoff | HOLD POINT
checkpoint | Water quality monitoring undertaken as per requirements in MRTS52 and Annexure
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl 8.2.1
checkpoint | Requirements relating to Erosion and Sediment Control are contained within MRTS52
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl 8.3
checkpoint | Construction activities have not resulted in air quality impacts that cause environmental nuisance or harm. Visual monitoring shall be conducted in accordance with Clause 6.3.1 of MRTS51.1 and recorded in the site diary.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl 8.7
checkpoint | No harm caused to native fauna. Areas of significance and related management requirements are stated in Cl 7 of Annexure MRTS51.1.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl 8.10
checkpoint | Where stated in Cl 7.2 of Annexure MRTS51.1 the contractor shall engage persons authorised by Queensland Parks and Wildlife Service to attend the site to carry out an inspection of the site and subsequent capture or relocation of any fauna. Injury or death of fauna know as rare, endangered, or vulnerble shall be reported immediately to the Administrator and reported in the monthly report
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl 8.10
checkpoint | Management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl 8.11
checkpoint | Clearing extents to be clearly defined by the Contractor and approved by the Contract Administrator. Should any clearing outside the defined clearing extents be required, the Contractor must notify the Contract Administrator and may only proceed with the written approval.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point
note | Reference - MRTS51.1 Cl 9.1.3
signoff | HOLD POINT
checkpoint | The Contractor shall undertake a pre-clearing weed and pest survey to document areas of existing prohibited and restricted invasive plants, and identify treatment and management requirements. Weekly inspections shall be carried out once clearing is complete to determine the success of the pest management procedures.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51.1 Cl 10.1
checkpoint | All chemicals and fuels within the worksite are contained so as not to cause environmental nuisance or harm. Spill kits response equipment are available on site for use in emergency.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 8.14
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 70.02 - Concrete Record
section | Details
checkpoint | 1 - Date
date | Truck 1:
date | Truck 2:
date | Truck 3:
date | Truck 4:
checkpoint | 2 - Docket
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 3 - Time Batched
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 4 - Truck Arrival Time
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 5 - Load Size (m3)
textbox | Truck 1: |  |  | m3
textbox | Truck 2: |  |  | m3
textbox | Truck 3: |  |  | m3
textbox | Truck 4: |  |  | m3
checkpoint | 6 - Mix
checkpoint | 7 - Slump (mm)
textbox | Truck 1: |  |  | mm
textbox | Truck 2: |  |  | mm
textbox | Truck 3: |  |  | mm
textbox | Truck 4: |  |  | mm
checkpoint | 8 - Slump Time
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 9 - Concrete Arrival Temperature (˚C)
textbox | Truck 1: |  |  | ˚C
textbox | Truck 2: |  |  | ˚C
textbox | Truck 3: |  |  | ˚C
textbox | Truck 4: |  |  | ˚C
checkpoint | 10 - Ambient Temperature at time of slump (˚C)
textbox | Truck 1: |  |  | ˚C
textbox | Truck 2: |  |  | ˚C
textbox | Truck 3: |  |  | ˚C
textbox | Truck 4: |  |  | ˚C
checkpoint | 11 - Time Start delivery
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 12 - Time Finish Delivery
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checklist | 14.08 - Demolition, Removal, Salvage & Re-erection of Road Furniture | itp
section | Details
checkpoint | The items of road furniture to be demolished and disposed of are listed in Clause 3 of MRTS14.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 7.2
checkpoint | Seven days prior to commencement, the Contractor shall submit a schedule of items to be salvaged in accordance with the design documentation.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS14 Cl 8.2
checkpoint | Dismantling and removal shall not commence until expiration of the seven day period.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS14 Cl 8.2
signoff | HOLD POINT
checkpoint | Salvaged materials shall be transported and stored in accordance with Cluase 1.2 of MRTS14.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 8.4
checkpoint | Seven days prior to commencement, the Contractor shall submit a schedule of items to be dismantled for re-erection in accordance with the design documentation.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS14 Cl 9.2
checkpoint | Dismantling and removal shall not commence until expiration of the seven day period.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS14 Cl 9.2
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 52.01 - Erosion and Sediment Control | itp
section | Details
checkpoint | Submit an Erosion and Sediment Control Plan (ESCP) for that section
note | Acceptance Criteria & Frequency (Project Specific) - 14 days prior to tree removal as per Annexure 52.1
note | Check Item - Check Item
note | Reference - MRTS52 Cl 6.1
checkpoint | Administrator assessed suitability of Erosion and Sediment Control Plan for each stage and/or section of the works where required
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS52 Cl 6.1
signoff | HOLD POINT
checkpoint | Installation of appropriate erosion and sediment controls in each section of the works
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS52 Cl 7.1
signoff | HOLD POINT
checkpoint | Any clearing required to be able to install sediment control must be discussed and approved by Administrator
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS52 Cl 7.1
checkpoint | Erosion and sediment controls maintained and reconfigured throughout the stages of the project
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS52 Cl 7.2
checkpoint | Remove temporary controls when permanent measures in place and/or site stabilisation occurred
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS52 Cl 7.3
checkpoint | Install a proprietary rain gauge and monitor/record rainfall in spreadsheet (mm)
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS52 Cl 8.2.1
checkpoint | There shall be no erosion resulting from construction practices unless there are provisions within the worksite to manage resultant sediment. Releases from site must not cause scour at the area of discharge. Implemented controls shall be sufficient to achieve the water quality investigation criteria as per Clause 8.2.2 of MRTS51.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS52 Cl 8.1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 70.01 - Placement of Concrete | itp
section | Details
checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Temp <35 Continuous
note | Check Item - Check Item
note | Reference - MRTS70 Cl 10.5
checkpoint | The Contractor shall supply the Administrator with detailed drawings of falsework at least four weeks prior to the commencement of erection
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS70 Cl 15.3
checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS70 Cl 15.3
signoff | HOLD POINT
checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 15.3
checkpoint | Procedure for underwater concreting submitted to Administrator 2 weeks prior to first pour
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 15.6.3
checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 15.11.1
checkpoint | All formwork shall be subject to inspection and approval by the Administrator
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 3/5
note | Reference - MRTS70 Cl 15.4.1
signoff | HOLD POINT
checkpoint | Concrete operations shall not commence until all relevant procedures have been approved by the Administrator
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS70 Cl 15.6
signoff | HOLD POINT
checkpoint | No concrete placed until formwork, reinforcement and stressing materials inspected, foreign material removed from forms and equipment and placement procedures approved.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 3/5
note | Reference - MRTS70 Cl 15.6.1
signoff | HOLD POINT
checkpoint | Administrator to be present for placement of concrete, with 24 hours notice.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS70 Cl 15.6.1
checkpoint | The placement of concrete underwater shall be carried out in the presence of the Administrator and shall comply with the requirements of Clause 19.2
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS70 Cl 15.6.3
checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
note | Acceptance Criteria & Frequency (Project Specific) - Slump Test:
note | ○ <60 - ±10
note | ○ 60<80 - ±15
note | ○ 80<110 - ±20
note | ○ 110<150 - ±30
note | ○ 150< - ±40
note | ○ Every Load
note | Check Item - Check Item
note | Reference - MRTS70 Cl 11.3 AS1379
checkpoint | Samples for testing taken as required - min 2 cylinders/sample
note | Acceptance Criteria & Frequency (Project Specific) - 1-3 Loads - Every Load
note | ○ 4-10 Loads - 4 Samples
note | ○ 11-23 Loads - 5 Samples
note | ○ >24 Loads - 1 per 4 loads
note | Check Item - Check Item
note | Reference - MRTS70 Cl 15.2.2
checkpoint | Compressive Strength Testing
note | Acceptance Criteria & Frequency (Project Specific) - f'c
note | ○ <2Mpa Difference/2 Cylinders
note | ○ <3Mpa Difference/2 Cylinders
note | Check Item - Check Item
note | Reference - MRTS70 Cl 12.3
checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - minimum of two vibrators used with at least one per 4m3 of concrete placed per hour.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 15.6
checkpoint | Additional construction joints approved by the Designer.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 7
note | Reference - MRTS70 Cl 15.13
signoff | HOLD POINT
checkpoint | Forms and Falsework not removed early unless approved by the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 6
note | Reference - MRTS70 Cl 15.8
signoff | HOLD POINT
checkpoint | Forms not removed until
note | ○ Non-structural - min(50% of 28 day strength or 3 days)
note | ○ Soffits of slabs, headstock and diaphragms - 7 days
note | ○ Side forms of structural concrete - 2 days (Exposure class A), 3 days (B1, B2) or 5 days (Exposure class C)
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 15.8
checkpoint | Forms removed with care and curing commence upon completion of finishing operations to approved procedures. If forms removed in under 7 days, curing commences within 1 hour
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS70 Cl 15.8
checkpoint | Following removal of forms
note | ○ Fins and unwanted projections are ground off
note | ○ Pockets and honeycombed areas repaired using approved methods
note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 15.12
checkpoint | Concrete installed to within positional, dimensional and relative tolerances. Should a specified tolerance be exceeded, the work shall be liable to rejection.
note | Acceptance Criteria & Frequency (Project Specific) - Visual <Specified MRTS70 Cl22 QR-CTS-Part 7
note | Check Item - Check Item
note | Reference - MRTS70 Cl 15.7.2
checkpoint | Acceptance or Rejection of Hardened Concrete
note | a) < 0.9 Fc (Any sample)
note | b) < Fc (Ave 3 consecutive samples from Lot)
note | c) > 1.4 Fc (Ave 3 consecutive samples from Lot)
note | In addition
note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consecutive weeks)
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 12.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 11.00 - Sealing Works | itp
section | Details
checkpoint | Permission to use construction procedures
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 1
note | Reference - MRTS11 CL5.2
signoff | HOLD POINT
checkpoint | Construction procedures and ITP submitted to the Administrator seven days prior to use
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS11 CL5.2
checkpoint | The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS11 CL6.1.2
checkpoint | Contractor notified of Principal's seal design
note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Principal
note | Check Item - Hold Point 2
note | Reference - MRTS11 CL6.2
signoff | HOLD POINT
checkpoint | Contractor provides Principal with seal design test results along with Ball Penetration test results
note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Principal
note | Check Item - Milestone
note | Reference - MRTS11 CL6.2
checkpoint | The Contractor shall submit the seal design report to the Administrator at least seven days prior to commencement of spraying operations.
note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
note | Check Item - Milestone
note | Reference - MRTS11 Cl. 6.3.2
checkpoint | Spraying operations shall not commence until the Administrator has approved the seal design report
note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
note | Check Item - Hold Point 3
note | Reference - MRTS11 Cl. 6.3.2
signoff | HOLD POINT
checkpoint | Cover aggregate is covered by a light plastic until it's implementation in the works
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 1
note | Reference - MRTS11 CL8.2
checkpoint | Binder storage temperature measured and recordered at delivery to site
note | Acceptance Criteria & Frequency (Project Specific) - Between 160 and 190 degrees celcius
note | Check Item - Witness Point 2
note | Reference - MRTS11 CL8.3.1
checkpoint | If binder temperature low, raise to within 160 and 190 degrees celcius. Heating shall be strictly observed.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 3
note | Reference - MRTS11 CL8.3.2
checkpoint | Three days prior to sealing operation, the Contractor shall submit details of all plant to be used.
note | Acceptance Criteria & Frequency (Project Specific) - As per MRTS11.1 Annexure
note | Check Item - Hold Point 4
note | Reference - MRTS11 CL9.0
signoff | HOLD POINT
checkpoint | Ball penetration test results < 4mm unless approved by the administrator
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 5
note | Reference - MRTS11 CL10.1.2
signoff | HOLD POINT
checkpoint | Ensure enough cover aggregate available on site to complete works
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 6
note | Reference - MRTS11 CL11.1
signoff | HOLD POINT
checkpoint | Pavement Temperature above minimum specified
note | Acceptance Criteria & Frequency (Project Specific) - Primes: >/=10 degrees
note | ○ Cutback Bitument: >/=15
note | ○ Polymer binder: >/=20
note | Check Item - Witness Point 4
note | Reference - MRTS11 CL11.2
checkpoint | Unless otherwise approved, sprayed bituminous treatments that will be trafficked shall not be sprayed if the air temperature is likely to fall below 10C at any time during the first two weeks.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 7
note | Reference - MRTS11 CL11.3
signoff | HOLD POINT
checkpoint | Current QLD sprayer certificate to be sighted
note | Acceptance Criteria & Frequency (Project Specific) - Current Certificate
note | Check Item - Witness Point 5
note | Reference - MRTS11 CL12.4
checkpoint | Nomination and recording of cutting requirements where required
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 6
note | Reference - MRTS11 CL12.7
checkpoint | Wet cover aggregate containing free surface water shall not be loaded in the aggregate spreader
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 7
note | Reference - MRTS11 CL14.1
checkpoint | Loose aggregate signage requirements prior to opening to traffic
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 8
note | Reference - MRTS11 CL14.8
signoff | HOLD POINT
checkpoint | Quality Verification Requirements
note | Acceptance Criteria & Frequency (Project Specific) - Testing Frequency
note | Check Item - MRTS11
note | Reference - Table 6.2
checkpoint | Particle Size Distribution, Flakiness Index, Avg. Least Dimension
note | Acceptance Criteria & Frequency (Project Specific) - One test per aggregate type, nominal size & source
note | ○ Repeat tests every 1000t
note | Check Item - Check Item
note | Reference - MRTS11 Table 6.2
checkpoint | Texture Depth: In and between the wheelpaths - that is, 3 tests at each test chainage per direction
note | Acceptance Criteria & Frequency (Project Specific) - Lesser of:
note | ○ Every 400m
note | ○ 3 test chainages per homogenous section
note | Check Item - Check Item
note | Reference - MRTS11 Table 6.2
checkpoint | Ball Penetration: Inner and outer wheelpaths - 2 tests at each test chainage per direction
note | Acceptance Criteria & Frequency (Project Specific) - 5 test chainages per homogenous section
note | Check Item - Check Item
note | Reference - MRTS11 Table 6.2
checkpoint | Spreading: Each spreader shall be tested in accordance with the Field Spread Rate Cover Aggregate Test (Q711A)
note | Acceptance Criteria & Frequency (Project Specific) - One test per spreader per day, Tolerance: ±10%
note | Check Item - Check Item
note | Reference - MRTS11 Cl. 14.4
checkpoint | Sampling of Bitumen (two x 1L samples) shall be undertaken before or during transfer of bitument to sprayers.
note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size
note | ○ Asphalt = Each new tank
note | ○ Sealing = 150 tonnes
note | Check Item - Witness Point
note | Reference - MRTS17 Cl. 9.3.3
checkpoint | The minimum frequencies for sampling and testings in regards to the cutter oil and flux oil shall be in accordance with Table 9.2 of MRTS19
note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.2
note | Check Item - Check Item
note | Reference - MRTS19 Cl. 9.2
checkpoint | The minimum frequencies for sampling and testings in regards to cutback bitumen shall be in accordance with Table 9.3 of MRTS20
note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.3
note | Check Item - Check Item
note | Reference - MRTS20 Cl. 9.3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 04.09 - Subgrade | itp
section | Details
checkpoint | CUTTINGS: Tests conducted in accordance with MRTS04 Cl 18.3.3.2
note | Acceptance Criteria & Frequency (Project Specific) - RDD
note | Check Item - Check Item
note | Reference - MRTS04 Cl 18.3.3.2
checkpoint | Work stopped when excavation has reached sugrade level. Contractor shall carry out the requirements of the relevant provisions of Clause 13.3.2.1
textbox | Specified Subgrade Treatement (A-K):
note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 Table 15.3-A, Table 15.3-B
note | Check Item - Hold Point 8
note | Reference - MRTS04 Cl13.3.2.1 Cl18.3.3
signoff | HOLD POINT
checkpoint | General fill material used for construction of subgrade where embankment or cutting treatment using general fill, if used in road embankments must comply with Cl 14.2.4
note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Embankment ITP or Related Lot)
note | Check Item - Check Item
note | Reference - MRTS04 Cl 18.2.1
checkpoint | Unbound pavement material shall conform with the requirements of MRTS05 Unbound Pavements and shall be at least of the subtype specified in Clause 12.1 of Annexure MRTS04.1, or where no such subtype is specified, at least subtype 2.4.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl 18.2.2
checkpoint | Quarry Registration Certificate submitted to Administrator 7 days prior to sourcing high permeability drainage materials.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS04 Cl18.2.4.1
checkpoint | A mix design shall be submitted atleast 14 days prior to commencement of subgrade stabilisation
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 11
note | Reference - Cl18.2.5.4
signoff | HOLD POINT
checkpoint | Subgrade and underlying work tested and conforming prior to placement of pavement.
note | Acceptance Criteria & Frequency (Project Specific) - ITP
note | Check Item - Hold Point 12
note | Reference - MRTS04 Cl18.3.1
signoff | HOLD POINT
checkpoint | Subgrade material provides a stable dense surface displaying no vertical movement under proof roll
note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Delfection, Continuous
note | Check Item - Witness Point 8
note | Reference - Cl18.3.2
checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
note | Acceptance Criteria & Frequency (Project Specific) - Visual, Tolerances: Table 6.3.1, Subgrade (individual results) = +25mm, Subgrade (average) = +10mm
note | Check Item - Check Item
note | Reference - Cl 18.3.3.1
checkpoint | Quality Verification Requirements Test Method
note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
note | Check Item - Check Item
note | Reference - Table A.2
checkpoint | Compaction/Moisture Ratio: AS1289.5.4.1 or AS1289.5.7.1
note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 500m2 (per layer), 4 per lot
note | Check Item - Check Item
note | Reference - MRTS04 Table A.2 No. 2.11
checkpoint | Grading (AS1289.3.6.1), PI (AS1289.3.3.1 or AS1289.3.3.2), WPI (Q252)
note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 1000m2 (per layer), 2 per lot
note | Check Item - Check Item
note | Reference - MRTS04 Table A.2 No. 2.11
checkpoint | Geometrics, Horizontal Position
note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
note | Check Item - Check Item
note | Reference - MRTS04 Table A.2
checkpoint | Geometrics, Vertical Level
note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
note | Check Item - Check Item
note | Reference - MRTS04 Table A.2
checkpoint | Geometrics, Deviation from a straight edge < 25mm
note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
note | Check Item - Check Item
note | Reference - MRTS04 Cl 6.3.2
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 28.01 - Contractor's Camp and Site Facilities | itp
section | Details
checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.2
checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.3
checkpoint | If stated in Clause 2 of MRTS28.1, a separate room shall be provided for the use of auditing, QA documentation and private meetings with the Administrator and Principal. The requirements of the room shall be as stated in Clause 4.4.1 of MRTS28.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.4.1
checkpoint | If stated in Clause 3 of MRTS28.1, a separate room shall be provided for the exclusive use of the administrator during Work Under the Contract. The requirements of the room shall be as stated in Clause 3 of MRTS28.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.4.2
checkpoint | If stated in Clause 4 of MRTS28.1, documentation of the Contractor's site facilities shall be provided to the Administrator for approval.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.5.1
checkpoint | If stated in Clause 5 of MRTS28.1, the Contractor's site facilities shall be screened from public view.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.5.2
checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.5.6
checkpoint | If no area's are included in Cl6 MRTS 28.1 the contractor shall be responsible for obtaining any necessary area's for the establishment of a camp.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 5.2
checkpoint | Contractors camp complies with all requirements of MRTS28 annexure, including any supplementary requirements.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28.1
checkpoint | If private property is to be used for the Contractor's facilities, written approval must be sought from the property owner and provided to the Administrator for approval. Restoration of these areas shall be in accordance with MRTS16, MRTS28 and MRTS51 and a plan shall be submitted to the Administrator for approval prior to commencement.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point
note | Reference - MRTS28.1 Clause 8
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 22.01 - Supply of Cover Aggregate | itp
section | Details
checkpoint | Cover aggregate supplied by a quarry registered and operated in accordance with DTMR's Quarry Registration System requirements. Submitted to Administrator 7 days prior to supply
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS22 Cl. 6
checkpoint | Material from a quarry shall not be supplid or used without written permission from the Administrator
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 1
note | Reference - MRTS22 Cl. 6
signoff | HOLD POINT
checkpoint | Construction procedure shall be submited to the administrator atleast 7 days prior to the commencement of aggregate production for the works
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS22 Cl. 6
checkpoint | The cover aggregate particles shall comply with the requirements of Table 7.1.3 of MRTS22
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS22 Cl. 7.1.3
checkpoint | Where precoated cover aggregate is specified the Contractor shall submit to the Administrator 7 days prior, the procedure to be used for application of the precoating agent
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS22 Cl. 7.1.4
checkpoint | If stated in Clause 3 of MRTS22.1, a sample of 40kg of each type of aggregate to be used shall be supplied to the Administrator 14 days prior to use.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS22 Cl 8.1
checkpoint | Prior to commencement of delivery of aggregate to any stockpile, the Contractor shall obtain the Administrators authorisation
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS22 Cl. 10
signoff | HOLD POINT
checkpoint | Except for prime cover materials, all cover aggregate stockpiles shall be protected with a light plastic material
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS22 Cl. 10
checkpoint | Quality Verification Requirements
note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
note | Check Item - MRTS22
note | Reference - Clause 8.3
checkpoint | Material compliance testing shall be conducted in accordance with the requirements of MRTS22 Cl. 8.3
note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 8.3.2(a) and 8.3.2(b)
note | Check Item - Check Item
note | Reference - Clause 8.3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 02.01 - Traffic Management | itp
section | Details
checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS02.1 Cl5.2
checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the contractor that the Traffic Management Plan has been submitted and approved
note | Acceptance Criteria & Frequency (Project Specific) - Written Approval
note | Check Item - Hold Point 1
note | Reference - MRTS02 Cl 5.3
signoff | HOLD POINT
checkpoint | All TGS's prepared by a suitably qualified person and submitted and approved by the Administrator
note | Acceptance Criteria & Frequency (Project Specific) - Written Submission
note | Check Item - Hold Point 2
note | Reference - MRTS02 Cl 6.2
signoff | HOLD POINT
checkpoint | Submission of Traffic Management Inspection Report
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS02 Cl 7.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 27.01 - Geotextile | itp
section | Details
checkpoint | Geotextile strength and filtration classes as specified on drawings or within MRTS27
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl6
checkpoint | Geotextile stored on site under protective covers, off the ground and in a manner unaffected by heat. Rolls clearly marked with manufacturer, type and batch.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl7
checkpoint | Proposed Geotextile submitted to and accepted by Adminstrator for acceptability to Cl6.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS27 Cl8.1
signoff | HOLD POINT
checkpoint | Geotextiles installed as specified in the contract
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.1
checkpoint | Area cleared and graded with all sharp objects and large stones removed and covered within 48hours of being placed
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.1
checkpoint | Initial uncompacted layer thickness for fill material placed over the geotextile shall be not less than 200mm of D85 of the fill material, whichever is greater.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.2
checkpoint | Jointing of geotextiles in accordance with clause 9.3. If overlap is not specified, it shall be a minimum of 500mm. If used to line subsoil drainage trenches, the geotextile shall fully envelop the drainage material with a minimum 300mm overlap at the top of the trench.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.3
checkpoint | Filling over installed geotextile shall be in accordance with clause 9.4. No construction equipment shall stand or travel directly on the laid geotextile. Rock placed directly on geotextile shall be placed with a drop height not exceeding 1.5m.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.4
checkpoint | Where batch size is <5000m2, sampling and testing need not be undertaken, provided the nominal strength of the material supplied is 20% higher than the requirements and the filtration properties are 20% lower than the requirements stated.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl10.2
checkpoint | Where directed, a testing sample shall be cut and provided to the administrator
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS27 Cl10.2
checkpoint | Sampled geotextile shall be tested by the Contractor for the range of properties specified in Table 6.2 and Table 6.3 in accordance with the requirements of Clause 10.3.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl10.3
checkpoint | Geotextile not placed until administrator accepts test results
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS27 Cl10.4
signoff | HOLD POINT
checkpoint | The administrator may select samples from the site for audit testing.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl10.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 16.01 - Landscape and Revegetation | itp
section | Soil Management Plan
checkpoint | Soil Management Plan - assessed for suitability by the Administrator in accordance with the conditions of Clause 5.2.1 of MRTS16
note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
note | Check Item - Hold Point 1
note | Reference - MRTS16 Cl 5.2.1
signoff | HOLD POINT
checkpoint | Where a Contractor proposes to water vegetation works with non-potable water a Non-Potable Water Management Plans shall be submmited and assessed for suitability by the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
note | Check Item - Hold Point 2
note | Reference - MRTS16 Cl 5.2.2
signoff | HOLD POINT
checkpoint | Seed Supply Proposal submitted for determination as to its suitability by the Administrator, within 30 days of the date of Possession of Site.
note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
note | Check Item - Hold Point 3
note | Reference - MRTS16 Cl 5.3.1
signoff | HOLD POINT
section | Materials
checkpoint | Materials imported to site shall be free of prohibited or restricted biosecurity matter.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7
checkpoint | Materials are stored to ensure no deterioration or contamination occurs
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7
checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7
checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8
section | Weed Control
checkpoint | Routine inspections of the site shall be undertaken to treat weeds as appropriate for their destruction prior to flowering/seeding. Weeds manually removed shall be disposed of off-site
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16.1 Cl 3.1.1
section | Subsoil and Topsoil Amelioration
checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.1 TMR SD 1644, TMR SD 1646
checkpoint | Site is weed free prior to ground preparation operations
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS16 Cl 8.1.1.2
checkpoint | Administrator notified at least 3 days before each of the following:
note | ○ Application and incorporation of amelioration agents
note | ○ Ripping
note | ○ Cultivation
note | ○ Roughening
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS16 Cl 8.1.1.3 Cl 8.1.1.4 Cl 8.1.1.5 Cl 8.1.1.6 Cl 8.1.2.4
checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 6
note | Reference - MRTS16 Cl 8.1.2.3
signoff | HOLD POINT
checkpoint | Topsoil installed evenly over the surface, within 5 days of subsoil preparation and at the required minimum depth
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.1.2.4
section | Grass seeding, Hydromulching and Turfing
checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.2.2
checkpoint | Application rate of hydro-compost, seeding mix and timing shall be submitted to the Administrator prior to application for approval.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16.1 Cl. 3.6
signoff | HOLD POINT
checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.2.2 with initial watering on the day of installation and at least 10L/m2
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.2.2
section | Establishment, Monitoring and Finalisation
checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.1
checkpoint | All Establishment operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.1.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 9.1.1
checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 10
note | Reference - MRTS16 Cl 9.1.1.5 Cl 9.2.1.5
signoff | HOLD POINT
checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.2
checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 9.2.1
checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.2
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | itp
section | Details
checkpoint | Items to be salvaged identified in accordance with Annexure MRTS03.1 Cl. 2.1. Items to be removed without damage and stored at a location as nominated in MRTS03.1 Cl. 2.2.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03.1
checkpoint | Any Kerb and Channel or concrete slab to be removed is sawcut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 9.4
checkpoint | Non Salvageable components, kerbs, gullies and access chambers removed or demolished as per drawings/specifications.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 9.2 & 9.5
checkpoint | Excavations backfilled where shown on the drawings or required to leave the area in a safe and free draining state. Kerb excavations backfilled to flush with the surrounding area.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 9.2 Cl. 9.4
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 04.01 - Clear and Grub Stripping of Topsoil | itp
section | Details
checkpoint | Clearing limit plan prepared and approved by Prinicpal with boundary limits clearly marked
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl1.1, 1.2, 1.4 & MRTS51 Cl3.1, 3.3, 3.7
checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the area concerned.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS04 Cl7.2.2
signoff | HOLD POINT
checkpoint | Marketable timber shall be clearly marked by contractor Prior to clearing. Marked trees felled and handled avoiding damage to the trunks. The trunks trimmed and stacked in neat manageable stockpiles approved by the Administrator at spacings of not more than 500 metres.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS04 Cl7.2.3
signoff | HOLD POINT
checkpoint | Material suitable for organic mulch shall be in accordance with MRTS16B Vegetation Ground Works
note | Acceptance Criteria & Frequency (Project Specific) - Visual, MRTS16B
note | Check Item - Check Item
note | Reference - MRTS04 Cl7.2.4
checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl7.2.5
checkpoint | Topsoil stripped as required in Cl 2.1 of Annexure MRTS.04.01. Depth of excavation shall be specified in the Cl 2.1 of Annexure MRTS04.01 or as directed.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl8.2
checkpoint | Surplus material and material considered not suitable for use as planting media in accordance with Cl 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed of in accordance with Cl 11
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl8.4.2
checkpoint | Material not removed from within drip lines of trees except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retainined are preserved where practical.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl8.4.3
checkpoint | Stripped material shall be stockpiled in the locations shown on the drawings, as stated in Clause 2.2 of Annexure MRTS04.1
note | Topsoil Stockpiles are;
note | ○ Less than 3m High
note | ○ Less than 10m wide
note | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
note | ○ Stockpiled for the minimum duration
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl8.4.4
checkpoint | Quality Verification Requirements, Test Method
note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
note | Check Item - MRTS04
note | Reference - Table A1
checkpoint | Geometrics, Clearance Limits
note | Acceptance Criteria & Frequency (Project Specific) - 1000m, 10m grid, 2 per lot
note | Check Item - Check Item
note | Reference - MRTS04 Table A.2
checkpoint | Geometrics, Vertical (Stripping of Topsoil only)
note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 100m per side
note | Check Item - Check Item
note | Reference - MRTS04 Table A.2
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments (Public Domain) | itp
section | Details
checkpoint | Manufacture of steel beam guardrail post, panel components and end treatments are maufactured by an approved manufacturer
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.2.1
checkpoint | Supply of steel beam guardrail post, panel components and end treatments are supplied by an approved supplier
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.3.1
checkpoint | All the steel manufacturer test certificates shall be supplied to the Administrator. The Administrator shall review and approve the certificates.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 7
note | Reference - MRTS14 Cl. 20.4.5
signoff | HOLD POINT
checkpoint | If test certificates are not available, the Contractor shall submit to the Administrator for approval a proposal for selecting samples for testing.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Witness Point 2
note | Reference - MRTS14 Cl. 20.4.5
checkpoint | All projects are to be supplied with a min. two extra posts and panels from each batch. The Administrator shall randomly select from each batch two post and two panels for Audit testing.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 3
note | Reference - MRTS14 Cl. 20.4.6.1
checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 8
note | Reference - MRTS14 Cl. 20.4.6.3
signoff | HOLD POINT
checkpoint | All welders must comply with the requirements of Clause 20.5.2 otherwise a TMR representative shall be present when macro samples are prepared to show conformorance
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 9
note | Reference - MRTS14 Cl. 20.5.2
signoff | HOLD POINT
checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.1
checkpoint | Steel Posts driven into ground except where posts are to be driven into asphalt, concrete or rock.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.2
checkpoint | Where ground is asphalt, concrete or rock, a hole shall be excavated in accordane with Cl 20.6.2
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.2
checkpoint | Terminals installed as per the design documentation
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.3
checkpoint | Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.5
checkpoint | Installed within Geometric Tolerances
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.6
checkpoint | Adminstrator accepts guardrail installation as per the design documentation
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 10
note | Reference - MRTS14 Cl 20.6.7
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 05.02 - Supply of Unbound Material | itp
section | Details
checkpoint | No unbound pavement works shall commence until all relevant construction procedures have been accepted by the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS05 Cl. 5.2.1
signoff | HOLD POINT
checkpoint | The aggregate production procedures shall be submitted to the Administrator at least 7 days prior to commencement of material production
note | Check Item - Milestone
note | Reference - MRTS05 Cl. 5.2.2
checkpoint | The unbound pavement construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement works
note | Check Item - Milestone
note | Reference - MRTS05 Cl. 5.2.3
checkpoint | The current TMR Quarry Registration Certificates for Type 1, 2 and 3 materials, shall be submitted to the Administrator at least 7 days before a material's supply or use.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS05 Cl6
checkpoint | Material from a quarry shall not be used until the quarry has been approved by the administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS05 Cl6.1
signoff | HOLD POINT
checkpoint | Type 1, Type 2, Type 3 and Type 4 materials to comply with the respective material properties from clauses 7.1 to 7.4.
note | Check Item - Check Item
note | Reference - MRTS05 Cl. 7.1 - Cl. 7.4
checkpoint | All pavement material incorporated into the finished pavement shall be free from sticks, organic matter, clay lumps and other deleterious material or contamination.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS05 Cl7.5
checkpoint | Stockpiles located as specified in MRTS05.01 Cl. 2.4 or if not specified, on clear, even, firm, well drained ground where it can be clearly identified with individual stockpiles separated by at least 2m.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS05 Cl7.7
checkpoint | Separate stockpiles for each production lot, or stockpiles incrementally created from a single material subtype with each added lot tested and approved prior to subsequent lots being added.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS05 Cl7.7
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 70.03 - Supply of Concrete | itp
section | Details
checkpoint | Mix designs for each class of concrete forwarded to Administrator at least 4 weeks prior to first delivery
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 9.2
checkpoint | Where travel or placement times are, by neccessity, longer than those listed in Table 10.4 a procedure shall be submitted to the Adminstrator for approval.
note | Acceptance Criteria & Frequency (Project Specific) - Written, 6 weeks notice
note | Check Item - Milestone
note | Reference - MRTS70 Cl 10.5.1, 15.1.1 & Cl 17.6.1
checkpoint | All mixes >20MPa have a trial mix complete and Administrator given 3 days notice.
note | Acceptance Criteria & Frequency (Project Specific) - f'c, Each Mix
note | Check Item - Witness Point 1
note | Reference - MRTS70 Cl 15.1.1
checkpoint | Concrete not incorporated into works until trial mix completed or ready mixed concrete supplier is approved.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS70 Cl 15.1
signoff | HOLD POINT
checkpoint | All aggregate shall be sampled in accordance with AS 2758.1 during concrete production and tested for conformance to the aggregate requirements in MRTS70 clause 7.8 or Quarry assessment and certification approved
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 7.5
checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
note | Acceptance Criteria & Frequency (Project Specific) - Visual, Ambient temp. > 35 degrees
note | Check Item - Milestone
note | Reference - MRTS70 Cl 13.1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 05.01 - Placement of Unbound Pavement | itp
section | Details
checkpoint | Pavement layers shall be constructed by either using a paver or grader, unless spceific plant is specified within Clause 3.1.1. of MRTS05.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS05 Cl8.3.1.1.3
checkpoint | If specified in Clause 3.1.2 of MRTS05.1, Intelligent Construction (IC) rollers shall be used to compact unbound material.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS05 Cl8.3.1.3
checkpoint | Primary Geometric Tolerances, Layer Thickness between 75mm and 250mm
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS05 Cl8.3.3
checkpoint | Materials not incorporated into the works unless it conforms with the requirements of MRTS05.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 5
note | Reference - MRTS05 Cl9.1
signoff | HOLD POINT
checkpoint | Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by construction equipment nominated
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 2
note | Reference - MRTS05 Cl9.4.7
checkpoint | No Layer of Pavement shall be covered by a subsequent layer of pavement or by surfacing until all testing has been completed and the layer has been presented to the administrator for permission to proceed
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 6
note | Reference - MRTS05 C9.5.1
signoff | HOLD POINT
checkpoint | Construction Testing Requirements: Test Method
note | Acceptance Criteria & Frequency (Project Specific) - Min. Testing Frequency, Min. No. of Tests
note | Check Item - MRTS05
note | Reference - Table A3
checkpoint | Segregation: Q103A
note | Acceptance Criteria & Frequency (Project Specific) - 1 per lot
note | Check Item - Check Item
note | Reference - MRTS05 Cl. 8.3.4.1
checkpoint | Degree of Saturation: Q146, Type 2: 65%
note | Acceptance Criteria & Frequency (Project Specific) - 1 per 500m2, 4 per lot
note | Check Item - Check Item
note | Reference - MRTS05 Cl. 8.3.4.1
checkpoint | Compaction: Q140A, C.V. of RDD >= 102% for all Type 1 Materials, C.V of RDD >= 100% for Type 2/3/4 Materials
note | Acceptance Criteria & Frequency (Project Specific) - 1 per 500m2, 4 per lot
note | Check Item - Check Item
note | Reference - MRTS05 Cl. 8.4.3
checkpoint | Vertical Position: Survey +/- 15mm
note | Acceptance Criteria & Frequency (Project Specific) - 1 per 20 linear meter
note | Check Item - Check Item
note | Reference - MRTS05 Table 8.4.4.3
checkpoint | Deviation from a Straight Edge: Q712, Types 2, 3 & 4 materials: 5mm
note | Acceptance Criteria & Frequency (Project Specific) - 1 per 20 linear meter
note | Check Item - Check Item
note | Reference - MRTS05 Table 8.4.5
checkpoint | Road Roughness: Q708B, Q708C & Q708D, Rs max. value: 2.31 (m/km)
note | Acceptance Criteria & Frequency (Project Specific) - As per Clause 9.4.10, Greater than 100m less than 500mm
note | Check Item - Check Item
note | Reference - MRTS05 Table 8.4.6
checkpoint | For layers to be covered by a sprayed bituminous treatment, the surface shall have a maximum ball penetration of 3mm.
note | Acceptance Criteria & Frequency (Project Specific) - 5 test chainages per lot
note | Check Item - Check Item
note | Reference - MRTS05 Table 8.4.7
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 04.06 - General Excavation | itp
section | Details
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceeding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL11.3
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS04 Cl9.4
signoff | HOLD POINT
checkpoint | Where material can be reasonably be expected to contain a possible acid sulphate potential, the test results shall be documented and reported to the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 5
note | Reference - MRTS04 Cl10.1.4
signoff | HOLD POINT
checkpoint | Work stopped when excavation has reached subgrade level. Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3
note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 Table 15.3-A, Table 15.3-B
note | Check Item - Hold Point 8
note | Reference - MRTS04 Cl13.3.2.1 Cl18.3.3
signoff | HOLD POINT
checkpoint | Bottom of excavation other than subgrade compacted to RDD 95% and completed to tolerances specified
note | Acceptance Criteria & Frequency (Project Specific) - 95% RDD Table 15.3-A, Table 15.3-B, Tolerances: Table 6.3.1
note | Check Item - Check Item
note | Reference - MRTS04 Table 6.3.1
checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings.
note | Acceptance Criteria & Frequency (Project Specific) - Visual, Tolerances: Table 6.3.1
note | Check Item - Check Item
note | Reference - MRTS04 Cl13.3.1 Table 6.3.1
checkpoint | Treatment of Batters shall commence as soon as practicable, but not later than 14 days after substantial completion of earthworks on each section.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 7
note | Reference - MRTS04 Cl16
checkpoint | Dewatering of excavations comply with requirements of EMP
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl13.3.8
checkpoint | Construction Testing Requirements: Test Method
note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
note | Check Item - MRTS04
note | Reference - Table A2.1
checkpoint | Compaction: AS1289.5.4.1 or AS1289.5.7.1, To a depth 150mm below bottom of excavation = 95%
note | Acceptance Criteria & Frequency (Project Specific) - Max Lot Size: each excavation, 1 per 50m2, 2 per lot
note | Check Item - Check Item
note | Reference - Table A2.1
checkpoint | Geometrics: Profile
note | Acceptance Criteria & Frequency (Project Specific) - Max Lot Size: each excavation, 1 per 100m, 1 per lot
note | Check Item - Check Item
note | Reference - Table A2.1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 04.08 - Embankment
section | Details
checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 10
note | Reference - MRTS04 Cl14.2.1
signoff | HOLD POINT
checkpoint | Rock Fill shall be sourced from a TMR regsitered quarry or other suitable source and shall comply with the properties states in Table 14.2.3.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.2.3
checkpoint | The foundation under rock fill shall be treated and shaped to maintain drainage and so erosion of the foundation will not occur.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.2.3
checkpoint | Rock fill shall be placed and spread in such a way to avoid segregation and contamination with foreign material. The uncompacted Rock Fill layer thickness must not exceed the thickness given in Table 15.4
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.2.3
checkpoint | Compact the Rock Fill using the mechanical interlock method of construction as per Clause 15.4
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.2.3
checkpoint | Embankments constructed to the shapes, zones and other requirements shown on the drawings or as otherwise specified.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.3.1
checkpoint | Geotextile placed at interchange between compaction methods
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.3.2
checkpoint | The ground surface on which embankments are to be constructed shall be stepped in accordance with the requirements of Cl14.3.3
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.3.3
checkpoint | The max thickness of an uncompacted layer shall be as per Table 15.4.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl15.4
checkpoint | Each layer rolled until the rolled surfaces do not exhibit any permanent deformation, rutting, yielding, signs of distress or instability.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 6
note | Reference - MRTS04 Cl15.4
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP

## Revised 27.03
checklist | 28.01 - Contractor's Camp and Site Facilities | itp
section | Details
checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.2
checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.3
checkpoint | If stated in Clause 2 of MRTS28.1, a separate room shall be provided for the use of auditing, QA documentation and private meetings with the Administrator and Principal. The requirements of the room shall be as stated in Clause 4.4.1 of MRTS28.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.4.1
checkpoint | If stated in Clause 3 of MRTS28.1, a separate room shall be provided for the exclusive use of the administrator during Work Under the Contract. The requirements of the room shall be as stated in Clause 3 of MRTS28.1
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.4.2
checkpoint | If stated in Clause 4 of MRTS28.1, documentation of the Contractor's site facilities shall be provided to the Administrator for approval.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.5.1
checkpoint | If stated in Clause 5 of MRTS28.1, the Contractor's site facilities shall be screened from public view.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.5.2
checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 4.5.6
checkpoint | If no area's are included in Cl6 MRTS 28.1 the contractor shall be responsible for obtaining any necessary area's for the establishment of a camp.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl 5.2
checkpoint | Contractors camp complies with all requirements of MRTS28 annexure, including any supplementary requirements.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28.1
checkpoint | If private property is to be used for the Contractor's facilities, written approval must be sought from the property owner and provided to the Administrator for approval. Restoration of these areas shall be in accordance with MRTS16, MRTS28 and MRTS51 and a plan shall be submitted to the Administrator for approval prior to commencement.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point
note | Reference - MRTS28.1 Clause 8
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 27.01 - Geotextile | itp
section | Details
checkpoint | Geotextile strength and filtration classes as specified on drawings or within MRTS27
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl6
checkpoint | Geotextile stored on site under protective covers, off the ground and in a manner unaffected by heat. Rolls clearly marked with manufacturer, type and batch.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl7
checkpoint | Proposed Geotextile submitted to and accepted by Adminstrator for acceptability to Cl6.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS27 Cl8.1
signoff | HOLD POINT
checkpoint | Geotextiles installed as specified in the contract
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.1
checkpoint | Area cleared and graded with all sharp objects and large stones removed and covered within 48hours of being placed
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.1
checkpoint | Initial uncompacted layer thickness for fill material placed over the geotextile shall be not less than 200mm of D85 of the fill material, whichever is greater.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.2
checkpoint | Jointing of geotextiles in accordance with clause 9.3. If overlap is not specified, it shall be a minimum of 500mm. If used to line subsoil drainage trenches, the geotextile shall fully envelop the drainage material with a minimum 300mm overlap at the top of the trench.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.3
checkpoint | Filling over installed geotextile shall be in accordance with clause 9.4. No construction equipment shall stand or travel directly on the laid geotextile. Rock placed directly on geotextile shall be placed with a drop height not exceeding 1.5m.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl9.4
checkpoint | Where batch size is <5000m2, sampling and testing need not be undertaken, provided the nominal strength of the material supplied is 20% higher than the requirements and the filtration properties are 20% lower than the requirements stated.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl10.2
checkpoint | Where directed, a testing sample shall be cut and provided to the administrator
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS27 Cl10.2
checkpoint | Sampled geotextile shall be tested by the Contractor for the range of properties specified in Table 6.2 and Table 6.3 in accordance with the requirements of Clause 10.3.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl10.3
checkpoint | Geotextile not placed until administrator accepts test results
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS27 Cl10.4
signoff | HOLD POINT
checkpoint | The administrator may select samples from the site for audit testing.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS27 Cl10.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments (Public Domain) | itp
section | Details
checkpoint | Manufacture of steel beam guardrail post, panel components and end treatments are maufactured by an approved manufacturer
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.2.1
checkpoint | Supply of steel beam guardrail post, panel components and end treatments are supplied by an approved supplier
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.3.1
checkpoint | All the steel manufacturer test certificates shall be supplied to the Administrator. The Administrator shall review and approve the certificates.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 7
note | Reference - MRTS14 Cl. 20.4.5
signoff | HOLD POINT
checkpoint | If test certificates are not available, the Contractor shall submit to the Administrator for approval a proposal for selecting samples for testing.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Witness Point 2
note | Reference - MRTS14 Cl. 20.4.5
checkpoint | All projects are to be supplied with a min. two extra posts and panels from each batch. The Administrator shall randomly select from each batch two post and two panels for Audit testing.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 3
note | Reference - MRTS14 Cl. 20.4.6.1
checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 8
note | Reference - MRTS14 Cl. 20.4.6.3
signoff | HOLD POINT
checkpoint | All welders must comply with the requirements of Clause 20.5.2 otherwise a TMR representative shall be present when macro samples are prepared to show conformorance
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 9
note | Reference - MRTS14 Cl. 20.5.2
signoff | HOLD POINT
checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.1
checkpoint | Steel Posts driven into ground except where posts are to be driven into asphalt, concrete or rock.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.2
checkpoint | Where ground is asphalt, concrete or rock, a hole shall be excavated in accordane with Cl 20.6.2
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.2
checkpoint | Terminals installed as per the design documentation
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.3
checkpoint | Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.5
checkpoint | Installed within Geometric Tolerances
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl20.6.6
checkpoint | Adminstrator accepts guardrail installation as per the design documentation
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 10
note | Reference - MRTS14 Cl 20.6.7
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 14.21 - Installation of Steel beam Guardrail and End Treatments (Proprietary Systems) | itp
section | Details
checkpoint | Proprietary road safety barrier systems and/or end treatment shall be manufactured, fabricated and assembled in accordance with the design and specifications provided by the system and/or device designer.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl21.2
checkpoint | The installer of proprietary road safety systems shall provide the required quality documentation in accordance with clause 21.2 to the Administrator.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point
note | Reference - MRTS14 Cl21.2
checkpoint | Proprietary barrier systems shall be installed as shown in and required by the design documentation and in accordance with the requirements of the installation manual.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl. 21.4.1
checkpoint | Where the design of the system is provided by the Contractor, the design, installation drawings, specifications and evidence and conditions of acceptance for use on state-controlled roads in Queensland shall be provided to the Administrator prior to commencement of installation.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 12
note | Reference - MRTS14 Cl. 21.4.1
signoff | HOLD POINT
checkpoint | Delineation shall conform to the requirements of Clause 10.2.4 of MRTS14 and shall be installed in accordance with Part 2 of the MUTCD.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl. 21.4.5
checkpoint | Proprietary systems shall be installed in accordance with the tolerances specified by the supplier. Where not specified, the alignment shall not deviate from the design by more than 20mm and the height shall not deviate by more than 10mm from the design.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl. 21.4.6.2
checkpoint | The quality records of proprietary systems shall include: - Evidence and conditions of acceptance for use on state-controlled roads in Queensland - Supplier's instructions or procedures for the installation and ongoing maintenance and repair - Details of the country of manufacture of all components - Quality documentation showing the supplied components are in accordance with the supplier's specification - A copy of the detailed design (where not provided by the Principal)
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl. 21.4.7
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 11.00 - Sealing Works | itp
section | Details
checkpoint | Permission to use construction procedures
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 1
note | Reference - MRTS11 CL5.2
signoff | HOLD POINT
checkpoint | Construction procedures and ITP submitted to the Administrator seven days prior to use
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS11 CL5.2
checkpoint | The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS11 CL6.1.2
checkpoint | The Contractor shall submit the seal design report to the Administrator at least seven days prior to commencement of spraying operations.
note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
note | Check Item - Milestone
note | Reference - MRTS11 Cl. 6.3.2 & MRTS11.1 Cl. 3.2
checkpoint | Spraying operations shall not commence until the Administrator has approved the seal design report
note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
note | Check Item - Hold Point 3
note | Reference - MRTS11 Cl. 6.3.2
signoff | HOLD POINT
checkpoint | Cover aggregate is covered by a light plastic until it's implementation in the works
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 1
note | Reference - MRTS11 CL8.2
checkpoint | Binder storage temperature measured and recordered at delivery to site
note | Acceptance Criteria & Frequency (Project Specific) - See Table 12.5 of MRTS11
note | Check Item - Witness Point 2
note | Reference - MRTS11 CL8.3.1
checkpoint | If binder temperature low, raise to within the spraying temperature range as per Table 12.5. Heating shall be strictly observed.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 3
note | Reference - MRTS11 CL8.3.2
checkpoint | Three days prior to sealing operation, the Contractor shall submit details of all plant to be used.
note | Acceptance Criteria & Frequency (Project Specific) - As per MRTS11.1 Annexure
note | Check Item - Hold Point 4
note | Reference - MRTS11 CL9.0
signoff | HOLD POINT
checkpoint | Ball penetration test results < 3mm unless approved by the administrator
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 5
note | Reference - MRTS11 CL10.1.2
signoff | HOLD POINT
checkpoint | Ensure enough cover aggregate available on site to complete works
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 6
note | Reference - MRTS11 CL11.1
signoff | HOLD POINT
checkpoint | Pavement Temperature above minimum specified
note | Acceptance Criteria & Frequency (Project Specific) - Primes: >/=10 degrees
note | ○ AMC4 to AMC6 Cutback Bitumen: >/=15
note | ○ AMC7 Cutback Bitumen, Bitumen Class 170, 240 & 320, multigrade bitumen, crumb rubber binders : >/=20
note | ○ Polymer binder: >/=25
note | Check Item - Witness Point 4
note | Reference - MRTS11 CL11.2
checkpoint | Spraying shall only take place under the weather conditions permitted as per clause 11.3 and clause 6.3 of MRTS11.1. Where additional measures are required to minimise the risk of early life stripping, the Contractor shall submit procedures to the Administrator for review 14 days prior to commencement of spraying. Spraying shall not commence until these procedures have been deemed suitable.
note | Acceptance Criteria & Frequency (Project Specific) - Written
note | Check Item - Hold Point 7
note | Reference - MRTS11 CL11.3
signoff | HOLD POINT
checkpoint | Current QLD sprayer certificate to be sighted
note | Acceptance Criteria & Frequency (Project Specific) - Current Certificate
note | Check Item - Witness Point 5
note | Reference - MRTS11 CL12.4
checkpoint | Nomination and recording of cutting requirements where required
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 6
note | Reference - MRTS11 CL12.7
checkpoint | Wet cover aggregate containing free surface water shall not be loaded in the aggregate spreader
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Witness Point 7
note | Reference - MRTS11 CL14.1
checkpoint | Prior to opening to traffic the requirements of Clause 14.8 shall be met.
note | Acceptance Criteria & Frequency (Project Specific) - Visual
note | Check Item - Hold Point 8
note | Reference - MRTS11 CL14.8
signoff | HOLD POINT
checkpoint | Quality Verification Requirements
note | Acceptance Criteria & Frequency (Project Specific) - Testing Frequency
note | Check Item - MRTS11
note | Reference - Table 6.2
checkpoint | Particle Size Distribution, Flakiness Index, Avg. Least Dimension
note | Acceptance Criteria & Frequency (Project Specific) - One test per aggregate type, nominal size & source
note | ○ Repeat tests every 1000t
note | Check Item - Check Item
note | Reference - MRTS11 Table 6.2
checkpoint | Texture Depth: In and between the wheelpaths - that is, 3 tests at each test chainage per direction
note | Acceptance Criteria & Frequency (Project Specific) - Lesser of:
note | ○ Every 400m
note | ○ 3 test chainages per homogenous section
note | Check Item - Check Item
note | Reference - MRTS11 Table 6.2
checkpoint | Ball Penetration: Inner and outer wheelpaths - 2 tests at each test chainage per direction
note | Acceptance Criteria & Frequency (Project Specific) - 5 test chainages per homogenous section
note | Check Item - Check Item
note | Reference - MRTS11 Table 6.2
checkpoint | Spreading: Each spreader shall be tested in accordance with the Field Spread Rate Cover Aggregate Test (Q711A)
note | Acceptance Criteria & Frequency (Project Specific) - One test per spreader per day, Tolerance: ±10%
note | Check Item - Check Item
note | Reference - MRTS11 Cl. 14.4
checkpoint | Sampling of Bitumen (two x 1L samples) shall be undertaken before or during transfer of bitumen to sprayers.
note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size
note | ○ Asphalt = Each new tank
note | ○ Sealing = 150 tonnes
note | Check Item - Witness Point
note | Reference - MRTS17 Cl. 9.3.1
checkpoint | The minimum frequencies for sampling and testings in regards to the cutter oil and flux oil shall be in accordance with Table 9.2 of MRTS19
note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.2
note | Check Item - Check Item
note | Reference - MRTS19 Cl. 9.2
checkpoint | The minimum frequencies for sampling and testings in regards to cutback bitumen shall be in accordance with Table 9.3 of MRTS20
note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.3
note | Check Item - Check Item
note | Reference - MRTS20 Cl. 9.3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP