## Guardrail & Wire Rope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | E3001A - SH05 - SIP-Site 2 |  | CPS Approver | Quality Approver | CPS Eng. | Caleb W & Brylee T
|  |  |  | Procedure: | Guardrail & Wire Rope Barriers |  | Name / Signature | Name / Signature | Site Engineer | Genald Sebastian
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Dharminder Singh
Lot No: E3001B |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:w:/s/ZONEE-SH5-HAWKESBAY/Efsr89PX3wtAjhV5bC0Wy-MBaC2NTThx4aN5wedK-KmcBQ?e=eLqbGQ |  | Compliance with Work Instructions and Specifications
Detailed Location :South of Dillon’s Hill Site 2
Chainage:RP249/0.530 to RP 249/2.040
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Setout & Checks
1.1 | Design Check | M | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | Document review | National Standard for Traffic Signal | OFI or NTD/NTC | Site Engineer
1.2 | Survey Setout | W | Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing. | Site Engineer
2 | Material Compliance
2.1 | Barrier Compliance | H | All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4 | Prior to commencement | Visual inspection/ Document review | TNZ M/23:2009 | Manufacturing certificates and delivery dockets | Site Engineer | CPS
2.2 | Material Suppliers | M | All materials to be sourced from registered suppliers | Prior to commencement | Document Review | Registered suppliers | Materials register | Site Engineer
2.3 | Galvanising Repair Methodology Approval | H | Proposed galvanising repair methodology to be approved by Engineer | Prior to commencement | Document Review | Best practice | Approved / Signature | Site Engineer | CPS
2.4 | Installer Certification | M | Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers | On Procurement of installer | Written confirmation | ASHTAS operative and installer course | Attendance Certificate | Site Engineer
3 | Guardrail Installation
3.1 | Guardrail Installation Locations | W | Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 Guardrail Installation Checksheet | Site Engineer
3.2 | W-Beam Guardrail Installation | M | W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checklist | Site Engineer
3.3 | Leading & Trailing End Terminal Installation | W | Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checklist | Site Engineer
3.4 | Fit for purpose Inspection | H | Barrier to undergo fit for purpose inspection by competent person System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM | Prior to trafficking, | Visual inspection | Pass inspection | Confirmation from inspector | Site Engineer | CPS
4 | Post-Construction Closeout
4.1 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | Quality
4.2 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer
4.3 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer