## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Guardrail | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Guardrail V2 | 1200b33f-c809-4ab4-8059-f814df22456c
checkpoint-group |  |  | section | 1 - Setout & Checks
checkpoint-status |  |  | checkpoint | Project Site reps.
text | cced162c-64d2-5efc-90aa-3b044f641676 |  | textbox | CPS Eng.
text | aef69642-1706-53cd-a2f5-9e37b3acdbf7 |  | textbox | Site Engineer
text | 1d5b771b-c7ac-5204-a1ca-3e64f12ab04e |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Design Check
label | f55b1984-6d0d-588a-8054-762a33dece0c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 177051a1-3506-595f-bb5b-b27b189c278d |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | f52bb312-076b-561b-bfcd-7ce0dc5287a8 |  | note | Frequency - Prior to commencement
label | 04c50c9c-b709-55ad-93f2-9fbdcc77cdc0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 3c9d089b-9c8d-5e1b-b82c-6c13d495c85d |  | note | Conformance Criteria - National Standard for Traffic Signal
label | abc6a079-aa01-55ea-b05e-b202cbfc7c2d |  | note | Records - OFI or NTD/NTC
checkpoint-status |  |  | checkpoint | 1.2 - Survey Setout
label | d58a41be-0d8e-55e0-83f7-9dddfd91717d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0fa7bbb5-4b90-51d6-9e71-d4f13369826e |  | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | 32bd05f5-da2b-52dc-8829-fa1d931f0471 |  | note | Frequency - Prior to commencement
label | a4ab71c4-fbac-586f-9fa2-c32656d81bde |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 4cc17b83-43ed-53b1-b84a-28c1c0984790 |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | 3976877d-188b-5908-8651-baae92e7a860 |  | note | Records - Approved Construction Drawing.
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Barrier Compliance
label | 6642b0ee-467b-5a79-b2a4-165f8d013434 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fb6250fd-1021-55f6-bd8b-467bc46d4ea0 |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | c11b72d7-da09-52de-9f79-6cfe258be655 |  | note | Frequency - Prior to commencement
label | 80e3d451-773d-565c-92a1-6ebf55337f2a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | dd9cbfe3-8e0d-5bdb-bb77-dd3f896ed60c |  | note | Conformance Criteria - TNZ M/23:2009
label | 62a4186d-cfbb-5db6-bf4f-401d19092eab |  | note | Records - Manufacturing certificates and delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Material Suppliers
label | ae7a70d1-5226-5090-b448-de63d47187e6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 074215fa-0917-5d71-8332-b2a18eceff3b |  | note | Detail - All materials to be sourced from registered suppliers
label | 3acaba4a-ec2b-5741-935f-d6a5ece44544 |  | note | Frequency - Prior to commencement
label | 16dcfb4e-b048-559b-a5de-9ecaaa0e1726 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7a66365a-7d74-52ff-823d-bc9d5c2c99bb |  | note | Conformance Criteria - Registered suppliers
label | 5e9394b5-2f67-525e-93ac-2696134895b5 |  | note | Records - Materials register
checkpoint-status |  |  | checkpoint | 2.3 - Galvanising Repair Methodology Approval
label | 5458f4ef-8ad2-55b6-97b9-80b56a22293d |  | note | ACTION (Hold, Monitor, Witness) - H
label | bb45e8f6-e4bf-53e8-8973-777656f5dc08 |  | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | 09fe0ce7-c87d-5515-8e8f-a1864b11daa8 |  | note | Frequency - Prior to commencement
label | b344cd9d-507f-5320-b1fc-5f693ae0dcb7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 43c2e41c-6eed-505a-a8a0-f48d823f4f96 |  | note | Conformance Criteria - Best practice
label | b45f1bcf-f0ad-5ad5-b313-cc5361b57092 |  | note | Records - Approved / Signature
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Installer Certification
label | 2bf988d0-e6d7-57db-b0f5-da2c54c4ff86 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 38f4f582-aae9-5588-b09f-83aa42c6f346 |  | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | 8407d565-4f9f-5c6d-9b8a-1a78020da663 |  | note | Frequency - On Procurement of installer
label | 2ed6ab0f-f8f9-5cc1-ab08-dd3b93aa0e57 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | 5043f194-ba45-5b63-a66a-70b1adac55f2 |  | note | Conformance Criteria - ASHTAS operative and installer course
label | 1d8c40ac-340a-534e-b0be-2bee538bf51a |  | note | Records - Attendance Certificate
checkpoint-group |  |  | section | 3 - Guardrail Installation
checkpoint-status |  |  | checkpoint | 3.1 - Guardrail Installation Locations
label | 9ab11576-eb0b-5230-a01f-7412ca3ac547 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 125dda90-41e1-568a-9db9-1d408fec3e67 |  | note | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | f3c68533-2408-5ee2-bdfa-1bd9bb994b67 |  | note | Frequency - During installation and on completion
label | 31f05e85-4b2d-5ca3-99fe-642ca022de65 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 3b221de2-71c4-5602-92a9-bcd83e09ae7f |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 339a93f5-74e7-5661-8ec2-9455ec461a03 |  | note | Records - CS-4117 Guardrail Installation Checksheet
checkpoint-status |  |  | checkpoint | 3.2 - W-Beam Guardrail Installation
label | 2ae331d7-3bdf-5227-adde-9dbb5562585a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 749e98f3-4830-55db-9df0-906d7dbdf65f |  | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | 47ea6e08-30c2-5a18-8c43-a78322f1d499 |  | note | Frequency - During installation and on completion
label | 25607303-c40d-5d31-a16b-c65d1e8b4665 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 8f916022-66f2-5fff-a690-f8f718dac095 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | ab67f5a5-59ed-5e53-9389-0085ce9fa182 |  | note | Records - Installation Checklist
checkpoint-status |  |  | checkpoint | 3.3 - Leading & Trailing End Terminal Installation
label | db2bc873-2ab8-5b4d-92e7-54851c13b655 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a9780095-b39c-5e2e-af4c-8f2e599c733b |  | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | e26f156e-2adb-5df8-b083-f513698e407e |  | note | Frequency - During installation and on completion
label | e7b375a6-5b2e-54db-b01b-75c6289def34 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | db187f75-ba9f-55ac-a3be-92ae9db66293 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 3fdc85c9-6642-5868-8c20-64faa03b69d5 |  | note | Records - Installation Checklist
checkpoint-status |  |  | checkpoint | 3.4 - Fit for purpose Inspection
label | 81653748-fe4e-59e2-aa85-5dfc65f7dc96 |  | note | ACTION (Hold, Monitor, Witness) - H
label | be809af1-7a0f-58b6-8ec2-efe97bb63f7d |  | note | Detail - Barrier to undergo fit for purpose inspection by competent person
label | e0a8a8b5-b7c5-51fe-8b09-94786272a958 |  | note | ○ System checklists to be completed and co signed by contractor and CPS.
label | 548e6c03-e4be-5f98-85af-0d482162e159 |  | note | ○ All faults to be rectified before acceptance into network maintenance and RAMM
label | c9a8501b-fc6b-5a2e-9861-00a41da50ed1 |  | note | Frequency - Prior to trafficking,
label | 5179012d-de5f-565c-bdd5-94a972918e03 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a381182b-331f-5750-b3d7-7dfac60abac9 |  | note | Conformance Criteria - Pass inspection
label | 09644748-d44f-5832-94fc-b603568c2796 |  | note | Records - Confirmation from inspector
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 4.1 - Final Walkover (Snags)
label | 8c9cc89a-ee3c-5480-a10b-b52368125ce3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7b5aa7e1-c4df-53f0-848d-64b165c388c5 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 3f42e5a5-ab83-53fb-a8a1-ae5b977036d6 |  | note | Frequency - At the completion of the Lot of work
label | b29a55f9-ada7-5b9b-9ad5-ceba13309e12 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 0942803a-602b-55a6-8105-80bcd1fa1e8e |  | note | Conformance Criteria - Completed report
label | 075d5e1e-2747-5f49-8170-a5cfcdd9e534 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Survey As-builts
label | 8744d8c5-e4f7-59d9-83d0-16eea6296b51 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d1236711-7d5f-517a-a9a5-0e80155ed85d |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 0c4f8a64-be53-5a7c-90d6-fc4a1ff4265e |  | note | ○ A survey as-built of completed work must be provided
label | f8a58bd6-76e1-5bab-a6f0-b5bb914dbeef |  | note | Frequency - At the completion of the CWP of work
label | 2edc01ab-4bee-530e-b917-115d1732a6a1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 1ff12ee5-faf1-59d0-a6e7-eb36c2ee8b9c |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 333266ae-9282-5075-b672-5a6d8dcd3924 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Quality Assurance Deliverables
label | efc5e96e-0a34-593d-921a-dab98da168f5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | edaf7a61-3df7-50ee-b512-d960651f7eb1 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | c4c767a3-1621-5e88-9529-deba8b5fcd1b |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | e2f731c1-645c-5c19-a342-4c0d792eed25 |  | note | Frequency - At the completion of the CWP
label | e7a22da3-7d7b-53a1-b926-29f2578c58bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c8cfbc51-4c54-5975-bb9d-04442f404870 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | f46dc4c1-27eb-5cfa-a51b-2023a17405bb |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn V2 | 466f43bf-47cf-454d-8ff3-ce59a4db76b9
checkpoint-group |  |  | section | 1 - Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 5eaf96ef-4314-51c3-9f83-46a410df3f49 |  | textbox | CPS Eng.
text | eb8a8ba7-f086-5223-9612-7ac0edbff6f1 |  | textbox | Site Engineer
text | 9a84afa8-eced-5584-ada9-eca26ae76aff |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | a327c703-085e-5291-8f76-e7375d4857be |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2e934403-7ebd-51ae-afea-f103c9f552e4 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | e9ff245b-7286-5d4b-9839-bb9cc1e28c0b |  | note | Frequency - Prior to commencement
label | 479d5542-d8cb-56ee-a74b-93ed89cd546b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | aaff4b60-b2b0-5ec2-a86e-65984f21282c |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | af8e8bf1-aee7-5314-84ec-67565e76df60 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a17ca7eb-a599-5e81-aed6-08c529d3ce7d |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | bb0712ce-9ca7-52a5-84db-48293a9c2f69 |  | note | Frequency - During construction
label | 39cbab90-9b5f-5d75-bac9-3714bbad40c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 264e3216-1680-5f8e-9fb8-6573a7657f9b |  | note | Conformance Criteria - Project Specification 6.6
label | 49fd88d4-3a20-5afd-a98a-abddfef0b226 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | 2a8c3ff1-c437-52b2-bfed-50738f176076 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f0af23a2-65bf-504d-977d-dcf88525ee1f |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 43f666e3-039a-553b-9866-faaec8eb0f49 |  | note | Frequency - Prior to commencement
label | b90dc7f4-d876-5911-9d1c-e3b513dbce91 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 7944c8b5-35d8-5348-8436-7fb5dd10acc7 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | e720a913-2a22-55b7-ba62-8f8870e5ef32 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 6b6260c8-7793-5168-b343-7f9539bd4124 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 14a42186-465c-5eb5-a26b-f33498e0e989 |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | ed3c1cb2-3569-56cc-aa60-2f611febf9a8 |  | note | Frequency - Prior to commencement
label | 32f9fcf6-1e06-5390-b6d6-6a946444b21f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | d5ee02ab-6a30-51d8-bd3b-03e9eae098ef |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | dc94aa75-d136-503c-86bd-264aa84ff144 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.3 - Concrete Pipes
label | e18f87a3-ee2d-5531-9690-8c38700cf570 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 12c6dbe7-22e4-5d41-8f7e-151478f73434 |  | note | Detail - Specification Compliance
label | c3398cf4-48d3-53cf-bbea-dd08600a5a85 |  | note | Frequency - Each delivery to site
label | 94e12109-2f98-54a3-b1ac-afe2e119dd95 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | f4a57f3f-30b3-5a09-ba4d-1791ac9a6980 |  | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
label | fb7e03e4-3874-568c-9c50-1f7f1f7bd425 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.4 - Pipe Bedding Material Compliance
label | 45c2faaa-1cc5-5c8f-8d2e-f5075d861d90 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 97f80f13-4bc9-50cd-9bb0-6cf77668d9d2 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 5c7b252a-7c35-5ff5-bc78-9fcc54b5ab2c |  | note | Frequency - Each material used
label | 77456db3-b046-553c-996d-94d7cd62810b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 14f0c562-51bc-5f3d-8b48-55f4e8fb144a |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | dcb5452b-0c64-5900-b8ee-47fe2c628d2b |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.5 - Pipe Backfill Compliance
label | bd71a89c-0d9c-50f1-a142-0f251eb51d48 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 81c61c7b-7b32-5881-8b31-85985c49a6ee |  | note | Detail - Material to meet specifications dependant on material type selected
label | 6924d00f-d2c6-5b6e-935b-c07aa745c786 |  | note | Frequency - Each material used
label | 8c1aab0d-c47a-54ad-93c4-02391d673db7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bba74deb-b5ee-5e58-b330-cdf1bd3a0fa0 |  | note | Conformance Criteria - Comply with grading specification
label | ba8afc2f-e634-517a-9faa-6719cebb1e9a |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.6 - Chip Seal design
label | 7141d653-f61e-5e65-8ee1-e4c6cf2f8e7e |  | note | ACTION (Hold, Monitor, Witness) - H
label | daba90c3-9c1d-5493-adc7-0aa6c541e2e7 |  | note | Detail - Seal design to be reviewed prior to sealing.
label | d615fe85-08f2-578b-b97f-10ba6a61eff0 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | 0c531b49-e418-5649-aafb-165f41a25c52 |  | note | Frequency - Prior to Sealing
label | 5948742b-e801-502d-823d-0030621557d8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 5b6b7248-0e3e-576c-9780-d7ea1662327d |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | 8b778e6c-0702-535b-97fa-c9b87151ca2a |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | 6da4f943-ed44-5248-b125-a8138ae14835 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7ae36348-7b5b-5809-84a6-ad818a7b53e5 |  | note | Detail - Determine Bearing strength of Sub Grade
label | 9f3df29c-d1a6-50e8-b30f-cd6a8c38ade9 |  | note | Frequency - After Dig out, every 10m
label | a6c2692a-a6d5-5048-8e7b-358d61167c0e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 0669672d-7551-55d5-b87a-73cedecc637d |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 77774cb8-1dbe-51e2-8491-6b21972f37e7 |  | note | ○ 2 blows = 4 CBR
label | ad96bdd9-c4d7-56d9-a5cc-c249aef9a2cd |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | 02a6fab6-b897-5ef0-8131-7f9b29a90f71 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6848d3a6-7bd7-5433-9f5e-ca343e66a3a7 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | 2050be43-53f0-50f0-a944-1241417d1979 |  | note | Frequency - Prior to Sub Base Construction
label | ff5f84f7-d1f8-562b-b0e1-dc5e4e478fd1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c8cf295b-8a28-5e8a-82fd-fe210e1c815c |  | note | Conformance Criteria - Engineers Acceptance
label | ac640f9f-79e0-57be-ac63-2111bdb40728 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | 750ebec3-5826-5019-bdd2-76bb74fcc738 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 16825082-e306-5463-9e9b-738179d634d7 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | dc5d245e-72b8-5809-8cab-518892dde74a |  | note | Frequency - During construction
label | 7976a289-eecd-5b93-bfb2-7d8cf7823d4f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | e0443362-6eb8-560e-84d1-b500d80a6fab |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | 9e82593e-ae23-5c5b-a87d-f11825e3818e |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | d2478fe4-5000-5dbb-9d0f-479195678693 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f49750e8-8e08-5afd-93c2-a41ef5eaff95 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 0cf51bfe-a5a9-5961-b227-5a72f6ab9705 |  | note | Frequency - During construction
label | 2494f8f1-f3a1-55fb-8672-6b81acc3a31b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c34fd02a-e77c-5f8f-b6f1-970f9f27c8de |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | bbb7fe81-b8a9-5137-8051-029aecbd9146 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e20dd6ef-75da-5e34-811b-c8b15907e95b |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | c7a22507-4e88-5871-a565-92f8fc1f3047 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | e84acccc-ceee-50b3-ad3b-11c28a142a25 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | ba4b7aa9-4117-554c-8fd0-faed860d4946 |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | 8deaceaf-cf49-55d0-88fa-8e0fedfcf84d |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 1a2a17e2-01d1-5e4d-96e4-ea4dc2192782 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7822b78a-b01b-5af9-a3e1-77c5b247d3c4 |  | note | Detail - Degree of Compaction.
label | 9aa73e5e-813b-5307-804c-23f7b6b1995a |  | note | ○ The subbase shall be constructed in two layers.
label | 6fd37884-d8f4-53fc-a590-0c091e8faf3c |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 36c0306e-f542-51bc-b547-d92addeb1de6 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 2caf7788-df59-5bd3-82fa-b0b35bbc5775 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 754ec960-82dd-588c-8a08-c007e6a39b30 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | daf1d0f2-95cb-5f14-83d9-4556cc5e577d |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | 492a1cca-0cb8-5ef1-855c-34c84ec92dc9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 444f0157-c8ad-5d14-a257-2c7004bcbeba |  | note | Detail - Degree of Compaction.
label | 3f95f327-68f0-5374-8e20-69baa4fb9510 |  | note | ○ The subbase shall be constructed in two layers.
label | 4011a8e7-e723-58ca-84fe-b429afa87a4e |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | 6e712283-22db-5cfb-9a1f-a1d627dc73c1 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 0aa83a10-ed8d-5b91-8882-7036d07a7b67 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 2f606761-eac4-581a-8029-71cb66dfa5d1 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 81ca589f-fa8e-5310-88ca-71a77ec549eb |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | 0772191b-7f19-58d2-94fa-6d90443d2b76 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f2d64243-230f-5e6e-85b3-2c3ca5bf1582 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | ac23a20c-d36d-5e1f-9dd3-f8c0f59da4d2 |  | note | Frequency - During construction
label | cc812f2d-cd46-5b53-80f8-ba78ed98564f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | efd5e964-acc1-58fc-bfde-bf2c7c47fabb |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | e012b8ab-c0fa-568c-a74a-2e5d991fa9a9 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | 00924602-560d-56d4-a2db-b7d452d599c1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1d7e339e-0819-5061-a6b0-dd0e71fe9a1e |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 56708092-193b-5039-a5af-5d1d71ae2fca |  | note | Frequency - During construction
label | 9b9b8925-2062-59b3-8e3b-09fb2864f924 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c5076003-747e-577e-bfdf-190979f5172c |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | dfe83787-9637-5c75-991a-d25b77dbe45b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1c28a6cd-7ea8-52ee-9330-ceabb6ae0325 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | f584e00d-55e7-51e4-af82-78a4a20431a8 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | b3a249c6-d695-59aa-a5c7-cc6006f6aa19 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | ed407575-8c65-556b-9e1f-564b0c09adaa |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | 8ffc541d-8b9f-5390-b2ac-d9168fbf9852 |  | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | cde82869-37d8-57da-b71f-4e40ac9c477d |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | a0ada81b-16b1-5e14-9d23-7ad45b9845ef |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9641131-5270-5435-8310-f616117a381d |  | note | Detail - Degree of Compaction
label | 1573ccad-0a0f-5da4-a6f5-8690af76728f |  | note | Frequency - 5 per Lot
label | 8d475302-e142-584b-a85b-1de3ad4cb850 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 14ded284-de5f-5657-88af-0f64908b785f |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 3c812792-602e-5392-bca9-45820752b78c |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 960b0fb5-cad2-5880-b8a7-f32323baea14 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8a919f01-7cce-5a87-b390-0e44d9ef3fdb |  | note | Detail - Surface shape check
label | 0052f421-f971-5292-bd73-fdf22a7ef3c4 |  | note | Frequency - Prior to sealing
label | 203cfeb6-cb7d-5e6a-b5de-e7f8239b01a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | f7bd6331-a35e-5fd6-9e35-7934927ca97b |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 52c6be31-0f19-5580-9c91-533e3160d1cb |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | f9b075ae-23a5-550b-84c4-664fa5ad8ccc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2dcc09d6-2fbc-5364-9e42-4485b5b88a58 |  | note | Detail - Surface finish check
label | 6fffd42b-c3b6-5c80-bf40-775f44f2b679 |  | note | Frequency - Prior to sealing
label | 3f00703f-b254-5468-af17-b05e0384f2bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 3b0260df-6d16-54ba-8f96-06af05ac97fc |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | c4718534-551a-547a-891a-3d199aa89730 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Extension of Culvert
checkpoint-status |  |  | checkpoint | 6.1 - Foundation Compliance
label | 45be92dc-8806-5427-8e2d-a61bb1a803a3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b27544d3-1dc4-581c-986d-97f3f6c4d77d |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 797a5bab-64ed-5ebd-b1a6-d550e665a434 |  | note | Frequency - One test per 5 linear metres
label | c7b969e6-eaf2-52df-a98c-14a744769917 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | aef78195-05bc-5d9f-8e8a-9bd0c23c2d46 |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 98cdcf13-72b3-53bc-bb1f-137930572c63 |  | note | ○ 2 blows = 4 CBR
label | 889981e6-d9a9-565f-8fca-5bc6e70dcf22 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Levels Compliance
label | 0e2b22cb-6aef-5430-b39a-5a96de8d206f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6059d5df-b1a6-5ee1-bef0-1a05ae073aa9 |  | note | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
label | f562a4f2-6922-5d86-8de6-961416598880 |  | note | Frequency - As stated
label | ae8b43c7-1d00-519f-b37c-25dab3bcf642 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 608cd521-7adc-52ae-a207-f12c90b70182 |  | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | da79f9b2-1ded-5f99-91cd-3d12e814d437 |  | note | Records - Photos, Visual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Sealing
checkpoint-status |  |  | checkpoint | 7.1 - Location/Size Confirmation
label | 55e08f24-1e4b-5d9c-be07-45d63498b79b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9ecb35f0-62f4-50f8-9937-62d87be0acf9 |  | note | Detail - Mark up extent of Chipseal
label | 68db4614-41ac-53dc-a59b-50603435e345 |  | note | Frequency - Prior to Sealing
label | 49ed456f-5ee1-5ec2-839b-93fd0b4509fc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | 606927db-485d-576b-84a1-99605c8ad3f0 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.2 - Surface Cleanliness
label | 1bcf7106-ce4b-5321-98b3-26d13274b4f6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6b72b169-48d4-5935-a1f0-a6d9a1e5dfce |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 630628cf-6b4c-5690-82bf-7ddba21ca546 |  | note | Frequency - Prior to application of binder
label | e3244862-29af-5af8-935e-3048754b079c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2fe5ae57-bfb7-52f5-b56d-f1bf26b8e8cd |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.3 - Binder Application
label | 8fc402e7-21cf-502b-9e5c-150d090f97b1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | aca03926-84bb-5f6e-b782-e646503ae1fe |  | note | Detail - Ensure the Binder application is according to the seal design
label | 6654e618-64cb-5483-a29d-c43214056299 |  | note | Frequency - During sealing
label | b2aba300-f0b7-5f09-a1b5-aaa16153b7f2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 7289c1c3-55fb-55fe-8f86-ef8340775f63 |  | note | Conformance Criteria - According to seal design
label | f62cabb9-28a2-5a13-bac4-69086d8820f2 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.4 - Chip Application
label | c59768f7-979c-571a-911c-7d8177946b91 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1cde60dd-1b29-59ad-849d-7466a299c173 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 24668de1-5505-55d6-9021-9099a8de0441 |  | note | Frequency - During sealing
label | da92bd03-998a-5a39-8230-894cb3f44542 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | bf968687-d8a1-578c-b698-5f8df0dd1f42 |  | note | Conformance Criteria - According to seal design
label | 02d6a1aa-bb79-5ec0-9e8d-a0cc5916f006 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.5 - Compaction
label | a239f1d7-efaa-5ab2-b804-52788389a8a4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a389fb1b-0761-5cf4-a645-7055cd1806d3 |  | note | Detail - At completion of rolling
label | fa1cbf5d-98f5-5ad9-be59-95901da3904b |  | note | Frequency - During sealing
label | 8e557790-feac-5f84-b8e2-4e53412f0a5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f03ac157-d2c7-51e5-8d8f-d6fbdded7dc3 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | bf719e1b-6fcf-5636-afd2-54c82a6259f6 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 7.6 - Removal of excess chip
label | 4834dd61-983c-5bed-8f13-b10937d9dba0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1407b561-6856-5e0a-9d85-113220284617 |  | note | Detail - Removal of excess chip
label | 8dd17909-414e-534c-8936-334525b8f346 |  | note | Frequency - Within 48 Hours of Sealing
label | e2c30be3-b24f-56c9-9612-1f85bf8d09d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 905bd7bc-c118-5c94-8005-a6401a5b5100 |  | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 82ff8530-8763-5d12-b66f-782aa3c6c8a7 |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 7.7 - Surface finish check
label | 2dea07ed-a233-5107-a8d2-320baf3d9ca7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82156e54-aeb5-57a7-97c7-55bfe1f39781 |  | note | Detail - Surface finish check
label | b641dec9-2a5f-5cfe-a0e1-2a0fd9b89d0a |  | note | Frequency - After sealing
label | c2e31100-0f81-5b00-9a39-69146fb84c0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 26806c68-067d-5216-bcb7-b3268a370267 |  | note | Conformance Criteria - Engineers Acceptance
label | e1a7bfdf-97bd-527f-b3db-d12009b1b569 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8 - Road Marking
checkpoint-status |  |  | checkpoint | 8.1 - Road Marking
label | 7948cc8f-6d46-5536-b77a-8a3956ce71e5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bd5a1ede-71e5-59b7-9294-4bd1851cbc80 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | eb713895-21a2-5c41-ab4e-9bb0c40bc96c |  | note | Frequency - Prior to the final line marking
label | 19ab4798-0e0f-58d5-89ed-1c3c095b43c9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 19c31483-9a4e-56e2-ac94-03a703cb092a |  | note | Conformance Criteria - Engineers Acceptance
label | 49c95b7a-cd66-54d5-ae1c-5ceb4d26aa17 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9 - Hydroseeding
checkpoint-status |  |  | checkpoint | 9.1 - Hydroseeding
label | fcf8aaef-026e-5b9f-97e4-253efba6fc98 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d7cea0e9-ef80-5992-824c-85b2b44e012c |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | bf1d6a3c-9f59-5a8f-a2e8-69c9e5dbab22 |  | note | Frequency - At the completion of the Lot of work
label | 407258fe-f443-52ff-b1f2-7fe5993c18c6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | e00d4925-9bf1-5fba-a9c7-6e8c63ff19d6 |  | note | Conformance Criteria - Engineers Acceptance
label | 8dc2e0f2-b37c-5cc0-abfd-9ea5abf664be |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 10.1 - Final Walkover (Snags)
label | 982ff868-c2dc-5490-8bc2-67f7bad93854 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 654640ab-95c1-53b3-b22e-df1313e2a73e |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 1ea94dee-7077-5903-bd4e-ad811867b177 |  | note | Frequency - At the completion of the Lot of work
label | 6aea82d3-d905-56eb-beb2-fb213708a934 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | bd2deeb8-ece0-59ea-a3aa-cdc98ff854c9 |  | note | Conformance Criteria - Completed report
label | 1a35418b-9150-5fd0-afe9-1c25026c59ad |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Survey As-builts
label | 5fa849e6-ff29-5444-a20c-1d6c6b055be9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9f3f221b-0d43-5f59-852a-e6be3f9a04d7 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 70bcab5e-2444-50a1-8c5a-9309b58e50b1 |  | note | ○ A survey as-built of completed work must be provided
label | a61a8f18-38b3-56c7-b898-2fbb816415da |  | note | Frequency - At the completion of the CWP of work
label | 6696f226-c05e-5b52-996c-7c6cb8ef6788 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | cfdffd97-8bc8-5110-9bf4-51bd7c641ce8 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | b6896e51-ee19-577f-9d69-28578241d0cd |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Quality Assurance Deliverables
label | 2b200a92-58ff-531c-82bc-864915f65f49 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d9a762f-49ad-5f0d-b927-6c501348f290 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 6dc7d01b-418b-535a-b225-a18817c22999 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 72e06a66-74d4-50e9-93f9-667a3483d7f5 |  | note | Frequency - At the completion of the CWP
label | c216d9a2-e74b-5efb-83bc-dcc963c463ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 28497fbf-1038-50e0-a395-6e4fbad63998 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 8b89c2d8-45c4-5a79-9258-621c7893e9aa |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Pavement Construction V2 | 3bc16a59-7963-4a6a-b5e7-809f99a8c25f
checkpoint-group |  |  | section | 1 - Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 5da27e37-9227-5bb1-a724-fbf532403a4f |  | textbox | CPS Eng.
text | dc9e46fd-eb2b-5473-9946-dd1dfb0a1aba |  | textbox | Site Engineer
text | 5a919999-991e-5160-9912-a294362d2c67 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 3ef15018-6208-511e-8c82-d1183059d622 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b8960be2-03b2-59ff-b4d8-752ba989392b |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 4ebf3757-7862-55c8-99b3-72880d3f1c73 |  | note | Frequency - Prior to commencement
label | ecb94d98-9750-599d-b303-158d244625de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | f269f329-a54a-5df0-9660-2e4daacc3c5d |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | 16ea99d8-ef40-59bd-8c5a-5f5ad20a5110 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ea533cdd-56ad-522d-9021-e49d7662d1f0 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | f3e10b10-6dab-5347-8aeb-febbad767d01 |  | note | Frequency - During construction
label | 286319d0-553d-54c1-b317-04b282f99c2e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e5809d11-6015-5a46-bcff-54894ea5223c |  | note | Conformance Criteria - Project Specification 6.6
label | 187f0fd6-12c9-5321-acd6-623c638caa1b |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | afc0c0bd-da12-554d-aa42-a96305fe4320 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ae94212e-d0a2-59dc-a902-db67d176c2f7 |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 6021f4f4-d3c6-5bea-9179-9aaeb88b902d |  | note | Frequency - Prior to commencement
label | 9e64e8a1-0a37-5bd4-b685-b822f88f00e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | ab7b2e55-1551-5fd8-985d-9094acab4a8b |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | ac9a0812-9c04-5ce7-90ec-c76cb17e20d1 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 5f00bf43-8d7d-585a-8daf-f14e112b6230 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 94e8cb67-85e3-5453-ae90-b5beacb67bba |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | 910048a7-84d0-5605-91f3-e55d0427aec9 |  | note | Frequency - Prior to commencement
label | 34a94167-7f5f-5aae-965a-1157570982d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 825117ee-e282-5ce8-a2fe-678e108c0a09 |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | df1c5b79-8441-528f-b877-ea5baba299a1 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.3 - Chip Seal design
label | 6242664b-32ed-53b6-a3ed-aeea5c5b0f3b |  | note | ACTION (Hold, Monitor, Witness) - H
label | b74310c5-c1c0-599c-a570-596cfd8df162 |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 951e56e0-2725-5124-8564-95ff58370f78 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | b57dd01e-989d-5b53-9e8e-9640c2257bdb |  | note | Frequency - Prior to Sealing
label | 31f6ccb1-de06-5196-b51a-defa7f1c713f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 47d962ce-af5a-5dfb-b1af-3e3e5b1eddcc |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | 1eaa35da-0f38-5de4-ac2b-ad95d8797e05 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | 9f98b8e7-cf56-5bfa-8271-39c4f3aa8879 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0243efe6-bd17-557b-88c8-845a3db28e60 |  | note | Detail - Determine Bearing strength of Sub Grade
label | ad87a623-204d-5161-aa18-282647c27b6b |  | note | Frequency - After Dig out, every 10m
label | d087639e-cdc1-5423-a4b4-332b524dee89 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 38629ae5-8331-582f-ac1d-83875c734bce |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 68cf7310-e3a2-5b71-a125-73c6ac686c21 |  | note | ○ 2 blows = 4 CBR
label | 9a668e70-3dfc-56e3-895d-cd70e2854daa |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | 8dda20b6-e36b-530d-9288-89ffc93618d8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b71fb06d-af66-5baf-8773-10b17ae2bed3 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | c954ded2-96e7-5af8-85c6-8a899101aa05 |  | note | Frequency - Prior to Sub Base Construction
label | 2d8a8f02-51f6-5430-8d53-686192d4fbed |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9cd4191b-ab63-5b8a-a832-2be3f7bd5e7b |  | note | Conformance Criteria - Engineers Acceptance
label | 37b503a9-dd84-5465-8229-af1577b39778 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | 4040404c-e33a-57ab-8e0c-9e510ca0b66e |  | note | ACTION (Hold, Monitor, Witness) - M
label | 07c4f95a-1c8e-5117-909c-c59c6a29b847 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 9ee68f3d-4159-505e-8cf5-17f39abb6bd6 |  | note | Frequency - During construction
label | 507c5590-3f67-519d-a544-d0a37cb4d8f9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | ca92ccb4-644a-5403-91f7-21d24a95bb8b |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | 29d4a6ff-41e0-5fa1-8b27-5444a7254413 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | 2ac3f7fa-7af8-549c-885b-b7c883addb17 |  | note | ACTION (Hold, Monitor, Witness) - M
label | c5d860c0-cc62-5398-a05e-06d3246cc065 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | cfcab3c5-c985-5dee-8a44-ab6c6b8d3113 |  | note | Frequency - During construction
label | e8d8dc0d-e5e9-54d5-9409-2c1fde4103f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | adaad07c-7bcc-5635-9a28-c76b5c0fb511 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | 74e426b2-2e49-5a32-873e-090e01d9080a |  | note | ACTION (Hold, Monitor, Witness) - H
label | a1d707ab-01c3-5683-80ba-d304fcecafb2 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | c51c1567-cc37-5801-86a0-1474c7db4695 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 28b40f97-5488-5e87-b9cd-4b8b51db9930 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 4320d227-1631-5656-bedb-032176d4b5a9 |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | f0aa8f9e-aa5f-55ab-b00d-a02d9e9f5cd5 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 83156ea3-8204-5ebc-b059-aa6bb2996063 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5cf1ad09-96c1-54e1-a81f-cb6583e36f79 |  | note | Detail - Degree of Compaction.
label | 88f560c6-a8b5-5eba-a0cd-5c23834c6362 |  | note | ○ The subbase shall be constructed in two layers.
label | 3ff8a5fd-7a5e-5a0c-a9a4-9dbaa34fb280 |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 451fe181-7218-5d50-82ec-456548e3a1fa |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 2b8674bf-18fa-526c-b779-32b2192e5da8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | eb3be03a-56a6-55f3-bec0-41400956e24b |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 1c3e1863-2578-5f19-a036-3815db278bc5 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | 39a2f529-fb2d-5734-aa4d-0612ea21993c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4301bd6b-0072-5bf8-ae06-5ac2fdd6a9ec |  | note | Detail - Degree of Compaction.
label | 96688400-c1d3-599f-8f72-4655db3c738e |  | note | ○ The subbase shall be constructed in two layers.
label | e811e220-aaf9-5719-84cd-08e13f2ad804 |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | 492b1a19-728f-5cea-bf6e-20ea2fd3f6e0 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 96d81701-9dd5-5363-8751-83268f9630c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 2eac3e29-6dc2-57c4-b553-03fa86a1cadb |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | aab71665-6f34-5ecc-885e-4c778e3defd0 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | a9505cc9-d657-5d0d-9013-ab2f18821ed1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 92f48eee-05e8-53ad-9199-c0d3493a373a |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | f8f8a5b1-41bf-5770-8fd5-c14e3ba0c648 |  | note | Frequency - During construction
label | 7f7168e5-a0aa-5225-a5bd-6a94acad8ae6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 9aef1535-8d7f-5449-aa05-9416ce4d817d |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 26fa8e8f-9ca2-5996-9859-30d768f362c7 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | 455a7bb4-2877-5879-befd-447ff47cd683 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 52b87140-99ed-5def-af1b-ba5836871a5d |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 83da7bc3-9eb5-5c40-9bf6-3a79c0c93442 |  | note | Frequency - During construction
label | db3561ae-16a3-5252-a5ec-07ab24948e07 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | abc8c789-c8ba-50cc-86fd-aa83851b6d93 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | ea7aabec-c7af-5eff-a2e7-ac1944cb3274 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 57681b45-f5f1-588d-a790-719b9037e9b9 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | f78a7bfe-40a0-54de-9eac-0d311f9fd842 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 1c1e8ac0-6dfd-5aab-b8ed-327fa25a1e0a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 02636fff-f1ea-529f-b67a-8da418d46658 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | 2e4aa163-4cf7-5182-936f-0c1190506a7a |  | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | 2fe400b7-361e-5c15-a881-79134691646e |  | note | Records - QA measurement Sheet CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | 7adbab00-8d87-5485-a1e0-2117e1b5f871 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5defd46b-293a-5b8c-bd17-9b32d463b084 |  | note | Detail - Degree of Compaction
label | 803620d0-d4d1-57f8-b00d-f3109f415968 |  | note | Frequency - 5 per Lot
label | 68bb47d5-4232-5f81-81a6-cab7c53e3021 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | ba7c8fbf-4ee6-5b05-82a7-9de90837f882 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 3f67cbb6-3129-55f2-b9b7-16b96c08926c |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 624b10ac-6c8b-5771-a808-dc7ef81602d5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | de94c82c-f275-5889-b2e7-7e1897299fd4 |  | note | Detail - Surface shape check
label | 77d1f411-78ec-5059-8591-3bdd0d36c8a9 |  | note | Frequency - Prior to sealing
label | 8bbe0891-aff3-589e-93af-f3ab94f1b2e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 85cda516-e41d-52b1-b739-7f0886a73f15 |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 05ed5353-ec27-5be9-835d-bba72c42a0b6 |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | 0220ad22-0840-56d5-919f-a0c33498fc4c |  | note | ACTION (Hold, Monitor, Witness) - H
label | aebf525d-4ed8-5718-a98f-1ea627e85d36 |  | note | Detail - Surface finish check
label | b079aa92-77d3-5094-8b1b-a86b322adfa9 |  | note | Frequency - Prior to sealing
label | d9ac9732-5dea-5224-9f27-fa763908fb54 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 3fa7dc4e-60bf-50a9-aeb4-217f1cf68970 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | 12abd0a8-cb91-58b9-a8f9-e11618432643 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Sealing
checkpoint-status |  |  | checkpoint | 6.1 - Location/Size Confirmation
label | 7485f261-d4f9-536b-8fdf-561601de76c2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c8d48b6d-db97-53fb-9758-4d4866adcbd6 |  | note | Detail - Mark up extent of Chipseal
label | cb8b1442-c99f-5f49-b1bd-e623891b21e3 |  | note | Frequency - Prior to Sealing
label | 739f9ab4-98f4-5175-a391-f34c4115690c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | 0948da8f-3868-588d-ab60-cc56197caa0a |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.2 - Surface Cleanliness
label | fb17b9dd-3a9c-5ae0-8483-0f7f73c208aa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 79aa985f-289a-5c62-a926-0b250674f747 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 1f2a42d5-f130-5ef4-9d62-f4e07e20dfda |  | note | Frequency - Prior to application of binder
label | 88900a8e-f43c-5a99-8559-6dd471a283da |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e6f8d306-45a8-5ad4-9639-9b6595ca4370 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.3 - Binder Application
label | 1422a60d-cd8d-5f49-b41b-d465972ef4fe |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1b4621f4-d8a0-53f2-bb18-1f9b358d2953 |  | note | Detail - Ensure the Binder application is according to the seal design
label | 2f077953-4c36-5d05-9d9c-a0db80e18ea9 |  | note | Frequency - During sealing
label | 9ba2946e-59bc-5470-9365-d7e27ce2acd7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | b6e772c4-0363-505a-8e8f-1239054c41bb |  | note | Conformance Criteria - According to seal design
label | f8648227-b271-5c91-ab7e-90f3439745a5 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.4 - Chip Application
label | b5a208fd-40f2-52e3-9cca-56711f730bed |  | note | ACTION (Hold, Monitor, Witness) - W
label | e72e3bf2-bda1-5f1a-b021-dbba356b5902 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 911e46fa-d246-5b30-82b5-a6ce46568fe6 |  | note | Frequency - During sealing
label | d66906f6-16a5-57c8-89a7-4ce475e38332 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | e8882c91-dcb9-5df7-bf00-d8de68422cfd |  | note | Conformance Criteria - According to seal design
label | baa65324-b804-5379-a4b8-95d634b02604 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.5 - Compaction
label | e20e83ee-4700-5b84-802b-eb87a3f87c4d |  | note | ACTION (Hold, Monitor, Witness) - W
label | c87001d6-cc7e-513d-a15d-023ce0485788 |  | note | Detail - At completion of rolling
label | 7073d984-be08-5ff7-83e0-9f902fc2f7a3 |  | note | Frequency - During sealing
label | 6a86c290-5f38-581b-99d8-e986fb728f94 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 84ae9be8-6762-521b-97a6-13b1d5623ac0 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 6721c5da-b99d-5168-8f75-73e0995eec47 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 6.6 - Removal of excess chip
label | d5c18bd0-667a-5346-a137-b810d639eb7b |  | note | ACTION (Hold, Monitor, Witness) - M
label | b5f3dfb8-3b48-5cbf-b61b-fa48d09663a0 |  | note | Detail - Removal of excess chip
label | 77e27586-729d-519b-a8f7-e5fb020fe37d |  | note | Frequency - Within 48 Hours of Sealing
label | 56722817-c9fa-5f36-b249-fd18e5ac83d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 964a8ccb-f1d8-574d-8f28-e2cccbb0be65 |  | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 4b248657-8678-5a28-bb34-5addfc697508 |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 6.7 - Surface finish check
label | 3f1b6df4-7b44-57d2-b3a9-15fa76642587 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 533c4c79-b617-5caf-bc14-d023edd661b3 |  | note | Detail - Surface finish check
label | 90dcc6c4-eade-54e3-9bc4-961129dbbf46 |  | note | Frequency - After sealing
label | 369264ef-d533-5e7f-9b79-c0a4cd5c456a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | a23abaf5-bf8e-5fdc-b686-71d39175140b |  | note | Conformance Criteria - Engineers Acceptance
label | bf63a106-238e-5a4b-9fb7-b25a2792b89f |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Road Marking
checkpoint-status |  |  | checkpoint | 7.1 - Road Marking
label | 0ef3fc74-de5c-5ac1-a095-308ca8073025 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 51b9f79e-12a5-56c6-af31-7a848ff256ea |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | 00cc6976-2ce6-555f-aaf9-a95542f79ff7 |  | note | Frequency - Prior to the final line marking
label | d8b2e7a1-ce8f-5cfc-b218-85635199b90e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 255b4cce-c383-5c84-9b14-da016543a7db |  | note | Conformance Criteria - Engineers Acceptance
label | b5bd9f51-4f6b-5269-968a-7e0689ca743f |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8 - Hydroseeding
checkpoint-status |  |  | checkpoint | 8.1 - Hydroseeding
label | b61e720a-f746-5e99-8c22-f0c969116f0b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c7c1bd4-2667-5e03-9979-0d3697094659 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | 0caf40e2-08fb-555c-8523-339f007b31a8 |  | note | Frequency - At the completion of the Lot of work
label | fa40d2df-0afb-558f-aad4-1237ac808457 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 39b44a5b-4b7d-5c2d-805f-d8d09fa4f680 |  | note | Conformance Criteria - Engineers Acceptance
label | f62e2122-ad8e-5238-92f4-0e05ec2196bc |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 9.1 - Final Walkover (Snags)
label | 7de9238b-1a82-5161-8d51-098bf31828ad |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0b7ef239-9499-5d42-b9b4-cc1a63f23e6d |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 7e6937b9-79a1-51e7-8579-eab1f02ac151 |  | note | Frequency - At the completion of the Lot of work
label | 5a2bc79f-d0cb-5cd9-a680-9673075515a5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | bbbc28a7-af8a-5ec5-a7d1-06a900682b58 |  | note | Conformance Criteria - Completed report
label | 719704c9-1130-5a5d-acac-368e46c466ff |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.2 - Survey As-builts
label | 734e3d95-654f-5b81-82f8-b9d64a879923 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ef15707e-fe22-56e7-87c8-34a64ac4757c |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 82d4a511-2815-5af5-8da5-d1c508bb0a13 |  | note | ○ A survey as-built of completed work must be provided
label | f5b03f3f-1e8b-55ae-9d2f-4b1ce0d7d12b |  | note | Frequency - At the completion of the CWP of work
label | b993bd80-b41b-55d8-8f97-c5031b30e84b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 2438aa1b-a84c-5a31-a735-61f723bafcbd |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 8a8d5207-5b2f-586d-a02b-2e19065886d9 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Quality Assurance Deliverables
label | ed06dd4d-f370-5f63-8ac9-aae4f6a5ef1b |  | note | ACTION (Hold, Monitor, Witness) - W
label | d8df4bc2-80b4-560d-b9bc-42e1479f532e |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 771cd758-4ead-5454-88a8-d990b48dbda0 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 531faa74-5e4e-5f16-bddc-c3798b50ab54 |  | note | Frequency - At the completion of the CWP
label | 31bfad75-8b62-5423-a0c3-50940d0d7582 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0755f4d6-f60e-566c-ae3b-09bfc793a11b |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 7c069f27-d304-5884-9994-f289940a2f88 |  | note | Records - As-builts, NCR's and RFI's