## Building A
Required ITP's for Building A Date 29/2/24
| Sprinkler Rough In 301 S | Drencher Rough In 301 D | Sprinkler Fit Off 302 S | Drencher Fit Off 302 D | Hydrant Install 303 | Sprinkler Control Valve Install & Operation 304 S | Drencher Control Valve Install & Operation 304 D | Vortex System Install & Operation 305 | Sprinkler Hydrostatic Test 401 S | Drencher Hydrostatic Test 401 D | Hydrant Hydrostatic Test 402 | Extinguisher Install 501 | Pump Install & Operation 601 | Booster Install 701 | Final Documentation and Signage 801
LG | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  | YES, Hydrant system tested for whole building. | YES | YES E&D | YES | YES, 1 X Doc required for whole building.
LGM
GRD | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
L1 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
L2 | YES | YES | YES | YES | YES | YES | YES |  | YES | YES |  | YES
L3 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L4 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L5 | YES |  | YES |  | YES | YES |  | YES | YES |  |  | YES

## Building B
Required ITP's for Building B Date 29/2/24
| Sprinkler Rough In 301 S | Drencher Rough In 301 D | Sprinkler Fit Off 302 S | Drencher Fit Off 302 D | Hydrant Install 303 | Sprinkler Control Valve Install & Operation 304 S | Drencher Control Valve Install & Operation 304 D | Vortex System Install & Operation 305 | Sprinkler Hydrostatic Test 401 S | Drencher Hydrostatic Test 401 D | Hydrant Hydrostatic Test 402 | Extinguisher Install 501 | Pump Install & Operation 601 | Booster Install 701 | Final Documentation and Signage 801
B2 | YES |  | YES |  | YES | YES |  |  | YES |  | YES, System tested for the whole of Stage 1 | YES |  |  | YES, 1 X Doc required for whole building.
B1 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
LG | YES X 2 | YES | YES X 2 | YES | YES | YES X 2 | YES |  | YES X 2 | YES |  | YES
LGM
GRD | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
L1 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
L2 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
L3 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
L4 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  | YES | YES X 2 |  |  | YES
L5 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  |  | YES
L6 | YES |  | YES |  | YES | YES |  |  | YES |  | YES, System tested for the whole of Stage 2 | YES
L7 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L8 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L9 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L10 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L11 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L12 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES

## Building C
Required ITP's for Building C Date 29/2/24
| Sprinkler Rough In 301 S | Drencher Rough In 301 D | Sprinkler Fit Off 302 S | Drencher Fit Off 302 D | Hydrant Install 303 | Sprinkler Control Valve Install & Operation 304 S | Drencher Control Valve Install & Operation 304 D | Vortex System Install & Operation 305 | Sprinkler Hydrostatic Test 401 S | Drencher Hydrostatic Test 401 D | Hydrant Hydrostatic Test 402 | Extinguisher Install 501 | Pump Install & Operation 601 | Booster Install 701 | Final Documentation and Signage 801
B1 | YES |  | YES |  | YES | YES |  |  | YES |  | YES, Hydrant system tested for whole building. | YES |  |  | YES, 1 X Doc required for whole building.
LG | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
LGM | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
GRD | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L1 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L2 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L3 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L4 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES

## Building D
Required ITP's for Building D Date 29/2/24
| Sprinkler Rough In 301 S | Drencher Rough In 301 D | Sprinkler Fit Off 302 S | Drencher Fit Off 302 D | Hydrant Install 303 | Sprinkler Control Valve Install & Operation 304 S | Drencher Control Valve Install & Operation 304 D | Vortex System Install & Operation 305 | Sprinkler Hydrostatic Test 401 S | Drencher Hydrostatic Test 401 D | Hydrant Hydrostatic Test 402 | Extinguisher Install 501 | Pump Install & Operation 601 | Booster Install 701 | Final Documentation and Signage 801
LG |  |  |  |  | YES | [5 empty] | YES, Hydrant system tested for whole building. | YES |  |  | YES, 1 X Doc required for whole building.
LGM | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
GRD | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L1 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L2 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L3 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L4 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L5 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES

## Building E
Required ITP's for Building E Date 29/2/24
| Sprinkler Rough In 301 S | Drencher Rough In 301 D | Sprinkler Fit Off 302 S | Drencher Fit Off 302 D | Hydrant Install 303 | Sprinkler Control Valve Install & Operation 304 S | Drencher Control Valve Install & Operation 304 D | Vortex System Install & Operation 305 | Sprinkler Hydrostatic Test 401 S | Drencher Hydrostatic Test 401 D | Hydrant Hydrostatic Test 402 | Extinguisher Install 501 | Pump Install & Operation 601 | Booster Install 701 | Final Documentation and Signage 801
LG | YES |  | YES |  | YES | YES |  |  | YES |  | YES, Hydrant system tested for whole building. | YES |  |  | YES, 1 X Doc required for whole building.
LGM | YES X 2 |  | YES |  | YES | YES X2 |  |  | YES X2 |  |  | YES
GRD | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L1 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L2 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L3 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L4 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L5 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES